## Page 1
Document Log Report
Contract Status : Active
Project : ASK : Aung Sinkha
Phase : 1A : Project Development Phase 1A (ASK)
Contract : MMC24-5001 : EPC of Wellhead Platforms for Aung Sinkha Development Project (ASK : 1A)
Asset Doctype : Engineering Document
Show Version :
Last Updated : 21-Sep-2026 08:19:05
Exported By : Jumpol Sudjitjul 21-Sep-2026 08:35:18
Submittal ID | Document No. | Document Title | Sht.No | Rev. | Creation Profile Type | Asset Doctype | Document Category | Area | Vendor Package Code | Vendor Package Name | Discipline Code | Discipline Name | Doc Type Code | Doc Type Name | Page Received | Status | Document Status Code | Document Status Name | Plan Submit In | Actual Submit In | Submitted By | Distribution Date | Distributed By | Reviewer Plan Finish | Reviewer Actual Finish | Focal Point | Focal Point Plan Finish | Focal Point Actual Finish | Approver | Approver Plan Finish | Approver Actual Finish | Return Status Code | Return Status Name | DC | DC Plan Validation | DC Actual Validation | Actual Submit Out | Page Return | Transmittal Out Date | Transmittal Out No. | Workflow | Open in D2
AO-001114 | INVOICE_ASK1A-TJE-26-0001 | PAYMENT FOR EPC WORK (SCOPE OF WORK - OUTSIDE MYANMAR) PERIOD FEBRUARY 2026 TO JULY 2026 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Latest | IFI | Issued for Information |  | 27-Aug-2026 18:02:04 | zm167dc@jutal.com | 28-Aug-2026 13:42:15 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 29-Aug-2026 20:17:11 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001116 | INVOICE_ASK1A-TJE-26-0002 | PAYMENT FOR EPC WORK (SCOPE OF WORK - OUTSIDE MYANMAR) PERIOD FEBRUARY 2026 TO JULY 2026 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Latest | IFI | Issued for Information |  | 27-Aug-2026 18:02:30 | zm167dc@jutal.com | 28-Aug-2026 13:42:38 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 29-Aug-2026 20:16:57 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000644 | MM-ASK-1A-GEN01-CON-MOM-5001 | CONSTRUCTION WEEKLY PROGRESS MEETING-1ST (10-JUN-2026) |  | - | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Jul-2026 16:15:22 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000645 | MM-ASK-1A-GEN01-CON-MOM-5002 | CONSTRUCTION WEEKLY PROGRESS MEETING-2ND (17-JUN-2026) |  | - | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Jul-2026 16:15:55 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000646 | MM-ASK-1A-GEN01-CON-MOM-5003 | CONSTRUCTION WEEKLY PROGRESS MEETING-3RD (01-JUL-2026) |  | - | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Jul-2026 16:16:22 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000854 | MM-ASK-1A-GEN01-CON-MOM-5004 | CONSTRUCTION WEEKLY PROGRESS MEETING-4TH (15-JUL-2026) |  | - | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 03-Aug-2026 09:57:48 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000855 | MM-ASK-1A-GEN01-CON-MOM-5005 | CONSTRUCTION WEEKLY PROGRESS MEETING-5TH (22-JUL-2026) |  | - | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 03-Aug-2026 09:58:24 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001269 | MM-ASK-1A-GEN01-CON-MOM-5006 | CONSTRUCTION WEEKLY PROGRESS MEETING-6TH (29-JUL-2026) |  | - | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 18:42:53 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001270 | MM-ASK-1A-GEN01-CON-MOM-5007 | CONSTRUCTION WEEKLY PROGRESS MEETING-7TH (05-AUG-2026) |  | - | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 18:43:18 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001272 | MM-ASK-1A-GEN01-CON-MOM-5008 | CONSTRUCTION WEEKLY PROGRESS MEETING-8TH (12-AUG-2026) |  | - | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 18:43:42 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001273 | MM-ASK-1A-GEN01-CON-MOM-5009 | CONSTRUCTION WEEKLY PROGRESS MEETING-9TH (19-AUG-2026) |  | - | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 18:44:10 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001045 | MM-ASK-1A-GEN01-CON-PDR-0001 | ONSHORE CONSTRUCTION PROCEDURE FOR JACKET |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 09:33:09 | zm167dc@jutal.com | 21-Aug-2026 14:02:42 | Jumpol Sudjitjul | 31-Aug-2026 | 22-Aug-2026 07:34:35 | Poramate Kamlangkeng | 01-Sep-2026 | 24-Aug-2026 07:47:24 | Apisit Tangwashirakul | 02-Sep-2026 | 27-Aug-2026 10:37:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 27-Aug-2026 11:44:34 | 27-Aug-2026 05:23:30 | 0 |  |  | Approver | Locate
AO-001019 | MM-ASK-1A-GEN01-CON-PDR-0002 | HANDLING AND LIFTING PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 19-Aug-2026 14:30:13 | zm167dc@jutal.com | 19-Aug-2026 15:25:22 | Jumpol Sudjitjul | 27-Aug-2026 |  | Poramate Kamlangkeng | 28-Aug-2026 | 24-Aug-2026 07:35:54 | Apisit Tangwashirakul | 31-Aug-2026 | 01-Sep-2026 15:47:53 | AWC-C | Approved with Comment (Proceed to Rev.C) | Soontaree Simpitak | 01-Sep-2026 | 02-Sep-2026 08:27:32 | 02-Sep-2026 02:11:33 | 0 |  |  | Approver | Locate
AO-001046 | MM-ASK-1A-GEN01-CON-PDR-0014 | ONSHORE CONSTRUCTION PROCEDURE FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 09:33:35 | zm167dc@jutal.com | 21-Aug-2026 14:03:39 | Jumpol Sudjitjul | 31-Aug-2026 | 22-Aug-2026 07:33:35 | Poramate Kamlangkeng | 01-Sep-2026 | 24-Aug-2026 07:42:36 | Apisit Tangwashirakul | 02-Sep-2026 | 31-Aug-2026 16:23:00 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Sep-2026 | 31-Aug-2026 16:29:49 | 31-Aug-2026 10:58:55 | 0 |  |  | Approver | Locate
AO-001049 | MM-ASK-1A-GEN01-CON-PDR-0025 | WEIGHTING CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 10:17:51 | zm167dc@jutal.com | 21-Aug-2026 14:05:27 | Jumpol Sudjitjul | 31-Aug-2026 | 22-Aug-2026 07:06:02 | Poramate Kamlangkeng | 01-Sep-2026 | 08-Sep-2026 09:20:05 | Apisit Tangwashirakul | 02-Sep-2026 | 16-Sep-2026 13:42:04 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Sep-2026 | 17-Sep-2026 08:22:09 | 17-Sep-2026 01:54:35 | 0 |  |  | Approver | Locate
AO-000348 | MM-ASK-1A-GEN01-COR-RPT-0001 | CORROSION ASSESSMENT AND MATERIAL SELECTION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | COR | Corrosion | RPT | Report | 0 | In Review | IFI | Issued for Information |  | 26-May-2026 11:26:48 | zm167dc@jutal.com | 05-Jun-2026 21:57:44 | Jumpol Sudjitjul |  |  | Pornlert Wanaphattharaphan | [11 empty] | 0 |  |  | For Info | Locate
AO-000113 | MM-ASK-1A-GEN01-ELE-BOD-0001 | ELECTRICAL BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 01-May-2026 10:28:58 | zm167dc@jutal.com | 01-May-2026 10:57:13 | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 08:29:13 | Noppadol Iamtanasinchai | 13-May-2026 | 18-May-2026 14:25:52 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 09:39:12 | APPR | Approved | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:20:28 | 19-May-2026 04:23:27 | 0 |  |  | Approver | Locate
AO-000335 | MM-ASK-1A-GEN01-ELE-BOD-0001 | ELECTRICAL BASIS OF DESIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 25-May-2026 14:46:53 | zm167dc@jutal.com | 25-May-2026 22:08:44 | Jumpol Sudjitjul | 05-Jun-2026 | 08-Jun-2026 17:08:50 | Noppadol Iamtanasinchai | 08-Jun-2026 | 10-Jun-2026 14:18:57 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 10-Jun-2026 21:26:01 | APPR | Approved | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 08:01:43 | 11-Jun-2026 01:22:01 | 0 |  |  | Approver | Locate
AO-000500 | MM-ASK-1A-GEN01-ELE-BOD-0001 | ELECTRICAL BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 17-Jun-2026 21:57:32 | zm167dc@jutal.com | 18-Jun-2026 10:11:14 | Jumpol Sudjitjul | 26-Jun-2026 |  | Danai Chaisalee | 29-Jun-2026 | 25-Jun-2026 14:03:05 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 28-Jun-2026 23:07:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 29-Jun-2026 09:14:26 | 29-Jun-2026 02:28:41 | 0 |  |  | Approver | Locate
AO-000146 | MM-ASK-1A-GEN01-ELE-MOM-0001 | ENGINEERING WEEKLY MEETING NO.1 12TH MARCH 2026 (8.00-9.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-May-2026 10:35:09 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000147 | MM-ASK-1A-GEN01-ELE-MOM-0002 | ENGINEERING WEEKLY MEETING NO.2 20TH MARCH 2026 (8.00-9.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-May-2026 10:35:42 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000148 | MM-ASK-1A-GEN01-ELE-MOM-0003 | ENGINEERING WEEKLY MEETING NO.3 27TH MARCH 2026 (13.30-14.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-May-2026 10:36:19 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000133 | MM-ASK-1A-GEN01-ELE-MOM-0004 | ENGINEERING WEEKLY MEETING NO.4 3RD APR 2026 (13.30-14.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 09:01:42 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000134 | MM-ASK-1A-GEN01-ELE-MOM-0005 | ENGINEERING WEEKLY MEETING NO.5 24TH APR 2026 (13.30-14.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 09:02:10 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000331 | MM-ASK-1A-GEN01-ELE-MOM-0006 | ENGINEERING WEEKLY MEETING NO.6 (8-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 25-May-2026 09:50:56 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000332 | MM-ASK-1A-GEN01-ELE-MOM-0007 | ENGINEERING WEEKLY MEETING NO.7 (15-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 25-May-2026 09:51:31 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000066 | MM-ASK-1A-GEN01-ELE-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR AC AND DC DISTRIBUTION BOARDS/PANELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 08:59:22 | zm167dc@jutal.com | 25-Apr-2026 09:10:25 | Jumpol Sudjitjul | 06-May-2026 | 05-May-2026 15:21:51 | Noppadol Iamtanasinchai | 07-May-2026 | 11-May-2026 17:30:13 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:14:31 | APPR | Approved | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 08:14:04 | 12-May-2026 08:37:44 | 0 |  |  | Approver | Locate
AO-000417 | MM-ASK-1A-GEN01-ELE-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR AC AND DC DISTRIBUTION BOARDS/PANELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 05-Jun-2026 17:52:41 | zm167dc@jutal.com | 05-Jun-2026 19:46:10 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 10:07:45 | Noppadol Iamtanasinchai | 17-Jun-2026 | 17-Jun-2026 08:24:13 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 17:57:45 | APPR | Approved | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 20:52:43 | 22-Jun-2026 01:07:11 | 0 |  |  | Approver | Locate
AO-000112 | MM-ASK-1A-GEN01-ELE-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR SOLAR POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 01-May-2026 10:29:24 | zm167dc@jutal.com | 01-May-2026 10:56:35 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 16:40:59 | Noppadol Iamtanasinchai | 13-May-2026 | 18-May-2026 14:24:44 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 21:17:42 | APPR | Approved | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:08:50 | 20-May-2026 08:13:58 | 0 |  |  | Approver | Locate
AO-000355 | MM-ASK-1A-GEN01-ELE-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR SOLAR POWER SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 26-May-2026 18:08:29 | zm167dc@jutal.com | 27-May-2026 09:11:11 | Jumpol Sudjitjul | 08-Jun-2026 | 08-Jun-2026 17:37:39 | Noppadol Iamtanasinchai | 09-Jun-2026 | 10-Jun-2026 14:24:47 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:28:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 07:58:09 | 11-Jun-2026 01:12:04 | 0 |  |  | Approver | Locate
AO-001003 | MM-ASK-1A-GEN01-ELE-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR SOLAR POWER SYSTEM |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 12:47:51 | zm167dc@jutal.com | 17-Aug-2026 13:31:03 | Jumpol Sudjitjul | 25-Aug-2026 |  | Danai Chaisalee | 26-Aug-2026 | 26-Aug-2026 07:44:32 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 22:52:33 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 15:27:26 | 30-Aug-2026 08:48:49 | 0 |  |  | Approver | Locate
AO-000215 | MM-ASK-1A-GEN01-ELE-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR NAVIGATION AID SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 07-May-2026 14:32:01 | zm167dc@jutal.com | 12-May-2026 11:13:45 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 17:43:37 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 11:03:31 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 13:14:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 16:27:22 | 31-May-2026 16:51:52 | 0 |  |  | Approver | Locate
AO-000452 | MM-ASK-1A-GEN01-ELE-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR NAVIGATION AID SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 11-Jun-2026 17:15:02 | zm167dc@jutal.com | 11-Jun-2026 17:44:33 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 17:28:07 | Noppadol Iamtanasinchai | 23-Jun-2026 | 21-Jun-2026 10:39:55 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 12:13:28 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 12:36:31 | 22-Jun-2026 05:49:31 | 0 |  |  | Approver | Locate
AO-000067 | MM-ASK-1A-GEN01-ELE-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR EXTERNAL BATTERY CHARGER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 08:59:46 | zm167dc@jutal.com | 25-Apr-2026 09:10:37 | Jumpol Sudjitjul | 06-May-2026 | 05-May-2026 16:01:08 | Noppadol Iamtanasinchai | 07-May-2026 | 14-May-2026 09:00:11 | Pornlert Wanaphattharaphan | 08-May-2026 | 14-May-2026 22:43:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 15-May-2026 08:35:49 | 15-May-2026 09:16:18 | 0 |  |  | Approver | Locate
AO-000361 | MM-ASK-1A-GEN01-ELE-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR EXTERNAL BATTERY CHARGER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 27-May-2026 14:43:37 | zm167dc@jutal.com | 27-May-2026 15:12:57 | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 10:39:23 | Noppadol Iamtanasinchai | 09-Jun-2026 | 10-Jun-2026 14:29:24 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:29:28 | APPR | Approved | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 07:59:08 | 11-Jun-2026 01:13:12 | 0 |  |  | Approver | Locate
AO-000068 | MM-ASK-1A-GEN01-ELE-SPE-0005 | PROJECT PARTICULAR SPECIFICATION FOR ELECTRICAL CABLES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:00:07 | zm167dc@jutal.com | 25-Apr-2026 09:10:52 | Jumpol Sudjitjul | 06-May-2026 | 05-May-2026 16:56:33 | Noppadol Iamtanasinchai | 07-May-2026 | 14-May-2026 09:02:11 | Pornlert Wanaphattharaphan | 08-May-2026 | 14-May-2026 22:46:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 15-May-2026 09:05:57 | 15-May-2026 09:26:51 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-GEN01-ELE-SPE-0005 | PROJECT PARTICULAR SPECIFICATION FOR ELECTRICAL CABLES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 11:57:53 | zm167dc@jutal.com | 12-Jun-2026 12:47:29 | Jumpol Sudjitjul | 22-Jun-2026 |  | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:51:39 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:54:50 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:19:09 | 25-Jun-2026 01:44:34 | 0 |  |  | Approver | Locate
AO-000069 | MM-ASK-1A-GEN01-ELE-SPE-0006 | PROJECT PARTICULAR SPECIFICATION FOR ELECTRICAL BULK MATERIALS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:00:30 | zm167dc@jutal.com | 25-Apr-2026 09:11:04 | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 11:27:44 | Noppadol Iamtanasinchai | 07-May-2026 | 11-May-2026 17:52:37 | Pornlert Wanaphattharaphan | 08-May-2026 | 12-May-2026 22:06:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 13-May-2026 08:20:49 | 13-May-2026 08:32:52 | 0 |  |  | Approver | Locate
AO-000356 | MM-ASK-1A-GEN01-ELE-SPE-0006 | PROJECT PARTICULAR SPECIFICATION FOR ELECTRICAL BULK MATERIALS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 26-May-2026 18:09:07 | zm167dc@jutal.com | 27-May-2026 09:11:34 | Jumpol Sudjitjul | 08-Jun-2026 | 08-Jun-2026 17:38:19 | Noppadol Iamtanasinchai | 09-Jun-2026 | 10-Jun-2026 14:28:14 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:29:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 08:00:52 | 11-Jun-2026 01:14:26 | 0 |  |  | Approver | Locate
AO-001010 | MM-ASK-1A-GEN01-ELE-SPE-0006 | PROJECT PARTICULAR SPECIFICATION FOR ELECTRICAL BULK MATERIALS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 18:40:00 | zm167dc@jutal.com | 18-Aug-2026 10:15:20 | Jumpol Sudjitjul | 26-Aug-2026 |  | Danai Chaisalee | 27-Aug-2026 | 27-Aug-2026 15:28:20 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 29-Aug-2026 23:20:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 30-Aug-2026 15:30:31 | 30-Aug-2026 08:47:43 | 0 |  |  | Approver | Locate
AO-000152 | MM-ASK-1A-GEN01-ELE-SPE-0007 | PROJECT PARTICULAR SPECIFICATION FOR FOG HORN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 07-May-2026 14:32:35 | zm167dc@jutal.com | 07-May-2026 14:54:48 | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:51:18 | Noppadol Iamtanasinchai | 18-May-2026 | 20-May-2026 10:47:21 | Pornlert Wanaphattharaphan | 19-May-2026 | 21-May-2026 20:44:39 | APPR | Approved | Jumpol Sudjitjul | 20-May-2026 | 21-May-2026 21:17:46 | 21-May-2026 22:17:03 | 0 |  |  | Approver | Locate
AO-000452 | MM-ASK-1A-GEN01-ELE-SPE-0007 | PROJECT PARTICULAR SPECIFICATION FOR FOG HORN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 11-Jun-2026 17:15:30 | zm167dc@jutal.com | 11-Jun-2026 17:44:49 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 17:28:24 | Noppadol Iamtanasinchai | 23-Jun-2026 | 21-Jun-2026 10:40:53 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 12:12:12 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 12:37:28 | 22-Jun-2026 05:50:50 | 0 |  |  | Approver | Locate
AO-000103 | MM-ASK-1A-GEN01-ELE-SPE-0008 | PROJECT PARTICULAR SPECIFICATION FOR MOTOR CONTROL CENTER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 14:52:11 | zm167dc@jutal.com | 30-Apr-2026 16:16:20 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 10:29:02 | Noppadol Iamtanasinchai | 13-May-2026 | 18-May-2026 13:12:46 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 20:42:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:12:29 | 20-May-2026 08:44:03 | 0 |  |  | Approver | Locate
AO-000498 | MM-ASK-1A-GEN01-ELE-SPE-0008 | PROJECT PARTICULAR SPECIFICATION FOR MOTOR CONTROL CENTER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 17-Jun-2026 15:32:53 | zm167dc@jutal.com | 17-Jun-2026 16:08:22 | Jumpol Sudjitjul | 25-Jun-2026 |  | Danai Chaisalee | 26-Jun-2026 | 26-Jun-2026 08:52:42 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 28-Jun-2026 21:43:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 29-Jun-2026 09:15:32 | 29-Jun-2026 02:30:08 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-GEN01-ELE-SPE-0008 | PROJECT PARTICULAR SPECIFICATION FOR MOTOR CONTROL CENTER |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 10:42:16 | zm167dc@jutal.com | 24-Jul-2026 11:36:07 | Jumpol Sudjitjul | 05-Aug-2026 | 24-Jul-2026 16:18:08 | Danai Chaisalee | 06-Aug-2026 | 05-Aug-2026 09:09:34 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 05-Aug-2026 23:36:20 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 06-Aug-2026 08:35:50 | 06-Aug-2026 03:14:46 | 0 |  |  | Approver | Locate
AO-000104 | MM-ASK-1A-GEN01-ELE-SPE-0009 | PROJECT PARTICULAR SPECIFICATION FOR AC GENERATOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 14:52:40 | zm167dc@jutal.com | 30-Apr-2026 16:16:37 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 11:38:37 | Noppadol Iamtanasinchai | 13-May-2026 | 18-May-2026 13:15:18 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 20:45:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:14:05 | 20-May-2026 08:45:12 | 0 |  |  | Approver | Locate
AO-000448 | MM-ASK-1A-GEN01-ELE-SPE-0009 | PROJECT PARTICULAR SPECIFICATION FOR AC GENERATOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 11-Jun-2026 14:53:00 | zm167dc@jutal.com | 11-Jun-2026 15:13:12 | Jumpol Sudjitjul | 19-Jun-2026 | 16-Jun-2026 16:05:18 | Noppadol Iamtanasinchai | 22-Jun-2026 | 17-Jun-2026 08:53:25 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 21-Jun-2026 08:06:12 | APPR | Approved | Jumpol Sudjitjul | 24-Jun-2026 | 22-Jun-2026 09:50:27 | 22-Jun-2026 03:38:54 | 0 |  |  | Approver | Locate
AO-000105 | MM-ASK-1A-GEN01-ELE-SPE-0010 | PROJECT PARTICULAR SPECIFICATION FOR INDUCTION MOTOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 14:53:07 | zm167dc@jutal.com | 30-Apr-2026 16:16:53 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 11:38:55 | Noppadol Iamtanasinchai | 13-May-2026 | 18-May-2026 13:17:01 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 20:48:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:17:12 | 20-May-2026 08:47:54 | 0 |  |  | Approver | Locate
AO-000448 | MM-ASK-1A-GEN01-ELE-SPE-0010 | PROJECT PARTICULAR SPECIFICATION FOR INDUCTION MOTOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 11-Jun-2026 14:53:27 | zm167dc@jutal.com | 11-Jun-2026 15:13:26 | Jumpol Sudjitjul | 19-Jun-2026 | 16-Jun-2026 16:05:39 | Noppadol Iamtanasinchai | 22-Jun-2026 | 17-Jun-2026 08:53:59 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 21-Jun-2026 08:07:27 | APPR | Approved | Jumpol Sudjitjul | 24-Jun-2026 | 22-Jun-2026 09:55:29 | 22-Jun-2026 03:40:15 | 0 |  |  | Approver | Locate
AO-000155 | MM-ASK-1A-GEN01-ENG-MDR-0001 | ENGINEERING MASTER DELIVERABLE REGISTER |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MDR | Master Deliverable Register | 0 | Submitted | IFR | Issued for Review |  | 07-May-2026 17:05:43 | zm167dc@jutal.com | 07-May-2026 17:13:12 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 15:34:41 | Pornlert Wanaphattharaphan | 19-May-2026 | 24-May-2026 15:20:27 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 15:23:32 | 24-May-2026 08:37:43 | 0 |  |  | Focal Point | Locate
AO-001223 | MM-ASK-1A-GEN01-ENG-MDR-0001 | ENGINEERING MASTER DELIVERABLE REGISTER |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MDR | Master Deliverable Register | 0 | In Review | IFA | Issued for Approval |  | 07-Sep-2026 13:17:42 | zm167dc@jutal.com | 08-Sep-2026 11:12:51 | Jumpol Sudjitjul | 16-Sep-2026 | 17-Sep-2026 17:13:39 | Pornlert Wanaphattharaphan | 17-Sep-2026 | [7 empty] | 21-Sep-2026 |  |  | 0 |  |  | Focal Point | Locate
AO-000019 | MM-ASK-1A-GEN01-ENG-MOM-0001 | ENGINEERING WEEKLY MEETING NO.1 10TH MARCH 2026 (9.00-11.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-Mar-2026 10:27:16 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000020 | MM-ASK-1A-GEN01-ENG-MOM-0002 | ENGINEERING WEEKLY MEETING NO.2 17TH MARCH 2026 (9.00-11.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-Mar-2026 10:27:39 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000043 | MM-ASK-1A-GEN01-ENG-MOM-0003 | ENGINEERING WEEKLY MEETING NO.3 24TH MARCH 2026 (9.00-11.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 19-Apr-2026 22:20:40 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000138 | MM-ASK-1A-GEN01-ENG-MOM-0004 | ENGINEERING WEEKLY MEETING NO.4 31ST MARCH 2026 (9.00-11.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 15:09:45 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000045 | MM-ASK-1A-GEN01-ENG-MOM-0005 | ENGINEERING WEEKLY MEETING NO.5 7TH APRIL 2026 (9.00-11.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 20-Apr-2026 12:52:28 | jumpols@pttep.com | [16 empty] | 0 |  |  |  | Locate
AO-000139 | MM-ASK-1A-GEN01-ENG-MOM-0006 | ENGINEERING WEEKLY MEETING NO.6 21ST APRIL 2026 (9.00-11.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Submitted | IFI | Issued for Information |  | 06-May-2026 15:55:22 | zm167dc@jutal.com | 06-May-2026 16:18:31 | Jumpol Sudjitjul |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:22:26 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 06-May-2026 16:25:22 | 06-May-2026 10:15:26 | 0 |  |  | For Info | Locate
AO-000141 | MM-ASK-1A-GEN01-ENG-MOM-0007 | ENGINEERING WEEKLY MEETING NO.7 28TH APRIL 2026 (9.00-11.00 BANGKOK TIME) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 15:55:55 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000214 | MM-ASK-1A-GEN01-ENG-MOM-0008 | ENGINEERING WEEKLY MEETING NO.8 05TH MAY 2026 (9.00-11.00 BANGKOK TIME) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 11-May-2026 18:05:44 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000279 | MM-ASK-1A-GEN01-ENG-MOM-0009 | ENGINEERING WEEKLY MEETING NO.9 (12-MAY-2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-May-2026 19:34:57 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000345 | MM-ASK-1A-GEN01-ENG-MOM-0010 | ENGINEERING WEEKLY MEETING NO.10 (19-MAY-2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-May-2026 10:55:42 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000481 | MM-ASK-1A-GEN01-ENG-MOM-0013 | ENGINEERING WEEKLY MEETING NO.13 (09-JUN-2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Jun-2026 11:30:51 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000291 | MM-ASK-1A-GEN01-ENG-PDR-0001 | 3D MODEL REVIEW PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 14:25:28 | zm167dc@jutal.com | 20-May-2026 15:46:56 | Jumpol Sudjitjul | 28-May-2026 | 04-Jun-2026 13:25:28 | Thanapat Sombatwattana | 29-May-2026 | 05-Jun-2026 17:06:37 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 10-Jun-2026 21:02:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 11-Jun-2026 08:02:58 | 11-Jun-2026 01:15:34 | 0 |  |  | Approver | Locate
AO-000814 | MM-ASK-1A-GEN01-ENG-PDR-0001 | 3D MODEL REVIEW PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 16:04:50 | zm167dc@jutal.com | 30-Jul-2026 16:37:02 | Jumpol Sudjitjul | 07-Aug-2026 | 03-Aug-2026 07:23:20 | Thanapat Sombatwattana | 10-Aug-2026 | 14-Aug-2026 09:43:58 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 16-Aug-2026 10:34:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 17-Aug-2026 08:29:22 | 17-Aug-2026 02:25:23 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-GEN01-ENG-PDR-0001 | 3D MODEL REVIEW PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:58:30 | zm167dc@jutal.com | 02-Sep-2026 20:25:34 | Soontaree Simpitak | 11-Sep-2026 | 10-Sep-2026 10:01:25 | Thanapat Sombatwattana | 14-Sep-2026 | 17-Sep-2026 15:19:31 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 18-Sep-2026 20:26:17 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 20-Sep-2026 14:23:28 | 20-Sep-2026 07:32:05 | 0 |  |  | Approver | Locate
AO-000010 | MM-ASK-1A-GEN01-ENG-PLN-0001 | ENGINEERING EXECUTION PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 11-Mar-2026 10:03:19 | zm167dc@jutal.com | 11-Mar-2026 15:53:30 | Jumpol Sudjitjul | 19-Mar-2026 | 19-Mar-2026 16:43:53 | Pornlert Wanaphattharaphan | 20-Mar-2026 | 19-Mar-2026 18:58:02 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Mar-2026 | 20-Mar-2026 08:01:43 | 20-Mar-2026 08:15:47 | 0 |  |  | Focal Point | Locate
AO-000100 | MM-ASK-1A-GEN01-ENG-PLN-0001 | ENGINEERING EXECUTION PLAN |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 30-Apr-2026 08:20:38 | zm167dc@jutal.com | 30-Apr-2026 14:10:08 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 16:34:30 | Pornlert Wanaphattharaphan | 13-May-2026 | 19-May-2026 23:58:27 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:19:45 | 20-May-2026 01:59:24 | 0 |  |  | Focal Point | Locate
AO-000574 | MM-ASK-1A-GEN01-ENG-PLN-0001 | ENGINEERING EXECUTION PLAN |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 29-Jun-2026 12:10:44 | zm167dc@jutal.com | 30-Jun-2026 10:05:10 | Jumpol Sudjitjul | 08-Jul-2026 | 06-Jul-2026 08:30:58 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 00:08:50 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 13-Jul-2026 | 08-Jul-2026 08:24:11 | 08-Jul-2026 02:19:20 | 0 |  |  | Focal Point | Locate
AO-000295 | MM-ASK-1A-GEN01-ENG-RPT-0001 | FEED VERIFICATION AND VALIDATION REPORT |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 18:06:31 | zm167dc@jutal.com | 21-May-2026 08:39:24 | Jumpol Sudjitjul | 29-May-2026 | 09-Jun-2026 01:19:38 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 14-Jun-2026 19:33:51 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 14-Jun-2026 21:44:40 | 14-Jun-2026 15:15:57 | 0 |  |  | Focal Point | Locate
AO-000018 | MM-ASK-1A-GEN01-INS-BOD-0001 | INSTRUMENT BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 26-Mar-2026 09:09:50 | zm167dc@jutal.com | 07-Apr-2026 07:04:41 | Jumpol Sudjitjul | 20-Apr-2026 |  | Payut Phatdamrongdet | 21-Apr-2026 | 23-Apr-2026 17:27:50 | Pornlert Wanaphattharaphan | 22-Apr-2026 | 25-Apr-2026 21:38:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Apr-2026 | 27-Apr-2026 10:02:40 | 27-Apr-2026 03:20:31 | 0 |  |  | Approver | Locate
AO-000951 | MM-ASK-1A-GEN01-INS-BOD-0001 | INSTRUMENT BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 10:43:34 | zm167dc@jutal.com | 11-Aug-2026 11:43:18 | Jumpol Sudjitjul | 20-Aug-2026 |  | Payut Phatdamrongdet | 21-Aug-2026 | 26-Aug-2026 08:50:32 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 27-Aug-2026 14:48:59 | APPR | Approved | Jumpol Sudjitjul | 25-Aug-2026 | 27-Aug-2026 14:55:18 | 27-Aug-2026 09:01:27 | 0 |  |  | Approver | Locate
AO-000328 | MM-ASK-1A-GEN01-INS-DTS-0001 | DATA SHEETS FOR SUPERVISORY CONTROL AND DATA ACQUISITION SYSTEM (SCADA) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:39:23 | zm167dc@jutal.com | 23-May-2026 09:16:00 | Jumpol Sudjitjul | 02-Jun-2026 | 05-Jun-2026 17:34:43 | Payut Phatdamrongdet | 04-Jun-2026 | 08-Jun-2026 17:00:25 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:15:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 08:03:32 | 11-Jun-2026 01:16:42 | 0 |  |  | Approver | Locate
AO-000531 | MM-ASK-1A-GEN01-INS-DTS-0001 | DATA SHEETS FOR SUPERVISORY CONTROL AND DATA ACQUISITION SYSTEM (SCADA) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 23-Jun-2026 10:39:12 | zm167dc@jutal.com | 23-Jun-2026 12:56:02 | Jumpol Sudjitjul | 01-Jul-2026 | 01-Jul-2026 09:32:47 | Payut Phatdamrongdet | 02-Jul-2026 | 02-Jul-2026 16:49:36 | Pornlert Wanaphattharaphan | 03-Jul-2026 | 03-Jul-2026 00:50:17 | APPR | Approved | Jumpol Sudjitjul | 06-Jul-2026 | 03-Jul-2026 15:54:23 | 03-Jul-2026 09:30:58 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-GEN01-INS-DTS-0001 | DATA SHEETS FOR SUPERVISORY CONTROL AND DATA ACQUISITION SYSTEM (SCADA) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:50:12 | zm167dc@jutal.com | 20-Jul-2026 11:55:38 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:33:40 | Payut Phatdamrongdet | 31-Jul-2026 | 30-Jul-2026 15:28:31 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 30-Jul-2026 18:12:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 30-Jul-2026 19:01:24 | 30-Jul-2026 12:21:40 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-GEN01-INS-LIS-0001 | CAUSE & EFFECT DIAGRAM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 12:05:00 | zm167dc@jutal.com | 22-Jun-2026 15:09:31 | Jumpol Sudjitjul | 23-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 24-Jun-2026 19:17:06 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 24-Jun-2026 22:26:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 25-Jun-2026 08:20:24 | 25-Jun-2026 01:45:47 | 0 |  |  | Approver | Locate
AO-000941 | MM-ASK-1A-GEN01-INS-LIS-0001 | CAUSE & EFFECT DIAGRAM |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:24:18 | zm167dc@jutal.com | 10-Aug-2026 16:07:24 | Jumpol Sudjitjul | 19-Aug-2026 | 19-Aug-2026 00:00:18 | Payut Phatdamrongdet | 20-Aug-2026 | 25-Aug-2026 12:38:52 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 27-Aug-2026 14:48:32 | APPR | Approved | Jumpol Sudjitjul | 25-Aug-2026 | 27-Aug-2026 15:16:21 | 27-Aug-2026 09:07:05 | 0 |  |  | Approver | Locate
AO-000040 | MM-ASK-1A-GEN01-INS-MOM-0001 | INSTRUMENT WEEKLY MEETING NO.1 20TH MARCH 2026 (9.00-10.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 10-Apr-2026 16:33:52 | angkana.k@mermaid-group.com | [16 empty] | 0 |  |  |  | Locate
AO-000041 | MM-ASK-1A-GEN01-INS-MOM-0002 | INSTRUMENT WEEKLY MEETING NO.2 27TH MARCH 2026 (2.30 PM-4.00 PM BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 10-Apr-2026 16:34:18 | angkana.k@mermaid-group.com | [16 empty] | 0 |  |  |  | Locate
AO-000217 | MM-ASK-1A-GEN01-INS-MOM-0003 | INSTRUMENT WEEKLY MEETING NO.3 (3-APR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 20:47:36 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000218 | MM-ASK-1A-GEN01-INS-MOM-0004 | INSTRUMENT WEEKLY MEETING NO.4 (24-APR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 20:48:06 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000275 | MM-ASK-1A-GEN01-INS-MOM-0005 | INSTRUMENT WEEKLY MEETING NO.5 (8-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-May-2026 18:50:45 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000302 | MM-ASK-1A-GEN01-INS-MOM-0006 | INSTRUMENT WEEKLY MEETING NO.6 (15-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-May-2026 12:10:09 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000482 | MM-ASK-1A-GEN01-INS-MOM-0007 | INSTRUMENT WEEKLY MEETING NO.7 (22-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Jun-2026 21:25:13 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000483 | MM-ASK-1A-GEN01-INS-MOM-0008 | INSTRUMENT WEEKLY MEETING NO.8 (29-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Jun-2026 21:25:37 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000497 | MM-ASK-1A-GEN01-INS-MOM-0009 | INSTRUMENT WEEKLY MEETING NO.9 (05-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 17-Jun-2026 14:18:45 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000591 | MM-ASK-1A-GEN01-INS-MOM-0010 | INSTRUMENT WEEKLY MEETING NO.10 (19-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 02-Jul-2026 12:03:48 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000698 | MM-ASK-1A-GEN01-INS-MOM-0011 | INSTRUMENT WEEKLY MEETING NO.11 (26-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 12:42:49 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000696 | MM-ASK-1A-GEN01-INS-MOM-0012 | INSTRUMENT WEEKLY MEETING NO.12 (03-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 11:34:08 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001088 | MM-ASK-1A-GEN01-INS-MOM-0015 | INSTRUMENT WEEKLY MEETING NO.15 (31-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Aug-2026 17:57:47 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001089 | MM-ASK-1A-GEN01-INS-MOM-0016 | INSTRUMENT WEEKLY MEETING NO.16 (14-AUG-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Aug-2026 17:58:14 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000092 | MM-ASK-1A-GEN01-INS-MR-0001 | MATERIAL REQUISITION FOR WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 28-Apr-2026 19:03:53 | zm167dc@jutal.com | 29-Apr-2026 10:02:06 | Jumpol Sudjitjul | 11-May-2026 |  | Payut Phatdamrongdet | 12-May-2026 | 12-May-2026 22:50:33 | Pornlert Wanaphattharaphan | 13-May-2026 | 15-May-2026 22:25:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 17-May-2026 00:01:08 | 17-May-2026 00:15:54 | 0 |  |  | Approver | Locate
AO-000508 | MM-ASK-1A-GEN01-INS-MR-0001 | MATERIAL REQUISITION FOR WELLHEAD CONTROL PANEL |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 19-Jun-2026 10:31:37 | zm167dc@jutal.com | 19-Jun-2026 10:36:01 | Jumpol Sudjitjul | 29-Jun-2026 | 26-Jun-2026 11:21:10 | Payut Phatdamrongdet | 30-Jun-2026 | 30-Jun-2026 10:01:05 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 01-Jul-2026 23:59:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 10:23:12 | 02-Jul-2026 04:30:51 | 0 |  |  | Approver | Locate
AO-000753 | MM-ASK-1A-GEN01-INS-MR-0001 | MATERIAL REQUISITION FOR WELLHEAD CONTROL PANEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 22-Jul-2026 10:16:17 | zm167dc@jutal.com | 22-Jul-2026 10:32:13 | Jumpol Sudjitjul | 03-Aug-2026 | 23-Jul-2026 17:35:32 | Payut Phatdamrongdet | 04-Aug-2026 | 24-Jul-2026 08:48:10 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 29-Jul-2026 09:02:06 | APPR | Approved | Jumpol Sudjitjul | 06-Aug-2026 | 30-Jul-2026 08:35:32 | 30-Jul-2026 01:57:18 | 0 |  |  | Approver | Locate
AO-000329 | MM-ASK-1A-GEN01-INS-MR-0002 | MATERIAL REQUISITION FOR SCADA |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 23-May-2026 08:39:47 | zm167dc@jutal.com | 23-May-2026 09:03:48 | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 18:08:21 | Payut Phatdamrongdet | 04-Jun-2026 | 08-Jun-2026 08:50:51 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 09-Jun-2026 09:44:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 10:25:43 | 09-Jun-2026 03:45:11 | 0 |  |  | Approver | Locate
AO-000727 | MM-ASK-1A-GEN01-INS-MR-0002 | MATERIAL REQUISITION FOR SCADA |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 09:50:44 | zm167dc@jutal.com | 20-Jul-2026 11:52:10 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:33:23 | Payut Phatdamrongdet | 31-Jul-2026 | 24-Jul-2026 08:42:12 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 27-Jul-2026 00:26:17 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 07:53:41 | 27-Jul-2026 01:14:06 | 0 |  |  | Approver | Locate
AO-001068 | MM-ASK-1A-GEN01-INS-MR-0002 | MATERIAL REQUISITION FOR SCADA |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:38:06 | zm167dc@jutal.com | 24-Aug-2026 18:31:44 | Jumpol Sudjitjul | 02-Sep-2026 | 25-Aug-2026 13:50:30 | Payut Phatdamrongdet | 03-Sep-2026 | 26-Aug-2026 11:49:12 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 00:06:58 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 15:32:30 | 30-Aug-2026 09:03:41 | 0 |  |  | Approver | Locate
AO-000322 | MM-ASK-1A-GEN01-INS-MR-0003 | MATERIAL REQUISITION FOR PLC SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 23-May-2026 08:40:10 | zm167dc@jutal.com | 23-May-2026 09:04:12 | Jumpol Sudjitjul | 02-Jun-2026 | 29-May-2026 11:45:32 | Payut Phatdamrongdet | 04-Jun-2026 | 08-Jun-2026 10:36:00 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 09-Jun-2026 09:45:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 10:26:53 | 09-Jun-2026 03:46:18 | 0 |  |  | Approver | Locate
AO-000705 | MM-ASK-1A-GEN01-INS-MR-0003 | MATERIAL REQUISITION FOR PLC SYSTEM |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 15-Jul-2026 18:41:53 | zm167dc@jutal.com | 15-Jul-2026 21:46:32 | Jumpol Sudjitjul | 24-Jul-2026 | 23-Jul-2026 17:13:28 | Payut Phatdamrongdet | 27-Jul-2026 | 24-Jul-2026 08:23:13 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 10:00:55 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 07:57:08 | 27-Jul-2026 01:15:18 | 0 |  |  | Approver | Locate
AO-000815 | MM-ASK-1A-GEN01-INS-MR-0003 | MATERIAL REQUISITION FOR PLC SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 30-Jul-2026 16:05:21 | zm167dc@jutal.com | 30-Jul-2026 16:38:42 | Jumpol Sudjitjul | 07-Aug-2026 |  | Payut Phatdamrongdet | 10-Aug-2026 | 31-Jul-2026 09:40:39 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 03-Aug-2026 00:20:02 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 03-Aug-2026 09:36:18 | 03-Aug-2026 03:08:52 | 0 |  |  | Approver | Locate
AO-000311 | MM-ASK-1A-GEN01-INS-MR-0004 | MATERIAL REQUISITION FOR CONTROL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 23-May-2026 08:40:33 | zm167dc@jutal.com | 23-May-2026 09:07:26 | Jumpol Sudjitjul | 02-Jun-2026 | 29-May-2026 17:33:25 | Payut Phatdamrongdet | 04-Jun-2026 | 08-Jun-2026 14:44:08 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 09-Jun-2026 09:47:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 10:28:26 | 09-Jun-2026 03:47:20 | 0 |  |  | Approver | Locate
AO-001038 | MM-ASK-1A-GEN01-INS-MR-0004 | MATERIAL REQUISITION FOR CONTROL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 16:07:15 | zm167dc@jutal.com | 20-Aug-2026 17:07:51 | Jumpol Sudjitjul | 31-Aug-2026 | 24-Aug-2026 13:41:14 | Payut Phatdamrongdet | 01-Sep-2026 | 26-Aug-2026 11:02:01 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:11:09 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 15:34:36 | 30-Aug-2026 09:04:52 | 0 |  |  | Approver | Locate
AO-000312 | MM-ASK-1A-GEN01-INS-MR-0005 | MATERIAL REQUISITION FOR SELF REGULATOR VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 23-May-2026 08:40:56 | zm167dc@jutal.com | 23-May-2026 09:08:56 | Jumpol Sudjitjul | 02-Jun-2026 | 02-Jun-2026 15:29:45 | Payut Phatdamrongdet | 04-Jun-2026 | 08-Jun-2026 16:15:28 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 09-Jun-2026 09:49:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 11:12:23 | 09-Jun-2026 04:22:11 | 0 |  |  | Approver | Locate
AO-001021 | MM-ASK-1A-GEN01-INS-MR-0005 | MATERIAL REQUISITION FOR SELF REGULATOR VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 15:54:46 | zm167dc@jutal.com | 19-Aug-2026 16:17:28 | Jumpol Sudjitjul | 27-Aug-2026 | 21-Aug-2026 16:20:49 | Payut Phatdamrongdet | 28-Aug-2026 | 26-Aug-2026 10:43:22 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 29-Aug-2026 23:21:44 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 15:37:04 | 30-Aug-2026 08:51:15 | 0 |  |  | Approver | Locate
AO-000313 | MM-ASK-1A-GEN01-INS-MR-0006 | MATERIAL REQUISITION FOR ACTUATED CHOKE VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 23-May-2026 08:41:19 | zm167dc@jutal.com | 23-May-2026 09:07:10 | Jumpol Sudjitjul | 02-Jun-2026 | 02-Jun-2026 15:27:41 | Payut Phatdamrongdet | 04-Jun-2026 | 08-Jun-2026 13:59:21 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 09-Jun-2026 09:46:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 10:35:51 | 09-Jun-2026 03:49:28 | 0 |  |  | Approver | Locate
AO-001014 | MM-ASK-1A-GEN01-INS-MR-0006 | MATERIAL REQUISITION FOR ACTUATED CHOKE VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 18-Aug-2026 16:15:05 | zm167dc@jutal.com | 18-Aug-2026 16:17:35 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:14:18 | Payut Phatdamrongdet | 27-Aug-2026 | 26-Aug-2026 10:39:13 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 29-Aug-2026 23:19:33 | APPR | Approved | Jumpol Sudjitjul | 31-Aug-2026 | 30-Aug-2026 15:40:49 | 30-Aug-2026 08:53:40 | 0 |  |  | Approver | Locate
AO-000408 | MM-ASK-1A-GEN01-INS-MR-0007 | MATERIAL REQUISITION FOR ACTUATED BALL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 13:02:45 | zm167dc@jutal.com | 05-Jun-2026 13:54:01 | Jumpol Sudjitjul | 15-Jun-2026 | 10-Jun-2026 15:38:37 | Payut Phatdamrongdet | 16-Jun-2026 | 11-Jun-2026 17:38:31 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 13-Jun-2026 00:51:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 13-Jun-2026 07:05:13 | 13-Jun-2026 00:31:15 | 0 |  |  | Approver | Locate
AO-001128 | MM-ASK-1A-GEN01-INS-MR-0007 | MATERIAL REQUISITION FOR ACTUATED BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:47:13 | zm167dc@jutal.com | 28-Aug-2026 17:30:21 | Jumpol Sudjitjul | 08-Sep-2026 | 01-Sep-2026 11:07:26 | Payut Phatdamrongdet | 09-Sep-2026 | 04-Sep-2026 10:51:16 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 05-Sep-2026 23:48:03 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 06-Sep-2026 09:18:09 | 06-Sep-2026 02:54:47 | 0 |  |  | Approver | Locate
AO-001252 | MM-ASK-1A-GEN01-INS-MR-0007 | MATERIAL REQUISITION FOR ACTUATED BALL VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 14:44:16 | zm167dc@jutal.com | 09-Sep-2026 16:54:24 | Jumpol Sudjitjul | 17-Sep-2026 |  | Payut Phatdamrongdet | 18-Sep-2026 | 11-Sep-2026 18:05:39 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 13-Sep-2026 22:49:14 | APPR | Approved | Jumpol Sudjitjul | 22-Sep-2026 | 13-Sep-2026 22:51:08 | 13-Sep-2026 17:04:58 | 0 |  |  | Approver | Locate
AO-000360 | MM-ASK-1A-GEN01-INS-MR-0008 | MATERIAL REQUISITION FOR ACTUATED COMPACT BALL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 27-May-2026 14:44:11 | zm167dc@jutal.com | 27-May-2026 15:11:18 | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 17:25:54 | Payut Phatdamrongdet | 09-Jun-2026 | 10-Jun-2026 15:34:54 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:29:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 08:04:12 | 11-Jun-2026 01:09:47 | 0 |  |  | Approver | Locate
AO-001026 | MM-ASK-1A-GEN01-INS-MR-0008 | MATERIAL REQUISITION FOR ACTUATED COMPACT BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 15:55:19 | zm167dc@jutal.com | 19-Aug-2026 16:17:48 | Jumpol Sudjitjul | 27-Aug-2026 | 21-Aug-2026 16:38:41 | Payut Phatdamrongdet | 28-Aug-2026 | 26-Aug-2026 10:52:18 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 29-Aug-2026 23:22:20 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 15:43:16 | 30-Aug-2026 08:54:52 | 0 |  |  | Approver | Locate
AO-000490 | MM-ASK-1A-GEN01-INS-MR-0009 | MATERIAL REQUISITION FOR SAFETY RELIEF VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 16-Jun-2026 19:24:39 | zm167dc@jutal.com | 17-Jun-2026 08:52:13 | Jumpol Sudjitjul | 25-Jun-2026 | 26-Jun-2026 10:23:04 | Payut Phatdamrongdet | 26-Jun-2026 | 29-Jun-2026 08:54:21 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 30-Jun-2026 22:15:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 01-Jul-2026 08:38:26 | 01-Jul-2026 02:14:21 | 0 |  |  | Approver | Locate
AO-001183 | MM-ASK-1A-GEN01-INS-MR-0009 | MATERIAL REQUISITION FOR SAFETY RELIEF VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 18:07:02 | zm167dc@jutal.com | 04-Sep-2026 11:29:30 | Jumpol Sudjitjul | 14-Sep-2026 |  | Payut Phatdamrongdet | 15-Sep-2026 | 04-Sep-2026 13:34:45 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 04-Sep-2026 23:46:48 | APPR | Approved | Jumpol Sudjitjul | 17-Sep-2026 | 05-Sep-2026 17:51:54 | 05-Sep-2026 11:48:10 | 0 |  |  | Approver | Locate
AO-000548 | MM-ASK-1A-GEN01-INS-MR-0010 | MATERIAL REQUISITION FOR CORIOLIS FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 14:21:50 | zm167dc@jutal.com | 25-Jun-2026 15:25:54 | Jumpol Sudjitjul | 03-Jul-2026 | 09-Jul-2026 15:22:06 | Payut Phatdamrongdet | 06-Jul-2026 | 15-Jul-2026 11:29:44 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 16-Jul-2026 22:07:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jul-2026 | 17-Jul-2026 08:15:30 | 17-Jul-2026 02:09:02 | 0 |  |  | Approver | Locate
AO-001252 | MM-ASK-1A-GEN01-INS-MR-0010 | MATERIAL REQUISITION FOR CORIOLIS FLOW METERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 14:44:47 | zm167dc@jutal.com | 09-Sep-2026 16:54:48 | Jumpol Sudjitjul | 17-Sep-2026 |  | Payut Phatdamrongdet | 18-Sep-2026 | 11-Sep-2026 18:06:16 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 13-Sep-2026 22:50:57 | APPR | Approved | Jumpol Sudjitjul | 22-Sep-2026 | 13-Sep-2026 22:53:25 | 13-Sep-2026 17:06:12 | 0 |  |  | Approver | Locate
AO-000538 | MM-ASK-1A-GEN01-INS-MR-0011 | MATERIAL REQUISITION FOR VORTEX FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 24-Jun-2026 13:14:54 | zm167dc@jutal.com | 24-Jun-2026 14:29:58 | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 14:39:02 | Payut Phatdamrongdet | 03-Jul-2026 | 07-Jul-2026 09:10:56 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 08-Jul-2026 00:00:47 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Jul-2026 | 08-Jul-2026 08:27:23 | 08-Jul-2026 02:38:47 | 0 |  |  | Approver | Locate
AO-001276 | MM-ASK-1A-GEN01-INS-MR-0011 | MATERIAL REQUISITION FOR VORTEX FLOW METERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 13:19:26 | zm167dc@jutal.com | 10-Sep-2026 16:19:59 | Jumpol Sudjitjul | 18-Sep-2026 |  | Payut Phatdamrongdet | 21-Sep-2026 | 11-Sep-2026 18:07:33 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 13-Sep-2026 22:56:11 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 13-Sep-2026 22:58:22 | 13-Sep-2026 17:11:25 | 0 |  |  | Approver | Locate
AO-000816 | MM-ASK-1A-GEN01-INS-MR-0013 | MATERIAL REQUISITION FOR PRESSURE GAUGES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 16:51:18 | zm167dc@jutal.com | 30-Jul-2026 17:01:03 | Jumpol Sudjitjul | 07-Aug-2026 |  | Payut Phatdamrongdet | 10-Aug-2026 | 31-Jul-2026 21:37:16 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 03-Aug-2026 00:19:13 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 13-Aug-2026 | 03-Aug-2026 09:37:40 | 03-Aug-2026 02:48:19 | 0 |  |  | Approver | Locate
AO-000885 | MM-ASK-1A-GEN01-INS-MR-0014 | MATERIAL REQUISITION FOR PRESSURE TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:49:58 | zm167dc@jutal.com | 05-Aug-2026 11:57:58 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 23:30:31 | Payut Phatdamrongdet | 17-Aug-2026 | 17-Aug-2026 13:40:45 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 17-Aug-2026 21:11:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 18-Aug-2026 08:01:34 | 18-Aug-2026 01:30:57 | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-GEN01-INS-MR-0015 | MATERIAL REQUISITION FOR TEMPERATURE GAUGES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 18:35:41 | zm167dc@jutal.com | 06-Aug-2026 14:17:24 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:10:17 | Payut Phatdamrongdet | 18-Aug-2026 | 24-Aug-2026 11:04:31 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 25-Aug-2026 22:30:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 26-Aug-2026 08:47:14 | 26-Aug-2026 01:54:20 | 0 |  |  | Approver | Locate
AO-000873 | MM-ASK-1A-GEN01-INS-MR-0016 | MATERIAL REQUISITION FOR TEMPERATURE TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 04-Aug-2026 15:25:02 | zm167dc@jutal.com | 04-Aug-2026 15:34:22 | Jumpol Sudjitjul | 13-Aug-2026 | 05-Aug-2026 13:55:35 | Payut Phatdamrongdet | 14-Aug-2026 | 17-Aug-2026 10:52:17 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 17-Aug-2026 21:12:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 18-Aug-2026 08:03:39 | 18-Aug-2026 01:25:34 | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-GEN01-INS-MR-0017 | MATERIAL REQUISITION FOR LEVEL GAUGE AND TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 30-Jun-2026 14:52:28 | zm167dc@jutal.com | 30-Jun-2026 16:11:24 | Jumpol Sudjitjul | 08-Jul-2026 | 09-Jul-2026 15:23:42 | Payut Phatdamrongdet | 09-Jul-2026 | 20-Jul-2026 09:19:58 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 22-Jul-2026 13:08:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 22-Jul-2026 13:18:18 | 22-Jul-2026 06:55:00 | 0 |  |  | Approver | Locate
AO-001287 | MM-ASK-1A-GEN01-INS-MR-0017 | MATERIAL REQUISITION FOR LEVEL GAUGE AND TRANSMITTERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 18:04:15 | zm167dc@jutal.com | 10-Sep-2026 19:56:53 | Jumpol Sudjitjul | 21-Sep-2026 |  | Payut Phatdamrongdet | 22-Sep-2026 | 11-Sep-2026 18:09:17 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 13-Sep-2026 22:54:01 | APPR | Approved | Jumpol Sudjitjul | 24-Sep-2026 | 13-Sep-2026 22:57:43 | 13-Sep-2026 17:10:10 | 0 |  |  | Approver | Locate
AO-000971 | MM-ASK-1A-GEN01-INS-MR-0019 | MATERIAL REQUISITION FOR LEVEL SWITCH |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:38:33 | zm167dc@jutal.com | 14-Aug-2026 08:51:49 | Jumpol Sudjitjul | 24-Aug-2026 | 23-Aug-2026 23:16:45 | Payut Phatdamrongdet | 25-Aug-2026 | 26-Aug-2026 09:28:24 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 21:20:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 09:24:54 | 28-Aug-2026 02:42:54 | 0 |  |  | Approver | Locate
AO-000589 | MM-ASK-1A-GEN01-INS-MR-0020 | MATERIAL REQUISITION FOR GUIDED WAVE RADAR LEVEL TRANSMITTER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 18:34:19 | zm167dc@jutal.com | 02-Jul-2026 14:27:11 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:27:43 | Payut Phatdamrongdet | 13-Jul-2026 | 20-Jul-2026 16:37:51 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 22-Jul-2026 22:39:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 23-Jul-2026 13:12:33 | 23-Jul-2026 06:22:32 | 0 |  |  | Approver | Locate
AO-000975 | MM-ASK-1A-GEN01-INS-MR-0021 | MATERIAL REQUISITION FOR DP LEVEL TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 11:29:02 | zm167dc@jutal.com | 14-Aug-2026 12:59:31 | Jumpol Sudjitjul | 24-Aug-2026 |  | Payut Phatdamrongdet | 25-Aug-2026 | 26-Aug-2026 10:24:16 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 22:23:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 09:23:22 | 28-Aug-2026 03:07:28 | 0 |  |  | Approver | Locate
AO-001047 | MM-ASK-1A-GEN01-INS-MR-0022 | MATERIAL REQUISITION FOR INSTRUMENT CABLES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 09:34:26 | zm167dc@jutal.com | 21-Aug-2026 13:45:01 | Jumpol Sudjitjul | 31-Aug-2026 | 25-Aug-2026 13:41:18 | Payut Phatdamrongdet | 01-Sep-2026 | 26-Aug-2026 12:27:52 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:13:52 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 15:28:39 | 30-Aug-2026 09:01:10 | 0 |  |  | Approver | Locate
AO-000624 | MM-ASK-1A-GEN01-INS-MR-0023 | MATERIAL REQUISITION FOR RESTRICTION ORIFICE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 18:36:49 | zm167dc@jutal.com | 03-Jul-2026 19:07:45 | Jumpol Sudjitjul | 14-Jul-2026 | 17-Jul-2026 10:50:13 | Payut Phatdamrongdet | 15-Jul-2026 | 20-Jul-2026 17:54:17 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 22-Jul-2026 22:56:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 23-Jul-2026 13:12:01 | 23-Jul-2026 06:24:02 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-GEN01-INS-MR-0024 | MATERIAL REQUISITION FOR FIRE & GAS DETECTORS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:03:08 | zm167dc@jutal.com | 06-Aug-2026 14:17:48 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:10:33 | Payut Phatdamrongdet | 18-Aug-2026 | 24-Aug-2026 12:03:56 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 25-Aug-2026 22:31:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 26-Aug-2026 08:46:29 | 26-Aug-2026 02:11:09 | 0 |  |  | Approver | Locate
AO-000975 | MM-ASK-1A-GEN01-INS-MR-0025 | MATERIAL REQUISITION FOR POSITION LIMIT SWITCHES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 11:29:28 | zm167dc@jutal.com | 14-Aug-2026 12:59:50 | Jumpol Sudjitjul | 24-Aug-2026 |  | Payut Phatdamrongdet | 25-Aug-2026 | 26-Aug-2026 10:38:01 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 22:24:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 09:22:24 | 28-Aug-2026 03:06:01 | 0 |  |  | Approver | Locate
AO-000582 | MM-ASK-1A-GEN01-INS-MR-0026 | MATERIAL REQUISITION FOR OIL IN WATER ANALYZER - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 11:50:09 | zm167dc@jutal.com | 01-Jul-2026 14:35:00 | Jumpol Sudjitjul | 09-Jul-2026 | 03-Jul-2026 15:23:44 | Payut Phatdamrongdet | 10-Jul-2026 | 20-Jul-2026 11:25:17 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 22-Jul-2026 19:36:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 23-Jul-2026 13:26:00 | 23-Jul-2026 06:48:50 | 0 |  |  | Approver | Locate
AO-001103 | MM-ASK-1A-GEN01-INS-MR-0026 | MATERIAL REQUISITION FOR OIL IN WATER ANALYZER - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:17:08 | zm167dc@jutal.com | 27-Aug-2026 09:20:38 | Jumpol Sudjitjul | 04-Sep-2026 |  | Payut Phatdamrongdet | 07-Sep-2026 | 27-Aug-2026 13:49:17 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 30-Aug-2026 18:35:28 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 30-Aug-2026 21:16:00 | 30-Aug-2026 14:26:41 | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-GEN01-INS-MR-0027 | MATERIAL REQUISITION FOR PIG SIGNALLER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 18:36:08 | zm167dc@jutal.com | 06-Aug-2026 14:18:07 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:10:50 | Payut Phatdamrongdet | 18-Aug-2026 | 24-Aug-2026 14:33:24 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 25-Aug-2026 22:33:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 26-Aug-2026 08:48:00 | 26-Aug-2026 01:55:39 | 0 |  |  | Approver | Locate
AO-000060 | MM-ASK-1A-GEN01-INS-PHI-0001 | INSTRUMENT / CONTROL AND SAFETY SYSTEM PHILOSOPHY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:03:06 | zm167dc@jutal.com | 25-Apr-2026 09:16:17 | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 17:57:15 | Payut Phatdamrongdet | 07-May-2026 | 12-May-2026 10:49:21 | Pornlert Wanaphattharaphan | 08-May-2026 | 12-May-2026 23:16:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 13-May-2026 08:26:09 | 13-May-2026 08:34:03 | 0 |  |  | Approver | Locate
AO-000285 | MM-ASK-1A-GEN01-INS-PHI-0001 | INSTRUMENT / CONTROL AND SAFETY SYSTEM PHILOSOPHY |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | PHI | Philosophy | 0 | Submitted | IFA | Issued for Approval |  | 19-May-2026 14:58:53 | zm167dc@jutal.com | 19-May-2026 15:44:41 | Jumpol Sudjitjul | 27-May-2026 | 28-May-2026 20:32:18 | Payut Phatdamrongdet | 28-May-2026 | 29-May-2026 17:35:39 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 21:00:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 08:04:58 | 11-Jun-2026 01:17:56 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-GEN01-INS-PHI-0001 | INSTRUMENT / CONTROL AND SAFETY SYSTEM PHILOSOPHY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | PHI | Philosophy | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:50:52 | zm167dc@jutal.com | 07-Aug-2026 10:50:31 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:13:19 | Payut Phatdamrongdet | 19-Aug-2026 | 24-Aug-2026 15:01:53 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 27-Aug-2026 14:26:08 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 27-Aug-2026 14:40:47 | 27-Aug-2026 08:54:45 | 0 |  |  | Approver | Locate
AO-000065 | MM-ASK-1A-GEN01-INS-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR SCADA SYSTEMS AND PLC GATEWAY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:03:30 | zm167dc@jutal.com | 25-Apr-2026 09:18:16 | Jumpol Sudjitjul | 06-May-2026 | 28-Apr-2026 16:46:02 | Payut Phatdamrongdet | 07-May-2026 | 11-May-2026 15:21:49 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:05:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 08:41:50 | 12-May-2026 09:11:59 | 0 |  |  | Approver | Locate
AO-000385 | MM-ASK-1A-GEN01-INS-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR SCADA SYSTEMS AND PLC GATEWAY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 29-May-2026 18:50:28 | zm167dc@jutal.com | 29-May-2026 19:11:48 | Jumpol Sudjitjul | 11-Jun-2026 | 10-Jun-2026 15:21:36 | Payut Phatdamrongdet | 12-Jun-2026 | 11-Jun-2026 10:09:17 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 13-Jun-2026 23:30:01 | APPR | Approved | Jumpol Sudjitjul | 16-Jun-2026 | 14-Jun-2026 21:45:04 | 14-Jun-2026 15:12:20 | 0 |  |  | Approver | Locate
AO-000061 | MM-ASK-1A-GEN01-INS-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR PLC SYSTEMS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:03:54 | zm167dc@jutal.com | 25-Apr-2026 09:18:34 | Jumpol Sudjitjul | 06-May-2026 | 28-Apr-2026 17:06:12 | Payut Phatdamrongdet | 07-May-2026 | 11-May-2026 15:58:05 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:06:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 08:47:23 | 12-May-2026 09:13:07 | 0 |  |  | Approver | Locate
AO-000410 | MM-ASK-1A-GEN01-INS-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR PLC SYSTEMS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 05-Jun-2026 13:47:41 | zm167dc@jutal.com | 05-Jun-2026 13:59:44 | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 13:05:07 | Payut Phatdamrongdet | 16-Jun-2026 | 15-Jun-2026 10:32:50 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 15-Jun-2026 22:54:16 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 16-Jun-2026 09:40:01 | 16-Jun-2026 03:36:12 | 0 |  |  | Approver | Locate
AO-000062 | MM-ASK-1A-GEN01-INS-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:04:16 | zm167dc@jutal.com | 25-Apr-2026 09:18:47 | Jumpol Sudjitjul | 06-May-2026 | 29-Apr-2026 10:12:37 | Payut Phatdamrongdet | 07-May-2026 | 07-May-2026 17:29:08 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:27:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:01:30 | 09-May-2026 08:05:18 | 0 |  |  | Approver | Locate
AO-000300 | MM-ASK-1A-GEN01-INS-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR WELLHEAD CONTROL PANEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 21-May-2026 08:56:51 | zm167dc@jutal.com | 21-May-2026 18:22:49 | Jumpol Sudjitjul | 02-Jun-2026 | 27-May-2026 18:01:17 | Payut Phatdamrongdet | 04-Jun-2026 | 05-Jun-2026 17:13:16 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:09:10 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 08:06:27 | 11-Jun-2026 01:23:56 | 0 |  |  | Approver | Locate
AO-000063 | MM-ASK-1A-GEN01-INS-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR INSTRUMENT FOR MEASUREMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:04:40 | zm167dc@jutal.com | 25-Apr-2026 09:20:04 | Jumpol Sudjitjul | 06-May-2026 | 27-Apr-2026 20:04:50 | Payut Phatdamrongdet | 07-May-2026 | 12-May-2026 13:36:53 | Pornlert Wanaphattharaphan | 08-May-2026 | 12-May-2026 23:46:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 13-May-2026 08:28:36 | 13-May-2026 01:35:15 | 0 |  |  | Approver | Locate
AO-000377 | MM-ASK-1A-GEN01-INS-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR INSTRUMENT FOR MEASUREMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 29-May-2026 10:49:34 | zm167dc@jutal.com | 29-May-2026 11:16:44 | Jumpol Sudjitjul | 10-Jun-2026 | 10-Jun-2026 15:13:53 | Payut Phatdamrongdet | 11-Jun-2026 | 10-Jun-2026 15:45:23 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:33:30 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:00:54 | 11-Jun-2026 02:44:55 | 0 |  |  | Approver | Locate
AO-000064 | MM-ASK-1A-GEN01-INS-SPE-0005 | PROJECT PARTICULAR SPECIFICATION FOR INSTRUMENT CABLES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:05:06 | zm167dc@jutal.com | 25-Apr-2026 09:19:52 | Jumpol Sudjitjul | 06-May-2026 |  | Payut Phatdamrongdet | 07-May-2026 | 11-May-2026 17:22:39 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:13:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 08:51:11 | 12-May-2026 09:14:20 | 0 |  |  | Approver | Locate
AO-000380 | MM-ASK-1A-GEN01-INS-SPE-0005 | PROJECT PARTICULAR SPECIFICATION FOR INSTRUMENT CABLES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 29-May-2026 14:05:13 | zm167dc@jutal.com | 29-May-2026 15:07:42 | Jumpol Sudjitjul | 10-Jun-2026 | 10-Jun-2026 15:19:36 | Payut Phatdamrongdet | 11-Jun-2026 | 10-Jun-2026 15:46:22 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:33:44 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 08:08:48 | 11-Jun-2026 02:07:53 | 0 |  |  | Approver | Locate
AO-000101 | MM-ASK-1A-GEN01-INS-SPE-0006 | PROJECT PARTICULAR SPECIFICATION FOR INSTRUMENT BULK MATERIAL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 14:53:33 | zm167dc@jutal.com | 30-Apr-2026 16:18:12 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 11:55:48 | Payut Phatdamrongdet | 13-May-2026 | 18-May-2026 08:58:09 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 20:34:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:31:59 | 20-May-2026 08:48:55 | 0 |  |  | Approver | Locate
AO-000434 | MM-ASK-1A-GEN01-INS-SPE-0006 | PROJECT PARTICULAR SPECIFICATION FOR INSTRUMENT BULK MATERIAL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 09-Jun-2026 17:10:48 | zm167dc@jutal.com | 10-Jun-2026 09:25:45 | Jumpol Sudjitjul | 18-Jun-2026 | 12-Jun-2026 13:11:43 | Payut Phatdamrongdet | 19-Jun-2026 | 16-Jun-2026 13:53:14 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 17-Jun-2026 00:29:14 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 17-Jun-2026 08:14:27 | 17-Jun-2026 01:52:47 | 0 |  |  | Approver | Locate
AO-000102 | MM-ASK-1A-GEN01-INS-SPE-0007 | PROJECT PARTICULAR SPECIFICATION FOR ACTUATED CHOKE VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 14:54:00 | zm167dc@jutal.com | 30-Apr-2026 16:18:32 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 14:45:12 | Payut Phatdamrongdet | 13-May-2026 | 18-May-2026 09:53:40 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 20:34:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:33:10 | 20-May-2026 08:50:04 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-GEN01-INS-SPE-0007 | PROJECT PARTICULAR SPECIFICATION FOR ACTUATED CHOKE VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 13-Jun-2026 08:07:26 | zm167dc@jutal.com | 13-Jun-2026 08:18:06 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 16-Jun-2026 15:29:16 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 17-Jun-2026 00:46:41 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 17-Jun-2026 08:15:23 | 17-Jun-2026 01:53:57 | 0 |  |  | Approver | Locate
AO-000129 | MM-ASK-1A-GEN01-INS-SPE-0008 | PROJECT PARTICULAR SPECIFICATION FOR ACTUATED BALL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:02:40 | zm167dc@jutal.com | 06-May-2026 11:22:46 | Jumpol Sudjitjul | 14-May-2026 | 19-May-2026 14:45:32 | Payut Phatdamrongdet | 15-May-2026 | 20-May-2026 08:28:54 | Pornlert Wanaphattharaphan | 18-May-2026 | 21-May-2026 21:17:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 21-May-2026 21:20:08 | 21-May-2026 22:18:04 | 0 |  |  | Approver | Locate
AO-000471 | MM-ASK-1A-GEN01-INS-SPE-0008 | PROJECT PARTICULAR SPECIFICATION FOR ACTUATED BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 18:00:59 | zm167dc@jutal.com | 13-Jun-2026 07:14:31 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 16-Jun-2026 14:27:59 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 17-Jun-2026 00:45:07 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 17-Jun-2026 08:16:03 | 17-Jun-2026 01:55:14 | 0 |  |  | Approver | Locate
AO-000130 | MM-ASK-1A-GEN01-INS-SPE-0009 | PROJECT PARTICULAR SPECIFICATION FOR ACUATED COMPACT BALL VALVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:03:11 | zm167dc@jutal.com | 06-May-2026 11:22:31 | Jumpol Sudjitjul | 14-May-2026 | 19-May-2026 14:45:14 | Payut Phatdamrongdet | 15-May-2026 | 19-May-2026 15:04:10 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 23:24:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 20-May-2026 08:34:49 | 20-May-2026 08:51:09 | 0 |  |  | Approver | Locate
AO-000466 | MM-ASK-1A-GEN01-INS-SPE-0009 | PROJECT PARTICULAR SPECIFICATION FOR ACUATED COMPACT BALL VALVE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 14:46:04 | zm167dc@jutal.com | 12-Jun-2026 15:40:13 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 16-Jun-2026 14:15:11 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 17-Jun-2026 00:40:53 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 17-Jun-2026 08:16:33 | 17-Jun-2026 01:56:22 | 0 |  |  | Approver | Locate
AO-000157 | MM-ASK-1A-GEN01-INS-SPE-0010 | PROJECT PARTICULAR SPECIFICATION FOR CONTROL VALVES AND SELF ACTUATED PCV |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 08:46:05 | zm167dc@jutal.com | 08-May-2026 09:40:25 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 15:54:30 | Payut Phatdamrongdet | 19-May-2026 | 20-May-2026 10:09:46 | Pornlert Wanaphattharaphan | 20-May-2026 | 22-May-2026 01:56:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 22-May-2026 08:18:20 | 22-May-2026 08:47:01 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-GEN01-INS-SPE-0010 | PROJECT PARTICULAR SPECIFICATION FOR CONTROL VALVES AND SELF ACTUATED PCV |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 13-Jun-2026 08:07:53 | zm167dc@jutal.com | 13-Jun-2026 08:18:33 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 16-Jun-2026 15:30:01 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 17-Jun-2026 00:50:44 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 17-Jun-2026 08:16:56 | 17-Jun-2026 02:33:08 | 0 |  |  | Approver | Locate
AO-000131 | MM-ASK-1A-GEN01-INS-SPE-0011 | PROJECT PARTICULAR SPECIFICATION FOR RELIEF VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:03:39 | zm167dc@jutal.com | 06-May-2026 11:22:16 | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 14:32:35 | Payut Phatdamrongdet | 15-May-2026 | 19-May-2026 14:14:53 | Pornlert Wanaphattharaphan | 18-May-2026 | 21-May-2026 21:45:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 22-May-2026 08:19:44 | 22-May-2026 08:39:06 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-GEN01-INS-SPE-0011 | PROJECT PARTICULAR SPECIFICATION FOR RELIEF VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:05:26 | zm167dc@jutal.com | 12-Jun-2026 12:49:28 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 16-Jun-2026 14:14:08 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 17-Jun-2026 00:37:16 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 17-Jun-2026 08:17:20 | 17-Jun-2026 02:34:16 | 0 |  |  | Approver | Locate
AO-000132 | MM-ASK-1A-GEN01-INS-SPE-0012 | PROJECT PARTICULAR SPECIFICATION FOR CORIOLIS FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:04:04 | zm167dc@jutal.com | 06-May-2026 11:21:56 | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 14:31:30 | Payut Phatdamrongdet | 15-May-2026 | 19-May-2026 13:26:25 | Pornlert Wanaphattharaphan | 18-May-2026 | 21-May-2026 21:30:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 21-May-2026 21:32:02 | 21-May-2026 22:19:07 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-GEN01-INS-SPE-0012 | PROJECT PARTICULAR SPECIFICATION FOR CORIOLIS FLOW METERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 10-Jun-2026 15:55:42 | zm167dc@jutal.com | 10-Jun-2026 16:10:54 | Jumpol Sudjitjul | 18-Jun-2026 |  | Payut Phatdamrongdet | 19-Jun-2026 | 16-Jun-2026 13:58:38 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 17-Jun-2026 00:30:00 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 17-Jun-2026 08:16:48 | 17-Jun-2026 01:57:29 | 0 |  |  | Approver | Locate
AO-000158 | MM-ASK-1A-GEN01-INS-SPE-0013 | PROJECT PARTICULAR SPECIFICATION FOR VORTEX FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 08:46:29 | zm167dc@jutal.com | 08-May-2026 09:40:50 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 15:46:39 | Payut Phatdamrongdet | 19-May-2026 | 20-May-2026 10:42:41 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 17:26:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 19:53:48 | 24-May-2026 20:01:09 | 0 |  |  | Approver | Locate
AO-000411 | MM-ASK-1A-GEN01-INS-SPE-0013 | PROJECT PARTICULAR SPECIFICATION FOR VORTEX FLOW METERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 05-Jun-2026 14:37:04 | zm167dc@jutal.com | 05-Jun-2026 15:01:38 | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 13:18:29 | Payut Phatdamrongdet | 16-Jun-2026 | 15-Jun-2026 10:35:58 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 15-Jun-2026 22:56:12 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 16-Jun-2026 09:41:19 | 16-Jun-2026 03:52:56 | 0 |  |  | Approver | Locate
AO-000216 | MM-ASK-1A-GEN01-INS-SPE-0014 | PROJECT PARTICULAR SPECIFICATION FOR FIRE & GAS DETECTORS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 16:11:29 | zm167dc@jutal.com | 12-May-2026 11:14:04 | Jumpol Sudjitjul | 20-May-2026 | 20-May-2026 11:05:45 | Payut Phatdamrongdet | 21-May-2026 | 21-May-2026 09:04:26 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:00:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 16:26:16 | 31-May-2026 16:49:36 | 0 |  |  | Approver | Locate
AO-000413 | MM-ASK-1A-GEN01-INS-SPE-0014 | PROJECT PARTICULAR SPECIFICATION FOR FIRE & GAS DETECTORS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 05-Jun-2026 14:37:33 | zm167dc@jutal.com | 05-Jun-2026 15:02:12 | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 13:17:00 | Payut Phatdamrongdet | 16-Jun-2026 | 15-Jun-2026 10:37:10 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 15-Jun-2026 22:57:27 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 16-Jun-2026 09:41:42 | 16-Jun-2026 03:53:56 | 0 |  |  | Approver | Locate
AO-000159 | MM-ASK-1A-GEN01-INS-SPE-0015 | PROJECT PARTICULAR SPECIFICATION FOR INSTALLATION OF INSTRUMENTAION AND CONTROL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 08:46:55 | zm167dc@jutal.com | 08-May-2026 09:41:13 | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 10:51:23 | Payut Phatdamrongdet | 19-May-2026 | 20-May-2026 12:31:35 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 19:32:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 19:55:32 | 24-May-2026 20:02:14 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-GEN01-INS-SPE-0015 | PROJECT PARTICULAR SPECIFICATION FOR INSTALLATION OF INSTRUMENTAION AND CONTROL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 13-Jun-2026 08:08:19 | zm167dc@jutal.com | 13-Jun-2026 08:19:01 | Jumpol Sudjitjul | 22-Jun-2026 | 03-Jul-2026 14:51:28 | Payut Phatdamrongdet | 23-Jun-2026 | 16-Jun-2026 15:31:36 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 17-Jun-2026 00:55:07 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 17-Jun-2026 08:17:47 | 17-Jun-2026 02:35:27 | 0 |  |  | Approver | Locate
AO-000811 | MM-ASK-1A-GEN01-INS-TBE-0001 | TECHNICAL BID EVALUATION FOR SCADA |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 30-Jul-2026 08:37:03 | zm167dc@jutal.com | 30-Jul-2026 09:54:03 | Jumpol Sudjitjul | 07-Aug-2026 |  | Payut Phatdamrongdet | 10-Aug-2026 | 31-Jul-2026 09:33:51 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 02-Aug-2026 13:13:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 02-Aug-2026 20:59:28 | 02-Aug-2026 14:49:06 | 0 |  |  | Approver | Locate
AO-000974 | MM-ASK-1A-GEN01-INS-TBE-0001 | TECHNICAL BID EVALUATION FOR SCADA |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 11:29:56 | zm167dc@jutal.com | 14-Aug-2026 12:49:39 | Jumpol Sudjitjul | 24-Aug-2026 |  | Payut Phatdamrongdet | 25-Aug-2026 | 14-Aug-2026 15:34:37 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 16-Aug-2026 17:50:06 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 17-Aug-2026 08:24:08 | 17-Aug-2026 02:23:58 | 0 |  |  | Approver | Locate
AO-000616 | MM-ASK-1A-GEN01-INS-TBE-0002 | TECHNICAL BID EVALUATION FOR WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 18:12:34 | zm167dc@jutal.com | 03-Jul-2026 18:30:18 | Jumpol Sudjitjul | 14-Jul-2026 | 07-Jul-2026 15:11:36 | Payut Phatdamrongdet | 15-Jul-2026 | 07-Jul-2026 16:21:58 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 07-Jul-2026 23:19:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 08-Jul-2026 08:28:28 | 08-Jul-2026 02:25:53 | 0 |  |  | Approver | Locate
AO-000727 | MM-ASK-1A-GEN01-INS-TBE-0002 | TECHNICAL BID EVALUATION FOR WELLHEAD CONTROL PANEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:51:24 | zm167dc@jutal.com | 20-Jul-2026 11:57:08 | Jumpol Sudjitjul | 30-Jul-2026 |  | Payut Phatdamrongdet | 31-Jul-2026 | 20-Jul-2026 23:39:41 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 20-Jul-2026 23:56:42 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 21-Jul-2026 07:43:51 | 22-Jul-2026 09:48:36 | 0 |  |  | Approver | Locate
AO-000679 | MM-ASK-1A-GEN01-INS-TBE-0003 | TECHNICAL BID EVALUATION FOR PLC SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 17:24:08 | zm167dc@jutal.com | 10-Jul-2026 17:58:43 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:27:13 | Payut Phatdamrongdet | 22-Jul-2026 | 15-Jul-2026 09:47:53 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 16-Jul-2026 14:28:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 16-Jul-2026 15:34:21 | 16-Jul-2026 08:56:40 | 0 |  |  | Approver | Locate
AO-000743 | MM-ASK-1A-GEN01-INS-TBE-0003 | TECHNICAL BID EVALUATION FOR PLC SYSTEM |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 08:34:24 | zm167dc@jutal.com | 21-Jul-2026 09:16:52 | Jumpol Sudjitjul | 31-Jul-2026 |  | Payut Phatdamrongdet | 03-Aug-2026 | 22-Jul-2026 08:47:14 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 22-Jul-2026 17:00:32 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 22-Jul-2026 17:02:34 | 22-Jul-2026 10:48:02 | 0 |  |  | Approver | Locate
AO-000996 | MM-ASK-1A-GEN01-INS-TBE-0004 | TECHNICAL BID EVALUATION FOR CONTROL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 18:11:29 | zm167dc@jutal.com | 15-Aug-2026 15:01:12 | Jumpol Sudjitjul | 24-Aug-2026 |  | Payut Phatdamrongdet | 25-Aug-2026 | 17-Aug-2026 08:54:10 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 18-Aug-2026 21:46:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 19-Aug-2026 09:46:44 | 19-Aug-2026 03:07:13 | 0 |  |  | Approver | Locate
AO-001058 | MM-ASK-1A-GEN01-INS-TBE-0004 | TECHNICAL BID EVALUATION FOR CONTROL VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 16:44:05 | zm167dc@jutal.com | 21-Aug-2026 17:16:51 | Jumpol Sudjitjul | 01-Sep-2026 |  | Payut Phatdamrongdet | 02-Sep-2026 | 24-Aug-2026 09:27:28 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 26-Aug-2026 00:44:42 | APPR | Approved | Jumpol Sudjitjul | 04-Sep-2026 | 26-Aug-2026 08:52:33 | 26-Aug-2026 02:45:54 | 0 |  |  | Approver | Locate
AO-001097 | MM-ASK-1A-GEN01-INS-TBE-0004A | TECHNICAL BID EVALUATION FOR CONTROL VALVES LOT 2 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 25-Aug-2026 19:47:42 | zm167dc@jutal.com | 26-Aug-2026 09:32:54 | Jumpol Sudjitjul | 03-Sep-2026 |  | Payut Phatdamrongdet | 04-Sep-2026 | 28-Aug-2026 14:53:57 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 29-Aug-2026 00:49:45 | APPR | Approved | Jumpol Sudjitjul | 08-Sep-2026 | 29-Aug-2026 13:41:58 | 29-Aug-2026 06:59:21 | 0 |  |  | Approver | Locate
AO-000801 | MM-ASK-1A-GEN01-INS-TBE-0005 | TECHNICAL BID EVALUATION FOR SELF REGULATOR VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 26-Jul-2026 22:32:53 | zm167dc@jutal.com | 27-Jul-2026 09:39:43 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 30-Jul-2026 16:58:17 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 18:00:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 18:57:54 | 30-Jul-2026 12:37:37 | 0 |  |  | Approver | Locate
AO-000950 | MM-ASK-1A-GEN01-INS-TBE-0005 | TECHNICAL BID EVALUATION FOR SELF REGULATOR VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 10:44:14 | zm167dc@jutal.com | 11-Aug-2026 11:35:13 | Jumpol Sudjitjul | 20-Aug-2026 |  | Payut Phatdamrongdet | 21-Aug-2026 | 14-Aug-2026 14:59:03 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 16-Aug-2026 17:56:50 | APPR | Approved | Jumpol Sudjitjul | 25-Aug-2026 | 17-Aug-2026 08:28:20 | 17-Aug-2026 01:59:06 | 0 |  |  | Approver | Locate
AO-001146 | MM-ASK-1A-GEN01-INS-TBE-0005 | TECHNICAL BID EVALUATION FOR SELF REGULATOR VALVES |  | C3 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:21:03 | zm167dc@jutal.com | 02-Sep-2026 20:30:24 | Soontaree Simpitak | 11-Sep-2026 |  | Payut Phatdamrongdet | 14-Sep-2026 | 04-Sep-2026 10:52:31 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 04-Sep-2026 23:41:10 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 05-Sep-2026 17:52:57 | 05-Sep-2026 11:20:08 | 0 |  |  | Approver | Locate
AO-000802 | MM-ASK-1A-GEN01-INS-TBE-0006 | TECHNICAL BID EVALUATION FOR ACTUATED CHOKE VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 26-Jul-2026 22:33:23 | zm167dc@jutal.com | 27-Jul-2026 09:40:00 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 31-Jul-2026 09:34:54 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 02-Aug-2026 16:45:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 20:58:59 | 02-Aug-2026 14:28:23 | 0 |  |  | Approver | Locate
AO-000895 | MM-ASK-1A-GEN01-INS-TBE-0006 | TECHNICAL BID EVALUATION FOR ACTUATED CHOKE VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 06-Aug-2026 11:32:10 | zm167dc@jutal.com | 06-Aug-2026 14:22:14 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:11:06 | Payut Phatdamrongdet | 18-Aug-2026 | 10-Aug-2026 08:20:55 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 11-Aug-2026 15:43:59 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 11-Aug-2026 15:46:14 | 11-Aug-2026 08:54:39 | 0 |  |  | Approver | Locate
AO-001007 | MM-ASK-1A-GEN01-INS-TBE-0007 | TECHNICAL BID EVALUATION FOR ACTUATED BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 12:48:29 | zm167dc@jutal.com | 17-Aug-2026 13:29:21 | Jumpol Sudjitjul | 25-Aug-2026 |  | Payut Phatdamrongdet | 26-Aug-2026 | 20-Aug-2026 08:52:17 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 20-Aug-2026 13:16:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 20-Aug-2026 13:27:23 | 20-Aug-2026 06:57:34 | 0 |  |  | Approver | Locate
AO-001121 | MM-ASK-1A-GEN01-INS-TBE-0007 | TECHNICAL BID EVALUATION FOR ACTUATED BALL VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 10:29:27 | zm167dc@jutal.com | 28-Aug-2026 14:35:58 | Jumpol Sudjitjul | 07-Sep-2026 |  | Payut Phatdamrongdet | 08-Sep-2026 | 02-Sep-2026 14:34:30 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 02-Sep-2026 23:52:13 | APPR | Approved | Soontaree Simpitak | 10-Sep-2026 | 03-Sep-2026 07:27:29 | 03-Sep-2026 00:53:02 | 0 |  |  | Approver | Locate
AO-000972 | MM-ASK-1A-GEN01-INS-TBE-0008 | TECHNICAL BID EVALUATION FOR ACTUATED COMPACT BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 08:41:59 | zm167dc@jutal.com | 14-Aug-2026 08:50:10 | Jumpol Sudjitjul | 24-Aug-2026 |  | Payut Phatdamrongdet | 25-Aug-2026 | 17-Aug-2026 16:41:46 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 17-Aug-2026 17:02:24 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 17-Aug-2026 17:05:15 | 20-Aug-2026 07:02:33 | 0 |  |  | Approver | Locate
AO-001064 | MM-ASK-1A-GEN01-INS-TBE-0009 | TECHNICAL BID EVALUATION FOR SAFETY RELIEF VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 17:29:22 | zm167dc@jutal.com | 21-Aug-2026 17:36:10 | Jumpol Sudjitjul | 01-Sep-2026 |  | Payut Phatdamrongdet | 02-Sep-2026 | 24-Aug-2026 09:29:31 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 26-Aug-2026 00:47:14 | APPR | Approved | Jumpol Sudjitjul | 04-Sep-2026 | 26-Aug-2026 08:53:49 | 26-Aug-2026 02:41:20 | 0 |  |  | Approver | Locate
AO-001173 | MM-ASK-1A-GEN01-INS-TBE-0009 | TECHNICAL BID EVALUATION FOR SAFETY RELIEF VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 16:04:09 | zm167dc@jutal.com | 03-Sep-2026 16:22:46 | Jumpol Sudjitjul | 11-Sep-2026 |  | Payut Phatdamrongdet | 14-Sep-2026 | 04-Sep-2026 10:53:28 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 04-Sep-2026 23:38:48 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 05-Sep-2026 17:53:23 | 05-Sep-2026 11:21:45 | 0 |  |  | Approver | Locate
AO-001465 | MM-ASK-1A-GEN01-INS-TBE-0025 | TECHNICAL BID EVALUATION FOR POSITION LIMIT SWITCHES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 14:53:57 | zm167dc@jutal.com | 18-Sep-2026 17:25:27 | Jumpol Sudjitjul | 29-Sep-2026 |  | Payut Phatdamrongdet | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000047 | MM-ASK-1A-GEN01-MEC-BOD-0001 | MECHANICAL BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:29:59 | jumpols@pttep.com | 21-Apr-2026 11:04:58 | Jumpol Sudjitjul | 29-Apr-2026 |  | Thanapat Sombatwattana | 30-Apr-2026 | 05-May-2026 09:02:35 | Pornlert Wanaphattharaphan | 05-May-2026 | 06-May-2026 00:40:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 09:00:37 | 06-May-2026 09:13:54 | 0 |  |  | Approver | Locate
AO-000287 | MM-ASK-1A-GEN01-MEC-BOD-0001 | MECHANICAL BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 19-May-2026 17:40:08 | zm167dc@jutal.com | 19-May-2026 18:42:02 | Jumpol Sudjitjul | 28-May-2026 | 04-Jun-2026 13:22:51 | Thanapat Sombatwattana | 29-May-2026 | 05-Jun-2026 09:59:14 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 10-Jun-2026 21:02:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 11-Jun-2026 08:09:25 | 11-Jun-2026 02:00:00 | 0 |  |  | Approver | Locate
AO-000558 | MM-ASK-1A-GEN01-MEC-BOD-0001 | MECHANICAL BASIS OF DESIGN |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 26-Jun-2026 14:44:37 | zm167dc@jutal.com | 26-Jun-2026 16:20:38 | Jumpol Sudjitjul | 06-Jul-2026 | 05-Jul-2026 16:28:03 | Thanapat Sombatwattana | 07-Jul-2026 | 08-Jul-2026 16:46:05 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 11-Jul-2026 13:32:26 | APPR | Approved | Jumpol Sudjitjul | 09-Jul-2026 | 12-Jul-2026 11:19:47 | 12-Jul-2026 04:53:00 | 0 |  |  | Approver | Locate
AO-000262 | MM-ASK-1A-GEN01-MEC-DTS-0001 | MECHANICAL DATASHEET FOR CORROSION INHIBITOR STORAGE TANK (T-09001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 13:25:56 | zm167dc@jutal.com | 15-May-2026 17:50:21 | Jumpol Sudjitjul | 26-May-2026 | 25-May-2026 17:22:57 | Thanapat Sombatwattana | 27-May-2026 | 27-May-2026 06:48:23 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 00:50:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:37:58 | 10-Jun-2026 13:51:47 | 0 |  |  | Approver | Locate
AO-000501 | MM-ASK-1A-GEN01-MEC-DTS-0001 | MECHANICAL DATASHEET FOR CORROSION INHIBITOR STORAGE TANK (T-09001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 14:02:03 | zm167dc@jutal.com | 18-Jun-2026 14:22:24 | Jumpol Sudjitjul | 26-Jun-2026 | 26-Jun-2026 10:10:47 | Thanapat Sombatwattana | 29-Jun-2026 | 29-Jun-2026 22:41:26 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 01-Jul-2026 23:05:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 02-Jul-2026 10:24:03 | 02-Jul-2026 04:32:24 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-GEN01-MEC-DTS-0001 | MECHANICAL DATASHEET FOR CORROSION INHIBITOR STORAGE TANK (T-09001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:41:27 | zm167dc@jutal.com | 17-Jul-2026 22:07:14 | Jumpol Sudjitjul | 30-Jul-2026 | 21-Jul-2026 08:15:40 | Thanapat Sombatwattana | 31-Jul-2026 | 22-Jul-2026 17:30:31 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:45:32 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 07:58:47 | 27-Jul-2026 01:20:42 | 0 |  |  | Approver | Locate
AO-000263 | MM-ASK-1A-GEN01-MEC-DTS-0002 | MECHANICAL DATASHEET FOR CORROSION INHIBITOR STORAGE TOTE TANK (T-09011) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 14:14:15 | zm167dc@jutal.com | 15-May-2026 17:50:52 | Jumpol Sudjitjul | 26-May-2026 | 25-May-2026 17:24:25 | Thanapat Sombatwattana | 27-May-2026 | 29-May-2026 14:34:10 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 00:58:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:56:51 | 10-Jun-2026 13:46:10 | 0 |  |  | Approver | Locate
AO-000463 | MM-ASK-1A-GEN01-MEC-DTS-0002 | MECHANICAL DATASHEET FOR CORROSION INHIBITOR STORAGE TOTE TANK (T-09011) |  | X | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Latest | VOID | Withdrawn or Superseded |  | 12-Jun-2026 12:28:16 | zm167dc@jutal.com | 12-Jun-2026 12:55:16 | Jumpol Sudjitjul |  | 16-Jun-2026 17:03:12 | Thanapat Sombatwattana |  | 18-Jun-2026 23:34:36 | Pornlert Wanaphattharaphan |  |  | APPR | Approved |  |  |  |  | 0 |  |  | For Info | Locate
AO-000264 | MM-ASK-1A-GEN01-MEC-DTS-0003 | MECHANICAL DATASHEET FOR UTILITY WATER STORAGE TOTE TANK (T-07003, T-07013) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 14:14:42 | zm167dc@jutal.com | 15-May-2026 17:58:42 | Jumpol Sudjitjul | 26-May-2026 | 25-May-2026 17:27:11 | Thanapat Sombatwattana | 27-May-2026 | 29-May-2026 14:34:29 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 01:13:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:56:26 | 10-Jun-2026 13:47:21 | 0 |  |  | Approver | Locate
AO-000501 | MM-ASK-1A-GEN01-MEC-DTS-0003 | MECHANICAL DATASHEET FOR UTILITY WATER STORAGE TOTE TANK (T-07003, T-07013) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 14:02:53 | zm167dc@jutal.com | 18-Jun-2026 14:22:56 | Jumpol Sudjitjul | 26-Jun-2026 | 26-Jun-2026 10:11:49 | Thanapat Sombatwattana | 29-Jun-2026 | 29-Jun-2026 10:30:56 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 30-Jun-2026 23:12:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 01-Jul-2026 08:39:20 | 01-Jul-2026 02:19:27 | 0 |  |  | Approver | Locate
AO-000723 | MM-ASK-1A-GEN01-MEC-DTS-0003 | MECHANICAL DATASHEET FOR UTILITY WATER STORAGE TOTE TANK (T-07003, T-07013) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:03:34 | zm167dc@jutal.com | 20-Jul-2026 11:35:55 | Jumpol Sudjitjul | 30-Jul-2026 | 21-Jul-2026 08:37:45 | Thanapat Sombatwattana | 31-Jul-2026 | 22-Jul-2026 17:34:26 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:49:25 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 08:00:19 | 27-Jul-2026 01:21:54 | 0 |  |  | Approver | Locate
AO-000265 | MM-ASK-1A-GEN01-MEC-DTS-0004 | MECHANICAL DATASHEET FOR DIESEL STORAGE TOTE TANK (T-07001,T-07011) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 14:15:07 | zm167dc@jutal.com | 15-May-2026 17:59:05 | Jumpol Sudjitjul | 26-May-2026 | 25-May-2026 17:31:19 | Pornlert Wanaphattharaphan | 27-May-2026 | 29-May-2026 09:58:48 | Pornlert Wanaphattharaphan | 28-May-2026 | 29-May-2026 13:12:16 | NA | Not Approved | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 13:22:31 | 29-May-2026 06:46:27 | 0 |  |  | Approver | Locate
AO-000466 | MM-ASK-1A-GEN01-MEC-DTS-0004 | MECHANICAL DATASHEET FOR DIESEL STORAGE TOTE TANK (T-07001,T-07011) |  | A2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 14:47:06 | zm167dc@jutal.com | 12-Jun-2026 15:36:05 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 09:44:08 | Thanapat Sombatwattana | 23-Jun-2026 | 24-Jun-2026 16:08:56 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:14:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:21:18 | 25-Jun-2026 01:47:05 | 0 |  |  | Approver | Locate
AO-000629 | MM-ASK-1A-GEN01-MEC-DTS-0004 | MECHANICAL DATASHEET FOR DIESEL STORAGE TOTE TANK (T-07001,T-07011) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 20:30:41 | zm167dc@jutal.com | 04-Jul-2026 13:58:43 | Jumpol Sudjitjul | 13-Jul-2026 | 12-Jul-2026 17:36:51 | Thanapat Sombatwattana | 14-Jul-2026 | 15-Jul-2026 17:07:19 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:06:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:16:36 | 17-Jul-2026 01:48:28 | 0 |  |  | Approver | Locate
AO-000755 | MM-ASK-1A-GEN01-MEC-DTS-0004 | MECHANICAL DATASHEET FOR DIESEL STORAGE TOTE TANK (T-07001,T-07011) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 22-Jul-2026 10:42:05 | zm167dc@jutal.com | 22-Jul-2026 11:19:47 | Jumpol Sudjitjul | 03-Aug-2026 | 22-Jul-2026 14:19:03 | Thanapat Sombatwattana | 04-Aug-2026 | 22-Jul-2026 17:41:28 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 29-Jul-2026 09:00:31 | APPR | Approved | Jumpol Sudjitjul | 06-Aug-2026 | 30-Jul-2026 08:43:24 | 30-Jul-2026 02:05:38 | 0 |  |  | Approver | Locate
AO-000036 | MM-ASK-1A-GEN01-MEC-DTS-0005 | MECHANICAL DATASHEET FOR OFFSHORE PEDESTAL CRANE CR-07001 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 10-Apr-2026 14:50:28 | zm167dc@jutal.com | 10-Apr-2026 17:03:11 | Jumpol Sudjitjul | 24-Apr-2026 | 14-Apr-2026 07:53:11 | Thanapat Sombatwattana | 27-Apr-2026 | 23-Apr-2026 17:23:08 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 29-Apr-2026 21:58:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Apr-2026 | 30-Apr-2026 08:18:24 | 30-Apr-2026 08:47:37 | 0 |  |  | Approver | Locate
AO-000221 | MM-ASK-1A-GEN01-MEC-DTS-0005 | MECHANICAL DATASHEET FOR OFFSHORE PEDESTAL CRANE CR-07001 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 13-May-2026 14:22:21 | zm167dc@jutal.com | 13-May-2026 15:27:35 | Jumpol Sudjitjul | 21-May-2026 | 22-May-2026 17:46:24 | Thanapat Sombatwattana | 22-May-2026 | 28-May-2026 15:34:52 | Pornlert Wanaphattharaphan | 25-May-2026 | 31-May-2026 14:58:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-May-2026 | 31-May-2026 16:28:52 | 31-May-2026 09:54:04 | 0 |  |  | Approver | Locate
AO-000588 | MM-ASK-1A-GEN01-MEC-DTS-0005 | MECHANICAL DATASHEET FOR OFFSHORE PEDESTAL CRANE CR-07001 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 01-Jul-2026 18:35:46 | zm167dc@jutal.com | 02-Jul-2026 14:21:06 | Jumpol Sudjitjul | 10-Jul-2026 | 05-Jul-2026 11:05:18 | Thanapat Sombatwattana | 13-Jul-2026 | 07-Jul-2026 17:34:22 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 14-Jul-2026 23:55:42 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 08:21:10 | 15-Jul-2026 02:00:43 | 0 |  |  | Approver | Locate
AO-000231 | MM-ASK-1A-GEN01-MEC-DTS-0007 | MECHANICAL DATASHEET FOR INSTRUMENT GAS FILTER COALESCER (V-03001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 16:13:46 | zm167dc@jutal.com | 14-May-2026 16:21:05 | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 18:28:36 | Thanapat Sombatwattana | 25-May-2026 | 27-May-2026 06:36:06 | Pornlert Wanaphattharaphan | 26-May-2026 | 01-Jun-2026 00:32:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-May-2026 | 01-Jun-2026 09:23:52 | 01-Jun-2026 10:01:25 | 0 |  |  | Approver | Locate
AO-000450 | MM-ASK-1A-GEN01-MEC-DTS-0007 | MECHANICAL DATASHEET FOR INSTRUMENT GAS FILTER COALESCER (V-03001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 15:26:18 | zm167dc@jutal.com | 11-Jun-2026 15:31:44 | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 10:50:31 | Thanapat Sombatwattana | 22-Jun-2026 | 25-Jun-2026 13:29:15 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 25-Jun-2026 21:25:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 25-Jun-2026 22:21:29 | 25-Jun-2026 15:25:49 | 0 |  |  | Approver | Locate
AO-000670 | MM-ASK-1A-GEN01-MEC-DTS-0007 | MECHANICAL DATASHEET FOR INSTRUMENT GAS FILTER COALESCER (V-03001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 14:43:11 | zm167dc@jutal.com | 10-Jul-2026 16:29:11 | Jumpol Sudjitjul | 20-Jul-2026 | 16-Jul-2026 14:05:47 | Thanapat Sombatwattana | 21-Jul-2026 | 17-Jul-2026 13:22:09 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 19-Jul-2026 17:13:08 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:34:36 | 20-Jul-2026 04:37:14 | 0 |  |  | Approver | Locate
AO-000344 | MM-ASK-1A-GEN01-MEC-DTS-0008 | MECHANICAL DATASHEET FOR DIESEL TRANSFER PUMP PACKAGE (SK-07001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 16:08:57 | zm167dc@jutal.com | 26-May-2026 09:22:58 | Jumpol Sudjitjul | 05-Jun-2026 | 05-Jun-2026 15:51:42 | Thanapat Sombatwattana | 08-Jun-2026 | 11-Jun-2026 11:21:16 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 11-Jun-2026 14:47:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 14:58:29 | 11-Jun-2026 08:46:04 | 0 |  |  | Approver | Locate
AO-000529 | MM-ASK-1A-GEN01-MEC-DTS-0008 | MECHANICAL DATASHEET FOR DIESEL TRANSFER PUMP PACKAGE (SK-07001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 23-Jun-2026 10:40:08 | zm167dc@jutal.com | 23-Jun-2026 12:50:15 | Jumpol Sudjitjul | 01-Jul-2026 | 05-Jul-2026 16:04:03 | Thanapat Sombatwattana | 02-Jul-2026 | 06-Jul-2026 16:19:53 | Pornlert Wanaphattharaphan | 03-Jul-2026 | 08-Jul-2026 00:39:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Jul-2026 | 08-Jul-2026 08:32:22 | 08-Jul-2026 02:33:03 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-GEN01-MEC-DTS-0008 | MECHANICAL DATASHEET FOR DIESEL TRANSFER PUMP PACKAGE (SK-07001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:41:52 | zm167dc@jutal.com | 17-Jul-2026 22:07:38 | Jumpol Sudjitjul | 30-Jul-2026 | 21-Jul-2026 08:33:13 | Thanapat Sombatwattana | 31-Jul-2026 | 22-Jul-2026 17:31:52 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:47:18 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 08:17:59 | 27-Jul-2026 01:48:29 | 0 |  |  | Approver | Locate
AO-000357 | MM-ASK-1A-GEN01-MEC-DTS-0009 | MECHANICAL DATASHEET FOR MATERIAL HANDLING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 27-May-2026 10:50:48 | zm167dc@jutal.com | 27-May-2026 11:13:42 | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 10:58:31 | Thanapat Sombatwattana | 09-Jun-2026 | 13-Jun-2026 14:35:28 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 13-Jun-2026 22:01:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 14-Jun-2026 21:45:26 | 14-Jun-2026 15:13:25 | 0 |  |  | Approver | Locate
AO-000533 | MM-ASK-1A-GEN01-MEC-DTS-0009 | MECHANICAL DATASHEET FOR MATERIAL HANDLING EQUIPMENT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 23-Jun-2026 16:41:22 | zm167dc@jutal.com | 23-Jun-2026 17:25:58 | Jumpol Sudjitjul | 02-Jul-2026 | 05-Jul-2026 16:16:31 | Thanapat Sombatwattana | 03-Jul-2026 | 07-Jul-2026 17:59:41 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 08-Jul-2026 00:55:05 | APPR | Approved | Jumpol Sudjitjul | 07-Jul-2026 | 08-Jul-2026 08:37:27 | 08-Jul-2026 02:41:30 | 0 |  |  | Approver | Locate
AO-000705 | MM-ASK-1A-GEN01-MEC-DTS-0009 | MECHANICAL DATASHEET FOR MATERIAL HANDLING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 15-Jul-2026 18:44:39 | zm167dc@jutal.com | 15-Jul-2026 21:38:06 | Jumpol Sudjitjul | 24-Jul-2026 | 17-Jul-2026 09:46:24 | Thanapat Sombatwattana | 27-Jul-2026 | 24-Jul-2026 12:54:57 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 10:02:35 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 08:18:41 | 27-Jul-2026 01:47:15 | 0 |  |  | Approver | Locate
AO-001407 | MM-ASK-1A-GEN01-MEC-DTS-0009 | MECHANICAL DATASHEET FOR MATERIAL HANDLING EQUIPMENT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 16-Sep-2026 10:02:12 | zm167dc@jutal.com | 16-Sep-2026 17:45:49 | Jumpol Sudjitjul | 25-Sep-2026 | 17-Sep-2026 16:34:19 | Thanapat Sombatwattana | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000952 | MM-ASK-1A-GEN01-MEC-DTS-0010 | MECHANICAL DATASHEET FOR BIOCIDE STORAGE TANKS (T-09002) (PROVISION FOR FUTURE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-Aug-2026 17:30:14 | zm167dc@jutal.com | 11-Aug-2026 17:43:49 | Jumpol Sudjitjul | 21-Aug-2026 | 25-Aug-2026 08:31:28 | Thanapat Sombatwattana | 24-Aug-2026 | 28-Aug-2026 14:43:35 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 29-Aug-2026 17:17:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 30-Aug-2026 15:45:52 | 30-Aug-2026 08:57:34 | 0 |  |  | Approver | Locate
AO-001357 | MM-ASK-1A-GEN01-MEC-DTS-0010 | MECHANICAL DATASHEET FOR BIOCIDE STORAGE TANKS (T-09002) (PROVISION FOR FUTURE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | In Review | IFA | Issued for Approval |  | 14-Sep-2026 20:45:33 | zm167dc@jutal.com | 15-Sep-2026 14:06:18 | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 10:40:57 | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000632 | MM-ASK-1A-GEN01-MEC-MOM-1001 | MECHANICAL DISCIPLINE WEEKLY MEETING (12-MAR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 11:48:19 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000632 | MM-ASK-1A-GEN01-MEC-MOM-1002 | MECHANICAL DISCIPLINE WEEKLY MEETING (19-MAR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 11:48:54 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000632 | MM-ASK-1A-GEN01-MEC-MOM-1003 | MECHANICAL DISCIPLINE WEEKLY MEETING (26-MAR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 11:49:32 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000632 | MM-ASK-1A-GEN01-MEC-MOM-1004 | MECHANICAL DISCIPLINE WEEKLY MEETING (02-APR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 11:50:16 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000632 | MM-ASK-1A-GEN01-MEC-MOM-1005 | MECHANICAL DISCIPLINE WEEKLY MEETING (09-APR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 11:50:51 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000632 | MM-ASK-1A-GEN01-MEC-MOM-1008 | MECHANICAL DISCIPLINE WEEKLY MEETING (29-APR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 11:51:20 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000632 | MM-ASK-1A-GEN01-MEC-MOM-1009 | MECHANICAL DISCIPLINE WEEKLY MEETING (06-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 11:51:48 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000632 | MM-ASK-1A-GEN01-MEC-MOM-1010 | MECHANICAL DISCIPLINE WEEKLY MEETING (20-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 11:52:21 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000633 | MM-ASK-1A-GEN01-MEC-MOM-1011 | MECHANICAL DISCIPLINE WEEKLY MEETING (27-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 12:24:42 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000633 | MM-ASK-1A-GEN01-MEC-MOM-1012 | MECHANICAL DISCIPLINE WEEKLY MEETING (03-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 12:25:09 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000633 | MM-ASK-1A-GEN01-MEC-MOM-1013 | MECHANICAL DISCIPLINE WEEKLY MEETING (10-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 12:25:36 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000633 | MM-ASK-1A-GEN01-MEC-MOM-1014 | MECHANICAL DISCIPLINE WEEKLY MEETING (17-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 12:26:03 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000633 | MM-ASK-1A-GEN01-MEC-MOM-1015 | MECHANICAL DISCIPLINE WEEKLY MEETING (24-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 12:26:36 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000633 | MM-ASK-1A-GEN01-MEC-MOM-1016 | MECHANICAL DISCIPLINE WEEKLY MEETING (01-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Jul-2026 12:27:02 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000700 | MM-ASK-1A-GEN01-MEC-MOM-1017 | MECHANICAL DISCIPLINE WEEKLY MEETING (08-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 16:35:07 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001039 | MM-ASK-1A-GEN01-MEC-MOM-1018 | MECHANICAL DISCIPLINE WEEKLY MEETING (15-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 20-Aug-2026 17:22:33 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001040 | MM-ASK-1A-GEN01-MEC-MOM-1019 | MECHANICAL DISCIPLINE WEEKLY MEETING (22-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 20-Aug-2026 17:23:02 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000259 | MM-ASK-1A-GEN01-MEC-MR-0001 | MATERIAL REQUISITION FOR TEST AND PRODUCTION SEPARATOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 13:26:27 | zm167dc@jutal.com | 15-May-2026 18:04:00 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 15:30:22 | Thanapat Sombatwattana | 27-May-2026 | 29-May-2026 14:39:55 | Pornlert Wanaphattharaphan | 28-May-2026 | 09-Jun-2026 07:57:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 09-Jun-2026 08:02:06 | 09-Jun-2026 08:33:47 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-GEN01-MEC-MR-0001 | MATERIAL REQUISITION FOR TEST AND PRODUCTION SEPARATOR |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:15:32 | zm167dc@jutal.com | 13-Jun-2026 08:27:01 | Jumpol Sudjitjul | 22-Jun-2026 | 21-Jun-2026 18:53:49 | Thanapat Sombatwattana | 23-Jun-2026 | 25-Jun-2026 14:42:09 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 07:42:53 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 29-Jun-2026 08:39:05 | 29-Jun-2026 01:51:28 | 0 |  |  | Approver | Locate
AO-000605 | MM-ASK-1A-GEN01-MEC-MR-0001 | MATERIAL REQUISITION FOR TEST AND PRODUCTION SEPARATOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 10:40:16 | zm167dc@jutal.com | 03-Jul-2026 13:49:06 | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 09:35:16 | Thanapat Sombatwattana | 14-Jul-2026 | 15-Jul-2026 09:27:54 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:37:30 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:14:01 | 17-Jul-2026 01:47:09 | 0 |  |  | Approver | Locate
AO-000319 | MM-ASK-1A-GEN01-MEC-MR-0002 | MATERIAL REQUISITION FOR INSTRUMENT GAS FILTER COALESCER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 23-May-2026 08:45:09 | zm167dc@jutal.com | 23-May-2026 09:20:08 | Jumpol Sudjitjul | 02-Jun-2026 | 25-May-2026 05:29:36 | Thanapat Sombatwattana | 04-Jun-2026 | 09-Jun-2026 22:01:09 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:17:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 08:10:11 | 11-Jun-2026 09:09:04 | 0 |  |  | Approver | Locate
AO-000501 | MM-ASK-1A-GEN01-MEC-MR-0002 | MATERIAL REQUISITION FOR INSTRUMENT GAS FILTER COALESCER |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 14:03:39 | zm167dc@jutal.com | 18-Jun-2026 14:24:04 | Jumpol Sudjitjul | 26-Jun-2026 | 23-Jun-2026 10:12:26 | Thanapat Sombatwattana | 29-Jun-2026 | 29-Jun-2026 22:43:31 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 01-Jul-2026 22:18:49 | APPR | Approved | Jumpol Sudjitjul | 01-Jul-2026 | 02-Jul-2026 10:24:49 | 02-Jul-2026 04:33:47 | 0 |  |  | Approver | Locate
AO-000629 | MM-ASK-1A-GEN01-MEC-MR-0002 | MATERIAL REQUISITION FOR INSTRUMENT GAS FILTER COALESCER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 20:31:07 | zm167dc@jutal.com | 04-Jul-2026 14:02:17 | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 11:41:28 | Thanapat Sombatwattana | 14-Jul-2026 | 15-Jul-2026 17:16:01 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:42:37 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:17:45 | 17-Jul-2026 01:49:37 | 0 |  |  | Approver | Locate
AO-000305 | MM-ASK-1A-GEN01-MEC-MR-0003 | MATERIAL REQUISITION FOR STORAGE TOTE TANKS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 21-May-2026 12:11:03 | zm167dc@jutal.com | 21-May-2026 17:50:05 | Jumpol Sudjitjul | 02-Jun-2026 | 24-May-2026 15:32:09 | Thanapat Sombatwattana | 04-Jun-2026 | 09-Jun-2026 01:20:12 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 09-Jun-2026 09:51:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 11:08:23 | 09-Jun-2026 11:25:13 | 0 |  |  | Approver | Locate
AO-000465 | MM-ASK-1A-GEN01-MEC-MR-0003 | MATERIAL REQUISITION FOR STORAGE TOTE TANKS |  | X | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Latest | VOID | Withdrawn or Superseded |  | 12-Jun-2026 12:28:40 | zm167dc@jutal.com | 12-Jun-2026 12:57:52 | Jumpol Sudjitjul |  |  | Thanapat Sombatwattana |  | 18-Jun-2026 23:35:15 | Pornlert Wanaphattharaphan |  |  | APPR | Approved |  |  |  |  | 0 |  |  | For Info | Locate
AO-000306 | MM-ASK-1A-GEN01-MEC-MR-0004 | MATERIAL REQUISITION FOR STORAGE TANKS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 21-May-2026 11:28:21 | zm167dc@jutal.com | 21-May-2026 17:50:23 | Jumpol Sudjitjul | 02-Jun-2026 | 24-May-2026 15:33:21 | Thanapat Sombatwattana | 04-Jun-2026 | 09-Jun-2026 01:20:28 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:16:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 08:11:18 | 11-Jun-2026 08:46:25 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-GEN01-MEC-MR-0004 | MATERIAL REQUISITION FOR STORAGE TANKS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:15:58 | zm167dc@jutal.com | 13-Jun-2026 08:27:17 | Jumpol Sudjitjul | 22-Jun-2026 | 21-Jun-2026 18:54:17 | Thanapat Sombatwattana | 23-Jun-2026 | 25-Jun-2026 21:56:28 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 08:18:23 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 28-Jun-2026 08:35:43 | 28-Jun-2026 01:38:41 | 0 |  |  | Approver | Locate
AO-000605 | MM-ASK-1A-GEN01-MEC-MR-0004 | MATERIAL REQUISITION FOR STORAGE TANKS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 10:40:59 | zm167dc@jutal.com | 03-Jul-2026 13:49:53 | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 09:38:02 | Thanapat Sombatwattana | 14-Jul-2026 | 15-Jul-2026 09:28:56 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:38:40 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:18:19 | 17-Jul-2026 01:50:44 | 0 |  |  | Approver | Locate
AO-000274 | MM-ASK-1A-GEN01-MEC-MR-0005 | MATERIAL REQUISITION FOR CHEMICAL INJECTION PUMPS PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:06:53 | zm167dc@jutal.com | 15-May-2026 18:28:45 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 21:52:18 | Thanapat Sombatwattana | 27-May-2026 | 29-May-2026 14:53:40 | Pornlert Wanaphattharaphan | 28-May-2026 | 09-Jun-2026 08:50:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 09-Jun-2026 08:56:18 | 09-Jun-2026 02:28:10 | 0 |  |  | Approver | Locate
AO-000542 | MM-ASK-1A-GEN01-MEC-MR-0005 | MATERIAL REQUISITION FOR CHEMICAL INJECTION PUMPS PACKAGE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 10:08:52 | zm167dc@jutal.com | 25-Jun-2026 15:00:30 | Jumpol Sudjitjul | 03-Jul-2026 | 05-Jul-2026 16:25:54 | Thanapat Sombatwattana | 06-Jul-2026 | 08-Jul-2026 16:24:22 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 10-Jul-2026 00:54:08 | APPR | Approved | Jumpol Sudjitjul | 08-Jul-2026 | 10-Jul-2026 08:13:03 | 10-Jul-2026 02:21:35 | 0 |  |  | Approver | Locate
AO-000691 | MM-ASK-1A-GEN01-MEC-MR-0005 | MATERIAL REQUISITION FOR CHEMICAL INJECTION PUMPS PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 13-Jul-2026 14:42:13 | zm167dc@jutal.com | 13-Jul-2026 14:45:58 | Jumpol Sudjitjul | 21-Jul-2026 | 17-Jul-2026 08:15:08 | Thanapat Sombatwattana | 22-Jul-2026 | 17-Jul-2026 14:27:24 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 19-Jul-2026 17:07:46 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 09:34:59 | 20-Jul-2026 04:14:35 | 0 |  |  | Approver | Locate
AO-000369 | MM-ASK-1A-GEN01-MEC-MR-0006 | MATERIAL REQUISITION FOR DIESEL TRANSFER PUMP PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 17:24:09 | zm167dc@jutal.com | 29-May-2026 09:49:13 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 11:01:34 | Thanapat Sombatwattana | 11-Jun-2026 | 15-Jun-2026 13:32:58 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 15-Jun-2026 22:17:45 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 15-Jun-2026 | 16-Jun-2026 09:42:04 | 16-Jun-2026 10:19:54 | 0 |  |  | Approver | Locate
AO-000506 | MM-ASK-1A-GEN01-MEC-MR-0006 | MATERIAL REQUISITION FOR DIESEL TRANSFER PUMP PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 19-Jun-2026 09:22:30 | zm167dc@jutal.com | 19-Jun-2026 10:30:53 | Jumpol Sudjitjul | 29-Jun-2026 | 23-Jun-2026 10:17:09 | Thanapat Sombatwattana | 30-Jun-2026 | 30-Jun-2026 10:14:29 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 00:12:11 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 10:25:38 | 02-Jul-2026 04:35:12 | 0 |  |  | Approver | Locate
AO-000035 | MM-ASK-1A-GEN01-MEC-MR-0007 | MATERIAL REQUISITION FOR OFFSHORE PEDESTAL CRANE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 10-Apr-2026 14:50:58 | zm167dc@jutal.com | 10-Apr-2026 17:01:35 | Jumpol Sudjitjul | 24-Apr-2026 | 14-Apr-2026 07:53:51 | Thanapat Sombatwattana | 27-Apr-2026 | 23-Apr-2026 17:22:45 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 25-Apr-2026 23:26:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Apr-2026 | 27-Apr-2026 09:55:49 | 27-Apr-2026 10:14:30 | 0 |  |  | Approver | Locate
AO-000438 | MM-ASK-1A-GEN01-MEC-MR-0007 | MATERIAL REQUISITION FOR OFFSHORE PEDESTAL CRANE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 09:59:18 | zm167dc@jutal.com | 10-Jun-2026 10:26:16 | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 17:35:28 | Thanapat Sombatwattana | 19-Jun-2026 | 22-Jun-2026 11:36:17 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 23-Jun-2026 00:51:30 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 23-Jun-2026 08:14:44 | 23-Jun-2026 01:45:44 | 0 |  |  | Approver | Locate
AO-000539 | MM-ASK-1A-GEN01-MEC-MR-0007 | MATERIAL REQUISITION FOR OFFSHORE PEDESTAL CRANE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Jun-2026 14:41:30 | zm167dc@jutal.com | 24-Jun-2026 15:43:04 | Jumpol Sudjitjul | 02-Jul-2026 | 25-Jun-2026 07:44:30 | Thanapat Sombatwattana | 03-Jul-2026 | 25-Jun-2026 17:01:10 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 28-Jun-2026 08:35:04 | APPR | Approved | Jumpol Sudjitjul | 07-Jul-2026 | 28-Jun-2026 08:36:39 | 28-Jun-2026 02:11:00 | 0 |  |  | Approver | Locate
AO-000260 | MM-ASK-1A-GEN01-MEC-MR-0008 | MATERIAL REQUISITION FOR CLOSED DRAIN SUMP VESSEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 13:26:54 | zm167dc@jutal.com | 15-May-2026 18:04:18 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 15:34:14 | Thanapat Sombatwattana | 27-May-2026 | 29-May-2026 14:42:49 | Pornlert Wanaphattharaphan | 28-May-2026 | 09-Jun-2026 07:55:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 09-Jun-2026 08:03:54 | 09-Jun-2026 08:35:57 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-GEN01-MEC-MR-0008 | MATERIAL REQUISITION FOR CLOSED DRAIN SUMP VESSEL |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:16:22 | zm167dc@jutal.com | 13-Jun-2026 08:27:34 | Jumpol Sudjitjul | 22-Jun-2026 | 21-Jun-2026 18:54:48 | Thanapat Sombatwattana | 23-Jun-2026 | 25-Jun-2026 21:58:10 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 08:22:45 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 28-Jun-2026 08:36:12 | 28-Jun-2026 02:18:35 | 0 |  |  | Approver | Locate
AO-000605 | MM-ASK-1A-GEN01-MEC-MR-0008 | MATERIAL REQUISITION FOR CLOSED DRAIN SUMP VESSEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 10:41:46 | zm167dc@jutal.com | 03-Jul-2026 13:51:03 | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 10:04:13 | Thanapat Sombatwattana | 14-Jul-2026 | 15-Jul-2026 09:29:57 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:39:22 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:19:48 | 17-Jul-2026 01:51:50 | 0 |  |  | Approver | Locate
AO-000261 | MM-ASK-1A-GEN01-MEC-MR-0009 | MATERIAL REQUISITION FOR CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 13:27:21 | zm167dc@jutal.com | 15-May-2026 18:04:36 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 15:35:04 | Thanapat Sombatwattana | 27-May-2026 | 29-May-2026 14:49:13 | Pornlert Wanaphattharaphan | 28-May-2026 | 09-Jun-2026 07:58:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 09-Jun-2026 08:03:05 | 09-Jun-2026 08:34:51 | 0 |  |  | Approver | Locate
AO-000501 | MM-ASK-1A-GEN01-MEC-MR-0009 | MATERIAL REQUISITION FOR CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP PACKAGE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 14:04:15 | zm167dc@jutal.com | 18-Jun-2026 14:24:35 | Jumpol Sudjitjul | 26-Jun-2026 | 26-Jun-2026 08:18:27 | Thanapat Sombatwattana | 29-Jun-2026 | 29-Jun-2026 22:46:55 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 01-Jul-2026 22:20:14 | APPR | Approved | Jumpol Sudjitjul | 01-Jul-2026 | 02-Jul-2026 10:26:29 | 02-Jul-2026 04:29:21 | 0 |  |  | Approver | Locate
AO-000709 | MM-ASK-1A-GEN01-MEC-MR-0009 | MATERIAL REQUISITION FOR CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 16:59:48 | zm167dc@jutal.com | 16-Jul-2026 20:47:58 | Jumpol Sudjitjul | 27-Jul-2026 | 17-Jul-2026 08:13:52 | Thanapat Sombatwattana | 30-Jul-2026 | 22-Jul-2026 17:28:38 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:13:41 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 08:19:29 | 27-Jul-2026 01:49:39 | 0 |  |  | Approver | Locate
AO-000368 | MM-ASK-1A-GEN01-MEC-MR-0010 | MATERIAL REQUISITION FOR MATERIAL HANDLING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Issued for Approval |  | 28-May-2026 17:24:34 | zm167dc@jutal.com | 28-May-2026 17:57:34 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 11:06:32 | Thanapat Sombatwattana | 11-Jun-2026 | 15-Jun-2026 11:20:17 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 15-Jun-2026 22:24:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 16-Jun-2026 09:42:29 | 16-Jun-2026 03:30:57 | 0 |  |  | Approver | Locate
AO-000536 | MM-ASK-1A-GEN01-MEC-MR-0010 | MATERIAL REQUISITION FOR MATERIAL HANDLING EQUIPMENT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Issued for Approval |  | 24-Jun-2026 09:17:13 | zm167dc@jutal.com | 24-Jun-2026 11:24:55 | Jumpol Sudjitjul | 02-Jul-2026 | 05-Jul-2026 16:22:42 | Thanapat Sombatwattana | 03-Jul-2026 | 08-Jul-2026 16:18:02 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 09-Jul-2026 08:49:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 09-Jul-2026 09:50:49 | 09-Jul-2026 04:14:46 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-GEN01-MEC-MR-0010 | MATERIAL REQUISITION FOR MATERIAL HANDLING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:42:17 | zm167dc@jutal.com | 17-Jul-2026 22:11:02 | Jumpol Sudjitjul | 30-Jul-2026 | 24-Jul-2026 09:11:35 | Thanapat Sombatwattana | 31-Jul-2026 | 24-Jul-2026 14:23:53 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 29-Jul-2026 00:47:04 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 30-Jul-2026 08:49:32 | 30-Jul-2026 02:48:51 | 0 |  |  | Approver | Locate
AO-001406 | MM-ASK-1A-GEN01-MEC-MR-0010 | MATERIAL REQUISITION FOR MATERIAL HANDLING EQUIPMENT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 16-Sep-2026 10:02:44 | zm167dc@jutal.com | 16-Sep-2026 17:44:36 | Jumpol Sudjitjul | 25-Sep-2026 | 17-Sep-2026 17:43:52 | Thanapat Sombatwattana | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000186 | MM-ASK-1A-GEN01-MEC-RPT-0001 | MATERIAL HANDLING STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 10-May-2026 23:36:32 | zm167dc@jutal.com | 11-May-2026 09:13:55 | Jumpol Sudjitjul | 19-May-2026 | 23-May-2026 21:28:51 | Thanapat Sombatwattana | 20-May-2026 | 27-May-2026 06:12:08 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:44:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 16:36:00 | 31-May-2026 09:59:19 | 0 |  |  | Approver | Locate
AO-000059 | MM-ASK-1A-GEN01-MEC-RPT-0002 | CRITICALITY RATING REPORT FOR EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:05:28 | zm167dc@jutal.com | 25-Apr-2026 09:21:53 | Jumpol Sudjitjul | 06-May-2026 | 30-Apr-2026 11:07:36 | Thanapat Sombatwattana | 07-May-2026 | 08-May-2026 16:45:08 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:30:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:03:54 | 09-May-2026 08:31:43 | 0 |  |  | Approver | Locate
AO-000327 | MM-ASK-1A-GEN01-MEC-RPT-0002 | CRITICALITY RATING REPORT FOR EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 23-May-2026 08:45:32 | zm167dc@jutal.com | 23-May-2026 09:25:33 | Jumpol Sudjitjul | 02-Jun-2026 | 03-Jun-2026 09:29:29 | Thanapat Sombatwattana | 04-Jun-2026 | 09-Jun-2026 22:42:51 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:18:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 08:12:52 | 11-Jun-2026 02:10:20 | 0 |  |  | Approver | Locate
AO-000534 | MM-ASK-1A-GEN01-MEC-RPT-0002 | CRITICALITY RATING REPORT FOR EQUIPMENT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 23-Jun-2026 16:41:52 | zm167dc@jutal.com | 23-Jun-2026 17:27:09 | Jumpol Sudjitjul | 02-Jul-2026 | 26-Jun-2026 17:08:23 | Thanapat Sombatwattana | 03-Jul-2026 | 03-Jul-2026 18:17:35 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 04-Jul-2026 19:20:40 | APPR | Approved | Jumpol Sudjitjul | 07-Jul-2026 | 05-Jul-2026 10:22:06 | 05-Jul-2026 04:16:49 | 0 |  |  | Approver | Locate
AO-000057 | MM-ASK-1A-GEN01-MEC-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR TEST & PRODUCTION SEPARATORS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 16:36:06 | zm167dc@jutal.com | 24-Apr-2026 17:55:58 | Jumpol Sudjitjul | 07-May-2026 | 01-May-2026 12:08:30 | Thanapat Sombatwattana | 08-May-2026 | 18-May-2026 08:19:49 | Pornlert Wanaphattharaphan | 11-May-2026 | 18-May-2026 22:31:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 19-May-2026 09:09:48 | 19-May-2026 10:25:35 | 0 |  |  | Approver | Locate
AO-000386 | MM-ASK-1A-GEN01-MEC-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR TEST & PRODUCTION SEPARATORS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 01-Jun-2026 10:51:07 | zm167dc@jutal.com | 01-Jun-2026 12:23:30 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 09:27:19 | Thanapat Sombatwattana | 11-Jun-2026 | 15-Jun-2026 23:35:51 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 17-Jun-2026 00:05:04 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 17-Jun-2026 08:18:17 | 17-Jun-2026 02:13:55 | 0 |  |  | Approver | Locate
AO-000058 | MM-ASK-1A-GEN01-MEC-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR INSTRUMENT GAS FILTER COALESCERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 16:36:30 | zm167dc@jutal.com | 24-Apr-2026 17:57:51 | Jumpol Sudjitjul | 07-May-2026 | 01-May-2026 12:08:44 | Thanapat Sombatwattana | 08-May-2026 | 12-May-2026 06:46:25 | Pornlert Wanaphattharaphan | 11-May-2026 | 15-May-2026 00:11:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 09:16:37 | 15-May-2026 09:44:27 | 0 |  |  | Approver | Locate
AO-000386 | MM-ASK-1A-GEN01-MEC-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR INSTRUMENT GAS FILTER COALESCERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 01-Jun-2026 10:51:31 | zm167dc@jutal.com | 01-Jun-2026 12:25:10 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 09:27:56 | Thanapat Sombatwattana | 11-Jun-2026 | 15-Jun-2026 23:39:10 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 17-Jun-2026 00:13:59 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 17-Jun-2026 08:19:02 | 17-Jun-2026 02:15:12 | 0 |  |  | Approver | Locate
AO-000127 | MM-ASK-1A-GEN01-MEC-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR STORAGE TOTE TANKS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 17:02:36 | zm167dc@jutal.com | 06-May-2026 10:42:18 | Jumpol Sudjitjul | 14-May-2026 | 08-May-2026 16:56:23 | Thanapat Sombatwattana | 15-May-2026 | 18-May-2026 10:05:13 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 22:30:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 20-May-2026 08:40:30 | 20-May-2026 09:02:16 | 0 |  |  | Approver | Locate
AO-000466 | MM-ASK-1A-GEN01-MEC-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR STORAGE TOTE TANKS |  | X | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Latest | VOID | Withdrawn or Superseded |  | 12-Jun-2026 14:47:36 | zm167dc@jutal.com | 12-Jun-2026 15:37:49 | Jumpol Sudjitjul |  | 14-Jun-2026 09:47:24 | Thanapat Sombatwattana |  | 18-Jun-2026 23:35:42 | Pornlert Wanaphattharaphan |  |  | APPR | Approved |  |  |  |  | 0 |  |  | For Info | Locate
AO-000128 | MM-ASK-1A-GEN01-MEC-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR STORAGE TANKS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 17:03:00 | zm167dc@jutal.com | 06-May-2026 10:42:45 | Jumpol Sudjitjul | 14-May-2026 | 08-May-2026 16:57:22 | Thanapat Sombatwattana | 15-May-2026 | 18-May-2026 10:05:55 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 22:40:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 20-May-2026 08:41:45 | 20-May-2026 09:03:19 | 0 |  |  | Approver | Locate
AO-000415 | MM-ASK-1A-GEN01-MEC-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR STORAGE TANKS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 05-Jun-2026 17:55:03 | zm167dc@jutal.com | 05-Jun-2026 19:51:06 | Jumpol Sudjitjul | 16-Jun-2026 | 12-Jun-2026 14:09:49 | Thanapat Sombatwattana | 17-Jun-2026 | 17-Jun-2026 16:44:34 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 20:37:58 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 09:56:03 | 22-Jun-2026 03:41:52 | 0 |  |  | Approver | Locate
AO-000747 | MM-ASK-1A-GEN01-MEC-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR STORAGE TANKS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 13:53:03 | zm167dc@jutal.com | 21-Jul-2026 14:30:35 | Jumpol Sudjitjul | 31-Jul-2026 | 21-Jul-2026 16:06:50 | Thanapat Sombatwattana | 03-Aug-2026 | 22-Jul-2026 17:39:23 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 29-Jul-2026 08:54:04 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 30-Jul-2026 08:50:24 | 30-Jul-2026 02:14:47 | 0 |  |  | Approver | Locate
AO-000111 | MM-ASK-1A-GEN01-MEC-SPE-0005 | PROJECT PARTICULAR SPECIFICATION FOR CHEMICAL INJECTION PUMPS PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 16:48:44 | zm167dc@jutal.com | 01-May-2026 10:52:52 | Jumpol Sudjitjul | 12-May-2026 | 12-May-2026 09:33:51 | Thanapat Sombatwattana | 13-May-2026 | 18-May-2026 08:28:59 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 09:37:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:26:56 | 19-May-2026 11:42:28 | 0 |  |  | Approver | Locate
AO-000354 | MM-ASK-1A-GEN01-MEC-SPE-0005 | PROJECT PARTICULAR SPECIFICATION FOR CHEMICAL INJECTION PUMPS PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 26-May-2026 18:09:48 | zm167dc@jutal.com | 27-May-2026 09:13:09 | Jumpol Sudjitjul | 08-Jun-2026 | 08-Jun-2026 10:56:24 | Thanapat Sombatwattana | 09-Jun-2026 | 13-Jun-2026 13:12:44 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 13-Jun-2026 21:33:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 14-Jun-2026 21:44:56 | 14-Jun-2026 15:17:07 | 0 |  |  | Approver | Locate
AO-000556 | MM-ASK-1A-GEN01-MEC-SPE-0005 | PROJECT PARTICULAR SPECIFICATION FOR CHEMICAL INJECTION PUMPS PACKAGE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 26-Jun-2026 11:16:07 | zm167dc@jutal.com | 26-Jun-2026 15:17:52 | Jumpol Sudjitjul | 06-Jul-2026 | 29-Jun-2026 08:28:16 | Thanapat Sombatwattana | 07-Jul-2026 | 08-Jul-2026 16:29:03 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 10-Jul-2026 00:55:18 | APPR | Approved | Jumpol Sudjitjul | 09-Jul-2026 | 10-Jul-2026 08:14:10 | 10-Jul-2026 02:12:27 | 0 |  |  | Approver | Locate
AO-000304 | MM-ASK-1A-GEN01-MEC-SPE-0006 | PROJECT PARTICULAR SPECIFICATION FOR DIESEL OIL TRANSFER PUMP PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 11:28:47 | zm167dc@jutal.com | 21-May-2026 17:47:22 | Jumpol Sudjitjul | 02-Jun-2026 | 24-May-2026 09:56:37 | Thanapat Sombatwattana | 04-Jun-2026 | 08-Jun-2026 23:50:16 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:16:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 08:13:45 | 11-Jun-2026 08:47:35 | 0 |  |  | Approver | Locate
AO-000505 | MM-ASK-1A-GEN01-MEC-SPE-0006 | PROJECT PARTICULAR SPECIFICATION FOR DIESEL OIL TRANSFER PUMP PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 18-Jun-2026 17:23:50 | zm167dc@jutal.com | 18-Jun-2026 18:01:09 | Jumpol Sudjitjul | 29-Jun-2026 | 23-Jun-2026 10:15:01 | Thanapat Sombatwattana | 30-Jun-2026 | 30-Jun-2026 10:24:23 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 00:12:37 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 10:27:25 | 02-Jul-2026 04:36:28 | 0 |  |  | Approver | Locate
AO-000037 | MM-ASK-1A-GEN01-MEC-SPE-0007 | PROJECT PARTICULAR SPECIFICATION FOR OFFSHORE PEDESTAL CRANE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 10-Apr-2026 14:51:25 | zm167dc@jutal.com | 10-Apr-2026 16:59:23 | Jumpol Sudjitjul | 23-Apr-2026 | 14-Apr-2026 07:54:24 | Thanapat Sombatwattana | 24-Apr-2026 | 23-Apr-2026 21:49:08 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 29-Apr-2026 08:38:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 29-Apr-2026 08:41:15 | 29-Apr-2026 16:21:20 | 0 |  |  | Approver | Locate
AO-000297 | MM-ASK-1A-GEN01-MEC-SPE-0007 | PROJECT PARTICULAR SPECIFICATION FOR OFFSHORE PEDESTAL CRANE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 21-May-2026 09:37:47 | zm167dc@jutal.com | 21-May-2026 13:52:34 | Jumpol Sudjitjul | 29-May-2026 | 04-Jun-2026 14:11:20 | Thanapat Sombatwattana | 02-Jun-2026 | 08-Jun-2026 23:13:09 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 10-Jun-2026 21:03:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 11-Jun-2026 08:14:24 | 11-Jun-2026 02:11:31 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-GEN01-MEC-SPE-0007 | PROJECT PARTICULAR SPECIFICATION FOR OFFSHORE PEDESTAL CRANE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:51:59 | zm167dc@jutal.com | 27-Jun-2026 19:53:13 | Jumpol Sudjitjul | 07-Jul-2026 | 28-Jun-2026 18:14:36 | Thanapat Sombatwattana | 08-Jul-2026 | 29-Jun-2026 13:30:02 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 01-Jul-2026 22:16:26 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:28:14 | 02-Jul-2026 05:01:30 | 0 |  |  | Approver | Locate
AO-000137 | MM-ASK-1A-GEN01-MEC-SPE-0008 | PROJECT PARTICULAR SPECIFICATION FOR CLOSED DRAIN SUMP VESSELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:46:08 | zm167dc@jutal.com | 06-May-2026 10:44:14 | Jumpol Sudjitjul | 14-May-2026 | 08-May-2026 16:55:19 | Thanapat Sombatwattana | 15-May-2026 | 18-May-2026 10:32:36 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 22:48:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 20-May-2026 08:45:20 | 20-May-2026 09:27:52 | 0 |  |  | Approver | Locate
AO-000386 | MM-ASK-1A-GEN01-MEC-SPE-0008 | PROJECT PARTICULAR SPECIFICATION FOR CLOSED DRAIN SUMP VESSELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 01-Jun-2026 10:51:55 | zm167dc@jutal.com | 01-Jun-2026 12:28:23 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 10:35:57 | Thanapat Sombatwattana | 11-Jun-2026 | 15-Jun-2026 23:43:16 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 17-Jun-2026 00:15:26 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 17-Jun-2026 08:20:16 | 17-Jun-2026 02:16:26 | 0 |  |  | Approver | Locate
AO-000153 | MM-ASK-1A-GEN01-MEC-SPE-0009 | PROJECT PARTICULAR SPECIFICATION FOR CLOSED DRAIN SUMP AND RECOVERED WATER PUMP PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 07-May-2026 17:06:10 | zm167dc@jutal.com | 07-May-2026 17:11:20 | Jumpol Sudjitjul | 18-May-2026 | 12-May-2026 09:36:58 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 00:00:18 | Pornlert Wanaphattharaphan | 20-May-2026 | 21-May-2026 23:11:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 22-May-2026 08:21:04 | 22-May-2026 08:34:01 | 0 |  |  | Approver | Locate
AO-000397 | MM-ASK-1A-GEN01-MEC-SPE-0009 | PROJECT PARTICULAR SPECIFICATION FOR CLOSED DRAIN SUMP AND RECOVERED WATER PUMP PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 04-Jun-2026 09:02:54 | zm167dc@jutal.com | 04-Jun-2026 11:50:02 | Jumpol Sudjitjul | 12-Jun-2026 | 12-Jun-2026 09:49:32 | Thanapat Sombatwattana | 15-Jun-2026 | 16-Jun-2026 17:12:36 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 17-Jun-2026 00:20:01 | APPR | Approved | Jumpol Sudjitjul | 17-Jun-2026 | 17-Jun-2026 08:20:51 | 17-Jun-2026 02:17:33 | 0 |  |  | Approver | Locate
AO-000323 | MM-ASK-1A-GEN01-MEC-SPE-0010 | PROJECT PARTICULAR SPECIFICATION FOR MATERIAL HANDLING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:45:55 | zm167dc@jutal.com | 23-May-2026 09:24:21 | Jumpol Sudjitjul | 02-Jun-2026 | 24-May-2026 09:58:42 | Thanapat Sombatwattana | 04-Jun-2026 | 09-Jun-2026 22:37:11 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:18:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 08:14:58 | 11-Jun-2026 02:12:38 | 0 |  |  | Approver | Locate
AO-000535 | MM-ASK-1A-GEN01-MEC-SPE-0010 | PROJECT PARTICULAR SPECIFICATION FOR MATERIAL HANDLING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 23-Jun-2026 17:25:28 | zm167dc@jutal.com | 23-Jun-2026 17:37:48 | Jumpol Sudjitjul | 02-Jul-2026 | 26-Jun-2026 17:13:50 | Thanapat Sombatwattana | 03-Jul-2026 | 08-Jul-2026 16:17:19 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 10-Jul-2026 00:07:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 10-Jul-2026 08:15:02 | 10-Jul-2026 02:13:43 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-GEN01-MEC-SPE-0010 | PROJECT PARTICULAR SPECIFICATION FOR MATERIAL HANDLING EQUIPMENT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:42:42 | zm167dc@jutal.com | 17-Jul-2026 22:08:46 | Jumpol Sudjitjul | 30-Jul-2026 | 21-Jul-2026 08:42:58 | Thanapat Sombatwattana | 31-Jul-2026 | 24-Jul-2026 12:58:35 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 27-Jul-2026 00:51:11 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 08:20:26 | 27-Jul-2026 01:50:51 | 0 |  |  | Approver | Locate
AO-000616 | MM-ASK-1A-GEN01-MEC-TBE-0001 | TECHNICAL BID EVALUATION FOR TEST AND PRODUCTION SEPARATOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 18:22:11 | zm167dc@jutal.com | 03-Jul-2026 19:56:59 | Jumpol Sudjitjul | 14-Jul-2026 | 07-Jul-2026 16:44:51 | Thanapat Sombatwattana | 15-Jul-2026 | 07-Jul-2026 17:46:06 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 07-Jul-2026 23:39:08 | APPR | Approved | Jumpol Sudjitjul | 17-Jul-2026 | 08-Jul-2026 08:38:45 | 08-Jul-2026 02:28:21 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-GEN01-MEC-TBE-0002 | TECHNICAL BID EVALUATION FOR INSTRUMENT GAS FILTER COALESCER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:43:09 | zm167dc@jutal.com | 17-Jul-2026 22:04:54 | Jumpol Sudjitjul | 30-Jul-2026 | 20-Jul-2026 09:54:52 | Thanapat Sombatwattana | 31-Jul-2026 | 20-Jul-2026 14:59:58 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 21-Jul-2026 00:28:55 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 21-Jul-2026 07:43:06 | 21-Jul-2026 00:56:31 | 0 |  |  | Approver | Locate
AO-000664 | MM-ASK-1A-GEN01-MEC-TBE-0004 | TECHNICAL BID EVALUATION FOR STORAGE TANKS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 09-Jul-2026 12:49:41 | zm167dc@jutal.com | 09-Jul-2026 13:07:31 | Jumpol Sudjitjul | 17-Jul-2026 | 13-Jul-2026 22:37:40 | Thanapat Sombatwattana | 20-Jul-2026 | 15-Jul-2026 13:11:45 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 16-Jul-2026 10:36:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 16-Jul-2026 10:47:00 | 16-Jul-2026 03:52:10 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-GEN01-MEC-TBE-0004 | TECHNICAL BID EVALUATION FOR STORAGE TANKS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:43:36 | zm167dc@jutal.com | 17-Jul-2026 22:05:29 | Jumpol Sudjitjul | 30-Jul-2026 | 20-Jul-2026 09:59:05 | Thanapat Sombatwattana | 31-Jul-2026 | 20-Jul-2026 15:41:42 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 21-Jul-2026 00:20:00 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 21-Jul-2026 07:38:17 | 21-Jul-2026 00:55:23 | 0 |  |  | Approver | Locate
AO-000627 | MM-ASK-1A-GEN01-MEC-TBE-0005 | TECHNICAL BID EVALUATION FOR CHEMICAL INJECTION PUMPS PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 19:09:54 | zm167dc@jutal.com | 03-Jul-2026 19:57:18 | Jumpol Sudjitjul | 14-Jul-2026 | 07-Jul-2026 08:49:00 | Thanapat Sombatwattana | 15-Jul-2026 | 07-Jul-2026 17:55:33 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 07-Jul-2026 23:44:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 08-Jul-2026 08:25:47 | 08-Jul-2026 02:37:16 | 0 |  |  | Approver | Locate
AO-000668 | MM-ASK-1A-GEN01-MEC-TBE-0005 | TECHNICAL BID EVALUATION FOR CHEMICAL INJECTION PUMPS PACKAGE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 12:16:19 | zm167dc@jutal.com | 10-Jul-2026 13:13:33 | Jumpol Sudjitjul | 20-Jul-2026 | 14-Jul-2026 09:42:52 | Thanapat Sombatwattana | 21-Jul-2026 | 14-Jul-2026 14:59:16 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 14-Jul-2026 21:04:52 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 15-Jul-2026 08:22:03 | 15-Jul-2026 02:08:38 | 0 |  |  | Approver | Locate
AO-000669 | MM-ASK-1A-GEN01-MEC-TBE-0006 | TECHNICAL BID EVALUATION FOR DIESEL TRANSFER PUMP PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 12:16:47 | zm167dc@jutal.com | 10-Jul-2026 13:14:09 | Jumpol Sudjitjul | 20-Jul-2026 | 13-Jul-2026 14:04:19 | Thanapat Sombatwattana | 21-Jul-2026 | 14-Jul-2026 17:42:37 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 14-Jul-2026 22:54:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 15-Jul-2026 08:25:58 | 15-Jul-2026 02:11:20 | 0 |  |  | Approver | Locate
AO-000748 | MM-ASK-1A-GEN01-MEC-TBE-0006 | TECHNICAL BID EVALUATION FOR DIESEL TRANSFER PUMP PACKAGE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 15:17:03 | zm167dc@jutal.com | 21-Jul-2026 15:30:33 | Jumpol Sudjitjul | 31-Jul-2026 | 21-Jul-2026 17:40:13 | Thanapat Sombatwattana | 03-Aug-2026 | 22-Jul-2026 17:10:20 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 24-Jul-2026 00:46:48 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 24-Jul-2026 10:09:19 | 24-Jul-2026 03:24:01 | 0 |  |  | Approver | Locate
AO-000471 | MM-ASK-1A-GEN01-MEC-TBE-0007 | TECHNICAL BID EVALUATION FOR OFFSHORE PEDESTAL CRANE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 18:02:22 | zm167dc@jutal.com | 13-Jun-2026 07:18:05 | Jumpol Sudjitjul | 22-Jun-2026 | 15-Jun-2026 11:24:51 | Thanapat Sombatwattana | 23-Jun-2026 | 15-Jun-2026 13:31:24 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 17-Jun-2026 10:08:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 17-Jun-2026 10:39:47 | 17-Jun-2026 11:06:33 | 0 |  |  | Approver | Locate
AO-000507 | MM-ASK-1A-GEN01-MEC-TBE-0007 | TECHNICAL BID EVALUATION FOR OFFSHORE PEDESTAL CRANE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 19-Jun-2026 09:23:06 | zm167dc@jutal.com | 19-Jun-2026 10:29:20 | Jumpol Sudjitjul | 29-Jun-2026 | 19-Jun-2026 11:26:22 | Thanapat Sombatwattana | 30-Jun-2026 | 22-Jun-2026 11:37:46 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 17:44:52 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 22-Jun-2026 17:50:29 | 22-Jun-2026 11:30:06 | 0 |  |  | Approver | Locate
AO-000616 | MM-ASK-1A-GEN01-MEC-TBE-0008 | TECHNICAL BID EVALUATION FOR CLOSED DRAIN SUMP VESSEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 18:22:41 | zm167dc@jutal.com | 03-Jul-2026 19:57:35 | Jumpol Sudjitjul | 14-Jul-2026 | 06-Jul-2026 18:59:55 | Thanapat Sombatwattana | 15-Jul-2026 | 07-Jul-2026 17:48:44 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 07-Jul-2026 23:43:14 | APPR | Approved | Jumpol Sudjitjul | 17-Jul-2026 | 08-Jul-2026 08:39:53 | 08-Jul-2026 02:29:52 | 0 |  |  | Approver | Locate
AO-000629 | MM-ASK-1A-GEN01-MEC-TBE-0009 | TECHNICAL BID EVALUATION FOR CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 20:31:36 | zm167dc@jutal.com | 04-Jul-2026 14:05:15 | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 08:49:42 | Thanapat Sombatwattana | 14-Jul-2026 | 07-Jul-2026 17:53:33 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 08-Jul-2026 08:03:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 08-Jul-2026 08:42:26 | 08-Jul-2026 02:21:50 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-GEN01-MEC-TBE-0009 | TECHNICAL BID EVALUATION FOR CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP PACKAGE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:44:04 | zm167dc@jutal.com | 17-Jul-2026 22:05:49 | Jumpol Sudjitjul | 30-Jul-2026 | 20-Jul-2026 10:26:49 | Thanapat Sombatwattana | 31-Jul-2026 | 22-Jul-2026 17:06:38 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 00:45:10 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 24-Jul-2026 10:11:03 | 24-Jul-2026 03:14:57 | 0 |  |  | Approver | Locate
AO-000932 | MM-ASK-1A-GEN01-MEC-TBE-0010 | TECHNICAL BID EVALUATION FOR MATERIAL HANDLING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 08-Aug-2026 11:23:58 | zm167dc@jutal.com | 08-Aug-2026 20:08:20 | Jumpol Sudjitjul | 19-Aug-2026 | 21-Aug-2026 08:31:46 | Thanapat Sombatwattana | 20-Aug-2026 | 21-Aug-2026 09:21:26 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 20:04:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 08:23:33 | 24-Aug-2026 01:58:46 | 0 |  |  | Approver | Locate
AO-001247 | MM-ASK-1A-GEN01-MEC-TBE-0010 | TECHNICAL BID EVALUATION FOR MATERIAL HANDLING EQUIPMENT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | In Review | AFC | Approved for Construction |  | 08-Sep-2026 16:44:29 | zm167dc@jutal.com | 08-Sep-2026 16:46:58 | Jumpol Sudjitjul | 16-Sep-2026 | 15-Sep-2026 09:42:14 | Thanapat Sombatwattana | 17-Sep-2026 |  | Pornlert Wanaphattharaphan | 18-Sep-2026 |  |  |  |  | 21-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001076 | MM-ASK-1A-GEN01-PCC-PDR-0001 | PIPING PRESSURE TEST PACKAGE PREPARATION PROCEDURE |  | A1 | Project Document | Engineering Document | Part G - Pre-Comm & Comm | GEN |  |  | COM | Commissioning | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:19:39 | zm167dc@jutal.com | 24-Aug-2026 20:17:57 | Jumpol Sudjitjul | 02-Sep-2026 | 01-Sep-2026 11:31:57 | Naphat Nirotsinlapachai | 03-Sep-2026 | 02-Sep-2026 08:17:13 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 05-Sep-2026 23:49:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:19:11 | 06-Sep-2026 03:02:43 | 0 |  |  | Approver | Locate
AO-000333 | MM-ASK-1A-GEN01-PIP-BOD-0001 | PIPING BASIS OF DESIGN (OFFSHORE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 09:45:46 | zm167dc@jutal.com | 25-May-2026 12:53:50 | Jumpol Sudjitjul | 04-Jun-2026 | 08-Jun-2026 17:02:09 | Thanapat Sombatwattana | 05-Jun-2026 | 12-Jun-2026 00:26:53 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 13-Jun-2026 00:36:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 13-Jun-2026 07:05:42 | 13-Jun-2026 00:25:06 | 0 |  |  | Approver | Locate
AO-000573 | MM-ASK-1A-GEN01-PIP-BOD-0001 | PIPING BASIS OF DESIGN (OFFSHORE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 29-Jun-2026 12:10:12 | zm167dc@jutal.com | 30-Jun-2026 10:01:48 | Jumpol Sudjitjul | 08-Jul-2026 | 03-Jul-2026 15:14:16 | Thanapat Sombatwattana | 09-Jul-2026 | 13-Jul-2026 13:28:28 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 14-Jul-2026 22:55:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 08:27:11 | 15-Jul-2026 02:12:44 | 0 |  |  | Approver | Locate
AO-000385 | MM-ASK-1A-GEN01-PIP-CAL-0001 | PIPING WALL THICKNESS CALCULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:49:27 | zm167dc@jutal.com | 29-May-2026 19:14:24 | Jumpol Sudjitjul | 11-Jun-2026 |  | Thanapat Sombatwattana | 12-Jun-2026 | 17-Jun-2026 16:10:15 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 18-Jun-2026 09:59:44 | NA | Not Approved | Jumpol Sudjitjul | 16-Jun-2026 | 18-Jun-2026 10:06:54 | 18-Jun-2026 03:39:57 | 0 |  |  | Approver | Locate
AO-000960 | MM-ASK-1A-GEN01-PIP-CAL-0001 | PIPING WALL THICKNESS CALCULATION |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:45:28 | zm167dc@jutal.com | 13-Aug-2026 13:58:36 | Jumpol Sudjitjul | 21-Aug-2026 | 20-Aug-2026 23:13:52 | Thanapat Sombatwattana | 24-Aug-2026 | 21-Aug-2026 10:35:28 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:25:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 09:40:54 | 24-Aug-2026 03:44:23 | 0 |  |  | Approver | Locate
AO-001204 | MM-ASK-1A-GEN01-PIP-CAL-0001 | PIPING WALL THICKNESS CALCULATION |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:16:12 | zm167dc@jutal.com | 08-Sep-2026 10:21:47 | Jumpol Sudjitjul | 16-Sep-2026 | 15-Sep-2026 23:57:22 | Thanapat Sombatwattana | 17-Sep-2026 | 17-Sep-2026 15:24:06 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 16:28:36 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 14:45:53 | 20-Sep-2026 08:25:36 | 0 |  |  | Approver | Locate
AO-000350 | MM-ASK-1A-GEN01-PIP-DTS-0001 | DATASHEET FOR MANUAL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 12:07:16 | zm167dc@jutal.com | 26-May-2026 14:31:19 | Jumpol Sudjitjul | 05-Jun-2026 | 09-Jun-2026 11:16:36 | Thanapat Sombatwattana | 08-Jun-2026 | 11-Jun-2026 13:45:54 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 11-Jun-2026 21:59:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jun-2026 | 12-Jun-2026 09:10:07 | 12-Jun-2026 02:28:32 | 0 |  |  | Approver | Locate
AO-000573 | MM-ASK-1A-GEN01-PIP-DTS-0001 | DATASHEET FOR MANUAL VALVES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 22:00:56 | zm167dc@jutal.com | 30-Jun-2026 10:16:06 | Jumpol Sudjitjul | 08-Jul-2026 |  | Thanapat Sombatwattana | 09-Jul-2026 | 13-Jul-2026 10:43:35 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 14-Jul-2026 22:55:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 08:30:10 | 15-Jul-2026 02:02:10 | 0 |  |  | Approver | Locate
AO-000793 | MM-ASK-1A-GEN01-PIP-DTS-0001 | DATASHEET FOR MANUAL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:48:01 | zm167dc@jutal.com | 27-Jul-2026 09:30:31 | Jumpol Sudjitjul | 06-Aug-2026 |  | Thanapat Sombatwattana | 07-Aug-2026 | 10-Aug-2026 17:11:03 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:02:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 08:16:38 | 13-Aug-2026 01:26:47 | 0 |  |  | Approver | Locate
AO-000428 | MM-ASK-1A-GEN01-PIP-DTS-0002 | DATASHEET FOR CORROSION FITTINGS (PROBE, COUPON AND CHEMICAL INJECTION QUILL) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:15:37 | zm167dc@jutal.com | 08-Jun-2026 10:29:25 | Jumpol Sudjitjul | 16-Jun-2026 | 11-Jun-2026 14:44:47 | Thanapat Sombatwattana | 17-Jun-2026 | 18-Jun-2026 23:27:15 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 21:17:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 09:56:35 | 22-Jun-2026 03:43:19 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-GEN01-PIP-DTS-0002 | DATASHEET FOR CORROSION FITTINGS (PROBE, COUPON AND CHEMICAL INJECTION QUILL) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 09:46:15 | zm167dc@jutal.com | 20-Jul-2026 12:00:00 | Jumpol Sudjitjul | 30-Jul-2026 | 22-Jul-2026 22:36:55 | Thanapat Sombatwattana | 31-Jul-2026 | 06-Aug-2026 16:06:33 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:31:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 09:19:49 | 07-Aug-2026 03:24:28 | 0 |  |  | Approver | Locate
AO-001078 | MM-ASK-1A-GEN01-PIP-DTS-0002 | DATASHEET FOR CORROSION FITTINGS (PROBE, COUPON AND CHEMICAL INJECTION QUILL) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:20:18 | zm167dc@jutal.com | 24-Aug-2026 18:37:15 | Jumpol Sudjitjul | 02-Sep-2026 | 02-Sep-2026 10:01:06 | Thanapat Sombatwattana | 03-Sep-2026 | 03-Sep-2026 16:21:24 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 05-Sep-2026 23:54:37 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:20:04 | 06-Sep-2026 03:04:08 | 0 |  |  | Approver | Locate
AO-000288 | MM-ASK-1A-GEN01-PIP-DTS-0009 | DATASHEET FOR QUICK OPENING CLOSURE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 17:39:35 | zm167dc@jutal.com | 20-May-2026 08:56:37 | Jumpol Sudjitjul | 28-May-2026 | 29-May-2026 17:45:07 | Thanapat Sombatwattana | 29-May-2026 | 02-Jun-2026 09:56:22 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 10-Jun-2026 01:37:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 10-Jun-2026 11:55:46 | 10-Jun-2026 06:44:14 | 0 |  |  | Approver | Locate
AO-000385 | MM-ASK-1A-GEN01-PIP-LIS-0001 | PIPING STRESS CRITICAL LINE LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:49:58 | zm167dc@jutal.com | 29-May-2026 19:13:08 | Jumpol Sudjitjul | 11-Jun-2026 |  | Thanapat Sombatwattana | 12-Jun-2026 | 16-Jun-2026 23:45:54 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 18-Jun-2026 09:58:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 18-Jun-2026 10:12:05 | 18-Jun-2026 03:41:14 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-GEN01-PIP-LIS-0001 | PIPING STRESS CRITICAL LINE LIST |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 09:46:50 | zm167dc@jutal.com | 20-Jul-2026 11:58:23 | Jumpol Sudjitjul | 30-Jul-2026 |  | Thanapat Sombatwattana | 31-Jul-2026 | 06-Aug-2026 10:39:21 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:30:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 09:20:21 | 07-Aug-2026 03:25:57 | 0 |  |  | Approver | Locate
AO-001074 | MM-ASK-1A-GEN01-PIP-LIS-0001 | PIPING STRESS CRITICAL LINE LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:34:51 | zm167dc@jutal.com | 24-Aug-2026 18:26:11 | Jumpol Sudjitjul | 02-Sep-2026 | 31-Aug-2026 16:17:00 | Thanapat Sombatwattana | 03-Sep-2026 | 03-Sep-2026 14:04:26 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 05-Sep-2026 23:55:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:21:27 | 06-Sep-2026 02:56:13 | 0 |  |  | Approver | Locate
AO-000383 | MM-ASK-1A-GEN01-PIP-LIS-0002 | PIPING SPECIALTY ITEM LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:38:05 | zm167dc@jutal.com | 29-May-2026 17:43:02 | Jumpol Sudjitjul | 11-Jun-2026 |  | Thanapat Sombatwattana | 12-Jun-2026 | 16-Jun-2026 02:06:26 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 18-Jun-2026 09:50:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 18-Jun-2026 09:51:58 | 18-Jun-2026 03:48:49 | 0 |  |  | Approver | Locate
AO-000727 | MM-ASK-1A-GEN01-PIP-LIS-0002 | PIPING SPECIALTY ITEM LIST |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 09:47:19 | zm167dc@jutal.com | 20-Jul-2026 11:58:49 | Jumpol Sudjitjul | 30-Jul-2026 | 04-Aug-2026 17:31:17 | Thanapat Sombatwattana | 31-Jul-2026 | 06-Aug-2026 16:05:32 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:31:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 09:22:13 | 07-Aug-2026 03:27:19 | 0 |  |  | Approver | Locate
AO-001067 | MM-ASK-1A-GEN01-PIP-LIS-0002 | PIPING SPECIALTY ITEM LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 17:25:52 | zm167dc@jutal.com | 21-Aug-2026 17:47:36 | Jumpol Sudjitjul | 01-Sep-2026 |  | Thanapat Sombatwattana | 02-Sep-2026 | 03-Sep-2026 11:13:26 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 05-Sep-2026 17:53:07 | APPR | Approved | Jumpol Sudjitjul | 04-Sep-2026 | 05-Sep-2026 17:56:46 | 05-Sep-2026 11:23:16 | 0 |  |  | Approver | Locate
AO-000333 | MM-ASK-1A-GEN01-PIP-MR-0001 | MATERIAL REQUISITION FOR BALL VALVE (FLANGE END) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 25-May-2026 09:46:10 | zm167dc@jutal.com | 25-May-2026 11:16:04 | Jumpol Sudjitjul | 04-Jun-2026 | 08-Jun-2026 15:11:24 | Thanapat Sombatwattana | 05-Jun-2026 | 09-Jun-2026 23:49:45 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:22:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 08:15:33 | 11-Jun-2026 01:48:43 | 0 |  |  | Approver | Locate
AO-001028 | MM-ASK-1A-GEN01-PIP-MR-0001 | MATERIAL REQUISITION FOR BALL VALVE (FLANGE END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:46:22 | zm167dc@jutal.com | 20-Aug-2026 09:01:20 | Jumpol Sudjitjul | 28-Aug-2026 |  | Thanapat Sombatwattana | 31-Aug-2026 | 21-Aug-2026 10:47:37 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 13:27:55 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 09:44:02 | 24-Aug-2026 03:48:15 | 0 |  |  | Approver | Locate
AO-000333 | MM-ASK-1A-GEN01-PIP-MR-0002 | MATERIAL REQUISITION FOR BALL VALVE (WELDED END) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 25-May-2026 09:46:46 | zm167dc@jutal.com | 25-May-2026 11:16:29 | Jumpol Sudjitjul | 04-Jun-2026 | 08-Jun-2026 15:12:06 | Thanapat Sombatwattana | 05-Jun-2026 | 09-Jun-2026 23:50:02 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:22:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 08:16:05 | 11-Jun-2026 01:49:49 | 0 |  |  | Approver | Locate
AO-001028 | MM-ASK-1A-GEN01-PIP-MR-0002 | MATERIAL REQUISITION FOR BALL VALVE (WELDED END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:46:57 | zm167dc@jutal.com | 20-Aug-2026 09:01:20 | Jumpol Sudjitjul | 28-Aug-2026 |  | Thanapat Sombatwattana | 31-Aug-2026 | 21-Aug-2026 10:47:48 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 14:53:16 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 09:45:18 | 24-Aug-2026 03:50:16 | 0 |  |  | Approver | Locate
AO-000333 | MM-ASK-1A-GEN01-PIP-MR-0003 | MATERIAL REQUISITION FOR GLOBE VALVE (FLANGE END) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 25-May-2026 09:47:23 | zm167dc@jutal.com | 25-May-2026 12:47:19 | Jumpol Sudjitjul | 04-Jun-2026 | 08-Jun-2026 15:12:49 | Thanapat Sombatwattana | 05-Jun-2026 | 09-Jun-2026 23:50:23 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:22:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 08:16:56 | 11-Jun-2026 01:50:58 | 0 |  |  | Approver | Locate
AO-001028 | MM-ASK-1A-GEN01-PIP-MR-0003 | MATERIAL REQUISITION FOR GLOBE VALVE (FLANGE END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:47:41 | zm167dc@jutal.com | 20-Aug-2026 09:01:20 | Jumpol Sudjitjul | 28-Aug-2026 |  | Thanapat Sombatwattana | 31-Aug-2026 | 21-Aug-2026 10:48:04 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 13:26:15 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 09:46:34 | 24-Aug-2026 03:51:24 | 0 |  |  | Approver | Locate
AO-000333 | MM-ASK-1A-GEN01-PIP-MR-0004 | MATERIAL REQUISITION FOR GLOBE VALVE (WELDED END) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 25-May-2026 09:47:55 | zm167dc@jutal.com | 25-May-2026 12:47:40 | Jumpol Sudjitjul | 04-Jun-2026 | 08-Jun-2026 15:13:31 | Thanapat Sombatwattana | 05-Jun-2026 | 09-Jun-2026 23:51:01 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:23:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 08:18:40 | 11-Jun-2026 01:52:04 | 0 |  |  | Approver | Locate
AO-001028 | MM-ASK-1A-GEN01-PIP-MR-0004 | MATERIAL REQUISITION FOR GLOBE VALVE (WELDED END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:48:08 | zm167dc@jutal.com | 20-Aug-2026 09:01:20 | Jumpol Sudjitjul | 28-Aug-2026 |  | Thanapat Sombatwattana | 31-Aug-2026 | 21-Aug-2026 10:47:25 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 14:54:03 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 09:53:40 | 24-Aug-2026 03:56:19 | 0 |  |  | Approver | Locate
AO-000333 | MM-ASK-1A-GEN01-PIP-MR-0005 | MATERIAL REQUISITION FOR CHECK VALVE (FLANGE END) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 25-May-2026 09:48:26 | zm167dc@jutal.com | 25-May-2026 12:50:09 | Jumpol Sudjitjul | 04-Jun-2026 | 08-Jun-2026 15:14:11 | Thanapat Sombatwattana | 05-Jun-2026 | 09-Jun-2026 23:51:23 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:23:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 08:20:20 | 11-Jun-2026 01:53:08 | 0 |  |  | Approver | Locate
AO-001028 | MM-ASK-1A-GEN01-PIP-MR-0005 | MATERIAL REQUISITION FOR CHECK VALVE (FLANGE END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:48:41 | zm167dc@jutal.com | 20-Aug-2026 09:01:26 | Jumpol Sudjitjul | 28-Aug-2026 |  | Thanapat Sombatwattana | 31-Aug-2026 | 21-Aug-2026 10:48:32 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 13:24:59 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 09:42:29 | 24-Aug-2026 03:46:21 | 0 |  |  | Approver | Locate
AO-000333 | MM-ASK-1A-GEN01-PIP-MR-0006 | MATERIAL REQUISITION FOR CHECK VALVE (WELDED END) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 25-May-2026 09:48:53 | zm167dc@jutal.com | 25-May-2026 12:50:32 | Jumpol Sudjitjul | 04-Jun-2026 | 08-Jun-2026 15:14:52 | Thanapat Sombatwattana | 05-Jun-2026 | 09-Jun-2026 23:52:12 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:23:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 08:20:55 | 11-Jun-2026 01:54:19 | 0 |  |  | Approver | Locate
AO-001028 | MM-ASK-1A-GEN01-PIP-MR-0006 | MATERIAL REQUISITION FOR CHECK VALVE (WELDED END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:49:13 | zm167dc@jutal.com | 20-Aug-2026 09:01:21 | Jumpol Sudjitjul | 28-Aug-2026 |  | Thanapat Sombatwattana | 31-Aug-2026 | 21-Aug-2026 10:48:16 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 13:25:39 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 09:54:38 | 24-Aug-2026 03:57:31 | 0 |  |  | Approver | Locate
AO-000333 | MM-ASK-1A-GEN01-PIP-MR-0007 | MATERIAL REQUISITION FOR COMPACT CHECK VALVE (WELDED END) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 25-May-2026 09:49:41 | zm167dc@jutal.com | 25-May-2026 12:51:34 | Jumpol Sudjitjul | 04-Jun-2026 | 08-Jun-2026 15:15:46 | Thanapat Sombatwattana | 05-Jun-2026 | 09-Jun-2026 23:52:32 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:24:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 08:21:42 | 11-Jun-2026 01:55:28 | 0 |  |  | Approver | Locate
AO-001028 | MM-ASK-1A-GEN01-PIP-MR-0007 | MATERIAL REQUISITION FOR COMPACT CHECK VALVE (WELDED END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:49:58 | zm167dc@jutal.com | 20-Aug-2026 09:01:26 | Jumpol Sudjitjul | 28-Aug-2026 |  | Thanapat Sombatwattana | 31-Aug-2026 | 20-Aug-2026 11:24:47 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 14:56:07 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 09:55:32 | 24-Aug-2026 03:58:37 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-GEN01-PIP-MR-0008 | MATERIAL REQUISITION FOR PIPES, FITTINGS AND FLANGES (CARBON STEEL) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:02:38 | zm167dc@jutal.com | 26-Jul-2026 22:41:59 | Jumpol Sudjitjul | 06-Aug-2026 | 28-Jul-2026 06:48:53 | Thanapat Sombatwattana | 07-Aug-2026 | 06-Aug-2026 16:55:51 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:29:58 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 10:55:51 | 10-Aug-2026 05:06:33 | 0 |  |  | Approver | Locate
AO-001327 | MM-ASK-1A-GEN01-PIP-MR-0008 | MATERIAL REQUISITION FOR PIPES, FITTINGS AND FLANGES (CARBON STEEL) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:15:53 | zm167dc@jutal.com | 11-Sep-2026 20:20:32 | Jumpol Sudjitjul | 22-Sep-2026 | 14-Sep-2026 17:09:56 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000714 | MM-ASK-1A-GEN01-PIP-MR-0011 | MATERIAL REQUISITION FOR PIPES, FITTINGS AND FLANGES (STAINLESS STEEL AND DUPLEX STAINLESS STEEL) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 11:52:24 | zm167dc@jutal.com | 17-Jul-2026 11:55:50 | Jumpol Sudjitjul | 27-Jul-2026 |  | Thanapat Sombatwattana | 30-Jul-2026 | 24-Jul-2026 08:04:19 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:14:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 09:05:50 | 27-Jul-2026 02:23:23 | 0 |  |  | Approver | Locate
AO-001328 | MM-ASK-1A-GEN01-PIP-MR-0011 | MATERIAL REQUISITION FOR PIPES, FITTINGS AND FLANGES (STAINLESS STEEL AND DUPLEX STAINLESS STEEL) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:16:30 | zm167dc@jutal.com | 11-Sep-2026 20:20:34 | Jumpol Sudjitjul | 22-Sep-2026 | 18-Sep-2026 13:18:04 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000773 | MM-ASK-1A-GEN01-PIP-MR-0014 | MATERIAL REQUISITION FOR STUD BOLTS AND NUTS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:03:13 | zm167dc@jutal.com | 26-Jul-2026 22:41:19 | Jumpol Sudjitjul | 06-Aug-2026 | 28-Jul-2026 06:47:28 | Thanapat Sombatwattana | 07-Aug-2026 | 06-Aug-2026 16:52:03 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:30:21 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:02:02 | 10-Aug-2026 05:09:23 | 0 |  |  | Approver | Locate
AO-001334 | MM-ASK-1A-GEN01-PIP-MR-0014 | MATERIAL REQUISITION FOR STUD BOLTS AND NUTS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:17:07 | zm167dc@jutal.com | 11-Sep-2026 20:20:38 | Jumpol Sudjitjul | 22-Sep-2026 | 14-Sep-2026 17:05:16 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000773 | MM-ASK-1A-GEN01-PIP-MR-0015 | MATERIAL REQUISITION FOR GASKETS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:03:41 | zm167dc@jutal.com | 26-Jul-2026 22:41:41 | Jumpol Sudjitjul | 06-Aug-2026 | 28-Jul-2026 07:07:43 | Thanapat Sombatwattana | 07-Aug-2026 | 06-Aug-2026 16:51:43 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:30:42 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:03:26 | 10-Aug-2026 05:10:50 | 0 |  |  | Approver | Locate
AO-001338 | MM-ASK-1A-GEN01-PIP-MR-0015 | MATERIAL REQUISITION FOR GASKETS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:17:35 | zm167dc@jutal.com | 11-Sep-2026 20:20:41 | Jumpol Sudjitjul | 22-Sep-2026 | 14-Sep-2026 17:01:25 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000362 | MM-ASK-1A-GEN01-PIP-MR-0016 | MATERIAL REQUISITION FOR PIPE SUPPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 27-May-2026 16:12:03 | zm167dc@jutal.com | 27-May-2026 16:28:19 | Jumpol Sudjitjul | 08-Jun-2026 | 10-Jun-2026 16:42:24 | Thanapat Sombatwattana | 09-Jun-2026 | 11-Jun-2026 15:01:45 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 11-Jun-2026 22:08:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 12-Jun-2026 09:13:58 | 12-Jun-2026 03:02:19 | 0 |  |  | Approver | Locate
AO-000362 | MM-ASK-1A-GEN01-PIP-MR-0017 | MATERIAL REQUISITION FOR CORROSION FITTINGS (PROBE, COUPON AND CHEMICAL INJECTION QUILL) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 27-May-2026 16:12:41 | zm167dc@jutal.com | 27-May-2026 16:29:06 | Jumpol Sudjitjul | 08-Jun-2026 | 10-Jun-2026 16:43:12 | Thanapat Sombatwattana | 09-Jun-2026 | 11-Jun-2026 15:02:30 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 11-Jun-2026 22:17:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 12-Jun-2026 09:13:08 | 12-Jun-2026 02:36:25 | 0 |  |  | Approver | Locate
AO-001349 | MM-ASK-1A-GEN01-PIP-MR-0017 | MATERIAL REQUISITION FOR CORROSION FITTINGS (PROBE, COUPON AND CHEMICAL INJECTION QUILL) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:00:08 | zm167dc@jutal.com | 15-Sep-2026 13:43:56 | Jumpol Sudjitjul | 23-Sep-2026 | 17-Sep-2026 17:46:38 | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000362 | MM-ASK-1A-GEN01-PIP-MR-0018 | MATERIAL REQUISITION FOR HOSE AND HOSE CONNECTOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 27-May-2026 16:13:29 | zm167dc@jutal.com | 27-May-2026 16:29:49 | Jumpol Sudjitjul | 08-Jun-2026 | 10-Jun-2026 16:53:28 | Thanapat Sombatwattana | 09-Jun-2026 | 11-Jun-2026 15:02:56 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 11-Jun-2026 22:20:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 12-Jun-2026 09:12:42 | 12-Jun-2026 02:35:21 | 0 |  |  | Approver | Locate
AO-001338 | MM-ASK-1A-GEN01-PIP-MR-0018 | MATERIAL REQUISITION FOR HOSE AND HOSE CONNECTOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:18:03 | zm167dc@jutal.com | 11-Sep-2026 20:20:35 | Jumpol Sudjitjul | 22-Sep-2026 | 18-Sep-2026 13:30:05 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000362 | MM-ASK-1A-GEN01-PIP-MR-0019 | MATERIAL REQUISITION FOR STRAINER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 27-May-2026 16:13:55 | zm167dc@jutal.com | 27-May-2026 16:49:09 | Jumpol Sudjitjul | 08-Jun-2026 | 10-Jun-2026 16:57:25 | Thanapat Sombatwattana | 09-Jun-2026 | 11-Jun-2026 15:03:39 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 11-Jun-2026 22:22:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 12-Jun-2026 09:11:08 | 12-Jun-2026 02:31:59 | 0 |  |  | Approver | Locate
AO-001338 | MM-ASK-1A-GEN01-PIP-MR-0019 | MATERIAL REQUISITION FOR STRAINER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:18:32 | zm167dc@jutal.com | 11-Sep-2026 20:20:33 | Jumpol Sudjitjul | 22-Sep-2026 | 18-Sep-2026 13:19:40 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000362 | MM-ASK-1A-GEN01-PIP-MR-0020 | MATERIAL REQUISITION FOR LIQUID TRAP |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 27-May-2026 16:14:21 | zm167dc@jutal.com | 27-May-2026 16:46:22 | Jumpol Sudjitjul | 08-Jun-2026 | 10-Jun-2026 16:54:28 | Thanapat Sombatwattana | 09-Jun-2026 | 11-Jun-2026 15:03:18 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 11-Jun-2026 22:21:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 12-Jun-2026 09:12:16 | 12-Jun-2026 02:34:16 | 0 |  |  | Approver | Locate
AO-001338 | MM-ASK-1A-GEN01-PIP-MR-0020 | MATERIAL REQUISITION FOR LIQUID TRAP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:19:02 | zm167dc@jutal.com | 11-Sep-2026 20:20:34 | Jumpol Sudjitjul | 22-Sep-2026 | 14-Sep-2026 16:39:46 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000362 | MM-ASK-1A-GEN01-PIP-MR-0021 | MATERIAL REQUISITION FOR G-CLAMP |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 27-May-2026 16:14:49 | zm167dc@jutal.com | 28-May-2026 11:33:49 | Jumpol Sudjitjul | 09-Jun-2026 | 10-Jun-2026 16:58:15 | Thanapat Sombatwattana | 10-Jun-2026 | 11-Jun-2026 15:04:00 | Pornlert Wanaphattharaphan | 11-Jun-2026 | 11-Jun-2026 22:23:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-Jun-2026 | 12-Jun-2026 09:11:53 | 12-Jun-2026 02:33:09 | 0 |  |  | Approver | Locate
AO-001338 | MM-ASK-1A-GEN01-PIP-MR-0021 | MATERIAL REQUISITION FOR G-CLAMP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:19:43 | zm167dc@jutal.com | 11-Sep-2026 20:20:37 | Jumpol Sudjitjul | 22-Sep-2026 | 18-Sep-2026 13:28:56 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000362 | MM-ASK-1A-GEN01-PIP-MR-0022 | MATERIAL REQUISITION FOR FLAME ARRESTOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 27-May-2026 16:15:14 | zm167dc@jutal.com | 28-May-2026 11:34:21 | Jumpol Sudjitjul | 09-Jun-2026 | 10-Jun-2026 16:58:59 | Thanapat Sombatwattana | 10-Jun-2026 | 11-Jun-2026 15:04:19 | Pornlert Wanaphattharaphan | 11-Jun-2026 | 11-Jun-2026 22:23:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-Jun-2026 | 12-Jun-2026 09:10:40 | 12-Jun-2026 02:30:49 | 0 |  |  | Approver | Locate
AO-001338 | MM-ASK-1A-GEN01-PIP-MR-0022 | MATERIAL REQUISITION FOR FLAME ARRESTOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:20:26 | zm167dc@jutal.com | 11-Sep-2026 20:20:38 | Jumpol Sudjitjul | 22-Sep-2026 | 18-Sep-2026 13:31:08 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000307 | MM-ASK-1A-GEN01-PIP-MR-0023 | MATERIAL REQUISITION FOR QUICK OPENING CLOSURE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 21-May-2026 15:41:11 | zm167dc@jutal.com | 21-May-2026 17:43:33 | Jumpol Sudjitjul | 02-Jun-2026 | 29-May-2026 17:44:36 | Thanapat Sombatwattana | 04-Jun-2026 | 08-Jun-2026 17:03:29 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 09-Jun-2026 09:49:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 11:16:36 | 09-Jun-2026 04:48:18 | 0 |  |  | Approver | Locate
AO-001063 | MM-ASK-1A-GEN01-PIP-MR-0023 | MATERIAL REQUISITION FOR QUICK OPENING CLOSURE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 17:26:21 | zm167dc@jutal.com | 21-Aug-2026 17:43:49 | Jumpol Sudjitjul | 01-Sep-2026 | 25-Aug-2026 13:29:04 | Thanapat Sombatwattana | 02-Sep-2026 | 26-Aug-2026 10:47:14 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 30-Aug-2026 00:06:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 30-Aug-2026 15:48:17 | 30-Aug-2026 09:42:22 | 0 |  |  | Approver | Locate
AO-000362 | MM-ASK-1A-GEN01-PIP-MR-0024 | MATERIAL REQUISITION FOR SIGHT GLASS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 27-May-2026 16:15:39 | zm167dc@jutal.com | 28-May-2026 11:34:47 | Jumpol Sudjitjul | 09-Jun-2026 | 10-Jun-2026 16:59:48 | Thanapat Sombatwattana | 10-Jun-2026 | 11-Jun-2026 15:04:38 | Pornlert Wanaphattharaphan | 11-Jun-2026 | 11-Jun-2026 22:24:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-Jun-2026 | 12-Jun-2026 09:10:25 | 12-Jun-2026 02:29:38 | 0 |  |  | Approver | Locate
AO-001349 | MM-ASK-1A-GEN01-PIP-MR-0024 | MATERIAL REQUISITION FOR SIGHT GLASS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:00:44 | zm167dc@jutal.com | 15-Sep-2026 13:44:35 | Jumpol Sudjitjul | 23-Sep-2026 | 17-Sep-2026 17:50:07 | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001417 | MM-ASK-1A-GEN01-PIP-MR-0025 | MATERIAL REQUISITION FOR PIPES, FITTINGS AND FLANGES (UPVC) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | In Review | IFR | Issued for Review |  | 16-Sep-2026 17:35:51 | zm167dc@jutal.com | 17-Sep-2026 10:25:02 | Jumpol Sudjitjul | 25-Sep-2026 | 17-Sep-2026 17:51:36 | Thanapat Sombatwattana | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-GEN01-PIP-MR-2002 | MATERIAL REQUISITION FOR BARRED TEE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 16:07:34 | zm167dc@jutal.com | 07-Jul-2026 18:43:16 | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 10:29:32 | Thanapat Sombatwattana | 17-Jul-2026 | 17-Jul-2026 11:59:39 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 19-Jul-2026 16:50:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:36:15 | 20-Jul-2026 04:24:11 | 0 |  |  | Approver | Locate
AO-001210 | MM-ASK-1A-GEN01-PIP-MR-2002 | MATERIAL REQUISITION FOR BARRED TEE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:16:43 | zm167dc@jutal.com | 08-Sep-2026 10:06:22 | Jumpol Sudjitjul | 16-Sep-2026 | 16-Sep-2026 14:14:59 | Thanapat Sombatwattana | 17-Sep-2026 | 16-Sep-2026 15:04:59 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 00:27:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 14:51:05 | 20-Sep-2026 08:26:55 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-GEN01-PIP-MR-2003 | MATERIAL REQUISITION FOR PIGGABLE WYE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 16:07:59 | zm167dc@jutal.com | 08-Jul-2026 14:26:12 | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 10:31:34 | Thanapat Sombatwattana | 17-Jul-2026 | 17-Jul-2026 11:59:26 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 19-Jul-2026 16:40:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:36:42 | 20-Jul-2026 04:25:29 | 0 |  |  | Approver | Locate
AO-001211 | MM-ASK-1A-GEN01-PIP-MR-2003 | MATERIAL REQUISITION FOR PIGGABLE WYE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:17:15 | zm167dc@jutal.com | 08-Sep-2026 10:06:58 | Jumpol Sudjitjul | 16-Sep-2026 | 16-Sep-2026 14:19:07 | Thanapat Sombatwattana | 17-Sep-2026 | 16-Sep-2026 15:04:46 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 23:04:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 08:37:51 | 18-Sep-2026 02:06:49 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-GEN01-PIP-MR-2004 | MATERIAL REQUISITION FOR BARREL REDUCER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 16:08:23 | zm167dc@jutal.com | 08-Jul-2026 14:27:07 | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 10:33:40 | Thanapat Sombatwattana | 17-Jul-2026 | 17-Jul-2026 11:59:16 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 19-Jul-2026 16:46:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:37:41 | 20-Jul-2026 04:17:00 | 0 |  |  | Approver | Locate
AO-001214 | MM-ASK-1A-GEN01-PIP-MR-2004 | MATERIAL REQUISITION FOR BARREL REDUCER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:17:43 | zm167dc@jutal.com | 08-Sep-2026 10:07:29 | Jumpol Sudjitjul | 16-Sep-2026 | 16-Sep-2026 14:21:15 | Thanapat Sombatwattana | 17-Sep-2026 | 16-Sep-2026 15:04:33 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 16:20:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 17-Sep-2026 16:23:34 | 17-Sep-2026 10:16:42 | 0 |  |  | Approver | Locate
AO-000326 | MM-ASK-1A-GEN01-PIP-RPT-0001 | 3D MODEL REVIEW REPORT - (30%) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:38:59 | zm167dc@jutal.com | 23-May-2026 09:15:00 | Jumpol Sudjitjul | 02-Jun-2026 | 08-Jun-2026 11:59:15 | Thanapat Sombatwattana | 04-Jun-2026 | 09-Jun-2026 12:44:11 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:16:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 08:22:29 | 11-Jun-2026 01:56:46 | 0 |  |  | Approver | Locate
AO-000836 | MM-ASK-1A-GEN01-PIP-RPT-0001 | 3D MODEL REVIEW REPORT - (30%) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:14:56 | zm167dc@jutal.com | 31-Jul-2026 21:50:56 | Jumpol Sudjitjul | 11-Aug-2026 | 03-Aug-2026 07:49:29 | Thanapat Sombatwattana | 13-Aug-2026 | 17-Aug-2026 09:24:07 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 20-Aug-2026 22:50:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 21-Aug-2026 08:50:13 | 21-Aug-2026 02:25:41 | 0 |  |  | Approver | Locate
AO-001320 | MM-ASK-1A-GEN01-PIP-RPT-0001 | 3D MODEL REVIEW REPORT - (30%) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:21:13 | zm167dc@jutal.com | 11-Sep-2026 20:22:41 | Jumpol Sudjitjul | 22-Sep-2026 |  | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001138 | MM-ASK-1A-GEN01-PIP-RPT-0002 | 3D MODEL REVIEW REPORT - (60%) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 29-Aug-2026 13:57:38 | zm167dc@jutal.com | 29-Aug-2026 14:06:55 | Jumpol Sudjitjul | 07-Sep-2026 |  | Thanapat Sombatwattana | 08-Sep-2026 | 13-Sep-2026 16:11:25 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 13-Sep-2026 16:52:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 13-Sep-2026 22:36:35 | 13-Sep-2026 15:53:41 | 0 |  |  | Approver | Locate
AO-000337 | MM-ASK-1A-GEN01-PIP-RPT-0004 | DRILLING RIG CLASH CHECK REPORT : WP01 AND WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 15:27:57 | zm167dc@jutal.com | 25-May-2026 22:11:03 | Jumpol Sudjitjul | 05-Jun-2026 | 08-Jun-2026 17:37:33 | Thanapat Sombatwattana | 08-Jun-2026 | 13-Jun-2026 14:08:55 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 13-Jun-2026 23:14:06 | NA | Not Approved | Jumpol Sudjitjul | 10-Jun-2026 | 14-Jun-2026 21:45:23 | 14-Jun-2026 15:02:25 | 0 |  |  | Approver | Locate
AO-001075 | MM-ASK-1A-GEN01-PIP-RPT-0004 | DRILLING RIG CLASH CHECK REPORT : WP01 AND WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:36:12 | zm167dc@jutal.com | 24-Aug-2026 18:27:22 | Jumpol Sudjitjul | 02-Sep-2026 | 02-Sep-2026 09:13:28 | Thanapat Sombatwattana | 03-Sep-2026 | 04-Sep-2026 11:40:42 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 05-Sep-2026 23:47:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:22:17 | 06-Sep-2026 03:13:39 | 0 |  |  | Approver | Locate
AO-000308 | MM-ASK-1A-GEN01-PIP-RPT-0005 | CRITICALITY RATING REPORT FOR PIPING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 15:41:37 | zm167dc@jutal.com | 21-May-2026 17:45:34 | Jumpol Sudjitjul | 02-Jun-2026 | 04-Jun-2026 14:12:38 | Thanapat Sombatwattana | 04-Jun-2026 | 08-Jun-2026 17:38:31 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:15:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:00:07 | 11-Jun-2026 02:31:23 | 0 |  |  | Approver | Locate
AO-001027 | MM-ASK-1A-GEN01-PIP-RPT-0005 | CRITICALITY RATING REPORT FOR PIPING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:50:34 | zm167dc@jutal.com | 20-Aug-2026 09:05:08 | Jumpol Sudjitjul | 28-Aug-2026 |  | Thanapat Sombatwattana | 31-Aug-2026 | 31-Aug-2026 10:56:35 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 02-Sep-2026 23:33:04 | APPR | Approved | Soontaree Simpitak | 02-Sep-2026 | 03-Sep-2026 07:35:42 | 03-Sep-2026 00:54:13 | 0 |  |  | Approver | Locate
AO-000382 | MM-ASK-1A-GEN01-PIP-SPE-0001 | PIPING MATERIAL SPECIFICATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:38:40 | zm167dc@jutal.com | 29-May-2026 17:45:14 | Jumpol Sudjitjul | 11-Jun-2026 | 15-Jun-2026 07:37:07 | Thanapat Sombatwattana | 12-Jun-2026 | 17-Jun-2026 01:11:40 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 18-Jun-2026 09:59:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 18-Jun-2026 10:13:39 | 18-Jun-2026 03:50:03 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-GEN01-PIP-SPE-0001 | PIPING MATERIAL SPECIFICATION |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 07-Jul-2026 16:08:50 | zm167dc@jutal.com | 07-Jul-2026 18:35:36 | Jumpol Sudjitjul | 16-Jul-2026 | 16-Jul-2026 16:03:32 | Thanapat Sombatwattana | 17-Jul-2026 | 17-Jul-2026 11:37:58 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 01:02:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:41:12 | 20-Jul-2026 04:26:45 | 0 |  |  | Approver | Locate
AO-000787 | MM-ASK-1A-GEN01-PIP-TBE-0001 | TECHNICAL BID EVALUATION FOR BALL VALVE (FLANGE END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:48:42 | zm167dc@jutal.com | 26-Jul-2026 23:21:08 | Jumpol Sudjitjul | 06-Aug-2026 | 30-Jul-2026 16:32:53 | Thanapat Sombatwattana | 07-Aug-2026 | 04-Aug-2026 11:19:34 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 05-Aug-2026 17:21:05 | NA | Not Approved | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 08:37:03 | 06-Aug-2026 02:34:09 | 0 |  |  | Approver | Locate
AO-001004 | MM-ASK-1A-GEN01-PIP-TBE-0001 | TECHNICAL BID EVALUATION FOR BALL VALVE (FLANGE END) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 12:46:39 | zm167dc@jutal.com | 17-Aug-2026 13:36:05 | Jumpol Sudjitjul | 25-Aug-2026 |  | Thanapat Sombatwattana | 26-Aug-2026 | 19-Aug-2026 09:18:13 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 20-Aug-2026 08:46:27 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 20-Aug-2026 08:53:27 | 20-Aug-2026 02:46:11 | 0 |  |  | Approver | Locate
AO-000792 | MM-ASK-1A-GEN01-PIP-TBE-0002 | TECHNICAL BID EVALUATION FOR BALL VALVE (WELDED END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:49:13 | zm167dc@jutal.com | 26-Jul-2026 23:21:08 | Jumpol Sudjitjul | 06-Aug-2026 | 30-Jul-2026 16:33:24 | Thanapat Sombatwattana | 07-Aug-2026 | 04-Aug-2026 11:19:47 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 05-Aug-2026 17:22:15 | NA | Not Approved | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 08:37:32 | 06-Aug-2026 02:35:35 | 0 |  |  | Approver | Locate
AO-001029 | MM-ASK-1A-GEN01-PIP-TBE-0002 | TECHNICAL BID EVALUATION FOR BALL VALVE (WELDED END) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:51:14 | zm167dc@jutal.com | 20-Aug-2026 09:15:27 | Jumpol Sudjitjul | 28-Aug-2026 |  | Thanapat Sombatwattana | 31-Aug-2026 | 20-Aug-2026 11:30:36 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 14:02:14 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 08:25:35 | 24-Aug-2026 01:51:50 | 0 |  |  | Approver | Locate
AO-000786 | MM-ASK-1A-GEN01-PIP-TBE-0003 | TECHNICAL BID EVALUATION FOR GLOBE VALVE (FLANGE END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 17:33:57 | zm167dc@jutal.com | 26-Jul-2026 23:21:10 | Jumpol Sudjitjul | 06-Aug-2026 | 30-Jul-2026 16:33:53 | Thanapat Sombatwattana | 07-Aug-2026 | 04-Aug-2026 14:46:41 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 05-Aug-2026 17:19:30 | NA | Not Approved | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 08:38:03 | 06-Aug-2026 02:45:46 | 0 |  |  | Approver | Locate
AO-000955 | MM-ASK-1A-GEN01-PIP-TBE-0003 | TECHNICAL BID EVALUATION FOR GLOBE VALVE (FLANGE END) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 17:28:47 | zm167dc@jutal.com | 11-Aug-2026 17:34:49 | Jumpol Sudjitjul | 21-Aug-2026 |  | Thanapat Sombatwattana | 24-Aug-2026 | 13-Aug-2026 16:12:20 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 14-Aug-2026 00:12:24 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 14-Aug-2026 08:12:20 | 14-Aug-2026 01:18:07 | 0 |  |  | Approver | Locate
AO-000790 | MM-ASK-1A-GEN01-PIP-TBE-0004 | TECHNICAL BID EVALUATION FOR GLOBE VALVE (WELDED END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:49:44 | zm167dc@jutal.com | 26-Jul-2026 23:21:12 | Jumpol Sudjitjul | 06-Aug-2026 | 30-Jul-2026 16:34:20 | Thanapat Sombatwattana | 07-Aug-2026 | 04-Aug-2026 14:46:56 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 05-Aug-2026 17:18:00 | NA | Not Approved | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 08:40:43 | 06-Aug-2026 02:38:31 | 0 |  |  | Approver | Locate
AO-001001 | MM-ASK-1A-GEN01-PIP-TBE-0004 | TECHNICAL BID EVALUATION FOR GLOBE VALVE (WELDED END) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 18:08:32 | zm167dc@jutal.com | 15-Aug-2026 14:52:34 | Jumpol Sudjitjul | 24-Aug-2026 | 17-Aug-2026 17:01:56 | Thanapat Sombatwattana | 25-Aug-2026 | 21-Aug-2026 09:10:21 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 13:08:08 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 08:58:12 | 28-Aug-2026 09:32:43 | 0 |  |  | Approver | Locate
AO-000795 | MM-ASK-1A-GEN01-PIP-TBE-0005 | TECHNICAL BID EVALUATION FOR CHECK VALVE (FLANGE END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:50:12 | zm167dc@jutal.com | 26-Jul-2026 23:21:14 | Jumpol Sudjitjul | 06-Aug-2026 | 30-Jul-2026 16:35:15 | Thanapat Sombatwattana | 07-Aug-2026 | 04-Aug-2026 17:34:14 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 05-Aug-2026 17:14:15 | NA | Not Approved | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 08:38:40 | 06-Aug-2026 02:37:04 | 0 |  |  | Approver | Locate
AO-001091 | MM-ASK-1A-GEN01-PIP-TBE-0005 | TECHNICAL BID EVALUATION FOR CHECK VALVE (FLANGE END) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 18:39:19 | zm167dc@jutal.com | 24-Aug-2026 20:20:12 | Jumpol Sudjitjul | 02-Sep-2026 |  | Thanapat Sombatwattana | 03-Sep-2026 | 25-Aug-2026 10:10:42 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 26-Aug-2026 00:49:54 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 26-Aug-2026 08:55:42 | 26-Aug-2026 02:49:42 | 0 |  |  | Approver | Locate
AO-000785 | MM-ASK-1A-GEN01-PIP-TBE-0006 | TECHNICAL BID EVALUATION FOR CHECK VALVE (WELDED END) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 17:34:25 | zm167dc@jutal.com | 26-Jul-2026 23:21:10 | Jumpol Sudjitjul | 06-Aug-2026 | 30-Jul-2026 16:34:44 | Thanapat Sombatwattana | 07-Aug-2026 | 04-Aug-2026 17:34:31 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 05-Aug-2026 17:12:48 | NA | Not Approved | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 08:39:30 | 06-Aug-2026 02:47:11 | 0 |  |  | Approver | Locate
AO-001000 | MM-ASK-1A-GEN01-PIP-TBE-0006 | TECHNICAL BID EVALUATION FOR CHECK VALVE (WELDED END) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 18:08:59 | zm167dc@jutal.com | 15-Aug-2026 14:53:06 | Jumpol Sudjitjul | 24-Aug-2026 | 17-Aug-2026 17:20:56 | Thanapat Sombatwattana | 25-Aug-2026 | 21-Aug-2026 09:10:10 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 13:10:51 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 09:56:59 | 28-Aug-2026 09:33:59 | 0 |  |  | Approver | Locate
AO-000762 | MM-ASK-1A-GEN01-PIP-TBE-0007 | TECHNICAL BID EVALUATION FOR COMPACT CHECK VALVE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 23-Jul-2026 12:48:26 | zm167dc@jutal.com | 23-Jul-2026 16:21:14 | Jumpol Sudjitjul | 04-Aug-2026 |  | Thanapat Sombatwattana | 05-Aug-2026 | 24-Jul-2026 14:20:45 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 27-Jul-2026 01:12:23 | NA | Not Approved | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 07:55:01 | 27-Jul-2026 01:16:37 | 0 |  |  | Approver | Locate
AO-000841 | MM-ASK-1A-GEN01-PIP-TBE-0007 | TECHNICAL BID EVALUATION FOR COMPACT CHECK VALVE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 18:12:58 | zm167dc@jutal.com | 31-Jul-2026 21:48:44 | Jumpol Sudjitjul | 11-Aug-2026 | 03-Aug-2026 17:33:57 | Thanapat Sombatwattana | 13-Aug-2026 | 05-Aug-2026 16:58:55 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 06-Aug-2026 22:16:59 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 09:20:52 | 07-Aug-2026 03:14:28 | 0 |  |  | Approver | Locate
AO-001143 | MM-ASK-1A-GEN01-PIP-TBE-0008 | TECHNICAL BID EVALUATION FOR CARBON STEEL PIPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 01-Sep-2026 08:34:55 | zm167dc@jutal.com | 01-Sep-2026 10:06:56 | Soontaree Simpitak | 09-Sep-2026 |  | Thanapat Sombatwattana | 10-Sep-2026 | 02-Sep-2026 16:27:18 | Pornlert Wanaphattharaphan | 11-Sep-2026 | 02-Sep-2026 23:49:20 | NA | Not Approved | Soontaree Simpitak | 14-Sep-2026 | 03-Sep-2026 07:37:28 | 03-Sep-2026 01:00:08 | 0 |  |  | Approver | Locate
AO-001136 | MM-ASK-1A-GEN01-PIP-TBE-0009 | TECHNICAL BID EVALUATION FOR CARBON STEEL FITTINGS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE |  | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 13:58:08 | zm167dc@jutal.com | 29-Aug-2026 14:09:51 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 11:35:56 | Thanapat Sombatwattana | 08-Sep-2026 | 01-Sep-2026 17:36:07 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 01-Sep-2026 23:16:58 | NA | Not Approved | Soontaree Simpitak | 10-Sep-2026 | 02-Sep-2026 07:40:20 | 02-Sep-2026 00:52:00 | 0 |  |  | Approver | Locate
AO-001137 | MM-ASK-1A-GEN01-PIP-TBE-0010 | TECHNICAL BID EVALUATION FOR CARBON STEEL FLANGES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 13:58:33 | zm167dc@jutal.com | 29-Aug-2026 14:10:11 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 11:34:30 | Thanapat Sombatwattana | 08-Sep-2026 | 01-Sep-2026 17:35:44 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 01-Sep-2026 23:14:53 | NA | Not Approved | Soontaree Simpitak | 10-Sep-2026 | 02-Sep-2026 08:21:23 | 02-Sep-2026 01:29:26 | 0 |  |  | Approver | Locate
AO-001144 | MM-ASK-1A-GEN01-PIP-TBE-0011 | TECHNICAL BID EVALUATION FOR STAINLESS STEEL AND DUPLEX STAINLESS STEEL PIPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 01-Sep-2026 08:35:21 | zm167dc@jutal.com | 01-Sep-2026 10:12:49 | Soontaree Simpitak | 09-Sep-2026 |  | Thanapat Sombatwattana | 10-Sep-2026 | 02-Sep-2026 16:27:45 | Pornlert Wanaphattharaphan | 11-Sep-2026 | 02-Sep-2026 23:50:20 | AWC | Approved with Comment | Soontaree Simpitak | 14-Sep-2026 | 03-Sep-2026 07:39:20 | 03-Sep-2026 01:01:35 | 0 |  |  | Approver | Locate
AO-001314 | MM-ASK-1A-GEN01-PIP-TBE-0011 | TECHNICAL BID EVALUATION FOR STAINLESS STEEL AND DUPLEX STAINLESS STEEL PIPE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:21:57 | zm167dc@jutal.com | 11-Sep-2026 20:23:30 | Jumpol Sudjitjul | 22-Sep-2026 | 14-Sep-2026 17:31:03 | Thanapat Sombatwattana | 23-Sep-2026 | 16-Sep-2026 15:10:04 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 18-Sep-2026 15:31:32 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 18-Sep-2026 17:56:55 | 18-Sep-2026 11:48:44 | 0 |  |  | Approver | Locate
AO-001132 | MM-ASK-1A-GEN01-PIP-TBE-0012 | TECHNICAL BID EVALUTION FOR STAINLESS STEEL AND DUPLEX STAINLESS STEEL FITTINGS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:07:41 | zm167dc@jutal.com | 29-Aug-2026 13:34:26 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 13:22:39 | Thanapat Sombatwattana | 08-Sep-2026 | 01-Sep-2026 16:02:27 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 01-Sep-2026 23:00:46 | AWC | Approved with Comment | Soontaree Simpitak | 10-Sep-2026 | 02-Sep-2026 08:37:39 | 02-Sep-2026 02:12:55 | 0 |  |  | Approver | Locate
AO-001408 | MM-ASK-1A-GEN01-PIP-TBE-0012 | TECHNICAL BID EVALUTION FOR STAINLESS STEEL AND DUPLEX STAINLESS STEEL FITTINGS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | In Review | AFC | Approved for Construction |  | 16-Sep-2026 09:10:33 | zm167dc@jutal.com | 16-Sep-2026 17:42:47 | Jumpol Sudjitjul | 25-Sep-2026 |  | Thanapat Sombatwattana | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001133 | MM-ASK-1A-GEN01-PIP-TBE-0013 | TECHNICAL BID EVALUTION FOR STAINLESS STEEL AND DUPLEX STAINLESS STEEL FLANGES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 17:21:15 | zm167dc@jutal.com | 28-Aug-2026 17:44:17 | Jumpol Sudjitjul | 08-Sep-2026 | 01-Sep-2026 13:25:25 | Thanapat Sombatwattana | 09-Sep-2026 | 01-Sep-2026 16:02:15 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 01-Sep-2026 23:18:46 | AWC | Approved with Comment | Soontaree Simpitak | 11-Sep-2026 | 02-Sep-2026 08:39:34 | 02-Sep-2026 02:08:03 | 0 |  |  | Approver | Locate
AO-001409 | MM-ASK-1A-GEN01-PIP-TBE-0013 | TECHNICAL BID EVALUTION FOR STAINLESS STEEL AND DUPLEX STAINLESS STEEL FLANGES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | In Review | AFC | Approved for Construction |  | 16-Sep-2026 09:11:12 | zm167dc@jutal.com | 16-Sep-2026 17:43:24 | Jumpol Sudjitjul | 25-Sep-2026 |  | Thanapat Sombatwattana | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001220 | MM-ASK-1A-GEN01-PIP-TBE-0014 | TECHNICAL BID EVALUATION FOR STUD BOLTS AND NUTS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 10:01:10 | zm167dc@jutal.com | 08-Sep-2026 11:10:39 | Jumpol Sudjitjul | 16-Sep-2026 | 14-Sep-2026 13:10:26 | Thanapat Sombatwattana | 17-Sep-2026 | 17-Sep-2026 15:25:16 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 18-Sep-2026 15:28:13 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 19:16:45 | 20-Sep-2026 06:05:31 | 0 |  |  | Approver | Locate
AO-001488 | MM-ASK-1A-GEN01-PIP-TBE-0020 | TECHNICAL BID EVALUATION FOR LIQUID TRAP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 17:17:29 | zm167dc@jutal.com | 18-Sep-2026 17:27:24 | Jumpol Sudjitjul | 29-Sep-2026 |  | Thanapat Sombatwattana | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000754 | MM-ASK-1A-GEN01-PIP-TBE-0023 | TECHNICAL BID EVALUATION FOR QUICK OPENING CLOSURE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 22-Jul-2026 10:13:36 | zm167dc@jutal.com | 22-Jul-2026 11:17:59 | Jumpol Sudjitjul | 03-Aug-2026 | 22-Jul-2026 17:55:36 | Thanapat Sombatwattana | 04-Aug-2026 | 23-Jul-2026 09:30:55 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 27-Jul-2026 00:52:22 | NA | Not Approved | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 09:06:53 | 27-Jul-2026 02:24:52 | 0 |  |  | Approver | Locate
AO-000843 | MM-ASK-1A-GEN01-PIP-TBE-0023 | TECHNICAL BID EVALUATION FOR QUICK OPENING CLOSURE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 18:13:38 | zm167dc@jutal.com | 31-Jul-2026 21:49:27 | Jumpol Sudjitjul | 11-Aug-2026 | 05-Aug-2026 14:02:48 | Thanapat Sombatwattana | 13-Aug-2026 | 06-Aug-2026 16:17:21 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 06-Aug-2026 23:44:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 09:22:52 | 07-Aug-2026 03:16:05 | 0 |  |  | Approver | Locate
AO-000963 | MM-ASK-1A-GEN01-PIP-TBE-0023 | TECHNICAL BID EVALUATION FOR QUICK OPENING CLOSURE |  | C3 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 10:47:08 | zm167dc@jutal.com | 13-Aug-2026 14:07:31 | Jumpol Sudjitjul | 21-Aug-2026 |  | Thanapat Sombatwattana | 24-Aug-2026 | 13-Aug-2026 14:15:39 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 13-Aug-2026 15:22:07 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 13-Aug-2026 16:23:34 | 13-Aug-2026 09:44:33 | 0 |  |  | Approver | Locate
AO-001418 | MM-ASK-1A-GEN01-PIP-TBE-0027 | TECHNICAL BID EVALUTION FOR PIGGABLE WYE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | In Review | AFC | Approved for Construction |  | 16-Sep-2026 17:36:26 | zm167dc@jutal.com | 17-Sep-2026 10:28:21 | Jumpol Sudjitjul | 25-Sep-2026 | 19-Sep-2026 14:18:32 | Thanapat Sombatwattana | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000569 | MM-ASK-1A-GEN01-PJM-COP-0001 | CHANGE ORDER PROPOSAL - 0001 : SERVICES AND FACILITIES TO COMPANY AT CONTRACTOR'S ENGINEERING OFFICE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | COP | Change Order Proposal (Contractor To Company) | 0 | Latest | IFI | Issued for Information |  | 28-Jun-2026 09:49:17 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000570 | MM-ASK-1A-GEN01-PJM-COP-0002 | CHANGE ORDER PROPOSAL - 0002 : SERVICES AND FACILITIES TO COMPANY AT CONTRACTOR'S WORKSITE (TJE YARD, ZHUHAI, GUANGDONG, CHINA) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | COP | Change Order Proposal (Contractor To Company) | 0 | Latest | IFI | Issued for Information |  | 28-Jun-2026 09:49:47 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001221 | MM-ASK-1A-GEN01-PJM-COP-0003 | CHANGE ORDER PROPOSAL - 0003 : SERVICES AND FACILITIES TO COMPANY - TRANSPORTATION AND ACCOMMODATION FOR COMPANY |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | COP | Change Order Proposal (Contractor To Company) | 0 | Latest | IFI | Issued for Information |  | 07-Sep-2026 12:35:31 | zm167dc@jutal.com | 08-Sep-2026 11:11:53 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 09-Sep-2026 15:40:24 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001224 | MM-ASK-1A-GEN01-PJM-COP-0004 | CHANGE ORDER PROPOSAL - 0004 : SERVICES AND FACILITIES TO COMPANY - MIDDAY LUNCH AND GENERAL OFFICE COSTS AT CONTRACTOR'S WORKSITE (ZHUHAI YARD, CHINA) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | COP | Change Order Proposal (Contractor To Company) | 0 | Latest | IFI | Issued for Information |  | 07-Sep-2026 15:54:50 | zm167dc@jutal.com | 08-Sep-2026 11:12:08 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 09-Sep-2026 15:41:18 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000185 | MM-ASK-1A-GEN01-PJM-MDR-0001 | MASTER DOCUMENT DELIVERABLES REGISTER |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFR | Issued for Review |  | 10-May-2026 23:36:03 | zm167dc@jutal.com | 11-May-2026 09:10:43 | Jumpol Sudjitjul | 19-May-2026 | 25-May-2026 13:39:50 | Apisit Tangwashirakul | 20-May-2026 | 29-May-2026 08:59:05 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 11:13:03 | 29-May-2026 04:28:04 | 0 |  |  | Focal Point | Locate
AO-000853 | MM-ASK-1A-GEN01-PJM-MDR-0001 | MASTER DOCUMENT DELIVERABLES REGISTER |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:04:44 | zm167dc@jutal.com | 03-Aug-2026 11:35:19 | Jumpol Sudjitjul | 11-Aug-2026 | 26-Aug-2026 17:48:37 | Apisit Tangwashirakul | 13-Aug-2026 | 02-Sep-2026 14:42:11 |  |  |  | AWC | Approved with Comment | Soontaree Simpitak | 17-Aug-2026 | 02-Sep-2026 22:44:38 | 02-Sep-2026 15:51:13 | 0 |  |  | Focal Point | Locate
AO-000142 | MM-ASK-1A-GEN01-PJM-MOM-0001 | AUNG SINKHA PROJECT - PMT WEEKLY MEETING NO.1 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 16:32:04 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000143 | MM-ASK-1A-GEN01-PJM-MOM-0002 | AUNG SINKHA PROJECT - PMT WEEKLY MEETING NO.2 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 16:32:29 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000144 | MM-ASK-1A-GEN01-PJM-MOM-0003 | AUNG SINKHA PROJECT - PMT WEEKLY MEETING NO.3 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 16:32:54 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000403 | MM-ASK-1A-GEN01-PJM-MOM-0004 | AUNG SINKHA PROJECT - PMT WEEKLY MEETING NO.4 (2ND APR 2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 04-Jun-2026 20:45:33 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000404 | MM-ASK-1A-GEN01-PJM-MOM-0005 | AUNG SINKHA PROJECT - PMT WEEKLY MEETING NO.5 (9TH APR 2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 04-Jun-2026 20:46:07 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000543 | MM-ASK-1A-GEN01-PJM-MOM-0006 | AUNG SINKHA PROJECT - PMT WEEKLY MEETING NO.6 (16TH APR 2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 25-Jun-2026 10:46:14 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000544 | MM-ASK-1A-GEN01-PJM-MOM-0007 | AUNG SINKHA PROJECT - PMT WEEKLY MEETING NO.7 (23RD APR 2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 25-Jun-2026 10:08:05 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000545 | MM-ASK-1A-GEN01-PJM-MOM-0008 | AUNG SINKHA PROJECT - PMT WEEKLY MEETING NO.8 (30TH APR 226) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 25-Jun-2026 09:23:40 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000015 | MM-ASK-1A-GEN01-PJM-MOM-1002 | ENGINEERING KICK-OFF MEETING 5TH MARCH 2026 (13.00-16.00 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Mar-2026 11:27:32 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000095 | MM-ASK-1A-GEN01-PJM-MOM-1304 | MINUTES OF MEEING EPC-01 &EPC-03 INTERFACE MEETING NO. 4 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 29-Apr-2026 08:22:58 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000024 | MM-ASK-1A-GEN01-PJM-MPR-0001 | PROJECT MONTHLY PROGRESS REPORT NO.01 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 31-Mar-2026 15:56:20 | zm167dc@jutal.com | 31-Mar-2026 16:17:25 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul |  | 07-Jul-2026 15:43:43 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 07-Jul-2026 18:00:12 | 07-Jul-2026 11:19:56 | 0 |  |  | For Info | Locate
AO-000286 | MM-ASK-1A-GEN01-PJM-MPR-0002 | PROJECT MONTHLY PROGRESS REPORT NO.02 CUT-OFF DATE 17 APR 2026 REPORT PERIOD: 21 MAR 2026-17 APR 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | In Review | IFI | Issued for Information |  | 18-May-2026 19:35:24 | zm167dc@jutal.com | 19-May-2026 17:21:15 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000349 | MM-ASK-1A-GEN01-PJM-MPR-0003 | PROJECT MONTHLY PROGRESS REPORT NO.03 CUT-OFF DATE 15 MAY 2026 REPORT PERIOD: 18 APR 2026 – 15 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | In Review | IFI | Issued for Information |  | 26-May-2026 12:08:13 | zm167dc@jutal.com | 26-May-2026 14:34:15 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000617 | MM-ASK-1A-GEN01-PJM-MPR-0004 | PROJECT MONTHLY PROGRESS REPORT NO.04 CUT-OFF DATE 19 JUN 2026 REPORT PERIOD: 16 MAY 2026 – 19 JUN 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | In Review | IFI | Issued for Information |  | 03-Jul-2026 18:21:38 | zm167dc@jutal.com | 03-Jul-2026 18:47:00 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000781 | MM-ASK-1A-GEN01-PJM-MPR-0005 | PROJECT MONTHLY PROGRESS REPORT NO.05 CUT-OFF DATE 17 JUL 2026 REPORT PERIOD: 20 JUN 2026 – 17 JUL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | In Review | IFI | Issued for Information |  | 24-Jul-2026 17:35:22 | zm167dc@jutal.com | 26-Jul-2026 23:23:09 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-001140 | MM-ASK-1A-GEN01-PJM-MPR-0006 | PROJECT MONTHLY PROGRESS REPORT NO.06 CUT-OFF DATE 21 AUG 2026 REPORT PERIOD: 18 JUL 2026 – 21 AUG 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | In Review | IFI | Issued for Information |  | 31-Aug-2026 08:34:16 | zm167dc@jutal.com | 31-Aug-2026 11:02:52 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000004 | MM-ASK-1A-GEN01-PJM-PDR-0001 | PROJECT DOCUMENT CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 24-Feb-2026 11:23:07 | zm167dc@jutal.com | 25-Feb-2026 08:18:07 | Jumpol Sudjitjul | 06-Mar-2026 | 09-Mar-2026 11:07:27 | Apisit Tangwashirakul | 09-Mar-2026 | 11-Mar-2026 19:43:32 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 11-Mar-2026 | 12-Mar-2026 07:50:11 | 12-Mar-2026 08:25:36 | 0 |  |  | Focal Point | Locate
AO-000031 | MM-ASK-1A-GEN01-PJM-PDR-0001 | PROJECT DOCUMENT CONTROL PROCEDURE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 06:46:00 | zm167dc@jutal.com | 03-Apr-2026 07:07:18 | Jumpol Sudjitjul | 17-Apr-2026 | 20-Apr-2026 10:58:32 | Apisit Tangwashirakul | 20-Apr-2026 | 22-Apr-2026 08:52:42 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 22-Apr-2026 09:44:18 | 22-Apr-2026 04:26:38 | 0 |  |  | Focal Point | Locate
AO-000559 | MM-ASK-1A-GEN01-PJM-PDR-0001 | PROJECT DOCUMENT CONTROL PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 15:26:33 | zm167dc@jutal.com | 26-Jun-2026 16:28:28 | Jumpol Sudjitjul | 06-Jul-2026 | 24-Jul-2026 08:54:43 | Apisit Tangwashirakul | 07-Jul-2026 | 30-Jul-2026 13:46:29 |  |  |  | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jul-2026 14:03:14 | 30-Jul-2026 07:37:58 | 0 |  |  | Focal Point | Locate
AO-000817 | MM-ASK-1A-GEN01-PJM-PDR-0001 | PROJECT DOCUMENT CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 09:25:16 | zm167dc@jutal.com | 31-Jul-2026 09:28:06 | Jumpol Sudjitjul | 10-Aug-2026 | 26-Aug-2026 14:28:06 | Apisit Tangwashirakul | 11-Aug-2026 | 02-Sep-2026 14:38:59 |  |  |  | APPR | Approved | Soontaree Simpitak | 14-Aug-2026 | 03-Sep-2026 07:23:40 | 03-Sep-2026 00:51:43 | 0 |  |  | Focal Point | Locate
AO-000007 | MM-ASK-1A-GEN01-PJM-PDR-0002 | PROJECT NUMBERING PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 04-Mar-2026 11:59:52 | zm167dc@jutal.com | 04-Mar-2026 13:05:57 | Jumpol Sudjitjul | 12-Mar-2026 | 13-Mar-2026 09:10:02 | Apisit Tangwashirakul | 13-Mar-2026 | 13-Mar-2026 13:42:17 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 17-Mar-2026 | 13-Mar-2026 13:54:45 | 13-Mar-2026 14:24:56 | 0 |  |  | Focal Point | Locate
AO-000029 | MM-ASK-1A-GEN01-PJM-PDR-0002 | PROJECT NUMBERING PROCEDURE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review | 27-Mar-2026 | 02-Apr-2026 19:31:18 | zm167dc@jutal.com | 02-Apr-2026 21:01:09 | Jumpol Sudjitjul | 17-Apr-2026 | 20-Apr-2026 11:16:38 | Apisit Tangwashirakul | 20-Apr-2026 | 22-Apr-2026 12:17:24 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 22-Apr-2026 13:47:21 | 22-Apr-2026 14:17:49 | 0 |  |  | Focal Point | Locate
AO-000479 | MM-ASK-1A-GEN01-PJM-PDR-0002 | PROJECT NUMBERING PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 10:01:33 | zm167dc@jutal.com | 14-Jun-2026 21:55:05 | Jumpol Sudjitjul | 23-Jun-2026 | 15-Jul-2026 13:10:33 | Apisit Tangwashirakul | 24-Jun-2026 | 30-Jul-2026 13:48:16 |  |  |  | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 26-Jun-2026 | 30-Jul-2026 14:05:06 | 30-Jul-2026 07:28:18 | 0 |  |  | Focal Point | Locate
AO-000819 | MM-ASK-1A-GEN01-PJM-PDR-0002 | PROJECT NUMBERING PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 09:25:45 | zm167dc@jutal.com | 31-Jul-2026 09:29:07 | Jumpol Sudjitjul | 10-Aug-2026 | 26-Aug-2026 18:23:44 | Apisit Tangwashirakul | 11-Aug-2026 | 01-Sep-2026 16:48:52 |  |  |  | APPR | Approved | Soontaree Simpitak | 14-Aug-2026 | 02-Sep-2026 08:28:11 | 02-Sep-2026 02:00:03 | 0 |  |  | Focal Point | Locate
AO-001426 | MM-ASK-1A-GEN01-PJM-PDR-0002 | PROJECT NUMBERING PROCEDURE |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 09:27:27 | zm167dc@jutal.com | 18-Sep-2026 17:21:55 | Jumpol Sudjitjul | 29-Sep-2026 | 19-Sep-2026 07:47:04 | Apisit Tangwashirakul | 30-Sep-2026 | [7 empty] | 02-Oct-2026 |  |  | 0 |  |  | Focal Point | Locate
AO-000749 | MM-ASK-1A-GEN01-PJM-PDR-0004 | PROJECT RISK MANAGEMENT PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 08:36:39 | zm167dc@jutal.com | 22-Jul-2026 08:45:31 | Jumpol Sudjitjul | 03-Aug-2026 | 26-Aug-2026 17:40:57 | Apisit Tangwashirakul | 04-Aug-2026 | 02-Sep-2026 09:15:02 |  |  |  | AWC | Approved with Comment | Soontaree Simpitak | 06-Aug-2026 | 02-Sep-2026 10:36:22 | 02-Sep-2026 03:59:40 | 0 |  |  | Focal Point | Locate
AO-001213 | MM-ASK-1A-GEN01-PJM-PDR-0004 | PROJECT RISK MANAGEMENT PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | In Review | AFC | Approved for Construction |  | 07-Sep-2026 09:29:47 | zm167dc@jutal.com | 08-Sep-2026 10:30:36 | Jumpol Sudjitjul | 16-Sep-2026 | 16-Sep-2026 15:00:15 | Apisit Tangwashirakul | 17-Sep-2026 | [7 empty] | 21-Sep-2026 |  |  | 0 |  |  | Focal Point | Locate
AO-000017 | MM-ASK-1A-GEN01-PJM-PDR-0005 | PROGRESS MEASUREMENT AND REPORTING PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 24-Mar-2026 18:02:13 | zm167dc@jutal.com | 25-Mar-2026 15:20:57 | Jumpol Sudjitjul | 02-Apr-2026 |  | Jirayu Pantito | 03-Apr-2026 | 27-Mar-2026 08:37:41 | Apisit Tangwashirakul | 07-Apr-2026 | 31-Mar-2026 16:29:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Apr-2026 | 01-Apr-2026 08:16:10 | 01-Apr-2026 10:14:29 | 0 |  |  | Approver | Locate
AO-000480 | MM-ASK-1A-GEN01-PJM-PDR-0005 | PROGRESS MEASUREMENT AND REPORTING PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 10:01:59 | zm167dc@jutal.com | 14-Jun-2026 21:57:05 | Jumpol Sudjitjul | 23-Jun-2026 | 15-Jun-2026 07:46:56 | Jirayu Pantito | 24-Jun-2026 | 17-Jun-2026 09:55:42 | Apisit Tangwashirakul | 25-Jun-2026 | 07-Jul-2026 14:34:55 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:55:28 | 07-Jul-2026 08:13:59 | 0 |  |  | Approver | Locate
AO-000654 | MM-ASK-1A-GEN01-PJM-PDR-0005 | PROGRESS MEASUREMENT AND REPORTING PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 16:59:46 | zm167dc@jutal.com | 08-Jul-2026 17:12:26 | Jumpol Sudjitjul | 17-Jul-2026 |  | Jirayu Pantito | 20-Jul-2026 | 11-Jul-2026 06:51:14 | Apisit Tangwashirakul | 21-Jul-2026 | 22-Jul-2026 23:15:01 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 13:26:32 | 23-Jul-2026 07:09:57 | 0 |  |  | Approver | Locate
AO-000014 | MM-ASK-1A-GEN01-PJM-PEP-0001 | PROJECT EXECUTION PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PEP | Project Execution Plan | 0 | Submitted | IFR | Issued for Review |  | 17-Mar-2026 15:35:23 | zm167dc@jutal.com | 19-Mar-2026 08:17:19 | Jumpol Sudjitjul | 27-Mar-2026 | 27-Mar-2026 07:31:54 | Apisit Tangwashirakul | 30-Mar-2026 | 27-Mar-2026 11:23:49 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 01-Apr-2026 | 28-Mar-2026 08:26:09 | 28-Mar-2026 01:30:03 | 0 |  |  | Focal Point | Locate
AO-001358 | MM-ASK-1A-GEN01-PJM-PEP-0001 | PROJECT EXECUTION PLAN |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PEP | Project Execution Plan | 0 | In Review | IFR | Issued for Review |  | 14-Sep-2026 20:44:17 | zm167dc@jutal.com | 15-Sep-2026 14:00:09 | Jumpol Sudjitjul | 23-Sep-2026 |  | Apisit Tangwashirakul | 24-Sep-2026 | [7 empty] | 28-Sep-2026 |  |  | 0 |  |  | Focal Point | Locate
AO-000006 | MM-ASK-1A-GEN01-PJM-PLN-0001 | 60 DAY LOOK AHEAD PLAN FOR EARLY WORK |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 25-Feb-2026 15:59:56 | zm167dc@jutal.com | 06-Mar-2026 15:04:02 | Jumpol Sudjitjul | 16-Mar-2026 |  | Apisit Tangwashirakul | 17-Mar-2026 | 06-Mar-2026 15:12:50 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 19-Mar-2026 | 06-Mar-2026 15:16:53 | 06-Mar-2026 15:19:37 | 0 |  |  | Focal Point | Locate
AO-000026 | MM-ASK-1A-GEN01-PJM-PLN-0001 | 60 DAY LOOK AHEAD PLAN FOR EARLY WORK |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review | 20-Mar-2026 | 01-Apr-2026 18:20:44 | zm167dc@jutal.com | 01-Apr-2026 22:14:27 | Jumpol Sudjitjul | 16-Apr-2026 | 16-Apr-2026 13:13:06 | Jirayu Pantito | 17-Apr-2026 | 17-Apr-2026 11:40:23 |  |  |  | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Apr-2026 | 17-Apr-2026 11:50:04 | 17-Apr-2026 12:12:35 | 0 |  |  | Focal Point | Locate
AO-000121 | MM-ASK-1A-GEN01-PJM-PLN-0001 | 60 DAY LOOK AHEAD PLAN FOR EARLY WORK |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 03-May-2026 16:31:42 | zm167dc@jutal.com | 04-May-2026 12:56:53 | Jumpol Sudjitjul | 12-May-2026 | 12-May-2026 22:59:01 | Jirayu Pantito | 13-May-2026 | 13-May-2026 07:20:45 | Apisit Tangwashirakul | 14-May-2026 | 21-May-2026 08:46:19 | APPR | Approved | Jumpol Sudjitjul | 15-May-2026 | 21-May-2026 09:23:18 | 21-May-2026 02:51:59 | 0 |  |  | Approver | Locate
AO-000006 | MM-ASK-1A-GEN01-PJM-PLN-0002 | PROJECT PLANNING AND CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 25-Feb-2026 16:00:21 | zm167dc@jutal.com | 25-Feb-2026 17:01:47 | Jumpol Sudjitjul | 09-Mar-2026 | 08-Mar-2026 09:18:38 | Jirayu Pantito | 09-Mar-2026 | 09-Mar-2026 07:51:07 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 12-Mar-2026 | 09-Mar-2026 08:55:44 | 09-Mar-2026 09:26:42 | 0 |  |  | Focal Point | Locate
AO-000022 | MM-ASK-1A-GEN01-PJM-PLN-0002 | PROJECT PLANNING AND CONTROL PROCEDURE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review | 23-Mar-2026 | 31-Mar-2026 10:23:09 | zm167dc@jutal.com | 31-Mar-2026 10:41:39 | Jumpol Sudjitjul | 09-Apr-2026 |  | Jirayu Pantito | 10-Apr-2026 | 10-Apr-2026 07:52:39 | Apisit Tangwashirakul | 16-Apr-2026 | 10-Apr-2026 10:32:23 | NA | Not Approved | Jumpol Sudjitjul | 17-Apr-2026 | 10-Apr-2026 11:44:59 | 10-Apr-2026 12:09:16 | 0 |  |  | Approver | Locate
AO-000145 | MM-ASK-1A-GEN01-PJM-PLN-0002 | PROJECT PLANNING AND CONTROL PROCEDURE |  | A3 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review | 29-Apr-2026 | 07-May-2026 09:53:59 | zm167dc@jutal.com | 07-May-2026 10:13:20 | Jumpol Sudjitjul | 15-May-2026 | 16-May-2026 13:34:23 | Jirayu Pantito | 18-May-2026 | 18-May-2026 10:22:04 | Apisit Tangwashirakul | 19-May-2026 | 18-May-2026 15:04:52 | NA | Not Approved | Jumpol Sudjitjul | 20-May-2026 | 18-May-2026 18:53:36 | 18-May-2026 19:04:30 | 0 |  |  | Approver | Locate
AO-000301 | MM-ASK-1A-GEN01-PJM-PLN-0002 | PROJECT PLANNING AND CONTROL PROCEDURE |  | A4 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review | 02-Jun-2026 | 21-May-2026 12:10:37 | zm167dc@jutal.com | 22-May-2026 12:34:59 | Jumpol Sudjitjul | 02-Jun-2026 |  | Jirayu Pantito | 04-Jun-2026 | 23-May-2026 05:57:07 | Apisit Tangwashirakul | 05-Jun-2026 | 11-Jun-2026 16:51:34 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 17:40:02 | 11-Jun-2026 18:28:28 | 0 |  |  | Approver | Locate
AO-000462 | MM-ASK-1A-GEN01-PJM-PLN-0002 | PROJECT PLANNING AND CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:27:50 | zm167dc@jutal.com | 12-Jun-2026 12:53:03 | Jumpol Sudjitjul | 22-Jun-2026 |  | Jirayu Pantito | 23-Jun-2026 | 17-Jun-2026 10:03:32 | Apisit Tangwashirakul | 24-Jun-2026 | 07-Jul-2026 14:21:40 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 07-Jul-2026 14:24:38 | 07-Jul-2026 08:05:43 | 0 |  |  | Approver | Locate
AO-000025 | MM-ASK-1A-GEN01-PJM-PLN-0003 | PROJECT RISK ASSESSMENT PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 01-Apr-2026 16:54:02 | zm167dc@jutal.com | 01-Apr-2026 17:03:49 | Jumpol Sudjitjul | 16-Apr-2026 | 16-Apr-2026 13:14:21 | Apisit Tangwashirakul | 17-Apr-2026 | 17-Apr-2026 16:27:15 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Apr-2026 | 17-Apr-2026 16:30:55 | 17-Apr-2026 17:03:59 | 0 |  |  | Focal Point | Locate
AO-000909 | MM-ASK-1A-GEN01-PJM-RPT-0001 | PROJECT RISK ASSESSMENT REPORT |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | RPT | Report | 0 | In Review | IFI | Issued for Information |  | 07-Aug-2026 15:03:22 | zm167dc@jutal.com | 07-Aug-2026 17:13:39 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000289 | MM-ASK-1A-GEN01-PJM-SCD-0001 | ROJECT MASTER SCHEDULE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 11:31:05 | zm167dc@jutal.com | 20-May-2026 13:42:28 | Jumpol Sudjitjul | 28-May-2026 | 04-Jun-2026 13:24:21 | Jirayu Pantito | 29-May-2026 | 05-Jun-2026 13:42:13 | Apisit Tangwashirakul | 02-Jun-2026 | 08-Jun-2026 00:06:32 | NA | Not Approved | Jumpol Sudjitjul | 04-Jun-2026 | 08-Jun-2026 08:45:37 | 08-Jun-2026 02:21:41 | 0 |  |  | Approver | Locate
AO-000966 | MM-ASK-1A-GEN01-PJM-SCD-0001 | ROJECT MASTER SCHEDULE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 14:44:20 | zm167dc@jutal.com | 13-Aug-2026 16:28:14 | Jumpol Sudjitjul | 21-Aug-2026 |  | Jirayu Pantito | 24-Aug-2026 | 28-Aug-2026 07:31:53 | Apisit Tangwashirakul | 25-Aug-2026 | 28-Aug-2026 13:43:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 28-Aug-2026 16:40:50 | 28-Aug-2026 09:55:30 | 0 |  |  | Approver | Locate
AO-001298 | MM-ASK-1A-GEN01-PJM-SCD-0001 | ROJECT MASTER SCHEDULE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 09:10:41 | zm167dc@jutal.com | 11-Sep-2026 20:00:08 | Jumpol Sudjitjul | 22-Sep-2026 |  | Jirayu Pantito | 23-Sep-2026 |  | Apisit Tangwashirakul | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000034 | MM-ASK-1A-GEN01-PJM-WPR-0001 | PROJECT WEEKLY PROGRESS REPORT NO.01 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 09-Apr-2026 10:55:42 | zm167dc@jutal.com | 10-Apr-2026 15:10:53 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul |  | 22-May-2026 11:45:52 |  |  |  | APPR | Approved |  |  |  |  | 0 |  |  | For Info | Locate
AO-000052 | MM-ASK-1A-GEN01-PJM-WPR-0002 | PROJECT WEEKLY PROGRESS REPORT NO.02 CUT-OFF DATE 03 APR 2026 REPORT PERIOD: 28 MAR 2026 – 03 APR 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 21-Apr-2026 13:56:10 | zm167dc@jutal.com | 21-Apr-2026 14:56:56 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul |  | 22-Jul-2026 23:12:38 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 23-Jul-2026 13:28:18 | 23-Jul-2026 06:50:30 | 0 |  |  | For Info | Locate
AO-000051 | MM-ASK-1A-GEN01-PJM-WPR-0003 | PROJECT WEEKLY PROGRESS REPORT NO.03 CUT-OFF DATE 10 APR 2026 REPORT PERIOD: 04 APR 2026 – 10 APR 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 21-Apr-2026 13:56:54 | zm167dc@jutal.com | 21-Apr-2026 14:57:37 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul |  | 21-Aug-2026 09:54:04 |  |  |  | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul |  | 21-Aug-2026 10:16:37 | 21-Aug-2026 04:14:02 | 0 |  |  | For Info | Locate
AO-000165 | MM-ASK-1A-GEN01-PJM-WPR-0004 | PROJECT WEEKLY PROGRESS REPORT NO.04 CUT-OFF DATE 17 APR 2026 REPORT PERIOD: 11 APR 2026 – 17 APR 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 08-May-2026 15:42:53 | zm167dc@jutal.com | 08-May-2026 17:08:23 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul |  | 21-Aug-2026 11:25:52 |  |  |  | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul |  | 21-Aug-2026 13:07:36 | 21-Aug-2026 06:20:59 | 0 |  |  | For Info | Locate
AO-000140 | MM-ASK-1A-GEN01-PJM-WPR-0005 | PROJECT WEEKLY PROGRESS REPORT NO.05 CUT-OFF DATE 24 APR 2026 REPORT PERIOD: 18 APR 2026 – 24 APR 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 06-May-2026 15:56:29 | zm167dc@jutal.com | 06-May-2026 17:25:41 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul |  | 21-Aug-2026 11:34:02 |  |  |  | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul |  | 21-Aug-2026 13:08:22 | 21-Aug-2026 06:17:40 | 0 |  |  | For Info | Locate
AO-000228 | MM-ASK-1A-GEN01-PJM-WPR-0006 | PROJECT WEEKLY PROGRESS REPORT NO.06 CUT-OFF DATE 01 MAY 2026 REPORT PERIOD: 25 APR 2026 – 01 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 14-May-2026 14:48:28 | zm167dc@jutal.com | 14-May-2026 14:55:27 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000229 | MM-ASK-1A-GEN01-PJM-WPR-0007 | PROJECT WEEKLY PROGRESS REPORT NO.07 CUT-OFF DATE 08 MAY 2026 REPORT PERIOD: 02 MAY 2026 – 08 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 14-May-2026 16:13:14 | zm167dc@jutal.com | 14-May-2026 16:18:04 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000290 | MM-ASK-1A-GEN01-PJM-WPR-0008 | PROJECT WEEKLY PROGRESS REPORT NO.08 CUT-OFF DATE 15 MAY 2026 REPORT PERIOD: 09 MAY 2026 – 15 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 20-May-2026 11:31:37 | zm167dc@jutal.com | 20-May-2026 13:22:07 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000389 | MM-ASK-1A-GEN01-PJM-WPR-0009 | PROJECT WEEKLY PROGRESS REPORT NO.09 CUT-OFF DATE 22 MAY 2026 REPORT PERIOD:16 MAY 2026 – 22 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 01-Jun-2026 10:50:39 | zm167dc@jutal.com | 01-Jun-2026 12:20:20 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000424 | MM-ASK-1A-GEN01-PJM-WPR-0010 | PROJECT WEEKLY PROGRESS REPORT NO.10 CUT-OFF DATE 29 MAY 2026 REPORT PERIOD: 23 MAY 2026 – 29 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 08-Jun-2026 09:17:38 | zm167dc@jutal.com | 08-Jun-2026 10:46:39 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000458 | MM-ASK-1A-GEN01-PJM-WPR-0011 | PROJECT WEEKLY PROGRESS REPORT NO.11 CUT-OFF DATE 05 JUN 2026 REPORT PERIOD: 30 MAY 2026 – 05 JUN 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 11-Jun-2026 15:25:51 | zm167dc@jutal.com | 12-Jun-2026 09:40:01 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000524 | MM-ASK-1A-GEN01-PJM-WPR-0012 | PROJECT WEEKLY PROGRESS REPORT NO.12 CUT-OFF DATE 12 JUN 2026 REPORT PERIOD: 06 JUN 2026 – 12 JUN 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 21-Jun-2026 22:08:27 | zm167dc@jutal.com | 22-Jun-2026 13:35:48 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000585 | MM-ASK-1A-GEN01-PJM-WPR-0013 | PROJECT WEEKLY PROGRESS REPORT NO.13 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 01-Jul-2026 17:19:09 | zm167dc@jutal.com | 02-Jul-2026 13:14:54 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000586 | MM-ASK-1A-GEN01-PJM-WPR-0014 | PROJECT WEEKLY PROGRESS REPORT NO.14 CUT-OFF DATE 26 JUN 2026 REPORT PERIOD: 20 JUN 2026 – 26 JUN 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 01-Jul-2026 18:35:18 | zm167dc@jutal.com | 02-Jul-2026 13:15:55 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000650 | MM-ASK-1A-GEN01-PJM-WPR-0015 | PROJECT WEEKLY PROGRESS REPORT NO.15 CUT-OFF DATE 03 JUL 2026 REPORT PERIOD: 27 JUN 2026 – 03 JUL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 07-Jul-2026 18:06:24 | zm167dc@jutal.com | 07-Jul-2026 18:32:04 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000717 | MM-ASK-1A-GEN01-PJM-WPR-0016 | PROJECT WEEKLY PROGRESS REPORT NO.16 CUT-OFF DATE 10 JUN 2026 REPORT PERIOD: 04 JUL 2026 – 10 JUL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 17-Jul-2026 15:49:50 | zm167dc@jutal.com | 17-Jul-2026 15:52:34 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000759 | MM-ASK-1A-GEN01-PJM-WPR-0017 | PROJECT WEEKLY PROGRESS REPORT NO.17 CUT-OFF DATE 17 JUL 2026 REPORT PERIOD: 11 JUL 2026 – 17 JUL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 22-Jul-2026 17:24:16 | zm167dc@jutal.com | 22-Jul-2026 18:37:49 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000852 | MM-ASK-1A-GEN01-PJM-WPR-0018 | PROJECT WEEKLY PROGRESS REPORT NO.18 CUT-OFF DATE 24 JUL 2026 REPORT PERIOD: 18 JUL 2026 – 24 JUL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 03-Aug-2026 10:05:34 | zm167dc@jutal.com | 03-Aug-2026 11:45:09 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000942 | MM-ASK-1A-GEN01-PJM-WPR-0019 | PROJECT WEEKLY PROGRESS REPORT NO.19 CUT-OFF DATE 31 JUL 2026 REPORT PERIOD: 25 JUL 2026 – 31 JUL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 10-Aug-2026 12:55:09 | zm167dc@jutal.com | 10-Aug-2026 15:20:19 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-000992 | MM-ASK-1A-GEN01-PJM-WPR-0020 | PROJECT WEEKLY PROGRESS REPORT NO.20 CUT-OFF DATE 07 AUG 2026 REPORT PERIOD: 01 AUG 2026 – 07 AUG 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 14-Aug-2026 17:24:39 | zm167dc@jutal.com | 14-Aug-2026 17:30:27 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-001077 | MM-ASK-1A-GEN01-PJM-WPR-0021 | PROJECT WEEKLY PROGRESS REPORT NO.21 CUT-OFF DATE 14 AUG 2026 REPORT PERIOD: 08 AUG 2026 – 14 AUG 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 24-Aug-2026 09:31:23 | zm167dc@jutal.com | 24-Aug-2026 20:19:26 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-001142 | MM-ASK-1A-GEN01-PJM-WPR-0022 | PROJECT WEEKLY PROGRESS REPORT NO.22 CUT-OFF DATE 21 AUG 2026 REPORT PERIOD: 15 AUG 2026 – 21 AUG 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 31-Aug-2026 12:06:42 | zm167dc@jutal.com | 31-Aug-2026 13:28:45 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-001212 | MM-ASK-1A-GEN01-PJM-WPR-0023 | PROJECT WEEKLY PROGRESS REPORT NO.23 CUT-OFF DATE 28 AUG 2026 REPORT PERIOD: 22 AUG 2026 – 28 AUG 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 07-Sep-2026 09:30:26 | zm167dc@jutal.com | 08-Sep-2026 10:32:11 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-001299 | MM-ASK-1A-GEN01-PJM-WPR-0024 | PROJECT WEEKLY PROGRESS REPORT NO.24 CUT-OFF DATE 04 SEP 2026 REPORT PERIOD: 29 AUG 2026 – 04 SEP 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 11-Sep-2026 09:11:28 | zm167dc@jutal.com | 11-Sep-2026 20:03:36 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-001364 | MM-ASK-1A-GEN01-PJM-WPR-0024 | PROJECT WEEKLY PROGRESS REPORT NO.24 CUT-OFF DATE 04 SEP 2026 REPORT PERIOD: 29 AUG 2026 – 04 SEP 2026 |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 14-Sep-2026 20:44:56 | zm167dc@jutal.com | 15-Sep-2026 14:02:46 | Jumpol Sudjitjul |  |  | Apisit Tangwashirakul | [11 empty] | 0 |  |  | For Info | Locate
AO-001113 | MM-ASK-1A-GEN01-PJM-WST-0001 | WORK STATEMENT NO.01 FOR PO NO.3200044978 (07-AUG-2026) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Latest | IFI | Issued for Information |  | 27-Aug-2026 18:03:00 | zm167dc@jutal.com | 28-Aug-2026 13:47:10 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 29-Aug-2026 20:12:07 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000640 | MM-ASK-1A-GEN01-PLR-MR-2001 | MATERIAL REQUISITION FOR PIPELINE FLANGES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 00:08:10 | zm167dc@jutal.com | 07-Jul-2026 11:46:01 | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 15:33:01 | Akkarapat Suntornsuttiwat | 16-Jul-2026 | 16-Jul-2026 16:56:30 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 17-Jul-2026 00:17:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 08:20:33 | 17-Jul-2026 01:53:02 | 0 |  |  | Approver | Locate
AO-001347 | MM-ASK-1A-GEN01-PLR-MR-2001 | MATERIAL REQUISITION FOR PIPELINE FLANGES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:20:15 | zm167dc@jutal.com | 15-Sep-2026 13:48:18 | Jumpol Sudjitjul | 23-Sep-2026 |  | Akkarapat Suntornsuttiwat | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001496 | MM-ASK-1A-GEN01-PLR-MR-2002 | MATERIAL REQUISITION FOR FITTINGS (RISER) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MR | Material Requisition | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 20:12:51 | zm167dc@jutal.com | 20-Sep-2026 14:12:06 | Jumpol Sudjitjul | 28-Sep-2026 |  | Akkarapat Suntornsuttiwat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001497 | MM-ASK-1A-GEN01-PLR-MR-2003 | MATERIAL REQUISITION FOR GASKETS (RISER) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MR | Material Requisition | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 20:13:17 | zm167dc@jutal.com | 20-Sep-2026 14:12:20 | Jumpol Sudjitjul | 28-Sep-2026 |  | Akkarapat Suntornsuttiwat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001498 | MM-ASK-1A-GEN01-PLR-MR-2004 | MATERIAL REQUISITION FOR FASTENERS (RISER) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MR | Material Requisition | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 20:13:42 | zm167dc@jutal.com | 20-Sep-2026 14:12:36 | Jumpol Sudjitjul | 28-Sep-2026 |  | Akkarapat Suntornsuttiwat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000734 | MM-ASK-1A-GEN01-PLR-MTO-2001 | MATERIAL TAKE OFF FOR FLANGES, FITTINGS, GASKETS AND FASTENERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 12:08:27 | zm167dc@jutal.com | 20-Jul-2026 13:57:56 | Jumpol Sudjitjul | 30-Jul-2026 |  | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 30-Jul-2026 10:49:01 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 30-Jul-2026 18:20:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 30-Jul-2026 19:03:39 | 30-Jul-2026 12:25:51 | 0 |  |  | Approver | Locate
AO-001197 | MM-ASK-1A-GEN01-PLR-MTO-2001 | MATERIAL TAKE OFF FOR FLANGES, FITTINGS, GASKETS AND FASTENERS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 17:18:30 | zm167dc@jutal.com | 05-Sep-2026 18:33:59 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 16-Sep-2026 | 17-Sep-2026 13:18:10 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:13:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 14:46:46 | 20-Sep-2026 08:36:10 | 0 |  |  | Approver | Locate
AO-001267 | MM-ASK-1A-GEN01-PLR-MTO-2002 | MTO FOR 20" LSAW LINE PIPE AND BEND MOTHER-PIPE (SUPPLY BY COMPANY) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 09-Sep-2026 18:41:58 | zm167dc@jutal.com | 10-Sep-2026 13:39:00 | Jumpol Sudjitjul | 18-Sep-2026 |  | Akkarapat Suntornsuttiwat | 21-Sep-2026 | 16-Sep-2026 09:11:56 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 20-Sep-2026 00:44:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 15:33:44 | 20-Sep-2026 09:35:08 | 0 |  |  | Approver | Locate
AO-001268 | MM-ASK-1A-GEN01-PLR-MTO-2003 | MATERIAL TAKE OFF FOR INDUCTION BEND |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 09-Sep-2026 18:42:23 | zm167dc@jutal.com | 10-Sep-2026 13:39:20 | Jumpol Sudjitjul | 18-Sep-2026 |  | Akkarapat Suntornsuttiwat | 21-Sep-2026 | 16-Sep-2026 10:58:51 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 20-Sep-2026 00:43:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 15:32:34 | 20-Sep-2026 09:33:51 | 0 |  |  | Approver | Locate
AO-001252 | MM-ASK-1A-GEN01-PLR-MTO-2004 | MTO FOR 12" SMLS LINE PIPE AND BEND MOTHER-PIPE (SUPPLY BY COMPANY) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 09-Sep-2026 14:43:46 | zm167dc@jutal.com | 10-Sep-2026 13:39:37 | Jumpol Sudjitjul | 18-Sep-2026 |  | Akkarapat Suntornsuttiwat | 21-Sep-2026 | 16-Sep-2026 09:13:28 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 20-Sep-2026 00:42:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 14:55:29 | 20-Sep-2026 08:28:11 | 0 |  |  | Approver | Locate
AO-000641 | MM-ASK-1A-GEN01-PLR-SPE-2001 | PROJECT PATICULAR SPECIFICATION FOR PIPELINE FLANGES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 00:08:36 | zm167dc@jutal.com | 07-Jul-2026 11:44:31 | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 15:32:34 | Akkarapat Suntornsuttiwat | 16-Jul-2026 | 16-Jul-2026 16:57:34 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 19-Jul-2026 17:09:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Jul-2026 | 20-Jul-2026 09:42:28 | 20-Jul-2026 04:07:22 | 0 |  |  | Approver | Locate
AO-001002 | MM-ASK-1A-GEN01-PLR-SPE-2001 | PROJECT PATICULAR SPECIFICATION FOR PIPELINE FLANGES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 18:09:26 | zm167dc@jutal.com | 15-Aug-2026 14:53:26 | Jumpol Sudjitjul | 24-Aug-2026 | 17-Aug-2026 11:51:58 | Akkarapat Suntornsuttiwat | 25-Aug-2026 | 19-Aug-2026 14:27:33 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 23:27:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 10:03:24 | 24-Aug-2026 03:27:03 | 0 |  |  | Approver | Locate
AO-001422 | MM-ASK-1A-GEN01-PLR-TBE-2001 | TECHNICAL BID EVALUATION FOR PIPELINE FLANGES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | In Review | AFC | Approved for Construction |  | 16-Sep-2026 17:36:56 | zm167dc@jutal.com | 17-Sep-2026 08:44:26 | Jumpol Sudjitjul | 25-Sep-2026 |  | Akkarapat Suntornsuttiwat | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000021 | MM-ASK-1A-GEN01-PRC-PLN-0001 | PROJECT PROCUREMENT PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 27-Mar-2026 17:05:20 | zm167dc@jutal.com | 27-Mar-2026 17:16:28 | Jumpol Sudjitjul | 08-Apr-2026 | 02-Apr-2026 14:12:17 | Jirayu Pantito | 09-Apr-2026 | 03-Apr-2026 10:17:48 | Apisit Tangwashirakul | 10-Apr-2026 | 12-Apr-2026 23:56:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Apr-2026 | 13-Apr-2026 08:18:41 | 13-Apr-2026 01:31:29 | 0 |  |  | Approver | Locate
AO-000661 | MM-ASK-1A-GEN01-PRC-PLN-0001 | PROJECT PROCUREMENT PLAN |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 08-Jul-2026 20:01:12 | zm167dc@jutal.com | 09-Jul-2026 10:25:24 | Jumpol Sudjitjul | 17-Jul-2026 | 16-Jul-2026 16:04:32 | Jirayu Pantito | 20-Jul-2026 | 17-Jul-2026 10:54:47 | Apisit Tangwashirakul | 21-Jul-2026 | 22-Jul-2026 23:13:29 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 13:29:12 | 23-Jul-2026 06:51:51 | 0 |  |  | Approver | Locate
AO-000812 | MM-ASK-1A-GEN01-PRC-PLN-0001 | PROJECT PROCUREMENT PLAN |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 30-Jul-2026 09:52:00 | zm167dc@jutal.com | 30-Jul-2026 10:18:37 | Jumpol Sudjitjul | 07-Aug-2026 |  | Jirayu Pantito | 10-Aug-2026 | 11-Aug-2026 07:54:19 | Apisit Tangwashirakul | 11-Aug-2026 | 22-Aug-2026 22:55:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 24-Aug-2026 10:37:48 | 24-Aug-2026 04:30:36 | 0 |  |  | Approver | Locate
AO-001330 | MM-ASK-1A-GEN01-PRC-PLN-0001 | PROJECT PROCUREMENT PLAN |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:36:05 | zm167dc@jutal.com | 11-Sep-2026 20:29:50 | Jumpol Sudjitjul | 22-Sep-2026 | 18-Sep-2026 13:34:15 | Jirayu Pantito | 23-Sep-2026 |  | Apisit Tangwashirakul | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001095 | MM-ASK-1A-GEN01-PRC-PLN-0003 | PASS DOWN PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 25-Aug-2026 19:47:12 | zm167dc@jutal.com | 26-Aug-2026 10:11:10 | Jumpol Sudjitjul | 03-Sep-2026 |  | Jirayu Pantito | 04-Sep-2026 | 16-Sep-2026 15:28:38 | Apisit Tangwashirakul | 07-Sep-2026 | 17-Sep-2026 17:43:39 | NA | Not Approved | Jumpol Sudjitjul | 08-Sep-2026 | 18-Sep-2026 08:58:39 | 18-Sep-2026 03:02:04 | 0 |  |  | Approver | Locate
AO-000720 | MM-ASK-1A-GEN01-PRC-UPO-0002 | UNPRICED PO FOR PRIMARY STEEL BEAM |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Latest | IFI | Issued for Information |  | 17-Jul-2026 20:39:44 | zm167dc@jutal.com | 17-Jul-2026 22:13:50 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 10:00:01 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000892 | MM-ASK-1A-GEN01-PRC-UPO-0003 | UPRICED PO FOR PEDESTAL CRANE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Latest | IFI | Issued for Information |  | 06-Aug-2026 08:52:42 | zm167dc@jutal.com | 06-Aug-2026 10:10:40 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 07:51:45 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000733 | MM-ASK-1A-GEN01-PRC-UPO-0004 | UNPRICED PO FOR PRESSURE VESSEL |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 16-Jul-2026 21:08:49 | zm167dc@jutal.com | 20-Jul-2026 13:21:18 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 12-Aug-2026 19:50:22 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 13-Aug-2026 08:17:25 | 13-Aug-2026 01:28:05 | 0 |  |  | For Info | Locate
AO-000712 | MM-ASK-1A-GEN01-PRC-UPO-0005 | UNPRICED PO FOR PRIMARY SEAMLESS PIPE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 17-Jul-2026 08:30:29 | zm167dc@jutal.com | 17-Jul-2026 10:28:25 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 10:13:53 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 31-Aug-2026 13:37:55 | 31-Aug-2026 07:09:24 | 0 |  |  | For Info | Locate
AO-000943 | MM-ASK-1A-GEN01-PRC-UPO-0006 | UNPRICED PO FOR WPA01 TOPSIDE SECONDARY-PLATE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 10-Aug-2026 16:12:51 | zm167dc@jutal.com | 10-Aug-2026 16:18:50 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 13-Sep-2026 16:16:47 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 13-Sep-2026 22:35:31 | 13-Sep-2026 15:50:51 | 0 |  |  | For Info | Locate
AO-000944 | MM-ASK-1A-GEN01-PRC-UPO-0007 | UNPRICED PO FOR PRIMARY STEEL-PLATES FOR JACKET |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 10-Aug-2026 16:13:25 | zm167dc@jutal.com | 10-Aug-2026 16:19:13 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 13-Sep-2026 16:13:32 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 13-Sep-2026 22:37:28 | 13-Sep-2026 15:52:09 | 0 |  |  | For Info | Locate
AO-001012 | MM-ASK-1A-GEN01-PRC-UPO-0008 | UNPRICED PO FOR CHEMICAL INJECTION PUMPS PACKAGE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 17-Aug-2026 18:38:08 | zm167dc@jutal.com | 18-Aug-2026 10:07:51 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 10:09:32 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 31-Aug-2026 13:37:20 | 31-Aug-2026 07:00:21 | 0 |  |  | For Info | Locate
AO-001012 | MM-ASK-1A-GEN01-PRC-UPO-0009 | UNPRICED PO FOR WELLHEAD CONTROL PANEL(WHCP) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Revised | IFI | Issued for Information |  | 17-Aug-2026 18:38:35 | zm167dc@jutal.com | 18-Aug-2026 10:08:27 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-001154 | MM-ASK-1A-GEN01-PRC-UPO-0009 | UNPRICED PO FOR WELLHEAD CONTROL PANEL(WHCP) |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  |  | zm167dc@jutal.com | 03-Sep-2026 16:10:31 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 13-Sep-2026 16:25:01 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 13-Sep-2026 22:38:21 | 13-Sep-2026 15:58:04 | 0 |  |  | For Info | Locate
AO-001012 | MM-ASK-1A-GEN01-PRC-UPO-0010 | UNPRICED PO FOR PUMP SKID PACKAGES |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 17-Aug-2026 18:39:01 | zm167dc@jutal.com | 18-Aug-2026 10:09:02 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 14-Sep-2026 16:43:52 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 14-Sep-2026 18:39:39 | 14-Sep-2026 11:59:24 | 0 |  |  | For Info | Locate
AO-001012 | MM-ASK-1A-GEN01-PRC-UPO-0011 | UNPRICED PO FOR SOLAR POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 17-Aug-2026 18:39:26 | zm167dc@jutal.com | 18-Aug-2026 10:10:14 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 10:35:49 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:36:23 | 20-Sep-2026 09:36:21 | 0 |  |  | For Info | Locate
AO-001087 | MM-ASK-1A-GEN01-PRC-UPO-0012 | UNPRICED PO FOR SECONDARY STEEL BEAM FOR TOPSIDE (W-TYPE) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Latest | IFI | Issued for Information |  | 24-Aug-2026 13:58:48 | zm167dc@jutal.com | 24-Aug-2026 20:23:59 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 13-Sep-2026 15:05:46 |  |  |  | AWC | Approved with Comment |  |  |  |  | 0 |  |  | For Info | Locate
AO-001087 | MM-ASK-1A-GEN01-PRC-UPO-0013 | UNPRICED PO FOR-SECONDARY STEEL-SEAMLESS PIPE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 24-Aug-2026 13:59:25 | zm167dc@jutal.com | 24-Aug-2026 20:24:15 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 09:33:17 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 20-Sep-2026 14:56:51 | 20-Sep-2026 08:37:23 | 0 |  |  | For Info | Locate
AO-001278 | MM-ASK-1A-GEN01-PRC-UPO-0014 | UNPRICED PO FOR PIRMAY STEEL-TUBULAR FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 10-Sep-2026 13:17:32 | zm167dc@jutal.com | 10-Sep-2026 13:33:18 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 10:46:34 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:35:19 | 20-Sep-2026 09:06:05 | 0 |  |  | For Info | Locate
AO-001086 | MM-ASK-1A-GEN01-PRC-UPO-0015 | UNPRICED PO FOR WELLHEAD CONTROL PANEL(WHCP) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 24-Aug-2026 14:00:34 | zm167dc@jutal.com | 24-Aug-2026 20:27:30 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 10:48:40 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:37:15 | 20-Sep-2026 09:07:21 | 0 |  |  | For Info | Locate
AO-001279 | MM-ASK-1A-GEN01-PRC-UPO-0016 | UNPRICED PO FOR PRIAMARY STEEL-PLATES FOR JACKET |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 10-Sep-2026 13:18:06 | zm167dc@jutal.com | 10-Sep-2026 13:34:09 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 09:18:41 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 14:57:49 | 20-Sep-2026 08:29:37 | 0 |  |  | For Info | Locate
AO-001280 | MM-ASK-1A-GEN01-PRC-UPO-0017 | UNPRICED PO FOR TUBULAR FOR ROLLING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 10-Sep-2026 13:18:46 | zm167dc@jutal.com | 10-Sep-2026 13:34:29 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 09:12:50 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:38:16 | 20-Sep-2026 09:10:09 | 0 |  |  | For Info | Locate
AO-001087 | MM-ASK-1A-GEN01-PRC-UPO-0018 | UNPRICED PO FOR COMPACT CHECK VALVE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 24-Aug-2026 14:02:21 | zm167dc@jutal.com | 24-Aug-2026 20:27:30 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 09:15:20 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:16:54 | 20-Sep-2026 08:30:54 | 0 |  |  | For Info | Locate
AO-001087 | MM-ASK-1A-GEN01-PRC-UPO-0019 | UNPRICED PO FOR ACTUATED CHOKE VALVE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 24-Aug-2026 14:02:49 | zm167dc@jutal.com | 24-Aug-2026 20:27:29 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 09:07:33 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:17:43 | 20-Sep-2026 08:32:13 | 0 |  |  | For Info | Locate
AO-001087 | MM-ASK-1A-GEN01-PRC-UPO-0020 | UNPRICED PO FOR QUICK OPENING CLOSURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 24-Aug-2026 14:03:19 | zm167dc@jutal.com | 24-Aug-2026 20:27:31 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 08:58:14 |  |  |  | NA | Not Approved | Jumpol Sudjitjul |  | 20-Sep-2026 15:40:09 | 20-Sep-2026 09:14:00 | 0 |  |  | For Info | Locate
AO-001092 | MM-ASK-1A-GEN01-PRC-UPO-0021 | UNPRICED PO FOR ACTUATED BALL VALVE AND ACTUATED COMPACT BALL VALVE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 25-Aug-2026 16:34:00 | zm167dc@jutal.com | 25-Aug-2026 16:36:40 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 08:43:29 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:39:16 | 20-Sep-2026 09:37:45 | 0 |  |  | For Info | Locate
AO-001105 | MM-ASK-1A-GEN01-PRC-UPO-0022 | UNPRICED PO FOR WHCP |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Revised | VOID | Issued for Information |  | 27-Aug-2026 12:01:11 | zm167dc@jutal.com | 27-Aug-2026 13:13:32 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-001155 | MM-ASK-1A-GEN01-PRC-UPO-0022 | UNPRICED PO FOR WHCP |  | X | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | VOID | Withdrawn or Superseded |  |  | zm167dc@jutal.com | 03-Sep-2026 16:25:52 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 11:27:22 |  |  |  | NA | [5 empty] | 0 |  |  | For Info | Locate
AO-001153 | MM-ASK-1A-GEN01-PRC-UPO-0023 | UNPRICED PO FOR BALL VALVE AND GLOBAL VALVE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 02-Sep-2026 19:18:41 | zm167dc@jutal.com | 03-Sep-2026 16:16:57 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 08:41:25 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:21:54 | 20-Sep-2026 08:34:50 | 0 |  |  | For Info | Locate
AO-001153 | MM-ASK-1A-GEN01-PRC-UPO-0024 | UNPRICED PO FOR CHECK VALVE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 02-Sep-2026 19:19:13 | zm167dc@jutal.com | 03-Sep-2026 16:17:55 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 11:33:31 |  |  |  | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul |  | 20-Sep-2026 14:54:52 | 20-Sep-2026 08:33:28 | 0 |  |  | For Info | Locate
AO-001153 | MM-ASK-1A-GEN01-PRC-UPO-0025 | UNPRICED PO FOR MATERIAL HANDLING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 02-Sep-2026 19:19:46 | zm167dc@jutal.com | 03-Sep-2026 16:17:16 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 08:35:06 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:41:02 | 20-Sep-2026 09:15:13 | 0 |  |  | For Info | Locate
AO-001297 | MM-ASK-1A-GEN01-PRC-UPO-0026 | UNPRICED PO FOR PRIMARY STEEL - PLATES TOPSIDE 02 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 11-Sep-2026 08:59:55 | zm167dc@jutal.com | 11-Sep-2026 19:51:43 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 11:39:41 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 15:41:49 | 20-Sep-2026 09:24:51 | 0 |  |  | For Info | Locate
AO-001362 | MM-ASK-1A-GEN01-PRC-UPO-0027 | UNPRICED PO FOR CS/SS/ DSS FITTING AND SS/DSS FLANGE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 14-Sep-2026 20:43:13 | zm167dc@jutal.com | 15-Sep-2026 16:07:28 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 19-Sep-2026 12:02:25 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 20-Sep-2026 15:42:35 | 21-Sep-2026 00:27:03 | 0 |  |  | For Info | Locate
AO-001363 | MM-ASK-1A-GEN01-PRC-UPO-0028 | UNPRICED PO FOR SAFETY RELIEF VALVE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 14-Sep-2026 20:43:44 | zm167dc@jutal.com | 15-Sep-2026 16:08:08 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-001424 | MM-ASK-1A-GEN01-PRC-UPO-0029 | UNPRICED PO FOR SS AND DSS PIPE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 16:34:55 | zm167dc@jutal.com | 20-Sep-2026 14:03:39 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Apisit Tangwashirakul | [8 empty] | 0 |  |  | For Info | Locate
AO-001425 | MM-ASK-1A-GEN01-PRC-UPO-0030 | UNPRICED PO FOR CONTROL VALVE AND SELF REGULATOR VALVE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 16:35:38 | zm167dc@jutal.com | 20-Sep-2026 14:02:21 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Apisit Tangwashirakul | [8 empty] | 0 |  |  | For Info | Locate
AO-000081 | MM-ASK-1A-GEN01-PRO-BOD-0001 | PROCESS BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:30:15 | zm167dc@jutal.com | 27-Apr-2026 13:46:17 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 09:05:23 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:19:20 | Pornlert Wanaphattharaphan | 11-May-2026 | 13-May-2026 22:17:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 08:28:43 | 14-May-2026 08:33:39 | 0 |  |  | Approver | Locate
AO-000473 | MM-ASK-1A-GEN01-PRO-BOD-0001 | PROCESS BASIS OF DESIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 18:03:18 | zm167dc@jutal.com | 13-Jun-2026 07:18:45 | Jumpol Sudjitjul | 22-Jun-2026 | 23-Jun-2026 13:37:10 | Naphat Nirotsinlapachai | 23-Jun-2026 | 24-Jun-2026 11:09:56 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:14:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:24:17 | 25-Jun-2026 01:48:20 | 0 |  |  | Approver | Locate
AO-000988 | MM-ASK-1A-GEN01-PRO-BOD-0001 | PROCESS BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 15:34:31 | zm167dc@jutal.com | 14-Aug-2026 15:42:06 | Jumpol Sudjitjul | 24-Aug-2026 |  | Naphat Nirotsinlapachai | 25-Aug-2026 | 23-Aug-2026 17:03:35 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 22:42:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 10:57:59 | 24-Aug-2026 04:39:35 | 0 |  |  | Approver | Locate
AO-000406 | MM-ASK-1A-GEN01-PRO-BOD-0002 | FLOW ASSURANCE BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 10:46:42 | zm167dc@jutal.com | 05-Jun-2026 11:04:12 | Jumpol Sudjitjul | 15-Jun-2026 |  | Naphat Nirotsinlapachai | 16-Jun-2026 | 16-Jun-2026 21:51:13 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 12:52:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 20:53:11 | 22-Jun-2026 00:49:45 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-GEN01-PRO-BOD-0002 | FLOW ASSURANCE BASIS OF DESIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:45:18 | zm167dc@jutal.com | 03-Jul-2026 13:40:58 | Jumpol Sudjitjul | 13-Jul-2026 | 06-Jul-2026 16:19:12 | Naphat Nirotsinlapachai | 14-Jul-2026 | 14-Jul-2026 20:20:40 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:33:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:34:49 | 17-Jul-2026 01:58:08 | 0 |  |  | Approver | Locate
AO-000826 | MM-ASK-1A-GEN01-PRO-BOD-0002 | FLOW ASSURANCE BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:57:31 | zm167dc@jutal.com | 31-Jul-2026 16:56:34 | Jumpol Sudjitjul | 10-Aug-2026 | 09-Aug-2026 23:58:14 | Naphat Nirotsinlapachai | 11-Aug-2026 | 10-Aug-2026 09:26:18 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 19:32:12 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:25:04 | 13-Aug-2026 02:47:14 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-GEN01-PRO-CAL-0001 | PROCESS CALCULATION NOTE FOR TEST SEPARATOR SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 12:43:52 | zm167dc@jutal.com | 29-May-2026 13:17:56 | Jumpol Sudjitjul | 10-Jun-2026 | 08-Jun-2026 22:46:08 | Naphat Nirotsinlapachai | 11-Jun-2026 | 10-Jun-2026 15:40:22 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:33:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:01:48 | 11-Jun-2026 03:02:26 | 0 |  |  | Approver | Locate
AO-000908 | MM-ASK-1A-GEN01-PRO-CAL-0001 | PROCESS CALCULATION NOTE FOR TEST SEPARATOR SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 15:36:17 | zm167dc@jutal.com | 07-Aug-2026 16:46:49 | Jumpol Sudjitjul | 18-Aug-2026 |  | Naphat Nirotsinlapachai | 19-Aug-2026 | 17-Aug-2026 15:25:12 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:35:39 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:50:46 | 21-Aug-2026 02:20:25 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-GEN01-PRO-CAL-0002 | PROCESS CALCULATION NOTE FOR DIESEL TOTE TANK, DAY TANK AND DIESEL TRANSFER PUMP |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 12:44:21 | zm167dc@jutal.com | 29-May-2026 13:30:53 | Jumpol Sudjitjul | 10-Jun-2026 |  | Naphat Nirotsinlapachai | 11-Jun-2026 | 10-Jun-2026 16:20:45 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:37:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:02:40 | 11-Jun-2026 03:03:40 | 0 |  |  | Approver | Locate
AO-001065 | MM-ASK-1A-GEN01-PRO-CAL-0002 | PROCESS CALCULATION NOTE FOR DIESEL TOTE TANK, DAY TANK AND DIESEL TRANSFER PUMP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 17:29:55 | zm167dc@jutal.com | 21-Aug-2026 17:33:25 | Jumpol Sudjitjul | 01-Sep-2026 | 31-Aug-2026 11:41:27 | Naphat Nirotsinlapachai | 02-Sep-2026 | 01-Sep-2026 10:07:38 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:40:08 | APPR | Approved | Soontaree Simpitak | 04-Sep-2026 | 03-Sep-2026 07:40:54 | 03-Sep-2026 01:02:48 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-GEN01-PRO-CAL-0003 | PROCESS CALCULATION NOTE FOR INSTRUMENT GAS FILTER COALESCER AND STAND PIPE SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:17:16 | zm167dc@jutal.com | 13-Jun-2026 08:28:21 | Jumpol Sudjitjul | 22-Jun-2026 | 23-Jun-2026 10:43:35 | Naphat Nirotsinlapachai | 23-Jun-2026 | 23-Jun-2026 21:36:02 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:11:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:26:12 | 25-Jun-2026 01:49:36 | 0 |  |  | Approver | Locate
AO-000827 | MM-ASK-1A-GEN01-PRO-CAL-0003 | PROCESS CALCULATION NOTE FOR INSTRUMENT GAS FILTER COALESCER AND STAND PIPE SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:58:00 | zm167dc@jutal.com | 31-Jul-2026 16:58:02 | Jumpol Sudjitjul | 10-Aug-2026 | 09-Aug-2026 23:58:44 | Naphat Nirotsinlapachai | 11-Aug-2026 | 11-Aug-2026 08:13:57 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:09:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:26:34 | 13-Aug-2026 02:48:32 | 0 |  |  | Approver | Locate
AO-001310 | MM-ASK-1A-GEN01-PRO-CAL-0003 | PROCESS CALCULATION NOTE FOR INSTRUMENT GAS FILTER COALESCER AND STAND PIPE SIZING |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 12:36:02 | zm167dc@jutal.com | 11-Sep-2026 20:08:25 | Jumpol Sudjitjul | 22-Sep-2026 |  | Naphat Nirotsinlapachai | 23-Sep-2026 | 14-Sep-2026 21:40:46 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:39:39 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 14:53:36 | 20-Sep-2026 08:39:56 | 0 |  |  | Approver | Locate
AO-000410 | MM-ASK-1A-GEN01-PRO-CAL-0004 | PROCESS CALCULATION NOTE FOR CORROSION INHIBITOR/VOLATILE CORROSION INHIBITOR TANK AND PUMP SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:48:34 | zm167dc@jutal.com | 05-Jun-2026 14:04:19 | Jumpol Sudjitjul | 15-Jun-2026 |  | Naphat Nirotsinlapachai | 16-Jun-2026 | 15-Jun-2026 20:05:10 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 09:06:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 20:53:50 | 22-Jun-2026 00:31:39 | 0 |  |  | Approver | Locate
AO-000936 | MM-ASK-1A-GEN01-PRO-CAL-0004 | PROCESS CALCULATION NOTE FOR CORROSION INHIBITOR/VOLATILE CORROSION INHIBITOR TANK AND PUMP SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:36:08 | zm167dc@jutal.com | 10-Aug-2026 16:04:21 | Jumpol Sudjitjul | 19-Aug-2026 | 19-Aug-2026 00:00:24 | Naphat Nirotsinlapachai | 20-Aug-2026 | 20-Aug-2026 21:06:05 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 20:02:57 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 10:39:14 | 24-Aug-2026 04:31:51 | 0 |  |  | Approver | Locate
AO-000410 | MM-ASK-1A-GEN01-PRO-CAL-0005 | PROCESS CALCULATION NOTE FOR BIOCIDE TANK AND PUMP SIZING (PROVISION) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:49:07 | zm167dc@jutal.com | 05-Jun-2026 14:05:58 | Jumpol Sudjitjul | 15-Jun-2026 |  | Naphat Nirotsinlapachai | 16-Jun-2026 | 15-Jun-2026 20:13:45 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 09:07:44 | NA | Not Approved | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 20:57:28 | 22-Jun-2026 00:32:56 | 0 |  |  | Approver | Locate
AO-001057 | MM-ASK-1A-GEN01-PRO-CAL-0005 | PROCESS CALCULATION NOTE FOR BIOCIDE TANK AND PUMP SIZING (PROVISION) |  | A2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 16:44:41 | zm167dc@jutal.com | 21-Aug-2026 17:10:37 | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 22:54:45 | Naphat Nirotsinlapachai | 02-Sep-2026 | 01-Sep-2026 10:09:13 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:41:33 | AWC | Approved with Comment | Soontaree Simpitak | 04-Sep-2026 | 03-Sep-2026 07:42:34 | 03-Sep-2026 00:50:34 | 0 |  |  | Approver | Locate
AO-001325 | MM-ASK-1A-GEN01-PRO-CAL-0005 | PROCESS CALCULATION NOTE FOR BIOCIDE TANK AND PUMP SIZING (PROVISION) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:48:34 | zm167dc@jutal.com | 11-Sep-2026 20:08:43 | Jumpol Sudjitjul | 22-Sep-2026 |  | Naphat Nirotsinlapachai | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000395 | MM-ASK-1A-GEN01-PRO-CAL-0006 | PROCESS CALCULATION NOTE FOR FRESH WATER TOTE TANK |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 09:03:37 | zm167dc@jutal.com | 04-Jun-2026 13:00:48 | Jumpol Sudjitjul | 12-Jun-2026 |  | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:20:13 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:28:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 09:57:28 | 22-Jun-2026 03:49:45 | 0 |  |  | Approver | Locate
AO-001066 | MM-ASK-1A-GEN01-PRO-CAL-0006 | PROCESS CALCULATION NOTE FOR FRESH WATER TOTE TANK |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 17:30:27 | zm167dc@jutal.com | 21-Aug-2026 17:33:42 | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 23:01:40 | Naphat Nirotsinlapachai | 02-Sep-2026 | 02-Sep-2026 08:14:35 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:42:52 | APPR | Approved | Soontaree Simpitak | 04-Sep-2026 | 03-Sep-2026 07:43:11 | 03-Sep-2026 01:04:06 | 0 |  |  | Approver | Locate
AO-000473 | MM-ASK-1A-GEN01-PRO-CAL-0007 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP VESSEL SIZING (V-05001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 18:03:48 | zm167dc@jutal.com | 13-Jun-2026 07:23:21 | Jumpol Sudjitjul | 22-Jun-2026 | 23-Jun-2026 09:56:29 | Naphat Nirotsinlapachai | 23-Jun-2026 | 23-Jun-2026 21:38:15 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:12:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:28:25 | 25-Jun-2026 01:50:55 | 0 |  |  | Approver | Locate
AO-000673 | MM-ASK-1A-GEN01-PRO-CAL-0007 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP VESSEL SIZING (V-05001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 16:54:54 | zm167dc@jutal.com | 10-Jul-2026 17:24:35 | Jumpol Sudjitjul | 21-Jul-2026 | 22-Jul-2026 11:38:38 | Naphat Nirotsinlapachai | 22-Jul-2026 | 22-Jul-2026 14:27:05 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 03:23:09 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 09:08:22 | 27-Jul-2026 02:27:08 | 0 |  |  | Approver | Locate
AO-000473 | MM-ASK-1A-GEN01-PRO-CAL-0008 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP PUMP SIZING (P-05001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 18:04:16 | zm167dc@jutal.com | 13-Jun-2026 07:23:35 | Jumpol Sudjitjul | 22-Jun-2026 | 23-Jun-2026 10:05:28 | Naphat Nirotsinlapachai | 23-Jun-2026 | 23-Jun-2026 21:39:56 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:13:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:29:16 | 25-Jun-2026 01:52:12 | 0 |  |  | Approver | Locate
AO-000784 | MM-ASK-1A-GEN01-PRO-CAL-0008 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP PUMP SIZING (P-05001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 17:35:49 | zm167dc@jutal.com | 26-Jul-2026 23:24:46 | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 10:59:53 | Naphat Nirotsinlapachai | 07-Aug-2026 | 07-Aug-2026 16:54:19 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 10:58:06 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:04:52 | 10-Aug-2026 05:23:05 | 0 |  |  | Approver | Locate
AO-000178 | MM-ASK-1A-GEN01-PRO-CAL-1001 | PROCESS CALCULATION NOTE FOR CHOKE VALVE SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 21:27:16 | zm167dc@jutal.com | 08-May-2026 21:31:38 | Jumpol Sudjitjul | 19-May-2026 | 20-May-2026 11:04:51 | Naphat Nirotsinlapachai | 20-May-2026 | 20-May-2026 21:02:10 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 21:42:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 28-May-2026 09:08:08 | 28-May-2026 02:31:26 | 0 |  |  | Approver | Locate
AO-000670 | MM-ASK-1A-GEN01-PRO-CAL-1001 | PROCESS CALCULATION NOTE FOR CHOKE VALVE SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 14:45:49 | zm167dc@jutal.com | 10-Jul-2026 17:25:03 | Jumpol Sudjitjul | 21-Jul-2026 | 22-Jul-2026 11:38:49 | Naphat Nirotsinlapachai | 22-Jul-2026 | 22-Jul-2026 19:34:21 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 03:23:29 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 09:09:12 | 27-Jul-2026 02:20:36 | 0 |  |  | Approver | Locate
AO-000385 | MM-ASK-1A-GEN01-PRO-CAL-1002 | PROCESS CALCULATION NOTE FOR CONTROL VALVE SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:51:02 | zm167dc@jutal.com | 29-May-2026 19:09:47 | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 09:39:58 | Naphat Nirotsinlapachai | 12-Jun-2026 | 11-Jun-2026 17:06:15 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 11-Jun-2026 23:39:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 12-Jun-2026 09:06:09 | 12-Jun-2026 03:00:57 | 0 |  |  | Approver | Locate
AO-000788 | MM-ASK-1A-GEN01-PRO-CAL-1002 | PROCESS CALCULATION NOTE FOR CONTROL VALVE SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:51:09 | zm167dc@jutal.com | 26-Jul-2026 23:25:04 | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 14:52:23 | Naphat Nirotsinlapachai | 07-Aug-2026 | 07-Aug-2026 09:56:06 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 11:00:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:07:56 | 10-Aug-2026 05:12:24 | 0 |  |  | Approver | Locate
AO-000513 | MM-ASK-1A-GEN01-PRO-CAL-1003 | PROCESS CALCULATION NOTE FOR PSV SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 15:17:32 | zm167dc@jutal.com | 19-Jun-2026 16:48:13 | Jumpol Sudjitjul | 29-Jun-2026 | 26-Jun-2026 17:10:26 | Naphat Nirotsinlapachai | 30-Jun-2026 | 30-Jun-2026 20:22:43 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 00:12:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 10:29:27 | 02-Jul-2026 04:37:57 | 0 |  |  | Approver | Locate
AO-000931 | MM-ASK-1A-GEN01-PRO-CAL-1003 | PROCESS CALCULATION NOTE FOR PSV SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 08-Aug-2026 11:24:31 | zm167dc@jutal.com | 08-Aug-2026 20:03:46 | Jumpol Sudjitjul | 19-Aug-2026 | 18-Aug-2026 23:59:26 | Naphat Nirotsinlapachai | 20-Aug-2026 | 19-Aug-2026 23:29:03 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:47:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 10:27:55 | 25-Aug-2026 04:44:34 | 0 |  |  | Approver | Locate
AO-000518 | MM-ASK-1A-GEN01-PRO-CAL-1004 | PROCESS CALCULATION NOTE FOR RO SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 17:26:59 | zm167dc@jutal.com | 19-Jun-2026 17:53:44 | Jumpol Sudjitjul | 30-Jun-2026 | 24-Jun-2026 20:56:34 | Naphat Nirotsinlapachai | 01-Jul-2026 | 30-Jun-2026 20:33:40 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:36:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 15:56:03 | 03-Jul-2026 09:37:18 | 0 |  |  | Approver | Locate
AO-001005 | MM-ASK-1A-GEN01-PRO-CAL-1004 | PROCESS CALCULATION NOTE FOR RO SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 12:49:09 | zm167dc@jutal.com | 17-Aug-2026 13:24:31 | Jumpol Sudjitjul | 25-Aug-2026 | 25-Aug-2026 23:35:38 | Naphat Nirotsinlapachai | 26-Aug-2026 | 26-Aug-2026 09:01:41 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 22:54:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 15:32:46 | 30-Aug-2026 08:50:07 | 0 |  |  | Approver | Locate
AO-000473 | MM-ASK-1A-GEN01-PRO-CAL-2001 | PROCESS CALCULATION NOTE FOR LINE SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 18:04:48 | zm167dc@jutal.com | 13-Jun-2026 07:21:19 | Jumpol Sudjitjul | 22-Jun-2026 |  | Naphat Nirotsinlapachai | 23-Jun-2026 | 24-Jun-2026 18:13:32 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:15:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:29:57 | 25-Jun-2026 01:53:34 | 0 |  |  | Approver | Locate
AO-001006 | MM-ASK-1A-GEN01-PRO-CAL-2001 | PROCESS CALCULATION NOTE FOR LINE SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 12:49:51 | zm167dc@jutal.com | 17-Aug-2026 13:25:14 | Jumpol Sudjitjul | 25-Aug-2026 | 24-Aug-2026 23:58:12 | Naphat Nirotsinlapachai | 26-Aug-2026 | 25-Aug-2026 10:00:18 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 22:23:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 15:55:03 | 30-Aug-2026 09:37:43 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-GEN01-PRO-CAL-2002 | PROCESS CALCULATION NOTE DEPRESSURIZATION AND BLOWDOWN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:54:10 | zm167dc@jutal.com | 29-Jun-2026 08:47:03 | Jumpol Sudjitjul | 07-Jul-2026 |  | Naphat Nirotsinlapachai | 08-Jul-2026 | 08-Jul-2026 15:36:58 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 14-Jul-2026 20:29:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 15-Jul-2026 08:31:57 | 15-Jul-2026 01:56:39 | 0 |  |  | Approver | Locate
AO-001205 | MM-ASK-1A-GEN01-PRO-CAL-2002 | PROCESS CALCULATION NOTE DEPRESSURIZATION AND BLOWDOWN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:31:02 | zm167dc@jutal.com | 08-Sep-2026 10:37:24 | Jumpol Sudjitjul | 16-Sep-2026 |  | Naphat Nirotsinlapachai | 17-Sep-2026 | 16-Sep-2026 19:38:59 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 16:19:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 15:43:27 | 20-Sep-2026 09:27:10 | 0 |  |  | Approver | Locate
AO-000346 | MM-ASK-1A-GEN01-PRO-LIS-0001 | PROCESS LINE LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 10:56:10 | zm167dc@jutal.com | 26-May-2026 11:10:52 | Jumpol Sudjitjul | 05-Jun-2026 | 04-Jun-2026 21:40:51 | Naphat Nirotsinlapachai | 08-Jun-2026 | 08-Jun-2026 11:45:53 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 10-Jun-2026 21:24:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 09:04:14 | 11-Jun-2026 03:04:46 | 0 |  |  | Approver | Locate
AO-000770 | MM-ASK-1A-GEN01-PRO-LIS-0001 | PROCESS LINE LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 14:10:04 | zm167dc@jutal.com | 24-Jul-2026 14:53:43 | Jumpol Sudjitjul | 05-Aug-2026 | 06-Aug-2026 09:35:26 | Naphat Nirotsinlapachai | 06-Aug-2026 | 06-Aug-2026 21:58:40 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 05:42:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 09:23:32 | 07-Aug-2026 03:29:38 | 0 |  |  | Approver | Locate
AO-000194 | MM-ASK-1A-GEN01-PRO-MOM-0001 | KICK OFF MEETING / PROCESS DISCIPLINE CLARIFICATION 5TH - 6TH MAR 26 (BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 11-May-2026 17:50:44 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000195 | MM-ASK-1A-GEN01-PRO-MOM-0002 | PROGRESS ENGINEERING WEEKLY MEETING (EVERY TRURSDAY FROM MARCH - APRILO 2026, 3:00 - 5:00 PM (BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 11-May-2026 17:51:11 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000593 | MM-ASK-1A-GEN01-PRO-MOM-0003 | PROCESS ENGINEERING MINUTES OF MEETING CHEMICAL INJECTION PACKAGES FOR WP01 AND WP02 (29 MAY 2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 02-Jul-2026 11:17:12 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000594 | MM-ASK-1A-GEN01-PRO-MOM-0004 | PROCESS ENGINEERING MINUTES OF MEETING (15-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 02-Jul-2026 12:31:34 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001042 | MM-ASK-1A-GEN01-PRO-MOM-0005 | PROCESS ENGINEERING WEEKLY MEETING (10-AUG-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 20-Aug-2026 17:23:36 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001186 | MM-ASK-1A-GEN01-PRO-PHI-0001 | OPERATING, CONTROL, SHUTDOWN AND BLACK START PHILOSOPHY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 04-Sep-2026 08:39:27 | zm167dc@jutal.com | 04-Sep-2026 11:21:46 | Jumpol Sudjitjul | 14-Sep-2026 |  | Naphat Nirotsinlapachai | 15-Sep-2026 | 15-Sep-2026 16:48:01 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 19-Sep-2026 00:08:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 20-Sep-2026 15:44:11 | 20-Sep-2026 09:16:29 | 0 |  |  | Approver | Locate
AO-000986 | MM-ASK-1A-GEN01-PRO-PHI-0002 | PROCESS CONTROL NARRATIVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 15:34:59 | zm167dc@jutal.com | 14-Aug-2026 15:44:53 | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 23:51:56 | Naphat Nirotsinlapachai | 25-Aug-2026 | 25-Aug-2026 20:51:52 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 21:19:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 09:24:23 | 28-Aug-2026 03:08:50 | 0 |  |  | Approver | Locate
AO-000082 | MM-ASK-1A-GEN01-PRO-PHI-0003 | ISOLATION PHILOSOPHY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:30:44 | zm167dc@jutal.com | 27-Apr-2026 13:41:31 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 11:45:57 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:21:50 | Pornlert Wanaphattharaphan | 11-May-2026 | 12-May-2026 23:58:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 13-May-2026 08:31:23 | 13-May-2026 01:38:30 | 0 |  |  | Approver | Locate
AO-000824 | MM-ASK-1A-GEN01-PRO-PHI-0003 | ISOLATION PHILOSOPHY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:10:27 | zm167dc@jutal.com | 31-Jul-2026 14:45:35 | Jumpol Sudjitjul | 10-Aug-2026 | 09-Aug-2026 23:56:02 | Naphat Nirotsinlapachai | 11-Aug-2026 | 11-Aug-2026 17:33:51 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 16-Aug-2026 10:40:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 17-Aug-2026 08:30:16 | 17-Aug-2026 02:11:57 | 0 |  |  | Approver | Locate
AO-001329 | MM-ASK-1A-GEN01-PRO-PHI-0003 | ISOLATION PHILOSOPHY |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:49:05 | zm167dc@jutal.com | 11-Sep-2026 20:39:39 | Jumpol Sudjitjul | 22-Sep-2026 |  | Naphat Nirotsinlapachai | 23-Sep-2026 | 14-Sep-2026 21:39:13 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:38:39 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 15:22:53 | 20-Sep-2026 08:38:38 | 0 |  |  | Approver | Locate
AO-000083 | MM-ASK-1A-GEN01-PRO-PHI-0004 | VENT AND DRAIN PHILOSOPHY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:48:10 | zm167dc@jutal.com | 27-Apr-2026 13:42:02 | Jumpol Sudjitjul | 07-May-2026 |  | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:23:58 | Pornlert Wanaphattharaphan | 11-May-2026 | 13-May-2026 00:11:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 13-May-2026 08:32:26 | 13-May-2026 02:07:57 | 0 |  |  | Approver | Locate
AO-000803 | MM-ASK-1A-GEN01-PRO-PHI-0004 | VENT AND DRAIN PHILOSOPHY |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 09:16:08 | zm167dc@jutal.com | 27-Jul-2026 15:45:43 | Jumpol Sudjitjul | 06-Aug-2026 | 05-Aug-2026 23:43:03 | Naphat Nirotsinlapachai | 07-Aug-2026 | 06-Aug-2026 14:39:16 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:44:04 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 08:27:15 | 13-Aug-2026 02:49:39 | 0 |  |  | Approver | Locate
AO-000519 | MM-ASK-1A-GEN01-PRO-RPT-0001 | PROCESS SIMULATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 17:27:29 | zm167dc@jutal.com | 19-Jun-2026 17:48:21 | Jumpol Sudjitjul | 30-Jun-2026 |  | Naphat Nirotsinlapachai | 01-Jul-2026 | 30-Jun-2026 20:28:29 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:35:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 15:56:42 | 03-Jul-2026 09:40:18 | 0 |  |  | Approver | Locate
AO-000989 | MM-ASK-1A-GEN01-PRO-RPT-0001 | PROCESS SIMULATION REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 15:35:27 | zm167dc@jutal.com | 14-Aug-2026 15:43:13 | Jumpol Sudjitjul | 24-Aug-2026 |  | Naphat Nirotsinlapachai | 25-Aug-2026 | 23-Aug-2026 17:06:55 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 22:49:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 10:58:57 | 24-Aug-2026 04:54:41 | 0 |  |  | Approver | Locate
AO-001311 | MM-ASK-1A-GEN01-PRO-RPT-0001 | PROCESS SIMULATION REPORT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 12:36:33 | zm167dc@jutal.com | 11-Sep-2026 20:07:08 | Jumpol Sudjitjul | 22-Sep-2026 |  | Naphat Nirotsinlapachai | 23-Sep-2026 | 14-Sep-2026 21:40:01 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:37:43 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 15:45:19 | 20-Sep-2026 09:17:43 | 0 |  |  | Approver | Locate
AO-000849 | MM-ASK-1A-GEN01-PRO-RPT-0002 | DEPRESSURIZATION AND LOW TEMPERATURE STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:06:21 | zm167dc@jutal.com | 03-Aug-2026 11:58:12 | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 00:38:22 | Naphat Nirotsinlapachai | 13-Aug-2026 | 13-Aug-2026 23:39:42 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:16:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 08:30:51 | 17-Aug-2026 02:00:30 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-GEN01-PRO-RPT-0003 | UTILITY BALANCE AND CONSUMPTION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:55:27 | zm167dc@jutal.com | 27-Jun-2026 19:59:25 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 15:13:12 | Naphat Nirotsinlapachai | 08-Jul-2026 | 08-Jul-2026 15:51:30 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 14-Jul-2026 20:34:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 15-Jul-2026 08:32:32 | 15-Jul-2026 01:58:05 | 0 |  |  | Approver | Locate
AO-000774 | MM-ASK-1A-GEN01-PRO-RPT-0004 | INSTRUMENT GAS SYSTEM STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:10:38 | zm167dc@jutal.com | 26-Jul-2026 22:53:17 | Jumpol Sudjitjul | 06-Aug-2026 | 05-Aug-2026 23:44:42 | Naphat Nirotsinlapachai | 07-Aug-2026 | 07-Aug-2026 10:19:36 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:44:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 08:28:01 | 13-Aug-2026 02:50:53 | 0 |  |  | Approver | Locate
AO-001342 | MM-ASK-1A-GEN01-PRO-RPT-0004 | INSTRUMENT GAS SYSTEM STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 20:01:12 | zm167dc@jutal.com | 11-Sep-2026 20:07:25 | Jumpol Sudjitjul | 22-Sep-2026 |  | Naphat Nirotsinlapachai | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000626 | MM-ASK-1A-GEN01-PRO-RPT-0005 | VENT SIZING AND RELIEF LOAD REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 19:11:45 | zm167dc@jutal.com | 04-Jul-2026 14:15:17 | Jumpol Sudjitjul | 13-Jul-2026 |  | Naphat Nirotsinlapachai | 14-Jul-2026 | 13-Jul-2026 22:33:58 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:36:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:33:45 | 17-Jul-2026 01:56:48 | 0 |  |  | Approver | Locate
AO-001131 | MM-ASK-1A-GEN01-PRO-RPT-0005 | VENT SIZING AND RELIEF LOAD REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:49:21 | zm167dc@jutal.com | 28-Aug-2026 17:35:51 | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 23:31:12 | Naphat Nirotsinlapachai | 09-Sep-2026 | 09-Sep-2026 17:21:28 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 10-Sep-2026 23:47:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 11-Sep-2026 12:27:58 | 17-Sep-2026 11:07:09 | 0 |  |  | Approver | Locate
AO-000517 | MM-ASK-1A-GEN01-PRO-RPT-0006 | AIV AND FIV STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 17:27:59 | zm167dc@jutal.com | 19-Jun-2026 17:49:36 | Jumpol Sudjitjul | 30-Jun-2026 | 30-Jun-2026 01:03:08 | Naphat Nirotsinlapachai | 01-Jul-2026 | 30-Jun-2026 20:26:05 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:34:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 15:57:46 | 03-Jul-2026 09:43:14 | 0 |  |  | Approver | Locate
AO-001205 | MM-ASK-1A-GEN01-PRO-RPT-0006 | AIV AND FIV STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:31:31 | zm167dc@jutal.com | 08-Sep-2026 11:05:59 | Jumpol Sudjitjul | 16-Sep-2026 | 16-Sep-2026 17:36:03 | Naphat Nirotsinlapachai | 17-Sep-2026 | 17-Sep-2026 08:21:17 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 16:24:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 15:46:09 | 20-Sep-2026 09:28:33 | 0 |  |  | Approver | Locate
AO-000618 | MM-ASK-1A-GEN01-PRO-RPT-0007 | TOPSIDE DYNAMIC OVERPRESSURE PROTECTION STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:23:39 | zm167dc@jutal.com | 03-Jul-2026 19:10:05 | Jumpol Sudjitjul | 14-Jul-2026 |  | Naphat Nirotsinlapachai | 15-Jul-2026 | 15-Jul-2026 20:08:49 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 19-Jul-2026 15:54:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 20-Jul-2026 09:34:11 | 20-Jul-2026 03:54:15 | 0 |  |  | Approver | Locate
AO-001129 | MM-ASK-1A-GEN01-PRO-RPT-0007 | TOPSIDE DYNAMIC OVERPRESSURE PROTECTION STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:49:56 | zm167dc@jutal.com | 28-Aug-2026 17:36:13 | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 23:37:13 | Naphat Nirotsinlapachai | 09-Sep-2026 | 09-Sep-2026 16:09:17 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:56:45 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 19:52:45 | 12-Sep-2026 13:22:56 | 0 |  |  | Approver | Locate
AO-000407 | MM-ASK-1A-GEN01-PRO-RPT-0008-1 | STEADY STATE FLOW ASSURANCE STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 10:47:33 | zm167dc@jutal.com | 05-Jun-2026 11:06:34 | Jumpol Sudjitjul | 15-Jun-2026 |  | Naphat Nirotsinlapachai | 16-Jun-2026 | 16-Jun-2026 21:52:31 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 16:40:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 20:59:47 | 22-Jun-2026 00:51:07 | 0 |  |  | Approver | Locate
AO-000832 | MM-ASK-1A-GEN01-PRO-RPT-0008-1 | STEADY STATE FLOW ASSURANCE STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:20:54 | zm167dc@jutal.com | 31-Jul-2026 21:54:05 | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 00:36:52 | Naphat Nirotsinlapachai | 13-Aug-2026 | 13-Aug-2026 23:41:06 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:17:24 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 08:32:03 | 17-Aug-2026 02:13:24 | 0 |  |  | Approver | Locate
AO-000517 | MM-ASK-1A-GEN01-PRO-RPT-0008-2 | TRANSIENT FLOW ASSURANCE STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 17:28:29 | zm167dc@jutal.com | 19-Jun-2026 17:51:21 | Jumpol Sudjitjul | 30-Jun-2026 | 22-Jun-2026 10:17:46 | Naphat Nirotsinlapachai | 01-Jul-2026 | 01-Jul-2026 16:17:23 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 04-Jul-2026 18:06:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 05-Jul-2026 10:23:36 | 05-Jul-2026 03:47:34 | 0 |  |  | Approver | Locate
AO-000724 | MM-ASK-1A-GEN01-PRO-RPT-0008-2 | TRANSIENT FLOW ASSURANCE STUDY REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:04:42 | zm167dc@jutal.com | 20-Jul-2026 11:28:15 | Jumpol Sudjitjul | 30-Jul-2026 |  | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:52:04 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 23:19:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 04-Aug-2026 08:52:58 | 04-Aug-2026 02:23:11 | 0 |  |  | Approver | Locate
AO-000982 | MM-ASK-1A-GEN01-PRO-RPT-0008-2 | TRANSIENT FLOW ASSURANCE STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 13:24:13 | zm167dc@jutal.com | 14-Aug-2026 13:51:00 | Jumpol Sudjitjul | 24-Aug-2026 |  | Naphat Nirotsinlapachai | 25-Aug-2026 | 23-Aug-2026 17:07:28 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 22:51:17 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 11:17:37 | 24-Aug-2026 04:48:21 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-GEN01-PRO-RPT-0009 | PRODUCED WATER TREATMENT STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:46:07 | zm167dc@jutal.com | 03-Jul-2026 14:43:43 | Jumpol Sudjitjul | 13-Jul-2026 | 03-Jul-2026 14:56:41 | Naphat Nirotsinlapachai | 14-Jul-2026 | 13-Jul-2026 23:01:51 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:22:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:20:41 | 17-Jul-2026 01:54:17 | 0 |  |  | Approver | Locate
AO-001489 | MM-ASK-1A-GEN01-PRO-RPT-0009 | PRODUCED WATER TREATMENT STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 17:21:27 | zm167dc@jutal.com | 18-Sep-2026 17:46:24 | Jumpol Sudjitjul | 29-Sep-2026 |  | Naphat Nirotsinlapachai | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001423 | MM-ASK-1A-GEN01-QAC-ARP-0001 | PROJECT AUDIT REPORT ENGINEERING AUDIT - GCME - SYNTERRA |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | ARP | Audit Report | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 08:41:19 | zm167dc@jutal.com | 17-Sep-2026 09:29:09 | Jumpol Sudjitjul |  | 17-Sep-2026 15:24:33 | Witsarut Wanitanukool |  |  | Apisit Tangwashirakul | [8 empty] | 0 |  |  | For Info | Locate
AO-001420 | MM-ASK-1A-GEN01-QAC-NCR-0001 | NON-CONFORMANCE IN THE PROCUREMENT TBE PROCESS |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | NCR | Nonconformity Report | 0 | In Review | IFI | Issued for Information |  | 16-Sep-2026 17:37:52 | zm167dc@jutal.com | 17-Sep-2026 09:35:36 | Jumpol Sudjitjul |  | 19-Sep-2026 11:36:32 | Witsarut Wanitanukool |  |  | Apisit Tangwashirakul | [8 empty] | 0 |  |  | For Info | Locate
AO-000905 | MM-ASK-1A-GEN01-QAC-PDR-0002 | NON-CONFORMANCE CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 11:34:54 | zm167dc@jutal.com | 07-Aug-2026 16:16:45 | Jumpol Sudjitjul | 18-Aug-2026 | 08-Aug-2026 06:56:00 | Poramate Kamlangkeng | 19-Aug-2026 | 15-Aug-2026 10:09:30 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 15-Aug-2026 14:29:20 | 15-Aug-2026 08:05:12 | 0 |  |  | Focal Point | Locate
AO-001413 | MM-ASK-1A-GEN01-QAC-PDR-0005 | WELD VISUAL INSPECTION PROCEDURE FOR PIPING, RISER |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | In Review | AFC | Approved for Construction |  | 16-Sep-2026 09:12:23 | zm167dc@jutal.com | 17-Sep-2026 09:10:49 | Jumpol Sudjitjul | 25-Sep-2026 |  | Witsarut Wanitanukool | 28-Sep-2026 |  | Poramate Kamlangkeng | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000905 | MM-ASK-1A-GEN01-QAC-PDR-0006 | WELD VISUAL INSPECTION PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 11:35:18 | zm167dc@jutal.com | 07-Aug-2026 16:28:31 | Jumpol Sudjitjul | 18-Aug-2026 | 08-Aug-2026 06:42:39 | Poramate Kamlangkeng | 19-Aug-2026 | 15-Aug-2026 10:12:25 |  |  |  | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Aug-2026 | 15-Aug-2026 14:28:44 | 15-Aug-2026 08:03:59 | 0 |  |  | Focal Point | Locate
AO-001050 | MM-ASK-1A-GEN01-QAC-PDR-0007 | LEVELING AND DIMENSIONAL CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 10:18:31 | zm167dc@jutal.com | 24-Aug-2026 18:29:43 | Jumpol Sudjitjul | 02-Sep-2026 | 27-Aug-2026 10:34:29 | Witsarut Wanitanukool | 03-Sep-2026 | 02-Sep-2026 09:05:10 |  |  |  | APPR-C | Approved (Proceed to Rev.C) | Soontaree Simpitak | 07-Sep-2026 | 02-Sep-2026 10:39:20 | 02-Sep-2026 04:07:31 | 0 |  |  | Focal Point | Locate
AO-001051 | MM-ASK-1A-GEN01-QAC-PDR-0008 | POSITIVE MATERIAL IDENTIFICATION PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 10:19:26 | zm167dc@jutal.com | 24-Aug-2026 18:30:01 | Jumpol Sudjitjul | 02-Sep-2026 | 27-Aug-2026 10:44:02 | Witsarut Wanitanukool | 03-Sep-2026 | 02-Sep-2026 09:27:52 |  |  |  | AWC | Approved with Comment | Soontaree Simpitak | 07-Sep-2026 | 02-Sep-2026 10:38:14 | 02-Sep-2026 04:06:16 | 0 |  |  | Focal Point | Locate
AO-000701 | MM-ASK-1A-GEN01-QAC-PDR-0011 | RT PROCEDURE FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 14-Jul-2026 17:31:28 | zm167dc@jutal.com | 14-Jul-2026 20:07:47 | Jumpol Sudjitjul | 23-Jul-2026 | 15-Jul-2026 10:12:20 | Poramate Kamlangkeng | 24-Jul-2026 | 16-Jul-2026 14:39:26 | Apisit Tangwashirakul | 27-Jul-2026 | 22-Aug-2026 22:50:24 | APPR | Approved | Jumpol Sudjitjul | 30-Jul-2026 | 24-Aug-2026 10:57:50 | 24-Aug-2026 04:38:16 | 0 |  |  | Approver | Locate
AO-000702 | MM-ASK-1A-GEN01-QAC-PDR-0012 | UT PROCEDURE FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 14-Jul-2026 17:31:58 | zm167dc@jutal.com | 14-Jul-2026 20:08:15 | Jumpol Sudjitjul | 23-Jul-2026 | 15-Jul-2026 10:13:00 | Poramate Kamlangkeng | 24-Jul-2026 | 16-Jul-2026 14:39:55 | Apisit Tangwashirakul | 27-Jul-2026 | 22-Aug-2026 22:49:11 | APPR | Approved | Jumpol Sudjitjul | 30-Jul-2026 | 24-Aug-2026 11:15:58 | 24-Aug-2026 04:47:11 | 0 |  |  | Approver | Locate
AO-000744 | MM-ASK-1A-GEN01-QAC-PDR-0013 | MT PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 08:34:54 | zm167dc@jutal.com | 21-Jul-2026 09:21:29 | Jumpol Sudjitjul | 31-Jul-2026 | 24-Jul-2026 14:21:53 | Poramate Kamlangkeng | 03-Aug-2026 | 27-Jul-2026 10:45:48 | Apisit Tangwashirakul | 04-Aug-2026 | 22-Aug-2026 22:52:20 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 24-Aug-2026 13:13:18 | 24-Aug-2026 06:15:51 | 0 |  |  | Approver | Locate
AO-000745 | MM-ASK-1A-GEN01-QAC-PDR-0014 | PT PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 08:35:18 | zm167dc@jutal.com | 21-Jul-2026 09:22:03 | Jumpol Sudjitjul | 31-Jul-2026 | 25-Jul-2026 07:56:35 | Poramate Kamlangkeng | 03-Aug-2026 | 27-Jul-2026 10:45:17 | Apisit Tangwashirakul | 04-Aug-2026 | 22-Aug-2026 22:51:33 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 24-Aug-2026 11:00:59 | 24-Aug-2026 04:26:15 | 0 |  |  | Approver | Locate
AO-000946 | MM-ASK-1A-GEN01-QAC-PDR-0019 | MEASURING & TESTING EQUIPMENT CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 19:22:31 | zm167dc@jutal.com | 11-Aug-2026 11:48:55 | Jumpol Sudjitjul | 20-Aug-2026 |  | Poramate Kamlangkeng | 21-Aug-2026 | 15-Aug-2026 10:23:05 | Witsarut Wanitanukool | 24-Aug-2026 | 26-Aug-2026 17:01:52 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Aug-2026 | 26-Aug-2026 18:06:52 | 26-Aug-2026 11:22:27 | 0 |  |  | Approver | Locate
AO-001250 | MM-ASK-1A-GEN01-QAC-PDR-0019 | MEASURING & TESTING EQUIPMENT CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | In Approval | AFC | Approved for Construction |  | 09-Sep-2026 14:47:31 | zm167dc@jutal.com | 10-Sep-2026 13:13:28 | Jumpol Sudjitjul | 18-Sep-2026 | 17-Sep-2026 15:31:57 | Poramate Kamlangkeng | 21-Sep-2026 | 18-Sep-2026 09:25:01 | Witsarut Wanitanukool | 22-Sep-2026 |  | APPR |  |  | 23-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000947 | MM-ASK-1A-GEN01-QAC-PDR-0024 | MATERIAL CONTROL AND TRACEABILITY PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 19:22:56 | zm167dc@jutal.com | 11-Aug-2026 08:37:50 | Jumpol Sudjitjul | 20-Aug-2026 | 12-Aug-2026 19:43:49 | Poramate Kamlangkeng | 21-Aug-2026 | 15-Aug-2026 10:19:35 | Witsarut Wanitanukool | 24-Aug-2026 | 26-Aug-2026 17:15:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Aug-2026 | 26-Aug-2026 18:05:55 | 26-Aug-2026 11:21:12 | 0 |  |  | Approver | Locate
AO-001251 | MM-ASK-1A-GEN01-QAC-PDR-0024 | MATERIAL CONTROL AND TRACEABILITY PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | In Approval | AFC | Approved for Construction |  | 09-Sep-2026 14:48:09 | zm167dc@jutal.com | 10-Sep-2026 13:14:02 | Jumpol Sudjitjul | 18-Sep-2026 | 17-Sep-2026 15:35:24 | Poramate Kamlangkeng | 21-Sep-2026 | 18-Sep-2026 09:26:07 | Witsarut Wanitanukool | 22-Sep-2026 |  | APPR |  |  | 23-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000905 | MM-ASK-1A-GEN01-QAC-PDR-0025 | HARDNESS TEST PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 11:35:44 | zm167dc@jutal.com | 07-Aug-2026 16:29:34 | Jumpol Sudjitjul | 18-Aug-2026 | 08-Aug-2026 06:43:30 | Poramate Kamlangkeng | 19-Aug-2026 | 15-Aug-2026 10:15:46 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 15-Aug-2026 14:28:13 | 15-Aug-2026 08:02:39 | 0 |  |  | Focal Point | Locate
AO-000009 | MM-ASK-1A-GEN01-QAC-QMP-0001 | PROJECT QUALITY PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | QMP | Quality Management System Certificate, Quality Plan | 0 | Submitted | IFR | Issued for Review |  | 11-Mar-2026 10:03:47 | zm167dc@jutal.com | 12-Mar-2026 09:17:09 | Jumpol Sudjitjul | 20-Mar-2026 | 20-Mar-2026 07:14:27 | Poramate Kamlangkeng | 23-Mar-2026 | 24-Mar-2026 13:29:30 | Apisit Tangwashirakul | 24-Mar-2026 | 24-Mar-2026 19:18:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Mar-2026 | 25-Mar-2026 08:49:14 | 25-Mar-2026 09:22:43 | 0 |  |  | Approver | Locate
AO-000042 | MM-ASK-1A-GEN01-QAC-QMP-0001 | PROJECT QUALITY PLAN |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | QMP | Quality Management System Certificate, Quality Plan | 0 | Submitted | IFR | Issued for Review |  | 16-Apr-2026 11:23:35 | zm167dc@jutal.com | 16-Apr-2026 12:25:04 | Jumpol Sudjitjul | 24-Apr-2026 | 21-Apr-2026 14:51:36 | Poramate Kamlangkeng | 27-Apr-2026 | 30-Apr-2026 16:04:55 | Apisit Tangwashirakul | 28-Apr-2026 | 01-May-2026 00:09:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Apr-2026 | 01-May-2026 10:42:22 | 01-May-2026 04:19:55 | 0 |  |  | Approver | Locate
AO-000478 | MM-ASK-1A-GEN01-QAC-QMP-0001 | PROJECT QUALITY PLAN |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | QMP | Quality Management System Certificate, Quality Plan | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 10:02:26 | zm167dc@jutal.com | 14-Jun-2026 21:58:09 | Jumpol Sudjitjul | 23-Jun-2026 | 23-Jun-2026 14:55:24 | Poramate Kamlangkeng | 24-Jun-2026 | 25-Jun-2026 12:47:03 | Apisit Tangwashirakul | 25-Jun-2026 | 27-Jun-2026 22:26:01 | NA | Not Approved | Jumpol Sudjitjul | 26-Jun-2026 | 28-Jun-2026 08:37:11 | 28-Jun-2026 02:12:20 | 0 |  |  | Approver | Locate
AO-000894 | MM-ASK-1A-GEN01-QAC-RGT-0001 | NDE PERSONNEL REGISTER, RESUME AND QUALIFICATION |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 08:54:53 | zm167dc@jutal.com | 06-Aug-2026 10:02:58 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 09:12:53 | Poramate Kamlangkeng | 18-Aug-2026 | 15-Aug-2026 10:04:49 |  |  |  | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 20-Aug-2026 | 15-Aug-2026 14:30:58 | 15-Aug-2026 08:17:40 | 0 |  |  | Focal Point | Locate
AO-000596 | MM-ASK-1A-GEN01-SAF-DTS-0026 | DATASHEET FOR FIREFIGHTING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 02-Jul-2026 16:06:19 | zm167dc@jutal.com | 02-Jul-2026 16:46:13 | Jumpol Sudjitjul | 10-Jul-2026 |  | Pongsakorn Monturat | 13-Jul-2026 | 03-Aug-2026 16:04:06 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 03-Aug-2026 22:10:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 04-Aug-2026 10:30:54 | 04-Aug-2026 03:54:55 | 0 |  |  | Approver | Locate
AO-001044 | MM-ASK-1A-GEN01-SAF-DTS-0026 | DATASHEET FOR FIREFIGHTING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 09:36:01 | zm167dc@jutal.com | 21-Aug-2026 13:20:23 | Jumpol Sudjitjul | 31-Aug-2026 |  | Pongsakorn Monturat | 01-Sep-2026 | 18-Sep-2026 11:22:58 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 18-Sep-2026 20:05:36 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 20-Sep-2026 15:48:04 | 20-Sep-2026 09:19:49 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-GEN01-SAF-DTS-0027 | DATASHEET FOR LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:16:14 | zm167dc@jutal.com | 03-Jul-2026 18:31:58 | Jumpol Sudjitjul | 14-Jul-2026 |  | Pongsakorn Monturat | 15-Jul-2026 | 07-Aug-2026 14:19:42 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 07-Aug-2026 21:39:37 | APPR | Approved | Jumpol Sudjitjul | 17-Jul-2026 | 08-Aug-2026 10:01:28 | 08-Aug-2026 03:19:00 | 0 |  |  | Approver | Locate
AO-001044 | MM-ASK-1A-GEN01-SAF-DTS-0027 | DATASHEET FOR LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 09:36:30 | zm167dc@jutal.com | 21-Aug-2026 13:20:51 | Jumpol Sudjitjul | 31-Aug-2026 |  | Pongsakorn Monturat | 01-Sep-2026 | 18-Sep-2026 11:37:16 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 18-Sep-2026 20:08:08 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 20-Sep-2026 15:49:39 | 20-Sep-2026 09:21:02 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-GEN01-SAF-DTS-0028 | DATASHEET FOR SAFETY SIGNS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:29:08 | zm167dc@jutal.com | 03-Jul-2026 13:28:06 | Jumpol Sudjitjul | 13-Jul-2026 |  | Pongsakorn Monturat | 14-Jul-2026 | 07-Aug-2026 14:19:12 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 07-Aug-2026 20:52:14 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 08-Aug-2026 10:02:45 | 08-Aug-2026 03:17:45 | 0 |  |  | Approver | Locate
AO-001044 | MM-ASK-1A-GEN01-SAF-DTS-0028 | DATASHEET FOR SAFETY SIGNS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 21-Aug-2026 09:37:02 | zm167dc@jutal.com | 21-Aug-2026 13:21:11 | Jumpol Sudjitjul | 31-Aug-2026 |  | Pongsakorn Monturat | 01-Sep-2026 |  | Pornlert Wanaphattharaphan | 02-Sep-2026 |  |  |  |  | 03-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000467 | MM-ASK-1A-GEN01-SAF-LIS-0029 | FIREFIGHTING, LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 15:50:49 | zm167dc@jutal.com | 12-Jun-2026 16:34:10 | Jumpol Sudjitjul | 22-Jun-2026 | 01-Jul-2026 08:34:59 | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 10:40:25 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 08-Jul-2026 23:16:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 09-Jul-2026 09:52:12 | 09-Jul-2026 03:56:47 | 0 |  |  | Approver | Locate
AO-000705 | MM-ASK-1A-GEN01-SAF-LIS-0029 | FIREFIGHTING, LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT LIST |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 15-Jul-2026 18:42:34 | zm167dc@jutal.com | 15-Jul-2026 21:45:36 | Jumpol Sudjitjul | 24-Jul-2026 |  | Pongsakorn Monturat | 27-Jul-2026 | 13-Aug-2026 10:47:23 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 15-Aug-2026 06:25:44 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 15-Aug-2026 14:30:03 | 15-Aug-2026 08:06:22 | 0 |  |  | Approver | Locate
AO-001152 | MM-ASK-1A-GEN01-SAF-LIS-0029 | FIREFIGHTING, LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | LIS | List, Index, Schedule, Listing | 0 | In Review | AFC | Approved for Construction |  | 02-Sep-2026 19:24:00 | zm167dc@jutal.com | 02-Sep-2026 20:44:35 | Soontaree Simpitak | 11-Sep-2026 |  | Pongsakorn Monturat | 14-Sep-2026 |  | Pornlert Wanaphattharaphan | 15-Sep-2026 |  |  |  |  | 16-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000705 | MM-ASK-1A-GEN01-SAF-MR-0119 | MATERIAL REQUISITION FOR FIREFIGHTING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 15-Jul-2026 18:43:03 | zm167dc@jutal.com | 15-Jul-2026 21:41:28 | Jumpol Sudjitjul | 24-Jul-2026 |  | Pongsakorn Monturat | 27-Jul-2026 | 13-Aug-2026 10:45:02 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 15-Aug-2026 06:20:31 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 15-Aug-2026 14:28:46 | 15-Aug-2026 08:25:05 | 0 |  |  | Approver | Locate
AO-000705 | MM-ASK-1A-GEN01-SAF-MR-0120 | MATERIAL REQUISITION FOR LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 15-Jul-2026 18:43:31 | zm167dc@jutal.com | 15-Jul-2026 21:43:36 | Jumpol Sudjitjul | 24-Jul-2026 |  | Pongsakorn Monturat | 27-Jul-2026 | 13-Aug-2026 10:46:20 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 15-Aug-2026 06:22:49 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 15-Aug-2026 14:29:37 | 15-Aug-2026 08:26:13 | 0 |  |  | Approver | Locate
AO-000705 | MM-ASK-1A-GEN01-SAF-MR-0121 | MATERIAL REQUISITION FOR SAFETY SIGNS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 15-Jul-2026 18:44:00 | zm167dc@jutal.com | 15-Jul-2026 21:44:12 | Jumpol Sudjitjul | 24-Jul-2026 |  | Pongsakorn Monturat | 27-Jul-2026 | 13-Aug-2026 10:46:44 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 15-Aug-2026 06:26:58 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 15-Aug-2026 14:31:55 | 15-Aug-2026 08:27:19 | 0 |  |  | Approver | Locate
AO-000227 | MM-ASK-1A-GEN01-SAF-PDR-0005 | HAZID TOR (OFFSHORE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 11:31:25 | zm167dc@jutal.com | 14-May-2026 13:20:57 | Jumpol Sudjitjul | 22-May-2026 |  | Pongsakorn Monturat | 25-May-2026 | 29-May-2026 17:16:12 | Pornlert Wanaphattharaphan | 26-May-2026 | 29-May-2026 19:29:11 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 27-May-2026 | 29-May-2026 19:32:25 | 29-May-2026 19:49:29 | 0 |  |  | Approver | Locate
AO-000387 | MM-ASK-1A-GEN01-SAF-PDR-0005 | HAZID TOR (OFFSHORE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 01-Jun-2026 10:50:10 | zm167dc@jutal.com | 01-Jun-2026 12:18:24 | Jumpol Sudjitjul | 10-Jun-2026 | 17-Jun-2026 20:15:41 | Warayut Ubolcharoen | 11-Jun-2026 | 18-Jun-2026 15:27:50 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 19-Jun-2026 08:06:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 19-Jun-2026 10:43:13 | 19-Jun-2026 04:23:31 | 0 |  |  | Approver | Locate
AO-000634 | MM-ASK-1A-GEN01-SAF-PDR-0005 | HAZID TOR (OFFSHORE) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 07-Jul-2026 00:10:12 | zm167dc@jutal.com | 07-Jul-2026 10:09:47 | Jumpol Sudjitjul | 15-Jul-2026 |  | Pongsakorn Monturat | 16-Jul-2026 | 07-Aug-2026 14:08:15 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 07-Aug-2026 21:41:02 | APPR | Approved | Jumpol Sudjitjul | 20-Jul-2026 | 08-Aug-2026 10:06:16 | 08-Aug-2026 03:20:17 | 0 |  |  | Approver | Locate
AO-000390 | MM-ASK-1A-GEN01-SAF-PDR-0007 | HAZOP TOR (OFFSHORE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 09:48:14 | zm167dc@jutal.com | 02-Jun-2026 10:24:07 | Jumpol Sudjitjul | 11-Jun-2026 | 17-Jun-2026 18:20:27 | Warayut Ubolcharoen | 12-Jun-2026 | 18-Jun-2026 15:32:14 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 19-Jun-2026 21:27:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 22-Jun-2026 08:42:30 | 22-Jun-2026 02:09:52 | 0 |  |  | Approver | Locate
AO-000581 | MM-ASK-1A-GEN01-SAF-PDR-0007 | HAZOP TOR (OFFSHORE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 01-Jul-2026 08:39:22 | zm167dc@jutal.com | 01-Jul-2026 10:25:12 | Jumpol Sudjitjul | 09-Jul-2026 |  | Pongsakorn Monturat | 10-Jul-2026 | 23-Jul-2026 15:07:00 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 24-Jul-2026 23:48:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 27-Jul-2026 09:09:50 | 27-Jul-2026 02:22:07 | 0 |  |  | Approver | Locate
AO-000857 | MM-ASK-1A-GEN01-SAF-PDR-0007 | HAZOP TOR (OFFSHORE) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 17:28:48 | zm167dc@jutal.com | 04-Aug-2026 08:02:41 | Jumpol Sudjitjul | 13-Aug-2026 | 10-Aug-2026 00:39:39 | Pongsakorn Monturat | 14-Aug-2026 | 24-Aug-2026 16:43:13 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 25-Aug-2026 22:24:40 | APPR | Approved | Jumpol Sudjitjul | 18-Aug-2026 | 26-Aug-2026 08:55:03 | 26-Aug-2026 02:42:34 | 0 |  |  | Approver | Locate
AO-000468 | MM-ASK-1A-GEN01-SAF-PDR-0009 | SIL TOR (OFFSHORE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 15:51:24 | zm167dc@jutal.com | 12-Jun-2026 16:37:26 | Jumpol Sudjitjul | 22-Jun-2026 |  | Warayut Ubolcharoen | 23-Jun-2026 | 18-Jun-2026 15:40:34 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 20-Jun-2026 17:51:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 21-Jun-2026 20:59:09 | 22-Jun-2026 00:35:21 | 0 |  |  | Approver | Locate
AO-000660 | MM-ASK-1A-GEN01-SAF-PDR-0009 | SIL TOR (OFFSHORE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 20:01:49 | zm167dc@jutal.com | 09-Jul-2026 10:23:51 | Jumpol Sudjitjul | 17-Jul-2026 | 24-Jul-2026 10:55:13 | Pongsakorn Monturat | 20-Jul-2026 | 07-Aug-2026 14:20:14 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 07-Aug-2026 21:41:36 | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 08-Aug-2026 10:06:58 | 08-Aug-2026 03:21:31 | 0 |  |  | Approver | Locate
AO-001303 | MM-ASK-1A-GEN01-SAF-PDR-0012 | ALARP STUDY TOR (OFFSHORE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PDR | Procedure | 0 | In Review | IFR | Issued for Review |  | 11-Sep-2026 09:06:34 | zm167dc@jutal.com | 11-Sep-2026 19:57:23 | Jumpol Sudjitjul | 22-Sep-2026 |  | Pongsakorn Monturat | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000156 | MM-ASK-1A-GEN01-SAF-PHI-0001 | SAFETY CONCEPT (OFFSHORE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 08:47:22 | zm167dc@jutal.com | 08-May-2026 16:12:24 | Jumpol Sudjitjul | 18-May-2026 | 10-May-2026 09:07:16 | Pongsakorn Monturat | 19-May-2026 | 18-May-2026 16:03:07 | Pornlert Wanaphattharaphan | 20-May-2026 | 19-May-2026 23:32:20 | NA | Not Approved | Jumpol Sudjitjul | 21-May-2026 | 20-May-2026 08:49:49 | 20-May-2026 09:30:30 | 0 |  |  | Approver | Locate
AO-000384 | MM-ASK-1A-GEN01-SAF-PHI-0001 | SAFETY CONCEPT (OFFSHORE) |  | A2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:09:19 | zm167dc@jutal.com | 29-May-2026 18:44:21 | Jumpol Sudjitjul | 11-Jun-2026 | 17-Jun-2026 18:17:58 | Warayut Ubolcharoen | 12-Jun-2026 | 18-Jun-2026 16:56:53 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 19-Jun-2026 21:46:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 21-Jun-2026 21:00:50 | 22-Jun-2026 00:10:35 | 0 |  |  | Approver | Locate
AO-000583 | MM-ASK-1A-GEN01-SAF-PHI-0001 | SAFETY CONCEPT (OFFSHORE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PHI | Philosophy | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 13:53:57 | zm167dc@jutal.com | 01-Jul-2026 14:38:50 | Jumpol Sudjitjul | 09-Jul-2026 | 14-Jul-2026 08:53:09 | Pongsakorn Monturat | 10-Jul-2026 | 23-Jul-2026 15:17:51 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 23-Jul-2026 23:59:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 24-Jul-2026 10:12:22 | 24-Jul-2026 03:16:28 | 0 |  |  | Approver | Locate
AO-001011 | MM-ASK-1A-GEN01-SAF-PHI-0001 | SAFETY CONCEPT (OFFSHORE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | PHI | Philosophy | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 18:40:26 | zm167dc@jutal.com | 18-Aug-2026 10:17:51 | Jumpol Sudjitjul | 26-Aug-2026 | 07-Sep-2026 17:49:43 | Pongsakorn Monturat | 27-Aug-2026 | 16-Sep-2026 13:28:04 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 17-Sep-2026 22:45:43 | APPR | Approved | Jumpol Sudjitjul | 31-Aug-2026 | 18-Sep-2026 08:45:49 | 18-Sep-2026 02:11:06 | 0 |  |  | Approver | Locate
AO-000272 | MM-ASK-1A-GEN01-SAF-RPT-0002 | SAFETY STUDY ASSUMPTION REGISTER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 16:16:52 | zm167dc@jutal.com | 18-May-2026 20:44:42 | Jumpol Sudjitjul | 27-May-2026 | 29-May-2026 14:43:37 | Pongsakorn Monturat | 28-May-2026 | 29-May-2026 17:15:01 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 21:00:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 09:04:57 | 11-Jun-2026 02:47:46 | 0 |  |  | Approver | Locate
AO-000560 | MM-ASK-1A-GEN01-SAF-RPT-0002 | SAFETY STUDY ASSUMPTION REGISTER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:38:19 | zm167dc@jutal.com | 26-Jun-2026 17:02:46 | Jumpol Sudjitjul | 07-Jul-2026 | 09-Jul-2026 17:10:13 | Pongsakorn Monturat | 08-Jul-2026 | 23-Jul-2026 15:04:03 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 23-Jul-2026 22:25:32 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 24-Jul-2026 10:19:30 | 24-Jul-2026 04:02:47 | 0 |  |  | Approver | Locate
AO-000704 | MM-ASK-1A-GEN01-SAF-RPT-0003 | RELIABILITY, AVAILABILITY AND MAINTAINABILITY (RAM) STUDY ASSUMPTION REGISTER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 15-Jul-2026 17:59:05 | zm167dc@jutal.com | 15-Jul-2026 18:05:16 | Jumpol Sudjitjul | 24-Jul-2026 | 03-Aug-2026 08:43:46 | Pongsakorn Monturat | 27-Jul-2026 | 10-Aug-2026 15:20:34 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 11-Aug-2026 23:34:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 13-Aug-2026 08:29:03 | 13-Aug-2026 02:31:03 | 0 |  |  | Approver | Locate
AO-001117 | MM-ASK-1A-GEN01-SAF-RPT-0003 | RELIABILITY, AVAILABILITY AND MAINTAINABILITY (RAM) STUDY ASSUMPTION REGISTER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 28-Aug-2026 12:03:21 | zm167dc@jutal.com | 28-Aug-2026 14:37:58 | Jumpol Sudjitjul | 07-Sep-2026 | 11-Sep-2026 07:52:35 | Pongsakorn Monturat | 08-Sep-2026 |  | Pornlert Wanaphattharaphan | 09-Sep-2026 |  |  |  |  | 10-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000766 | MM-ASK-1A-GEN01-SAF-RPT-0004 | HAZARD REGISTER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 23-Jul-2026 16:44:11 | zm167dc@jutal.com | 23-Jul-2026 17:10:37 | Jumpol Sudjitjul | 05-Aug-2026 | 21-Aug-2026 13:38:18 | Pongsakorn Monturat | 06-Aug-2026 | 24-Aug-2026 16:30:25 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 25-Aug-2026 21:50:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 26-Aug-2026 08:55:57 | 26-Aug-2026 02:48:25 | 0 |  |  | Approver | Locate
AO-001252 | MM-ASK-1A-GEN01-SAF-RPT-0004 | HAZARD REGISTER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 09-Sep-2026 14:46:25 | zm167dc@jutal.com | 10-Sep-2026 13:17:44 | Jumpol Sudjitjul | 18-Sep-2026 | 17-Sep-2026 23:11:23 | Pongsakorn Monturat | 21-Sep-2026 |  | Pornlert Wanaphattharaphan | 22-Sep-2026 |  |  |  |  | 23-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000433 | MM-ASK-1A-GEN01-SAF-RPT-0006 | HAZID REPORT (OFFSHORE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:11:27 | zm167dc@jutal.com | 10-Jun-2026 09:30:35 | Jumpol Sudjitjul | 18-Jun-2026 | 30-Jun-2026 12:16:09 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 10:37:48 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 13:25:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 13:29:26 | 08-Jul-2026 06:52:21 | 0 |  |  | Approver | Locate
AO-000714 | MM-ASK-1A-GEN01-SAF-RPT-0006 | HAZID REPORT (OFFSHORE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 17-Jul-2026 11:57:52 | zm167dc@jutal.com | 17-Jul-2026 12:56:06 | Jumpol Sudjitjul | 27-Jul-2026 | 06-Aug-2026 07:59:30 | Pongsakorn Monturat | 30-Jul-2026 | 10-Aug-2026 13:07:11 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 11-Aug-2026 23:39:28 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 13-Aug-2026 08:30:54 | 13-Aug-2026 02:33:44 | 0 |  |  | Approver | Locate
AO-000619 | MM-ASK-1A-GEN01-SAF-RPT-0008 | HAZOP REPORT (OFFSHORE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:16:43 | zm167dc@jutal.com | 03-Jul-2026 18:33:51 | Jumpol Sudjitjul | 14-Jul-2026 | 17-Jul-2026 10:37:23 | Pongsakorn Monturat | 15-Jul-2026 | 23-Jul-2026 15:18:31 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 24-Jul-2026 00:00:28 | APPR | Approved | Jumpol Sudjitjul | 17-Jul-2026 | 24-Jul-2026 10:21:40 | 24-Jul-2026 04:17:50 | 0 |  |  | Approver | Locate
AO-000825 | MM-ASK-1A-GEN01-SAF-RPT-0008 | HAZOP REPORT (OFFSHORE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:56:31 | zm167dc@jutal.com | 31-Jul-2026 14:59:01 | Jumpol Sudjitjul | 10-Aug-2026 | 09-Aug-2026 23:56:41 | Pongsakorn Monturat | 11-Aug-2026 | 24-Aug-2026 16:39:54 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 25-Aug-2026 22:18:36 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 26-Aug-2026 08:55:33 | 26-Aug-2026 02:43:46 | 0 |  |  | Approver | Locate
AO-000676 | MM-ASK-1A-GEN01-SAF-RPT-0010 | SIL CLASSIFICATION REPORT (OFFSHORE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 17:24:36 | zm167dc@jutal.com | 10-Jul-2026 18:00:28 | Jumpol Sudjitjul | 21-Jul-2026 | 30-Jul-2026 16:23:40 | Pongsakorn Monturat | 22-Jul-2026 | 03-Aug-2026 14:57:39 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 03-Aug-2026 23:17:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 04-Aug-2026 10:32:30 | 04-Aug-2026 04:00:21 | 0 |  |  | Approver | Locate
AO-000976 | MM-ASK-1A-GEN01-SAF-RPT-0010 | SIL CLASSIFICATION REPORT (OFFSHORE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 11:30:28 | zm167dc@jutal.com | 14-Aug-2026 12:51:33 | Jumpol Sudjitjul | 24-Aug-2026 | 21-Aug-2026 00:02:51 | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 13:06:17 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 21:48:02 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 12:54:32 | 08-Sep-2026 06:55:10 | 0 |  |  | Approver | Locate
AO-000714 | MM-ASK-1A-GEN01-SAF-RPT-0014 | VENT DISPERSION & THERMAL RADIATION STUDY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 17-Jul-2026 12:36:38 | zm167dc@jutal.com | 17-Jul-2026 12:58:41 | Jumpol Sudjitjul | 27-Jul-2026 | 27-Jul-2026 15:43:39 | Pongsakorn Monturat | 30-Jul-2026 | 18-Aug-2026 05:59:45 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 18-Aug-2026 20:03:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 19-Aug-2026 09:50:49 | 19-Aug-2026 03:10:20 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-GEN01-SAF-RPT-0014 | VENT DISPERSION & THERMAL RADIATION STUDY |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:39:50 | zm167dc@jutal.com | 11-Sep-2026 19:56:16 | Jumpol Sudjitjul | 22-Sep-2026 |  | Pongsakorn Monturat | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000704 | MM-ASK-1A-GEN01-SAF-RPT-0015 | DROPPED OBJECT STUDY (DOS) (TOPSIDE & ASSOCIATE PIPELINES) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 15-Jul-2026 17:59:47 | zm167dc@jutal.com | 15-Jul-2026 18:07:58 | Jumpol Sudjitjul | 24-Jul-2026 | 06-Aug-2026 15:14:35 | Pongsakorn Monturat | 27-Jul-2026 | 13-Aug-2026 10:38:45 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 15-Aug-2026 06:19:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 15-Aug-2026 14:30:28 | 15-Aug-2026 08:16:31 | 0 |  |  | Approver | Locate
AO-001123 | MM-ASK-1A-GEN01-SAF-RPT-0015 | DROPPED OBJECT STUDY (DOS) (TOPSIDE & ASSOCIATE PIPELINES) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 28-Aug-2026 16:48:47 | zm167dc@jutal.com | 28-Aug-2026 17:22:22 | Jumpol Sudjitjul | 08-Sep-2026 | 31-Aug-2026 11:12:38 | Pongsakorn Monturat | 09-Sep-2026 |  | Pornlert Wanaphattharaphan | 10-Sep-2026 |  |  |  |  | 11-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000772 | MM-ASK-1A-GEN01-SAF-RPT-0016 | FIRE AND EXPLOSION RISK ANALYSIS (FERA) STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:06:01 | zm167dc@jutal.com | 26-Jul-2026 22:43:08 | Jumpol Sudjitjul | 06-Aug-2026 | 05-Aug-2026 23:25:07 | Pongsakorn Monturat | 07-Aug-2026 | 15-Aug-2026 19:33:53 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 16-Aug-2026 10:23:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 17-Aug-2026 08:40:11 | 17-Aug-2026 02:42:46 | 0 |  |  | Approver | Locate
AO-001199 | MM-ASK-1A-GEN01-SAF-RPT-0016 | FIRE AND EXPLOSION RISK ANALYSIS (FERA) STUDY REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 04-Sep-2026 17:20:40 | zm167dc@jutal.com | 05-Sep-2026 18:20:32 | Jumpol Sudjitjul | 15-Sep-2026 | 14-Sep-2026 16:54:13 | Pongsakorn Monturat | 16-Sep-2026 |  | Pornlert Wanaphattharaphan | 17-Sep-2026 |  |  |  |  | 18-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001096 | MM-ASK-1A-GEN01-SAF-RPT-0017 | QUANTITATIVE RISK ASSESSMENT (QRA) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | IFR | Issued for Review |  | 25-Aug-2026 19:48:07 | zm167dc@jutal.com | 26-Aug-2026 09:31:20 | Jumpol Sudjitjul | 03-Sep-2026 | 10-Sep-2026 13:05:09 | Pongsakorn Monturat | 04-Sep-2026 |  | Pornlert Wanaphattharaphan | 07-Sep-2026 |  |  |  |  | 08-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001090 | MM-ASK-1A-GEN01-SAF-RPT-0018 | ESCAPE, EVACUATION AND RESCUE ANALYSIS (EERA) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | IFR | Issued for Review |  | 24-Aug-2026 17:58:46 | zm167dc@jutal.com | 24-Aug-2026 20:21:50 | Jumpol Sudjitjul | 02-Sep-2026 | 13-Sep-2026 10:42:01 | Pongsakorn Monturat | 03-Sep-2026 |  | Pornlert Wanaphattharaphan | 04-Sep-2026 |  |  |  |  | 07-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001414 | MM-ASK-1A-GEN01-SAF-RPT-0019 | DESIGN SAFETY CRITICAL ELEMENT AND PERFORMANCE STANDARD (SCE PS) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | IFR | Issued for Review |  | 16-Sep-2026 14:52:53 | zm167dc@jutal.com | 17-Sep-2026 08:51:26 | Jumpol Sudjitjul | 25-Sep-2026 |  | Pongsakorn Monturat | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000758 | MM-ASK-1A-GEN01-SAF-RPT-0021 | BOW-TIE STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 16:42:29 | zm167dc@jutal.com | 22-Jul-2026 17:06:10 | Jumpol Sudjitjul | 04-Aug-2026 | 21-Aug-2026 13:34:47 | Pongsakorn Monturat | 05-Aug-2026 | 24-Aug-2026 16:28:52 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 25-Aug-2026 21:44:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 26-Aug-2026 08:53:21 | 26-Aug-2026 02:47:10 | 0 |  |  | Approver | Locate
AO-001302 | MM-ASK-1A-GEN01-SAF-RPT-0021 | BOW-TIE STUDY REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 09:07:10 | zm167dc@jutal.com | 11-Sep-2026 19:55:47 | Jumpol Sudjitjul | 22-Sep-2026 |  | Pongsakorn Monturat | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001200 | MM-ASK-1A-GEN01-SAF-RPT-0022 | DESIGN SAFETY CASE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | IFR | Issued for Review |  | 04-Sep-2026 17:21:10 | zm167dc@jutal.com | 05-Sep-2026 18:21:29 | Jumpol Sudjitjul | 15-Sep-2026 | 15-Sep-2026 23:55:39 | Pongsakorn Monturat | 16-Sep-2026 |  | Pornlert Wanaphattharaphan | 17-Sep-2026 |  |  |  |  | 18-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000933 | MM-ASK-1A-GEN01-SAF-RPT-0024 | HAZOP CLOSED OUT REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 08-Aug-2026 11:23:27 | zm167dc@jutal.com | 08-Aug-2026 20:10:00 | Jumpol Sudjitjul | 19-Aug-2026 | 07-Sep-2026 17:48:45 | Pongsakorn Monturat | 20-Aug-2026 | 14-Sep-2026 19:33:50 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 14-Sep-2026 23:50:51 | NA | Not Approved | Jumpol Sudjitjul | 24-Aug-2026 | 15-Sep-2026 16:58:30 | 15-Sep-2026 10:22:30 | 0 |  |  | Approver | Locate
AO-000858 | MM-ASK-1A-GEN01-SAF-RPT-0025 | HAZID CLOSED OUT REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 19:13:06 | zm167dc@jutal.com | 04-Aug-2026 08:31:59 | Jumpol Sudjitjul | 13-Aug-2026 | 07-Sep-2026 17:48:05 | Pongsakorn Monturat | 14-Aug-2026 | 14-Sep-2026 19:16:00 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 14-Sep-2026 23:47:46 | NA | Not Approved | Jumpol Sudjitjul | 18-Aug-2026 | 15-Sep-2026 16:58:57 | 15-Sep-2026 10:37:53 | 0 |  |  | Approver | Locate
AO-000372 | MM-ASK-1A-GEN01-SAF-RPT-0030 | HAZARDOUS EQUIPMENT SCHEDULE (NORMAL OPERATIONS, SIMOPS) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 21:00:11 | zm167dc@jutal.com | 29-May-2026 09:55:10 | Jumpol Sudjitjul | 10-Jun-2026 | 17-Jun-2026 18:16:47 | Warayut Ubolcharoen | 11-Jun-2026 | 18-Jun-2026 17:13:36 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 19-Jun-2026 21:25:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 21:01:23 | 22-Jun-2026 01:14:31 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-GEN01-SAF-RPT-0030 | HAZARDOUS EQUIPMENT SCHEDULE (NORMAL OPERATIONS, SIMOPS) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 20:40:10 | zm167dc@jutal.com | 17-Jul-2026 22:12:34 | Jumpol Sudjitjul | 30-Jul-2026 | 02-Aug-2026 20:56:58 | Pongsakorn Monturat | 31-Jul-2026 | 18-Aug-2026 12:41:13 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 18-Aug-2026 20:23:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 19-Aug-2026 09:51:19 | 19-Aug-2026 03:00:05 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-GEN01-SAF-RPT-0030 | HAZARDOUS EQUIPMENT SCHEDULE (NORMAL OPERATIONS, SIMOPS) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 02-Sep-2026 19:59:12 | zm167dc@jutal.com | 02-Sep-2026 20:47:59 | Soontaree Simpitak | 11-Sep-2026 | 08-Sep-2026 11:50:20 | Pongsakorn Monturat | 14-Sep-2026 |  | Pornlert Wanaphattharaphan | 15-Sep-2026 |  |  |  |  | 16-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000172 | MM-ASK-1A-GEN01-SAF-SPE-0023 | SPECIFICATION FOR FIREFIGHTING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 17:29:59 | zm167dc@jutal.com | 08-May-2026 17:33:37 | Jumpol Sudjitjul | 19-May-2026 |  | Pongsakorn Monturat | 20-May-2026 | 18-May-2026 17:15:45 | Pornlert Wanaphattharaphan | 21-May-2026 | 25-May-2026 21:48:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 21:53:36 | 25-May-2026 21:59:34 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-GEN01-SAF-SPE-0023 | SPECIFICATION FOR FIREFIGHTING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 11-Jun-2026 14:57:17 | zm167dc@jutal.com | 11-Jun-2026 15:14:39 | Jumpol Sudjitjul | 19-Jun-2026 | 01-Jul-2026 08:08:50 | Jumpol Sudjitjul | 22-Jun-2026 | 08-Jul-2026 10:38:52 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 08-Jul-2026 23:10:26 | APPR | Approved | Jumpol Sudjitjul | 24-Jun-2026 | 09-Jul-2026 09:54:43 | 09-Jul-2026 03:59:27 | 0 |  |  | Approver | Locate
AO-000196 | MM-ASK-1A-GEN01-SAF-SPE-0024 | SPECIFICATION FOR LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:44:58 | zm167dc@jutal.com | 11-May-2026 17:51:14 | Jumpol Sudjitjul | 20-May-2026 |  | Pongsakorn Monturat | 21-May-2026 | 29-May-2026 15:15:43 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 00:34:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 16:26:37 | 31-May-2026 16:50:45 | 0 |  |  | Approver | Locate
AO-000453 | MM-ASK-1A-GEN01-SAF-SPE-0024 | SPECIFICATION FOR LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 11-Jun-2026 18:09:40 | zm167dc@jutal.com | 12-Jun-2026 09:31:34 | Jumpol Sudjitjul | 22-Jun-2026 | 30-Jun-2026 12:16:58 | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 10:40:38 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 08-Jul-2026 23:17:07 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 09-Jul-2026 09:56:10 | 09-Jul-2026 04:17:20 | 0 |  |  | Approver | Locate
AO-001044 | MM-ASK-1A-GEN01-SAF-SPE-0024 | SPECIFICATION FOR LIFESAVING EQUIPMENT AND SAFETY EQUIPMENT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | In Review | AFC | Approved for Construction |  | 21-Aug-2026 09:37:38 | zm167dc@jutal.com | 21-Aug-2026 13:40:36 | Jumpol Sudjitjul | 31-Aug-2026 | 16-Sep-2026 15:03:05 | Pongsakorn Monturat | 01-Sep-2026 |  | Pornlert Wanaphattharaphan | 02-Sep-2026 |  |  |  |  | 03-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000173 | MM-ASK-1A-GEN01-SAF-SPE-0025 | SPECIFICATION FOR SAFETY SIGNS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 17:30:29 | zm167dc@jutal.com | 08-May-2026 17:33:56 | Jumpol Sudjitjul | 19-May-2026 |  | Pongsakorn Monturat | 20-May-2026 | 18-May-2026 18:02:10 | Pornlert Wanaphattharaphan | 21-May-2026 | 25-May-2026 21:50:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 22:04:49 | 25-May-2026 22:30:14 | 0 |  |  | Approver | Locate
AO-000430 | MM-ASK-1A-GEN01-SAF-SPE-0025 | SPECIFICATION FOR SAFETY SIGNS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Revised | IFA | Issued for Approval | 10-Jun-2026 | 08-Jun-2026 17:54:02 | zm167dc@jutal.com | 08-Jun-2026 18:16:55 | Jumpol Sudjitjul | 17-Jun-2026 |  | Warayut Ubolcharoen | 18-Jun-2026 |  | Pornlert Wanaphattharaphan | 19-Jun-2026 |  |  |  |  | 22-Jun-2026 |  |  | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-GEN01-SAF-SPE-0025 | SPECIFICATION FOR SAFETY SIGNS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  |  | zm167dc@jutal.com | 10-Jun-2026 14:02:18 | Jumpol Sudjitjul | 18-Jun-2026 | 30-Jun-2026 12:17:58 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 10:41:22 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 13:26:25 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 13:30:48 | 08-Jul-2026 06:53:39 | 0 |  |  | Approver | Locate
AO-001044 | MM-ASK-1A-GEN01-SAF-SPE-0025 | SPECIFICATION FOR SAFETY SIGNS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | In Review | AFC | Approved for Construction |  | 21-Aug-2026 09:38:08 | zm167dc@jutal.com | 21-Aug-2026 13:41:30 | Jumpol Sudjitjul | 31-Aug-2026 | 08-Sep-2026 08:45:21 | Pongsakorn Monturat | 01-Sep-2026 |  | Pornlert Wanaphattharaphan | 02-Sep-2026 |  |  |  |  | 03-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000027 | MM-ASK-1A-GEN01-SSHE-PDR-0001 | SSHE BRIDGING DOCUMENT |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 02-Apr-2026 19:30:52 | zm167dc@jutal.com | 02-Apr-2026 21:05:21 | Jumpol Sudjitjul | 17-Apr-2026 | 15-Apr-2026 16:32:54 | Ananchai Mongkonpanyanan | 20-Apr-2026 | 25-Apr-2026 18:07:44 | Apisit Tangwashirakul | 21-Apr-2026 | 27-Apr-2026 08:19:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 27-Apr-2026 09:57:09 | 27-Apr-2026 10:16:59 | 0 |  |  | Approver | Locate
AO-000182 | MM-ASK-1A-GEN01-SSHE-PDR-0001 | SSHE BRIDGING DOCUMENT |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval | 13-May-2026 | 10-May-2026 23:35:38 | zm167dc@jutal.com | 10-May-2026 23:38:47 | Jumpol Sudjitjul | 19-May-2026 |  | Ananchai Mongkonpanyanan | 20-May-2026 | 12-May-2026 20:39:36 | Apisit Tangwashirakul | 21-May-2026 | 18-May-2026 10:11:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 18-May-2026 18:55:25 | 18-May-2026 19:16:35 | 0 |  |  | Approver | Locate
AO-000493 | MM-ASK-1A-GEN01-SSHE-PDR-0001 | SSHE BRIDGING DOCUMENT |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 17-Jun-2026 12:48:50 | zm167dc@jutal.com | 17-Jun-2026 16:04:18 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 16:32:51 | Ananchai Mongkonpanyanan | 26-Jun-2026 | 27-Jun-2026 11:25:43 | Apisit Tangwashirakul | 29-Jun-2026 | 27-Jun-2026 22:27:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 28-Jun-2026 08:38:02 | 28-Jun-2026 02:17:28 | 0 |  |  | Approver | Locate
AO-000610 | MM-ASK-1A-GEN01-SSHE-PDR-0001 | SSHE BRIDGING DOCUMENT |  | B3 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 14:17:02 | zm167dc@jutal.com | 03-Jul-2026 14:41:47 | Jumpol Sudjitjul | 13-Jul-2026 |  | Ananchai Mongkonpanyanan | 14-Jul-2026 | 13-Jul-2026 08:44:02 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 09:56:07 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 10:18:41 | 17-Jul-2026 03:55:59 | 0 |  |  | Approver | Locate
AO-000716 | MM-ASK-1A-GEN01-SSHE-PDR-0001 | SSHE BRIDGING DOCUMENT |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 14:52:40 | zm167dc@jutal.com | 17-Jul-2026 14:56:16 | Jumpol Sudjitjul | 27-Jul-2026 |  | Ananchai Mongkonpanyanan | 30-Jul-2026 | 27-Jul-2026 11:13:14 | Apisit Tangwashirakul | 31-Jul-2026 | 21-Aug-2026 14:33:22 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 21-Aug-2026 14:40:41 | 21-Aug-2026 08:27:11 | 0 |  |  | Approver | Locate
AO-000567 | MM-ASK-1A-GEN01-SSHE-PDR-0002 | SAFETY CRITICAL ELEMENT (SCE) LISTS AND PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:44:53 | zm167dc@jutal.com | 27-Jun-2026 19:42:09 | Jumpol Sudjitjul | 07-Jul-2026 |  | Ananchai Mongkonpanyanan | 08-Jul-2026 | 30-Jun-2026 14:04:25 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 04-Jul-2026 19:38:35 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 05-Jul-2026 10:25:20 | 05-Jul-2026 03:57:41 | 0 |  |  | Approver | Locate
AO-000703 | MM-ASK-1A-GEN01-SSHE-PDR-0002 | SAFETY CRITICAL ELEMENT (SCE) LISTS AND PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 14-Jul-2026 18:09:00 | zm167dc@jutal.com | 14-Jul-2026 20:09:50 | Jumpol Sudjitjul | 23-Jul-2026 | 15-Jul-2026 23:25:33 | Ananchai Mongkonpanyanan | 24-Jul-2026 | 27-Jul-2026 11:17:03 | Apisit Tangwashirakul | 27-Jul-2026 | 21-Aug-2026 12:53:59 | APPR | Approved | Jumpol Sudjitjul | 30-Jul-2026 | 21-Aug-2026 13:08:27 | 21-Aug-2026 06:22:15 | 0 |  |  | Approver | Locate
AO-000568 | MM-ASK-1A-GEN01-SSHE-PDR-0003 | SSHE PROGRESS MEASUREMENT PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:45:29 | zm167dc@jutal.com | 27-Jun-2026 19:45:03 | Jumpol Sudjitjul | 07-Jul-2026 |  | Ananchai Mongkonpanyanan | 08-Jul-2026 | 30-Jun-2026 12:03:59 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 04-Jul-2026 19:38:03 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 05-Jul-2026 10:26:17 | 05-Jul-2026 03:58:57 | 0 |  |  | Approver | Locate
AO-000768 | MM-ASK-1A-GEN01-SSHE-PDR-0003 | SSHE PROGRESS MEASUREMENT PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 10:43:53 | zm167dc@jutal.com | 24-Jul-2026 11:37:18 | Jumpol Sudjitjul | 05-Aug-2026 |  | Ananchai Mongkonpanyanan | 06-Aug-2026 | 27-Jul-2026 11:18:29 | Jumpol Sudjitjul | 07-Aug-2026 | 11-Aug-2026 16:52:52 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 11-Aug-2026 16:56:56 | 11-Aug-2026 11:27:57 | 0 |  |  | Approver | Locate
AO-000122 | MM-ASK-1A-GEN01-SSHE-PLN-0001 | SSHE MANAGEMENT AND EXECUTION PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:31:18 | zm167dc@jutal.com | 04-May-2026 12:59:32 | Jumpol Sudjitjul | 12-May-2026 |  | Ananchai Mongkonpanyanan | 13-May-2026 | 11-May-2026 21:23:51 | Apisit Tangwashirakul | 14-May-2026 | 18-May-2026 10:09:18 | NA | Not Approved | Jumpol Sudjitjul | 15-May-2026 | 18-May-2026 18:54:23 | 18-May-2026 19:15:23 | 0 |  |  | Approver | Locate
AO-000499 | MM-ASK-1A-GEN01-SSHE-PLN-0001 | SSHE MANAGEMENT AND EXECUTION PLAN |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 17-Jun-2026 15:33:24 | zm167dc@jutal.com | 17-Jun-2026 16:09:35 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 16:15:18 | Ananchai Mongkonpanyanan | 26-Jun-2026 | 22-Jun-2026 11:55:04 | Apisit Tangwashirakul | 29-Jun-2026 | 07-Jul-2026 15:06:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 07-Jul-2026 15:37:25 | 07-Jul-2026 08:59:47 | 0 |  |  | Approver | Locate
AO-000760 | MM-ASK-1A-GEN01-SSHE-PLN-0001 | SSHE MANAGEMENT AND EXECUTION PLAN |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 23-Jul-2026 11:00:52 | zm167dc@jutal.com | 23-Jul-2026 16:11:50 | Jumpol Sudjitjul | 04-Aug-2026 |  | Ananchai Mongkonpanyanan | 05-Aug-2026 | 27-Jul-2026 18:11:21 | Jumpol Sudjitjul | 06-Aug-2026 | 11-Aug-2026 16:52:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 11-Aug-2026 16:55:46 | 11-Aug-2026 09:58:33 | 0 |  |  | Approver | Locate
AO-000969 | MM-ASK-1A-GEN01-SSHE-PLN-0001 | SSHE MANAGEMENT AND EXECUTION PLAN |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 16:52:34 | zm167dc@jutal.com | 13-Aug-2026 17:04:40 | Jumpol Sudjitjul | 24-Aug-2026 |  | Minttita Vararathsitanonlt | 25-Aug-2026 | 03-Sep-2026 11:11:49 | Ananchai Mongkonpanyanan | 26-Aug-2026 | 04-Sep-2026 14:18:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 04-Sep-2026 15:24:14 | 04-Sep-2026 08:43:46 | 0 |  |  | Approver | Locate
AO-001256 | MM-ASK-1A-GEN01-SSHE-PLN-0001 | SSHE MANAGEMENT AND EXECUTION PLAN |  | C3 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | In Review | AFC | Approved for Construction |  | 09-Sep-2026 14:46:56 | zm167dc@jutal.com | 09-Sep-2026 16:56:35 | Jumpol Sudjitjul | 17-Sep-2026 |  | Minttita Vararathsitanonlt | 18-Sep-2026 |  | Ananchai Mongkonpanyanan | 21-Sep-2026 |  |  |  |  | 22-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000860 | MM-ASK-1A-GEN01-SSHE-RPT-0001 | SSHE RISK ASSESSMENT AND JOB SAFETY ANALYSIS (JSA) REPORT |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Aug-2026 11:56:01 | zm167dc@jutal.com | 04-Aug-2026 13:16:11 | Jumpol Sudjitjul | 13-Aug-2026 | 05-Aug-2026 17:34:27 | Ananchai Mongkonpanyanan | 14-Aug-2026 | 16-Aug-2026 14:17:47 | Apisit Tangwashirakul | 17-Aug-2026 | 22-Aug-2026 22:53:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 24-Aug-2026 11:12:02 | 24-Aug-2026 04:44:47 | 0 |  |  | Approver | Locate
AO-000861 | MM-ASK-1A-GEN01-SSHE-RPT-0002 | PRE-MOBILIZATION AUDIT REPORT AND ACTION TRACKING/CLOSE-OUT REPORTS |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Aug-2026 11:56:28 | zm167dc@jutal.com | 04-Aug-2026 13:31:21 | Jumpol Sudjitjul | 13-Aug-2026 |  | Ananchai Mongkonpanyanan | 14-Aug-2026 | 16-Aug-2026 13:49:50 | Apisit Tangwashirakul | 17-Aug-2026 | 22-Aug-2026 22:54:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 24-Aug-2026 11:17:48 | 24-Aug-2026 04:49:41 | 0 |  |  | Approver | Locate
AO-000862 | MM-ASK-1A-GEN01-SSHE-RPT-0003 | SSHE COMMENCEMENT CERTIFICATE REPORTS |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Aug-2026 11:56:51 | zm167dc@jutal.com | 04-Aug-2026 13:13:53 | Jumpol Sudjitjul | 13-Aug-2026 |  | Ananchai Mongkonpanyanan | 14-Aug-2026 | 16-Aug-2026 13:45:39 | Apisit Tangwashirakul | 17-Aug-2026 | 27-Aug-2026 10:34:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 27-Aug-2026 11:43:12 | 27-Aug-2026 05:27:27 | 0 |  |  | Approver | Locate
AO-000164 | MM-ASK-1A-GEN01-STR-BOD-0001 | STRUCTURAL DESIGN BASIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 14:10:54 | zm167dc@jutal.com | 08-May-2026 15:26:40 | Jumpol Sudjitjul | 18-May-2026 |  | Washira Kaew-amatawong | 19-May-2026 | 19-May-2026 15:30:28 | Pornlert Wanaphattharaphan | 20-May-2026 | 19-May-2026 23:59:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 20-May-2026 08:56:31 | 20-May-2026 02:36:51 | 0 |  |  | Approver | Locate
AO-000689 | MM-ASK-1A-GEN01-STR-BOD-0001 | STRUCTURAL DESIGN BASIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:35:32 | zm167dc@jutal.com | 12-Jul-2026 11:48:40 | Jumpol Sudjitjul | 20-Jul-2026 | 15-Jul-2026 17:53:52 | Washira Kaew-amatawong | 21-Jul-2026 | 23-Jul-2026 13:10:31 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 13:44:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 13:56:27 | 24-Jul-2026 07:28:33 | 0 |  |  | Approver | Locate
AO-000223 | MM-ASK-1A-GEN01-STR-MOM-0001 | STRUCTURAL WEEKLY MEETING NO.1 (06-MAR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-May-2026 08:49:04 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000224 | MM-ASK-1A-GEN01-STR-MOM-0002 | STRUCTURAL WEEKLY MEETING NO.2 (16-MAR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-May-2026 08:49:36 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000225 | MM-ASK-1A-GEN01-STR-MOM-0003 | STRUCTURAL WEEKLY MEETING NO.3 (23-MAR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-May-2026 08:50:05 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000226 | MM-ASK-1A-GEN01-STR-MOM-0004 | STRUCTURAL WEEKLY MEETING NO.4 (1-APR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-May-2026 08:50:33 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000192 | MM-ASK-1A-GEN01-STR-MOM-0005 | STRUCTURAL WEEKLY MEETING NO.5 (10-APR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 11-May-2026 10:24:28 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000219 | MM-ASK-1A-GEN01-STR-MOM-0006 | STRUCTURAL WEEKLY MEETING NO.6 (22-APR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 20:46:46 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000220 | MM-ASK-1A-GEN01-STR-MOM-0007 | STRUCTURAL WEEKLY MEETING NO.7 (29-APR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 20:47:10 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000222 | MM-ASK-1A-GEN01-STR-MOM-0008 | STRUCTURAL WEEKLY MEETING NO.8 (6-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-May-2026 08:51:04 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000334 | MM-ASK-1A-GEN01-STR-MOM-0009 | STRUCTURAL WEEKLY MEETING NO.9 (15-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 25-May-2026 12:44:35 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000363 | MM-ASK-1A-GEN01-STR-MOM-0010 | STRUCTURAL WEEKLY MEETING NO.10 (20-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 17:33:35 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000511 | MM-ASK-1A-GEN01-STR-MOM-0012 | STRUCTURAL WEEKLY MEETING NO.12 (05-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 19-Jun-2026 11:48:17 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000694 | MM-ASK-1A-GEN01-STR-MOM-0013 | STRUCTURAL WEEKLY MEETING NO.13 |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 08:36:54 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000692 | MM-ASK-1A-GEN01-STR-MOM-0014 | STRUCTURAL WEEKLY MEETING NO.14 |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-Jul-2026 16:49:34 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000821 | MM-ASK-1A-GEN01-STR-MOM-0016 | STRUCTURAL WEEKLY MEETING NO.16 (08-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 31-Jul-2026 11:26:26 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000973 | MM-ASK-1A-GEN01-STR-MOM-0018 | STRUCTURAL WEEKLY MEETING NO.18 (22-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Aug-2026 08:41:27 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001098 | MM-ASK-1A-GEN01-STR-MOM-0019 | STRUCTURAL WEEKLY MEETING NO.19 (30-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 19:15:09 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001099 | MM-ASK-1A-GEN01-STR-MOM-0020 | STRUCTURAL WEEKLY MEETING NO.20 (5-AUG-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 19:15:33 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000296 | MM-ASK-1A-GEN01-STR-MR-1001 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET PRIMARY STEEL STRUCTURE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 21-May-2026 09:29:01 | zm167dc@jutal.com | 21-May-2026 09:50:47 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:06:01 | Washira Kaew-amatawong | 02-Jun-2026 | 02-Jun-2026 09:39:47 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 02-Jun-2026 19:41:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 03-Jun-2026 08:56:22 | 03-Jun-2026 02:20:38 | 0 |  |  | Approver | Locate
AO-000572 | MM-ASK-1A-GEN01-STR-MR-1001 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET PRIMARY STEEL STRUCTURE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 22:01:26 | zm167dc@jutal.com | 30-Jun-2026 10:17:05 | Jumpol Sudjitjul | 08-Jul-2026 |  | Washira Kaew-amatawong | 09-Jul-2026 | 01-Jul-2026 10:47:38 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 02-Jul-2026 00:31:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 02-Jul-2026 10:30:09 | 02-Jul-2026 05:05:36 | 0 |  |  | Approver | Locate
AO-000292 | MM-ASK-1A-GEN01-STR-MR-1002 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET PRIMARY STEEL (HG STEEL SHAPES) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 20-May-2026 16:53:18 | zm167dc@jutal.com | 20-May-2026 18:00:13 | Jumpol Sudjitjul | 29-May-2026 | 27-May-2026 08:20:12 | Washira Kaew-amatawong | 02-Jun-2026 | 02-Jun-2026 09:41:03 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 02-Jun-2026 19:44:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 03-Jun-2026 08:56:55 | 03-Jun-2026 02:21:46 | 0 |  |  | Approver | Locate
AO-000608 | MM-ASK-1A-GEN01-STR-MR-1002 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET PRIMARY STEEL (HG STEEL SHAPES) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 14:16:15 | zm167dc@jutal.com | 03-Jul-2026 14:37:35 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 10-Jul-2026 15:57:24 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 11-Jul-2026 09:43:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 12-Jul-2026 11:21:13 | 12-Jul-2026 05:03:02 | 0 |  |  | Approver | Locate
AO-000293 | MM-ASK-1A-GEN01-STR-MR-1003 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET PRIMARY STEEL (HG STEEL PLATES) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 20-May-2026 16:53:49 | zm167dc@jutal.com | 20-May-2026 18:00:47 | Jumpol Sudjitjul | 29-May-2026 | 28-May-2026 14:14:01 | Washira Kaew-amatawong | 02-Jun-2026 | 02-Jun-2026 09:42:57 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 02-Jun-2026 19:49:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 03-Jun-2026 08:55:50 | 03-Jun-2026 02:19:33 | 0 |  |  | Approver | Locate
AO-000609 | MM-ASK-1A-GEN01-STR-MR-1003 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET PRIMARY STEEL (HG STEEL PLATES) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 11:55:10 | zm167dc@jutal.com | 03-Jul-2026 13:50:02 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 10-Jul-2026 16:02:02 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 11-Jul-2026 09:42:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 12-Jul-2026 11:21:47 | 12-Jul-2026 05:04:20 | 0 |  |  | Approver | Locate
AO-000587 | MM-ASK-1A-GEN01-STR-MR-1004 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET SECONDARY STEEL STRUCTURE (SHAPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 18:33:50 | zm167dc@jutal.com | 02-Jul-2026 14:29:23 | Jumpol Sudjitjul | 10-Jul-2026 |  | Washira Kaew-amatawong | 13-Jul-2026 | 10-Jul-2026 15:05:20 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 13-Jul-2026 22:31:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 14-Jul-2026 08:32:58 | 14-Jul-2026 01:59:32 | 0 |  |  | Approver | Locate
AO-000649 | MM-ASK-1A-GEN01-STR-MR-1005 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET SECONDARY STEEL PLATE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 18:41:40 | zm167dc@jutal.com | 07-Jul-2026 20:43:39 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:41:48 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 07:34:26 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 19-Jul-2026 16:02:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:33:38 | 20-Jul-2026 03:52:58 | 0 |  |  | Approver | Locate
AO-000649 | MM-ASK-1A-GEN01-STR-MR-1006 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET SECONDARY STEEL TUBULAR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 18:42:05 | zm167dc@jutal.com | 07-Jul-2026 20:43:53 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:42:47 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 07:35:56 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 19-Jul-2026 16:05:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:42:54 | 20-Jul-2026 04:40:40 | 0 |  |  | Approver | Locate
AO-000649 | MM-ASK-1A-GEN01-STR-MR-1007 | MATERIAL REQUISITION FOR ANODE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 18:42:33 | zm167dc@jutal.com | 07-Jul-2026 20:44:57 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:43:06 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 08:06:51 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 19-Jul-2026 16:11:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:33:10 | 20-Jul-2026 04:32:51 | 0 |  |  | Approver | Locate
AO-000818 | MM-ASK-1A-GEN01-STR-MR-1008 | MATERIAL REQUISITION FOR TOPSIDE AND JACKET SECONDARY STEEL STRUCTURE (L&C SHAPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 09:24:48 | zm167dc@jutal.com | 31-Jul-2026 09:31:59 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 14:51:40 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 21:10:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:31:48 | 13-Aug-2026 02:12:38 | 0 |  |  | Approver | Locate
AO-000099 | MM-ASK-1A-GEN01-STR-PDR-0001 | WEIGHT CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 19:02:03 | zm167dc@jutal.com | 30-Apr-2026 10:24:46 | Jumpol Sudjitjul | 12-May-2026 |  | Washira Kaew-amatawong | 13-May-2026 | 11-May-2026 15:29:16 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:43:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:15:40 | 19-May-2026 10:54:30 | 0 |  |  | Approver | Locate
AO-000347 | MM-ASK-1A-GEN01-STR-PDR-0001 | WEIGHT CONTROL PROCEDURE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 26-May-2026 10:55:14 | zm167dc@jutal.com | 26-May-2026 11:12:29 | Jumpol Sudjitjul | 05-Jun-2026 |  | Washira Kaew-amatawong | 08-Jun-2026 | 02-Jun-2026 11:24:33 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 02-Jun-2026 20:37:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 08:57:43 | 03-Jun-2026 02:22:54 | 0 |  |  | Approver | Locate
AO-000560 | MM-ASK-1A-GEN01-STR-PDR-0001 | WEIGHT CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 16:33:26 | zm167dc@jutal.com | 26-Jun-2026 16:41:46 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 30-Jun-2026 13:50:24 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 02-Jul-2026 00:55:33 | APPR | Approved | Jumpol Sudjitjul | 09-Jul-2026 | 02-Jul-2026 10:30:50 | 02-Jul-2026 05:04:15 | 0 |  |  | Approver | Locate
AO-000830 | MM-ASK-1A-GEN01-STR-RPT-2001 | BARGE MOTION ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 16:42:54 | zm167dc@jutal.com | 31-Jul-2026 17:07:24 | Jumpol Sudjitjul | 11-Aug-2026 |  | Washira Kaew-amatawong | 13-Aug-2026 | 13-Aug-2026 16:03:13 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 14-Aug-2026 00:09:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 08:11:52 | 14-Aug-2026 01:15:37 | 0 |  |  | Approver | Locate
AO-000751 | MM-ASK-1A-GEN01-STR-TBE-1001 | TECHNICAL BID EVALUATION FOR PRIMARY STEEL PLATE FOR TOPSIDES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 22-Jul-2026 08:34:33 | zm167dc@jutal.com | 22-Jul-2026 08:39:15 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 03-Aug-2026 09:10:13 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 03-Aug-2026 23:25:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 04-Aug-2026 10:33:51 | 04-Aug-2026 03:56:14 | 0 |  |  | Approver | Locate
AO-000752 | MM-ASK-1A-GEN01-STR-TBE-1002 | TECHNICAL BID EVALUATION FOR PRIMARY STEEL PLATE FOR JACKETS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 22-Jul-2026 08:35:07 | zm167dc@jutal.com | 22-Jul-2026 08:39:47 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 03-Aug-2026 09:11:56 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 03-Aug-2026 23:27:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 04-Aug-2026 10:35:16 | 04-Aug-2026 03:57:37 | 0 |  |  | Approver | Locate
AO-000470 | MM-ASK-1A-GEN01-STR-TBE-1003 | TECHNICAL BID EVALUATION FOR PRIMARY STEEL PLATE FOR PILES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 15:50:15 | zm167dc@jutal.com | 12-Jun-2026 16:31:29 | Jumpol Sudjitjul | 22-Jun-2026 |  | Washira Kaew-amatawong | 23-Jun-2026 | 15-Jun-2026 14:31:31 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 17-Jun-2026 11:03:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 17-Jun-2026 11:29:16 | 17-Jun-2026 05:18:17 | 0 |  |  | Approver | Locate
AO-000750 | MM-ASK-1A-GEN01-STR-TBE-1003 | TECHNICAL BID EVALUATION FOR PRIMARY STEEL PLATE FOR PILES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 22-Jul-2026 08:36:00 | zm167dc@jutal.com | 22-Jul-2026 08:41:09 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 03-Aug-2026 09:14:09 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 03-Aug-2026 23:30:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 04-Aug-2026 10:36:39 | 04-Aug-2026 03:58:58 | 0 |  |  | Approver | Locate
AO-000653 | MM-ASK-1A-GEN01-STR-TBE-1004 | TECHNICAL BID EVALUATION FOR PRIMARY STEEL SEAMLESS PIPES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 11:44:29 | zm167dc@jutal.com | 08-Jul-2026 14:29:53 | Jumpol Sudjitjul | 16-Jul-2026 |  | Washira Kaew-amatawong | 17-Jul-2026 | 13-Jul-2026 08:53:37 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 13-Jul-2026 13:29:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 13-Jul-2026 13:34:22 | 13-Jul-2026 07:06:30 | 0 |  |  | Approver | Locate
AO-000680 | MM-ASK-1A-GEN01-STR-TBE-1005 | TECHNICAL BID EVALUATION FOR PRIMARY STRUCTURAL STEEL BEAMS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 17:22:44 | zm167dc@jutal.com | 10-Jul-2026 17:57:06 | Jumpol Sudjitjul | 21-Jul-2026 |  | Washira Kaew-amatawong | 22-Jul-2026 | 14-Jul-2026 09:20:40 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 14-Jul-2026 22:52:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 15-Jul-2026 08:33:55 | 15-Jul-2026 02:03:32 | 0 |  |  | Approver | Locate
AO-001009 | MM-ASK-1A-GEN01-STR-TBE-1006 | TECHNICAL BID EVALUATION FOR TOPSIDE AND JACKET SECONDARY STEEL STRUCTURE (W SHAPE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 17:13:06 | zm167dc@jutal.com | 18-Aug-2026 09:36:20 | Jumpol Sudjitjul | 26-Aug-2026 | 21-Aug-2026 09:14:43 | Washira Kaew-amatawong | 27-Aug-2026 | 26-Aug-2026 17:48:15 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 29-Aug-2026 00:41:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 29-Aug-2026 13:42:44 | 29-Aug-2026 07:09:29 | 0 |  |  | Approver | Locate
AO-001296 | MM-ASK-1A-GEN01-STR-TBE-1008 | TECHNICAL BID EVALUATION FOR TOPSIDE, JACKET AND PILE SECONDARY STEEL PLATE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 08:49:39 | zm167dc@jutal.com | 11-Sep-2026 19:50:35 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 22:55:07 | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000945 | MM-ASK-1A-GEN01-STR-TBE-1009 | TECHNICAL BID EVALUATION FOR SECONDARY STEEL SEAMLESS PIPES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 19:22:06 | zm167dc@jutal.com | 11-Aug-2026 08:42:38 | Jumpol Sudjitjul | 20-Aug-2026 |  | Washira Kaew-amatawong | 21-Aug-2026 | 20-Aug-2026 15:46:26 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 21-Aug-2026 20:07:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Aug-2026 | 24-Aug-2026 13:14:32 | 24-Aug-2026 06:55:14 | 0 |  |  | Approver | Locate
AO-001145 | MM-ASK-1A-GEN01-STR-TBE-1011 | TECHNICAL BID EVALUATION FOR ANODE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:15:48 | zm167dc@jutal.com | 02-Sep-2026 20:54:18 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 14-Sep-2026 08:48:51 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 14-Sep-2026 23:53:59 | APPR | Approved | Soontaree Simpitak | 16-Sep-2026 | 15-Sep-2026 08:13:49 | 15-Sep-2026 01:30:49 | 0 |  |  | Approver | Locate
AO-000076 | MM-ASK-1A-GEN01-TEL-BOD-0001 | TELECOMMUNICATION BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 08:58:58 | zm167dc@jutal.com | 25-Apr-2026 09:08:10 | Jumpol Sudjitjul | 06-May-2026 | 05-May-2026 14:40:15 | Noppadol Iamtanasinchai | 07-May-2026 | 11-May-2026 17:25:08 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:14:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 08:54:14 | 12-May-2026 09:09:55 | 0 |  |  | Approver | Locate
AO-000243 | MM-ASK-1A-GEN01-TEL-BOD-0001 | TELECOMMUNICATION BASIS OF DESIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval | 26-May-2026 | 15-May-2026 08:55:01 | zm167dc@jutal.com | 18-May-2026 20:44:22 | Jumpol Sudjitjul | 27-May-2026 | 26-May-2026 14:35:11 | Noppadol Iamtanasinchai | 28-May-2026 | 27-May-2026 17:14:59 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 20:58:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 09:05:27 | 11-Jun-2026 10:06:54 | 0 |  |  | Approver | Locate
AO-000486 | MM-ASK-1A-GEN01-TEL-BOD-0001 | TELECOMMUNICATION BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 16-Jun-2026 19:23:45 | zm167dc@jutal.com | 17-Jun-2026 08:34:33 | Jumpol Sudjitjul | 25-Jun-2026 |  | Danai Chaisalee | 26-Jun-2026 | 25-Jun-2026 14:04:33 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 28-Jun-2026 12:59:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 29-Jun-2026 09:16:28 | 29-Jun-2026 02:23:08 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-GEN01-TEL-LIS-0001 | TELECOMMUNICTION EQUIPMENT AND EX-CERTIFICATES LIST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 16:49:56 | zm167dc@jutal.com | 10-Jul-2026 17:51:56 | Jumpol Sudjitjul | 21-Jul-2026 | 17-Jul-2026 09:03:12 | Danai Chaisalee | 22-Jul-2026 | 17-Jul-2026 09:53:09 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:28:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 09:43:27 | 20-Jul-2026 04:09:51 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-GEN01-TEL-LIS-0001 | TELECOMMUNICTION EQUIPMENT AND EX-CERTIFICATES LIST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:35:22 | zm167dc@jutal.com | 14-Aug-2026 08:43:46 | Jumpol Sudjitjul | 24-Aug-2026 | 19-Aug-2026 14:37:27 | Danai Chaisalee | 25-Aug-2026 | 25-Aug-2026 07:27:13 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 15:00:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 27-Aug-2026 15:42:02 | 27-Aug-2026 10:40:31 | 0 |  |  | Approver | Locate
AO-001182 | MM-ASK-1A-GEN01-TEL-LIS-0001 | TELECOMMUNICTION EQUIPMENT AND EX-CERTIFICATES LIST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 18:05:43 | zm167dc@jutal.com | 04-Sep-2026 11:25:15 | Jumpol Sudjitjul | 14-Sep-2026 |  | Danai Chaisalee | 15-Sep-2026 | 14-Sep-2026 14:27:32 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 19-Sep-2026 00:05:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 20-Sep-2026 15:50:30 | 20-Sep-2026 09:44:47 | 0 |  |  | Approver | Locate
AO-000038 | MM-ASK-1A-GEN01-TEL-MOM-0001 | TELECOM. WEEKLY MEETING NO.1 |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 10-Apr-2026 16:32:59 | angkana.k@mermaid-group.com | [16 empty] | 0 |  |  |  | Locate
AO-000039 | MM-ASK-1A-GEN01-TEL-MOM-0002 | TELECOM. WEEKLY MEETING NO.2 |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 10-Apr-2026 16:33:27 | angkana.k@mermaid-group.com | [16 empty] | 0 |  |  |  | Locate
AO-000191 | MM-ASK-1A-GEN01-TEL-MOM-0003 | TELECOM. WEEKLY MEETING NO.3 3-APR-26 (14.30-15.30 BANGKOK TIME) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 10-May-2026 23:35:11 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000276 | MM-ASK-1A-GEN01-TEL-MOM-0005 | TELECOM. WEEKLY MEETING NO.5 (8-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-May-2026 18:49:33 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000303 | MM-ASK-1A-GEN01-TEL-MOM-0006 | TELECOM. WEEKLY MEETING NO.6 (15-MAR-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-May-2026 12:09:45 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000484 | MM-ASK-1A-GEN01-TEL-MOM-0007 | TELECOM. WEEKLY MEETING NO.7 (25-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Jun-2026 21:24:22 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000485 | MM-ASK-1A-GEN01-TEL-MOM-0008 | TELECOM. WEEKLY MEETING NO.8 (29-MAY-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Jun-2026 21:24:49 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000496 | MM-ASK-1A-GEN01-TEL-MOM-0009 | TELECOM. WEEKLY MEETING NO.9 (05-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 17-Jun-2026 14:18:05 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000592 | MM-ASK-1A-GEN01-TEL-MOM-0011 | TELECOM. WEEKLY MEETING NO.11 (19-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 02-Jul-2026 11:16:42 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000699 | MM-ASK-1A-GEN01-TEL-MOM-0012 | TELECOM. WEEKLY MEETING NO.12 (25-JUN-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 12:42:13 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000697 | MM-ASK-1A-GEN01-TEL-MOM-0013 | TELECOM. WEEKLY MEETING NO.13 (03-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 11:33:37 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001048 | MM-ASK-1A-GEN01-TEL-MOM-0014 | TELECOM. WEEKLY MEETING NO.14 (10-JUL-2026) |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 09:33:59 | zm167dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000437 | MM-ASK-1A-GEN01-TEL-MR-0001 | MATERIAL REQUISITION FOR TELECOMMUNICATION SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 17:05:38 | zm167dc@jutal.com | 10-Jun-2026 13:57:05 | Jumpol Sudjitjul | 18-Jun-2026 | 12-Jun-2026 15:48:05 | Noppadol Iamtanasinchai | 19-Jun-2026 | 15-Jun-2026 15:44:08 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 15-Jun-2026 22:30:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 16-Jun-2026 09:42:43 | 16-Jun-2026 03:22:57 | 0 |  |  | Approver | Locate
AO-000662 | MM-ASK-1A-GEN01-TEL-MR-0001 | MATERIAL REQUISITION FOR TELECOMMUNICATION SYSTEM |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 09-Jul-2026 12:13:54 | zm167dc@jutal.com | 09-Jul-2026 13:03:31 | Jumpol Sudjitjul | 17-Jul-2026 | 16-Jul-2026 16:05:14 | Danai Chaisalee | 20-Jul-2026 | 17-Jul-2026 09:49:05 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 19-Jul-2026 17:02:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 20-Jul-2026 09:43:52 | 20-Jul-2026 04:28:07 | 0 |  |  | Approver | Locate
AO-000918 | MM-ASK-1A-GEN01-TEL-MR-0001 | MATERIAL REQUISITION FOR TELECOMMUNICATION SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 15:35:48 | zm167dc@jutal.com | 07-Aug-2026 17:06:38 | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 10:50:54 | Danai Chaisalee | 20-Aug-2026 | 18-Aug-2026 14:24:34 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:33:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 11:14:27 | 24-Aug-2026 04:46:05 | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-GEN01-TEL-MR-0002 | MATERIAL REQUISITION FOR MARINE RACON (RACON) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 17:06:13 | zm167dc@jutal.com | 10-Jun-2026 13:57:31 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 08:29:39 | Noppadol Iamtanasinchai | 19-Jun-2026 | 15-Jun-2026 15:45:17 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 15-Jun-2026 22:32:31 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 16-Jun-2026 09:42:22 | 16-Jun-2026 10:20:56 | 0 |  |  | Approver | Locate
AO-000491 | MM-ASK-1A-GEN01-TEL-MR-0002 | MATERIAL REQUISITION FOR MARINE RACON (RACON) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 17-Jun-2026 12:47:57 | zm167dc@jutal.com | 17-Jun-2026 15:59:14 | Jumpol Sudjitjul | 25-Jun-2026 | 20-Jun-2026 20:18:13 | Danai Chaisalee | 26-Jun-2026 | 25-Jun-2026 14:29:22 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 28-Jun-2026 08:40:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 28-Jun-2026 08:42:24 | 28-Jun-2026 02:20:58 | 0 |  |  | Approver | Locate
AO-000662 | MM-ASK-1A-GEN01-TEL-MR-0002 | MATERIAL REQUISITION FOR MARINE RACON (RACON) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 09-Jul-2026 12:14:19 | zm167dc@jutal.com | 09-Jul-2026 13:04:01 | Jumpol Sudjitjul | 17-Jul-2026 | 14-Jul-2026 11:02:59 | Danai Chaisalee | 20-Jul-2026 | 17-Jul-2026 09:49:35 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 19-Jul-2026 17:03:54 | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 20-Jul-2026 09:44:17 | 20-Jul-2026 04:29:19 | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-GEN01-TEL-MR-0003 | MATERIAL REQUISITION FOR TELECOMMUNICATION BULK MATERIAL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 17:06:48 | zm167dc@jutal.com | 10-Jun-2026 13:57:53 | Jumpol Sudjitjul | 18-Jun-2026 | 11-Jun-2026 15:26:44 | Noppadol Iamtanasinchai | 19-Jun-2026 | 15-Jun-2026 15:46:40 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 15-Jun-2026 22:34:21 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 16-Jun-2026 09:41:53 | 16-Jun-2026 10:18:54 | 0 |  |  | Approver | Locate
AO-000492 | MM-ASK-1A-GEN01-TEL-MR-0003 | MATERIAL REQUISITION FOR TELECOMMUNICATION BULK MATERIAL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 17-Jun-2026 12:48:23 | zm167dc@jutal.com | 17-Jun-2026 16:00:38 | Jumpol Sudjitjul | 25-Jun-2026 | 20-Jun-2026 20:17:40 | Danai Chaisalee | 26-Jun-2026 | 26-Jun-2026 08:54:23 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 28-Jun-2026 08:41:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 28-Jun-2026 08:43:16 | 28-Jun-2026 02:22:13 | 0 |  |  | Approver | Locate
AO-000663 | MM-ASK-1A-GEN01-TEL-MR-0003 | MATERIAL REQUISITION FOR TELECOMMUNICATION BULK MATERIAL |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 09-Jul-2026 12:49:09 | zm167dc@jutal.com | 09-Jul-2026 13:04:17 | Jumpol Sudjitjul | 17-Jul-2026 | 14-Jul-2026 11:03:27 | Danai Chaisalee | 20-Jul-2026 | 17-Jul-2026 09:50:23 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 19-Jul-2026 17:04:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 20-Jul-2026 09:32:39 | 20-Jul-2026 04:20:29 | 0 |  |  | Approver | Locate
AO-000119 | MM-ASK-1A-GEN01-TEL-PHI-0001 | WHP TELECOMMUNIACTION SYSTEM PHILOSOPHY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 01-May-2026 10:27:43 | zm167dc@jutal.com | 01-May-2026 10:55:28 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 16:37:14 | Noppadol Iamtanasinchai | 13-May-2026 | 18-May-2026 14:16:55 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 21:14:40 | APPR | Approved | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 09:12:57 | 20-May-2026 09:42:15 | 0 |  |  | Approver | Locate
AO-000338 | MM-ASK-1A-GEN01-TEL-PHI-0001 | WHP TELECOMMUNIACTION SYSTEM PHILOSOPHY |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | PHI | Philosophy | 0 | Submitted | IFA | Issued for Approval | 05-Jun-2026 | 25-May-2026 15:28:27 | zm167dc@jutal.com | 25-May-2026 22:07:25 | Jumpol Sudjitjul | 05-Jun-2026 | 08-Jun-2026 17:07:48 | Noppadol Iamtanasinchai | 08-Jun-2026 | 10-Jun-2026 14:07:04 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 10-Jun-2026 21:25:42 | APPR | Approved | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 09:06:07 | 11-Jun-2026 10:09:03 | 0 |  |  | Approver | Locate
AO-000487 | MM-ASK-1A-GEN01-TEL-PHI-0001 | WHP TELECOMMUNIACTION SYSTEM PHILOSOPHY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | PHI | Philosophy | 0 | Submitted | AFC | Approved for Construction |  | 16-Jun-2026 19:24:12 | zm167dc@jutal.com | 17-Jun-2026 08:36:11 | Jumpol Sudjitjul | 25-Jun-2026 |  | Danai Chaisalee | 26-Jun-2026 | 25-Jun-2026 14:05:50 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 28-Jun-2026 13:08:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 29-Jun-2026 09:17:47 | 29-Jun-2026 02:24:32 | 0 |  |  | Approver | Locate
AO-000117 | MM-ASK-1A-GEN01-TEL-SPE-0001 | PROJECT SPECIFICATION FOR TELECOMMUNICATION PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 01-May-2026 10:28:09 | zm167dc@jutal.com | 01-May-2026 10:54:14 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 14:59:23 | Noppadol Iamtanasinchai | 13-May-2026 | 18-May-2026 14:13:15 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 20:50:06 | APPR | Approved | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:54:37 | 20-May-2026 10:42:00 | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-GEN01-TEL-SPE-0001 | PROJECT SPECIFICATION FOR TELECOMMUNICATION PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 25-May-2026 15:28:57 | zm167dc@jutal.com | 10-Jun-2026 14:00:05 | Jumpol Sudjitjul | 18-Jun-2026 | 16-Jun-2026 15:55:49 | Noppadol Iamtanasinchai | 19-Jun-2026 | 17-Jun-2026 08:52:55 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 07:52:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 09:59:37 | 22-Jun-2026 03:31:50 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-GEN01-TEL-SPE-0001 | PROJECT SPECIFICATION FOR TELECOMMUNICATION PACKAGE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 14:49:08 | zm167dc@jutal.com | 26-Jul-2026 22:57:16 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:41:50 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:50:47 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 17:26:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 09-Aug-2026 18:17:02 | 09-Aug-2026 11:34:24 | 0 |  |  | Approver | Locate
AO-000118 | MM-ASK-1A-GEN01-TEL-SPE-0002 | PROJECT SPECIFICATION FOR MARINE RACON |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 01-May-2026 10:28:32 | zm167dc@jutal.com | 01-May-2026 10:54:26 | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 15:10:23 | Noppadol Iamtanasinchai | 13-May-2026 | 18-May-2026 14:15:40 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 21:04:22 | APPR | Approved | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:12:24 | 20-May-2026 10:42:59 | 0 |  |  | Approver | Locate
AO-000340 | MM-ASK-1A-GEN01-TEL-SPE-0002 | PROJECT SPECIFICATION FOR MARINE RACON |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 25-May-2026 14:46:19 | zm167dc@jutal.com | 25-May-2026 22:04:39 | Jumpol Sudjitjul | 05-Jun-2026 | 08-Jun-2026 17:03:52 | Noppadol Iamtanasinchai | 08-Jun-2026 | 10-Jun-2026 14:01:16 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 10-Jun-2026 21:25:26 | APPR | Approved | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 09:07:32 | 11-Jun-2026 02:48:54 | 0 |  |  | Approver | Locate
AO-000526 | MM-ASK-1A-GEN01-TEL-STU-0001 | VSAT LOCATION OPTIONS AND SELECTION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | IFR | Issued for Review |  | 22-Jun-2026 15:59:12 | zm167dc@jutal.com | 22-Jun-2026 16:43:09 | Jumpol Sudjitjul | 30-Jun-2026 | 29-Jun-2026 15:11:16 | Danai Chaisalee | 01-Jul-2026 | 01-Jul-2026 07:08:18 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:37:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 15:59:05 | 03-Jul-2026 09:44:45 | 0 |  |  | Approver | Locate
AO-000780 | MM-ASK-1A-GEN01-TEL-STU-0001 | VSAT LOCATION OPTIONS AND SELECTION REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 17:04:34 | zm167dc@jutal.com | 26-Jul-2026 22:56:00 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:39:42 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:43:29 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 08-Aug-2026 07:40:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:07:49 | 08-Aug-2026 03:24:12 | 0 |  |  | Approver | Locate
AO-001017 | MM-ASK-1A-GEN01-TEL-STU-0001 | VSAT LOCATION OPTIONS AND SELECTION REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 14:30:56 | zm167dc@jutal.com | 19-Aug-2026 15:21:06 | Jumpol Sudjitjul | 27-Aug-2026 |  | Danai Chaisalee | 28-Aug-2026 | 28-Aug-2026 08:00:21 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 29-Aug-2026 23:26:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 15:41:41 | 30-Aug-2026 09:00:02 | 0 |  |  | Approver | Locate
AO-000476 | MM-ASK-1A-GEN01-TEL-STU-0002 | DESIGN REPORT FOR COMMUNICATION LINKS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:04:51 | zm167dc@jutal.com | 13-Jun-2026 08:13:50 | Jumpol Sudjitjul | 22-Jun-2026 | 17-Jun-2026 10:11:56 | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 11:47:21 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:29:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:36:51 | 25-Jun-2026 01:54:46 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-GEN01-TEL-STU-0002 | DESIGN REPORT FOR COMMUNICATION LINKS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:49:41 | zm167dc@jutal.com | 26-Jul-2026 22:56:18 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:40:01 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:45:05 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 08-Aug-2026 09:02:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:11:15 | 08-Aug-2026 03:25:33 | 0 |  |  | Approver | Locate
AO-001018 | MM-ASK-1A-GEN01-TEL-STU-0002 | DESIGN REPORT FOR COMMUNICATION LINKS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:43:29 | zm167dc@jutal.com | 19-Aug-2026 15:21:37 | Jumpol Sudjitjul | 27-Aug-2026 |  | Danai Chaisalee | 28-Aug-2026 | 28-Aug-2026 08:01:24 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 29-Aug-2026 23:29:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 15:30:26 | 30-Aug-2026 09:02:31 | 0 |  |  | Approver | Locate
AO-000527 | MM-ASK-1A-GEN01-TEL-STU-0003 | DESIGN REPORT FOR OVERALL TRANSMISSION MEDIA REQUIREMENTS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | IFR | Issued for Review |  | 22-Jun-2026 15:59:45 | zm167dc@jutal.com | 22-Jun-2026 17:34:51 | Jumpol Sudjitjul | 01-Jul-2026 | 29-Jun-2026 16:28:23 | Danai Chaisalee | 02-Jul-2026 | 01-Jul-2026 07:10:58 | Pornlert Wanaphattharaphan | 03-Jul-2026 | 03-Jul-2026 00:48:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Jul-2026 | 03-Jul-2026 16:00:09 | 03-Jul-2026 09:47:37 | 0 |  |  | Approver | Locate
AO-000761 | MM-ASK-1A-GEN01-TEL-STU-0003 | DESIGN REPORT FOR OVERALL TRANSMISSION MEDIA REQUIREMENTS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 11:00:19 | zm167dc@jutal.com | 23-Jul-2026 16:14:07 | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 16:55:51 | Danai Chaisalee | 05-Aug-2026 | 04-Aug-2026 14:48:31 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 05-Aug-2026 23:32:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 06-Aug-2026 08:41:08 | 06-Aug-2026 02:48:35 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-GEN01-TEL-STU-0003 | DESIGN REPORT FOR OVERALL TRANSMISSION MEDIA REQUIREMENTS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 17:35:52 | zm167dc@jutal.com | 14-Aug-2026 08:46:35 | Jumpol Sudjitjul | 24-Aug-2026 | 19-Aug-2026 14:41:16 | Danai Chaisalee | 25-Aug-2026 | 25-Aug-2026 07:29:40 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:48:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 09:27:31 | 28-Aug-2026 02:44:14 | 0 |  |  | Approver | Locate
AO-000528 | MM-ASK-1A-GEN01-TEL-STU-0004 | DESIGN REPORT FOR TELECOMMUNICATION EQUIPMENT ON WHP'S SAFETY ZONE WITH FIRE AND EXPLOSION RISK ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | IFR | Issued for Review |  | 22-Jun-2026 16:00:28 | zm167dc@jutal.com | 22-Jun-2026 17:35:24 | Jumpol Sudjitjul | 01-Jul-2026 | 30-Jun-2026 15:42:47 | Danai Chaisalee | 02-Jul-2026 | 01-Jul-2026 07:13:20 | Pornlert Wanaphattharaphan | 03-Jul-2026 | 03-Jul-2026 00:49:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Jul-2026 | 03-Jul-2026 16:02:02 | 03-Jul-2026 09:48:55 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-GEN01-TEL-STU-0004 | DESIGN REPORT FOR TELECOMMUNICATION EQUIPMENT ON WHP'S SAFETY ZONE WITH FIRE AND EXPLOSION RISK ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:50:15 | zm167dc@jutal.com | 26-Jul-2026 22:56:34 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:40:20 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:45:57 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 17:25:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 09-Aug-2026 18:17:25 | 09-Aug-2026 11:35:53 | 0 |  |  | Approver | Locate
AO-000999 | MM-ASK-1A-GEN01-TEL-STU-0004 | DESIGN REPORT FOR TELECOMMUNICATION EQUIPMENT ON WHP'S SAFETY ZONE WITH FIRE AND EXPLOSION RISK ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | STU | Study Report | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 18:10:58 | zm167dc@jutal.com | 15-Aug-2026 14:58:48 | Jumpol Sudjitjul | 24-Aug-2026 | 21-Aug-2026 17:17:36 | Danai Chaisalee | 25-Aug-2026 | 25-Aug-2026 07:28:26 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:48:01 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 09:28:14 | 28-Aug-2026 02:54:32 | 0 |  |  | Approver | Locate
AO-001346 | MM-ASK-1A-GEN01-TEL-TBE-0001 | TECHNICAL BID EVALUATION FOR TELECOMMUNICATION SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | TBE | Technical Bid Evaluation | 0 | In Review | IFA | Issued for Approval |  | 14-Sep-2026 09:22:28 | zm167dc@jutal.com | 15-Sep-2026 13:50:34 | Jumpol Sudjitjul | 23-Sep-2026 |  | Danai Chaisalee | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001146 | MM-ASK-1A-GEN01-TEL-TBE-0002 | TECHNICAL BID EVALUATION FOR MARINE RACON (RACON) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:20:19 | zm167dc@jutal.com | 02-Sep-2026 20:59:40 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 04-Sep-2026 10:59:38 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 04-Sep-2026 23:46:12 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Sep-2026 | 05-Sep-2026 17:57:34 | 05-Sep-2026 11:24:44 | 0 |  |  | Approver | Locate
AO-000509 | MM-ASK-1A-GEN-PRC-UPO-0001 | UNPRICED PO FOR PRIMARY STEEL PLATES - TOPSIDES |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 19-Jun-2026 10:30:59 | zm167dc@jutal.com | 19-Jun-2026 13:36:31 | Jumpol Sudjitjul | 29-Jun-2026 | 22-Jun-2026 08:20:42 | Jirayu Pantito | 30-Jun-2026 | 27-Jun-2026 21:57:21 | Apisit Tangwashirakul | 01-Jul-2026 | 27-Jun-2026 22:29:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 28-Jun-2026 08:35:19 | 28-Jun-2026 01:37:30 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP01-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:17:08 | zm167dc@jutal.com | 03-Jul-2026 18:35:11 | Jumpol Sudjitjul | 14-Jul-2026 |  | Danai Chaisalee | 15-Jul-2026 | 14-Jul-2026 10:25:15 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 19-Jul-2026 15:41:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 20-Jul-2026 09:43:44 | 20-Jul-2026 03:55:30 | 0 |  |  | Approver | Locate
AO-000893 | MM-ASK-1A-WP01-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 08:53:16 | zm167dc@jutal.com | 06-Aug-2026 10:08:54 | Jumpol Sudjitjul | 17-Aug-2026 | 06-Aug-2026 10:53:25 | Danai Chaisalee | 18-Aug-2026 | 13-Aug-2026 08:11:39 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 17-Aug-2026 00:08:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 08:39:23 | 17-Aug-2026 02:41:19 | 0 |  |  | Approver | Locate
AO-001158 | MM-ASK-1A-WP01-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:24:40 | zm167dc@jutal.com | 02-Sep-2026 21:02:41 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:35:21 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 16:07:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 17-Sep-2026 16:12:30 | 17-Sep-2026 10:01:01 | 0 |  |  | Approver | Locate
AO-000114 | MM-ASK-1A-WP01-ELE-CAL-0001 | ELECTRICAL EQUIPMENT SIZING CALCULATIONS - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 01-May-2026 10:29:51 | zm167dc@jutal.com | 01-May-2026 10:58:19 | Jumpol Sudjitjul | 12-May-2026 | 18-May-2026 18:05:18 | Noppadol Iamtanasinchai | 13-May-2026 | 19-May-2026 13:18:12 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 21:27:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:53:05 | 20-May-2026 09:31:52 | 0 |  |  | Approver | Locate
AO-000476 | MM-ASK-1A-WP01-ELE-CAL-0001 | ELECTRICAL EQUIPMENT SIZING CALCULATIONS - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:09:38 | zm167dc@jutal.com | 13-Jun-2026 08:20:45 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 12:30:56 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:32:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:38:27 | 25-Jun-2026 01:56:05 | 0 |  |  | Approver | Locate
AO-000742 | MM-ASK-1A-WP01-ELE-CAL-0001 | ELECTRICAL EQUIPMENT SIZING CALCULATIONS - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 15:00:46 | zm167dc@jutal.com | 20-Jul-2026 15:47:53 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:34:25 | Danai Chaisalee | 31-Jul-2026 | 24-Jul-2026 09:26:35 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 27-Jul-2026 00:47:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:14:11 | 27-Jul-2026 02:28:30 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WP01-ELE-CAL-0002 | ELECTRICAL CABLE SIZING CALCULATIONS - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 11:58:21 | zm167dc@jutal.com | 12-Jun-2026 12:46:04 | Jumpol Sudjitjul | 22-Jun-2026 | 23-Jun-2026 08:52:56 | Noppadol Iamtanasinchai | 23-Jun-2026 | 23-Jun-2026 11:05:29 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:08:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:39:18 | 25-Jun-2026 01:57:16 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-WP01-ELE-CAL-0002 | ELECTRICAL CABLE SIZING CALCULATIONS - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 21:14:34 | zm167dc@jutal.com | 17-Jul-2026 21:59:55 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 21-Jul-2026 16:00:12 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 12:33:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:57:48 | 27-Jul-2026 03:25:23 | 0 |  |  | Approver | Locate
AO-000900 | MM-ASK-1A-WP01-ELE-CAL-0002 | ELECTRICAL CABLE SIZING CALCULATIONS - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:55:08 | zm167dc@jutal.com | 07-Aug-2026 11:07:26 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:17:06 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:46:31 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:40:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:51:29 | 21-Aug-2026 02:27:04 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-WP01-ELE-CAL-0003 | ELECTRICAL CABLE TRAY / CABLE LADDER SIZING - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 16:51:15 | zm167dc@jutal.com | 10-Jul-2026 17:49:07 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:25:57 | Danai Chaisalee | 22-Jul-2026 | 20-Jul-2026 15:21:56 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 03:01:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 10:01:25 | 27-Jul-2026 03:34:41 | 0 |  |  | Approver | Locate
AO-001245 | MM-ASK-1A-WP01-ELE-CAL-0003 | ELECTRICAL CABLE TRAY / CABLE LADDER SIZING - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 08-Sep-2026 14:11:36 | zm167dc@jutal.com | 08-Sep-2026 14:15:19 | Jumpol Sudjitjul | 16-Sep-2026 |  | Danai Chaisalee | 17-Sep-2026 | 14-Sep-2026 14:21:55 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 16:13:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 17-Sep-2026 16:21:32 | 17-Sep-2026 10:13:00 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-WP01-ELE-CAL-0004 | ILLUMINATION CALCULATIONS - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 16:51:40 | zm167dc@jutal.com | 10-Jul-2026 17:49:25 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:26:18 | Danai Chaisalee | 22-Jul-2026 | 20-Jul-2026 16:07:34 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 03:12:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 10:08:25 | 27-Jul-2026 03:37:03 | 0 |  |  | Approver | Locate
AO-000928 | MM-ASK-1A-WP01-ELE-CAL-0004 | ILLUMINATION CALCULATIONS - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 17:26:02 | zm167dc@jutal.com | 07-Aug-2026 17:32:25 | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 10:53:54 | Danai Chaisalee | 20-Aug-2026 | 19-Aug-2026 14:37:55 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:46:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 10:59:45 | 24-Aug-2026 04:33:10 | 0 |  |  | Approver | Locate
AO-001118 | MM-ASK-1A-WP01-ELE-CAL-0004 | ILLUMINATION CALCULATIONS - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 11:35:02 | zm167dc@jutal.com | 28-Aug-2026 14:33:07 | Jumpol Sudjitjul | 07-Sep-2026 |  | Danai Chaisalee | 08-Sep-2026 | 08-Sep-2026 13:12:53 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 10-Sep-2026 22:57:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 12:28:48 | 11-Sep-2026 06:11:41 | 0 |  |  | Approver | Locate
AO-000070 | MM-ASK-1A-WP01-ELE-DTS-0001 | DATA SHEET FOR AC AND DC DISTRIBTUTION BOARDS/PANELS – WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:00:52 | zm167dc@jutal.com | 25-Apr-2026 09:12:21 | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 15:39:37 | Noppadol Iamtanasinchai | 07-May-2026 | 14-May-2026 09:03:59 | Pornlert Wanaphattharaphan | 08-May-2026 | 14-May-2026 22:50:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 15-May-2026 09:19:44 | 15-May-2026 09:41:30 | 0 |  |  | Approver | Locate
AO-000373 | MM-ASK-1A-WP01-ELE-DTS-0001 | DATA SHEET FOR AC AND DC DISTRIBTUTION BOARDS/PANELS – WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 21:00:47 | zm167dc@jutal.com | 29-May-2026 09:58:58 | Jumpol Sudjitjul | 10-Jun-2026 | 09-Jun-2026 10:46:59 | Noppadol Iamtanasinchai | 11-Jun-2026 | 10-Jun-2026 14:37:26 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:31:43 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:08:19 | 11-Jun-2026 02:50:00 | 0 |  |  | Approver | Locate
AO-000710 | MM-ASK-1A-WP01-ELE-DTS-0001 | DATA SHEET FOR AC AND DC DISTRIBTUTION BOARDS/PANELS – WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 16:57:44 | zm167dc@jutal.com | 16-Jul-2026 20:44:47 | Jumpol Sudjitjul | 27-Jul-2026 |  | Danai Chaisalee | 30-Jul-2026 | 22-Jul-2026 15:14:50 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:11:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:00:00 | 27-Jul-2026 03:33:30 | 0 |  |  | Approver | Locate
AO-001035 | MM-ASK-1A-WP01-ELE-DTS-0001 | DATA SHEET FOR AC AND DC DISTRIBTUTION BOARDS/PANELS – WP01 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 14:17:52 | zm167dc@jutal.com | 20-Aug-2026 14:35:34 | Jumpol Sudjitjul | 28-Aug-2026 |  | Danai Chaisalee | 31-Aug-2026 | 31-Aug-2026 09:35:26 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 02-Sep-2026 23:21:09 | AWC | Approved with Comment | Soontaree Simpitak | 02-Sep-2026 | 03-Sep-2026 07:44:06 | 03-Sep-2026 00:56:42 | 0 |  |  | Approver | Locate
AO-000071 | MM-ASK-1A-WP01-ELE-DTS-0002 | DATA SHEET FOR SOLAR POWER SYSTEM – WPA01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:01:14 | zm167dc@jutal.com | 25-Apr-2026 09:12:32 | Jumpol Sudjitjul | 06-May-2026 | 07-May-2026 16:39:33 | Noppadol Iamtanasinchai | 07-May-2026 | 14-May-2026 09:06:47 | Pornlert Wanaphattharaphan | 08-May-2026 | 14-May-2026 22:51:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 15-May-2026 08:38:08 | 15-May-2026 09:17:22 | 0 |  |  | Approver | Locate
AO-000380 | MM-ASK-1A-WP01-ELE-DTS-0002 | DATA SHEET FOR SOLAR POWER SYSTEM – WPA01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 14:05:41 | zm167dc@jutal.com | 29-May-2026 15:10:14 | Jumpol Sudjitjul | 10-Jun-2026 | 09-Jun-2026 16:25:25 | Noppadol Iamtanasinchai | 11-Jun-2026 | 10-Jun-2026 15:04:20 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:32:45 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:09:13 | 11-Jun-2026 02:51:02 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-WP01-ELE-DTS-0002 | DATA SHEET FOR SOLAR POWER SYSTEM – WPA01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:46:17 | zm167dc@jutal.com | 27-Jun-2026 19:46:31 | Jumpol Sudjitjul | 07-Jul-2026 |  | Danai Chaisalee | 08-Jul-2026 | 02-Jul-2026 11:10:52 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:27:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 08:16:01 | 10-Jul-2026 01:51:31 | 0 |  |  | Approver | Locate
AO-001035 | MM-ASK-1A-WP01-ELE-DTS-0002 | DATA SHEET FOR SOLAR POWER SYSTEM – WPA01 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 14:18:33 | zm167dc@jutal.com | 20-Aug-2026 14:36:00 | Jumpol Sudjitjul | 28-Aug-2026 |  | Danai Chaisalee | 31-Aug-2026 | 31-Aug-2026 09:36:12 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 02-Sep-2026 23:29:56 | AWC | Approved with Comment | Soontaree Simpitak | 02-Sep-2026 | 03-Sep-2026 07:44:58 | 03-Sep-2026 00:58:01 | 0 |  |  | Approver | Locate
AO-000176 | MM-ASK-1A-WP01-ELE-DTS-0003 | DATASHEET FOR NAVIGATION AID SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 18:11:05 | zm167dc@jutal.com | 08-May-2026 20:23:54 | Jumpol Sudjitjul | 19-May-2026 | 21-May-2026 14:07:26 | Noppadol Iamtanasinchai | 20-May-2026 | 23-May-2026 10:31:40 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 22:16:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 28-May-2026 09:04:27 | 28-May-2026 09:38:47 | 0 |  |  | Approver | Locate
AO-000418 | MM-ASK-1A-WP01-ELE-DTS-0003 | DATASHEET FOR NAVIGATION AID SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 17:53:28 | zm167dc@jutal.com | 05-Jun-2026 19:47:19 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 10:19:18 | Noppadol Iamtanasinchai | 17-Jun-2026 | 17-Jun-2026 08:27:53 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 18:01:33 | APPR | Approved | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:01:55 | 22-Jun-2026 01:09:33 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-WP01-ELE-DTS-0003 | DATASHEET FOR NAVIGATION AID SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:51:52 | zm167dc@jutal.com | 20-Jul-2026 11:44:02 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 22-Jul-2026 15:19:54 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:22:47 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:30:38 | 27-Jul-2026 02:55:35 | 0 |  |  | Approver | Locate
AO-000074 | MM-ASK-1A-WP01-ELE-DTS-0004 | DATA SHEET FOR EXTERNAL BATTERY CHARGER - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:01:36 | zm167dc@jutal.com | 25-Apr-2026 09:12:43 | Jumpol Sudjitjul | 06-May-2026 | 07-May-2026 16:52:12 | Noppadol Iamtanasinchai | 07-May-2026 | 12-May-2026 10:40:39 | Pornlert Wanaphattharaphan | 08-May-2026 | 13-May-2026 08:14:14 | APPR | Approved | Jumpol Sudjitjul | 11-May-2026 | 13-May-2026 08:44:16 | 13-May-2026 09:19:57 | 0 |  |  | Approver | Locate
AO-000374 | MM-ASK-1A-WP01-ELE-DTS-0004 | DATA SHEET FOR EXTERNAL BATTERY CHARGER - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 21:01:20 | zm167dc@jutal.com | 29-May-2026 09:59:32 | Jumpol Sudjitjul | 10-Jun-2026 | 09-Jun-2026 10:55:08 | Noppadol Iamtanasinchai | 11-Jun-2026 | 10-Jun-2026 15:00:08 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:32:15 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:10:00 | 11-Jun-2026 02:52:03 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-WP01-ELE-DTS-0004 | DATA SHEET FOR EXTERNAL BATTERY CHARGER - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:52:31 | zm167dc@jutal.com | 20-Jul-2026 11:44:22 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 22-Jul-2026 15:21:07 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:27:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:32:36 | 27-Jul-2026 02:56:53 | 0 |  |  | Approver | Locate
AO-001024 | MM-ASK-1A-WP01-ELE-DTS-0004 | DATA SHEET FOR EXTERNAL BATTERY CHARGER - WP01 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 15:55:51 | zm167dc@jutal.com | 19-Aug-2026 16:11:46 | Jumpol Sudjitjul | 27-Aug-2026 |  | Danai Chaisalee | 28-Aug-2026 | 28-Aug-2026 08:01:49 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 29-Aug-2026 23:29:47 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 15:35:41 | 30-Aug-2026 08:58:45 | 0 |  |  | Approver | Locate
AO-000707 | MM-ASK-1A-WP01-ELE-DTS-0005 | DATASHEET FOR ELECTRICAL CABLES - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 15:33:55 | zm167dc@jutal.com | 16-Jul-2026 15:36:52 | Jumpol Sudjitjul | 24-Jul-2026 |  | Danai Chaisalee | 27-Jul-2026 | 22-Jul-2026 15:13:10 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 09:59:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 10:11:57 | 27-Jul-2026 03:32:16 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP01-ELE-DTS-0005 | DATASHEET FOR ELECTRICAL CABLES - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:55:36 | zm167dc@jutal.com | 07-Aug-2026 11:05:57 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:16:33 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:45:16 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:39:50 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:52:07 | 21-Aug-2026 02:28:14 | 0 |  |  | Approver | Locate
AO-001162 | MM-ASK-1A-WP01-ELE-DTS-0006 | DATASHEET FOR ELECTRICAL BULK MATERIALS - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 02-Sep-2026 19:59:46 | zm167dc@jutal.com | 02-Sep-2026 21:06:39 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:43:53 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 16:13:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 17-Sep-2026 16:15:47 | 17-Sep-2026 10:03:54 | 0 |  |  | Approver | Locate
AO-000723 | MM-ASK-1A-WP01-ELE-DTS-0007 | DATASHEET FOR FOG HORN - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 09:52:57 | zm167dc@jutal.com | 20-Jul-2026 11:46:46 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 22-Jul-2026 15:22:40 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:40:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:15:02 | 27-Jul-2026 02:29:48 | 0 |  |  | Approver | Locate
AO-000958 | MM-ASK-1A-WP01-ELE-DTS-0007 | DATASHEET FOR FOG HORN - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Aug-2026 18:27:08 | zm167dc@jutal.com | 13-Aug-2026 13:16:45 | Jumpol Sudjitjul | 21-Aug-2026 |  | Danai Chaisalee | 24-Aug-2026 | 20-Aug-2026 14:20:49 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:10:14 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 13:15:36 | 24-Aug-2026 06:56:31 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-ELE-DWG-0001 | ELECTRICAL DRAWING INDEX - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:51:15 | zm167dc@jutal.com | 26-Jul-2026 23:06:50 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:51:34 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:11:37 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:07:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:07:07 | 10-Aug-2026 05:24:25 | 0 |  |  | Approver | Locate
AO-000565 | MM-ASK-1A-WP01-ELE-DWG-0002 | EQUIPMENT LOCATION PLAN - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:46:52 | zm167dc@jutal.com | 27-Jun-2026 19:49:08 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 15:09:11 | Danai Chaisalee | 08-Jul-2026 | 07-Jul-2026 10:41:37 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:16:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 08:17:20 | 10-Jul-2026 01:52:46 | 0 |  |  | Approver | Locate
AO-000935 | MM-ASK-1A-WP01-ELE-DWG-0002 | EQUIPMENT LOCATION PLAN - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:25:37 | zm167dc@jutal.com | 10-Aug-2026 15:49:45 | Jumpol Sudjitjul | 19-Aug-2026 |  | Danai Chaisalee | 20-Aug-2026 | 20-Aug-2026 09:36:48 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:51:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 13:16:34 | 24-Aug-2026 07:05:56 | 0 |  |  | Approver | Locate
AO-001187 | MM-ASK-1A-WP01-ELE-DWG-0002 | EQUIPMENT LOCATION PLAN - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 08:38:02 | zm167dc@jutal.com | 04-Sep-2026 11:08:20 | Jumpol Sudjitjul | 14-Sep-2026 |  | Danai Chaisalee | 15-Sep-2026 | 15-Sep-2026 13:18:39 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 17-Sep-2026 16:14:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 17-Sep-2026 16:19:12 | 17-Sep-2026 10:08:53 | 0 |  |  | Approver | Locate
AO-000565 | MM-ASK-1A-WP01-ELE-DWG-0003 | EQUIPMENT LOCATION PLAN - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:47:20 | zm167dc@jutal.com | 27-Jun-2026 19:49:09 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 15:10:04 | Danai Chaisalee | 08-Jul-2026 | 07-Jul-2026 10:43:07 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:16:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 08:20:07 | 10-Jul-2026 01:54:05 | 0 |  |  | Approver | Locate
AO-000935 | MM-ASK-1A-WP01-ELE-DWG-0003 | EQUIPMENT LOCATION PLAN - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:26:06 | zm167dc@jutal.com | 10-Aug-2026 15:49:39 | Jumpol Sudjitjul | 19-Aug-2026 |  | Danai Chaisalee | 20-Aug-2026 | 20-Aug-2026 09:40:30 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:53:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 11:19:00 | 24-Aug-2026 04:34:29 | 0 |  |  | Approver | Locate
AO-001188 | MM-ASK-1A-WP01-ELE-DWG-0003 | EQUIPMENT LOCATION PLAN - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 08:38:32 | zm167dc@jutal.com | 04-Sep-2026 11:08:49 | Jumpol Sudjitjul | 14-Sep-2026 |  | Danai Chaisalee | 15-Sep-2026 | 15-Sep-2026 13:20:14 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 17-Sep-2026 16:15:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 17-Sep-2026 16:20:22 | 17-Sep-2026 10:10:25 | 0 |  |  | Approver | Locate
AO-000565 | MM-ASK-1A-WP01-ELE-DWG-0004 | EQUIPMENT LOCATION PLAN - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:47:45 | zm167dc@jutal.com | 27-Jun-2026 19:49:09 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 15:09:37 | Danai Chaisalee | 08-Jul-2026 | 07-Jul-2026 10:40:46 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:15:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 08:21:04 | 10-Jul-2026 01:55:19 | 0 |  |  | Approver | Locate
AO-000935 | MM-ASK-1A-WP01-ELE-DWG-0004 | EQUIPMENT LOCATION PLAN - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:26:38 | zm167dc@jutal.com | 10-Aug-2026 15:49:37 | Jumpol Sudjitjul | 19-Aug-2026 |  | Danai Chaisalee | 20-Aug-2026 | 20-Aug-2026 09:34:14 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:50:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 13:18:03 | 24-Aug-2026 07:08:35 | 0 |  |  | Approver | Locate
AO-001189 | MM-ASK-1A-WP01-ELE-DWG-0004 | EQUIPMENT LOCATION PLAN - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 08:38:57 | zm167dc@jutal.com | 04-Sep-2026 11:09:10 | Jumpol Sudjitjul | 14-Sep-2026 |  | Danai Chaisalee | 15-Sep-2026 | 15-Sep-2026 15:44:58 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 17-Sep-2026 16:22:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 17-Sep-2026 16:25:34 | 17-Sep-2026 10:21:20 | 0 |  |  | Approver | Locate
AO-000603 | MM-ASK-1A-WP01-ELE-DWG-0005-001 | LIGHTING AND SMALL POWER PLAN - WP01 MEZZANINE DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:30:03 | zm167dc@jutal.com | 03-Jul-2026 13:33:35 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:16:23 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:30:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:39:04 | 17-Jul-2026 02:00:07 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-WP01-ELE-DWG-0005-001 | LIGHTING AND SMALL POWER PLAN - WP01 MEZZANINE DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:21:34 | zm167dc@jutal.com | 03-Sep-2026 16:03:04 | Jumpol Sudjitjul | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:36:21 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 16:39:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 08:43:26 | 18-Sep-2026 02:21:10 | 0 |  |  | Approver | Locate
AO-000603 | MM-ASK-1A-WP01-ELE-DWG-0005-002 | LIGHTING AND SMALL POWER PLAN - WP01 LOWER DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:30:53 | zm167dc@jutal.com | 03-Jul-2026 13:33:39 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:32:19 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:50:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:41:44 | 17-Jul-2026 02:01:29 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-WP01-ELE-DWG-0005-002 | LIGHTING AND SMALL POWER PLAN - WP01 LOWER DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:22:01 | zm167dc@jutal.com | 03-Sep-2026 16:03:43 | Jumpol Sudjitjul | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:37:19 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 17:06:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 09:24:35 | 18-Sep-2026 02:47:00 | 0 |  |  | Approver | Locate
AO-000603 | MM-ASK-1A-WP01-ELE-DWG-0005-003 | LIGHTING AND SMALL POWER PLAN - WP01 SUMP DECK AND BOAT LANDING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:31:56 | zm167dc@jutal.com | 03-Jul-2026 13:33:28 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:14:35 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:28:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:42:38 | 17-Jul-2026 02:02:49 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-WP01-ELE-DWG-0005-003 | LIGHTING AND SMALL POWER PLAN - WP01 SUMP DECK AND BOAT LANDING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:22:30 | zm167dc@jutal.com | 03-Sep-2026 16:04:13 | Jumpol Sudjitjul | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:38:20 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 17:09:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 08:42:41 | 18-Sep-2026 01:59:03 | 0 |  |  | Approver | Locate
AO-000606 | MM-ASK-1A-WP01-ELE-DWG-0006-001 | LIGHTING AND SMALL POWER PLAN - WP01 MEZZANINE DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 14:18:06 | zm167dc@jutal.com | 03-Jul-2026 14:38:39 | Jumpol Sudjitjul | 13-Jul-2026 | 03-Jul-2026 14:54:16 | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:36:18 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:56:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:44:11 | 17-Jul-2026 02:04:09 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP01-ELE-DWG-0006-001 | LIGHTING AND SMALL POWER PLAN - WP01 MEZZANINE DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:25:21 | zm167dc@jutal.com | 02-Sep-2026 21:10:35 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:45:07 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 21:56:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 08:38:17 | 18-Sep-2026 01:57:41 | 0 |  |  | Approver | Locate
AO-000606 | MM-ASK-1A-WP01-ELE-DWG-0006-002 | LIGHTING AND SMALL POWER PLAN - WP01 LOWER DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 14:18:59 | zm167dc@jutal.com | 03-Jul-2026 14:38:50 | Jumpol Sudjitjul | 13-Jul-2026 | 03-Jul-2026 14:55:33 | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:38:48 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:05:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:44:42 | 17-Jul-2026 02:05:25 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP01-ELE-DWG-0006-002 | LIGHTING AND SMALL POWER PLAN - WP01 LOWER DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 20:00:20 | zm167dc@jutal.com | 02-Sep-2026 21:14:10 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:46:10 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 21:57:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 08:41:40 | 18-Sep-2026 02:08:24 | 0 |  |  | Approver | Locate
AO-000606 | MM-ASK-1A-WP01-ELE-DWG-0006-003 | LIGHTING AND SMALL POWER PLAN - WP01 SUMP DECK AND BOAT LANDING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 14:19:57 | zm167dc@jutal.com | 03-Jul-2026 14:39:01 | Jumpol Sudjitjul | 13-Jul-2026 | 03-Jul-2026 14:55:10 | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:37:54 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:08:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:45:10 | 17-Jul-2026 02:07:49 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP01-ELE-DWG-0006-003 | LIGHTING AND SMALL POWER PLAN - WP01 SUMP DECK AND BOAT LANDING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 20:00:56 | zm167dc@jutal.com | 02-Sep-2026 21:18:01 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:47:08 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 21:58:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 08:57:34 | 18-Sep-2026 03:11:15 | 0 |  |  | Approver | Locate
AO-000629 | MM-ASK-1A-WP01-ELE-DWG-0007 | ELECTRICAL OVERALL EARTHING AND BONDING DIAGRAMS- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 20:29:47 | zm167dc@jutal.com | 04-Jul-2026 14:08:22 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:58:39 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:42:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 08:21:54 | 10-Jul-2026 01:48:49 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP01-ELE-DWG-0007 | ELECTRICAL OVERALL EARTHING AND BONDING DIAGRAMS- WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:56:07 | zm167dc@jutal.com | 07-Aug-2026 11:03:52 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:15:58 | Danai Chaisalee | 19-Aug-2026 | 13-Aug-2026 08:13:53 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 17-Aug-2026 00:10:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 17-Aug-2026 08:41:23 | 17-Aug-2026 02:44:21 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-WP01-ELE-DWG-0007 | ELECTRICAL OVERALL EARTHING AND BONDING DIAGRAMS- WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:01:28 | zm167dc@jutal.com | 02-Sep-2026 21:20:19 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:48:04 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 21:59:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 08:55:16 | 18-Sep-2026 03:09:52 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP01-ELE-LAY-0001 | SOLAR PANEL LAYOUT - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY |  | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:45:41 | zm167dc@jutal.com | 07-Jun-2026 19:31:45 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 13:14:49 | Noppadol Iamtanasinchai | 17-Jun-2026 | 17-Jun-2026 08:32:21 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 20:01:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:02:32 | 22-Jun-2026 01:13:15 | 0 |  |  | Approver | Locate
AO-000801 | MM-ASK-1A-WP01-ELE-LAY-0001 | SOLAR PANEL LAYOUT - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY |  | 0 | Submitted | IFA | Issued for Approval |  | 26-Jul-2026 22:35:09 | zm167dc@jutal.com | 26-Jul-2026 23:02:28 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:44:35 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:54:52 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 18:25:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 09-Aug-2026 18:27:20 | 09-Aug-2026 12:08:56 | 0 |  |  | Approver | Locate
AO-001469 | MM-ASK-1A-WP01-ELE-LAY-0001 | SOLAR PANEL LAYOUT - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY |  | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 14:56:48 | zm167dc@jutal.com | 18-Sep-2026 17:12:09 | Jumpol Sudjitjul | 29-Sep-2026 |  | Danai Chaisalee | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000573 | MM-ASK-1A-WP01-ELE-LAY-0002-001 | E&I ROOM EQUIPMENT LAYOUT PLAN - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-Jun-2026 22:01:58 | zm167dc@jutal.com | 30-Jun-2026 10:09:56 | Jumpol Sudjitjul | 08-Jul-2026 | 03-Jul-2026 15:15:49 | Danai Chaisalee | 09-Jul-2026 | 07-Jul-2026 10:44:05 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:34:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 08:22:57 | 10-Jul-2026 02:00:28 | 0 |  |  | Approver | Locate
AO-000984 | MM-ASK-1A-WP01-ELE-LAY-0002-001 | E&I ROOM EQUIPMENT LAYOUT PLAN - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 14:47:51 | zm167dc@jutal.com | 14-Aug-2026 15:21:58 | Jumpol Sudjitjul | 24-Aug-2026 |  | Danai Chaisalee | 25-Aug-2026 | 19-Aug-2026 13:12:02 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 23:46:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 13:18:56 | 24-Aug-2026 06:51:04 | 0 |  |  | Approver | Locate
AO-000573 | MM-ASK-1A-WP01-ELE-LAY-0002-002 | E&I ROOM EQUIPMENT LAYOUT PLAN - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-Jun-2026 22:02:30 | zm167dc@jutal.com | 30-Jun-2026 10:10:15 | Jumpol Sudjitjul | 08-Jul-2026 | 03-Jul-2026 15:16:37 | Danai Chaisalee | 09-Jul-2026 | 07-Jul-2026 10:45:07 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:40:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 08:25:18 | 10-Jul-2026 02:01:45 | 0 |  |  | Approver | Locate
AO-000984 | MM-ASK-1A-WP01-ELE-LAY-0002-002 | E&I ROOM EQUIPMENT LAYOUT PLAN - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 14:48:19 | zm167dc@jutal.com | 14-Aug-2026 15:22:24 | Jumpol Sudjitjul | 24-Aug-2026 |  | Danai Chaisalee | 25-Aug-2026 | 19-Aug-2026 13:13:05 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 08:06:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 13:24:18 | 24-Aug-2026 06:52:25 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-ELE-LAY-0003-001 | CABLE TRAYS/LADDERS LAYOUT DRAWINGS - WP01 UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:51:40 | zm167dc@jutal.com | 26-Jul-2026 23:02:27 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:43:51 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:52:55 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 17:29:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 09-Aug-2026 18:17:48 | 09-Aug-2026 11:37:10 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-ELE-LAY-0003-002 | CABLE TRAYS/LADDERS LAYOUT DRAWINGS - WP01 LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:08:18 | zm167dc@jutal.com | 26-Jul-2026 23:02:28 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:43:29 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:52:02 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 17:28:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 09-Aug-2026 18:19:09 | 09-Aug-2026 11:39:45 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-ELE-LAY-0003-003 | CABLE TRAYS/LADDERS LAYOUT DRAWINGS - WP01 SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:52:10 | zm167dc@jutal.com | 26-Jul-2026 23:02:29 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:44:53 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:56:05 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 22:23:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:09:29 | 10-Aug-2026 05:25:49 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-ELE-LAY-0003-004 | CABLE TRAYS/LADDERS LAYOUT DRAWINGS - WP01 E&I ROOM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:52:46 | zm167dc@jutal.com | 26-Jul-2026 23:02:28 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:44:13 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:53:54 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 18:14:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 09-Aug-2026 18:19:41 | 09-Aug-2026 11:38:29 | 0 |  |  | Approver | Locate
AO-000780 | MM-ASK-1A-WP01-ELE-LAY-0004-0001 | CABLES ROUTING PLAN/LAYOUT DRAWINGS - WP01 UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:04:59 | zm167dc@jutal.com | 26-Jul-2026 23:02:36 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:46:09 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:00:26 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 22:51:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:13:23 | 10-Aug-2026 05:27:23 | 0 |  |  | Approver | Locate
AO-000780 | MM-ASK-1A-WP01-ELE-LAY-0004-0002 | CABLES ROUTING PLAN/LAYOUT DRAWINGS - WP01 LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:05:23 | zm167dc@jutal.com | 26-Jul-2026 23:02:30 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:45:14 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:57:03 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 22:32:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:14:58 | 10-Aug-2026 05:29:12 | 0 |  |  | Approver | Locate
AO-000780 | MM-ASK-1A-WP01-ELE-LAY-0004-0003 | CABLES ROUTING PLAN/LAYOUT DRAWINGS - WP01 SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:05:45 | zm167dc@jutal.com | 26-Jul-2026 23:02:32 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:45:32 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:57:58 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 22:35:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:18:29 | 10-Aug-2026 05:31:51 | 0 |  |  | Approver | Locate
AO-000780 | MM-ASK-1A-WP01-ELE-LAY-0004-0004 | CABLES ROUTING PLAN/LAYOUT DRAWINGS - WP01 E&I ROOM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:08:45 | zm167dc@jutal.com | 26-Jul-2026 23:02:35 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:45:48 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:59:12 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 22:44:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:29:30 | 10-Aug-2026 06:16:33 | 0 |  |  | Approver | Locate
AO-000116 | MM-ASK-1A-WP01-ELE-LIS-0001 | ELECTRICAL LOAD LIST & LOAD ANALYSIS – WPA01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 01-May-2026 10:30:15 | zm167dc@jutal.com | 01-May-2026 10:59:13 | Jumpol Sudjitjul | 12-May-2026 | 18-May-2026 18:06:31 | Noppadol Iamtanasinchai | 13-May-2026 | 19-May-2026 13:25:29 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 21:56:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:13:30 | 20-May-2026 09:05:31 | 0 |  |  | Approver | Locate
AO-000452 | MM-ASK-1A-WP01-ELE-LIS-0001 | ELECTRICAL LOAD LIST & LOAD ANALYSIS – WPA01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 17:15:59 | zm167dc@jutal.com | 11-Jun-2026 17:46:07 | Jumpol Sudjitjul |  | 16-Jun-2026 17:00:48 | Noppadol Iamtanasinchai |  | 17-Jun-2026 08:40:10 | Pornlert Wanaphattharaphan |  | 21-Jun-2026 00:03:32 | AWC | Approved with Comment | Jumpol Sudjitjul |  | 22-Jun-2026 10:00:33 | 22-Jun-2026 03:44:45 | 0 |  |  | For Info | Locate
AO-000718 | MM-ASK-1A-WP01-ELE-LIS-0001 | ELECTRICAL LOAD LIST & LOAD ANALYSIS – WPA01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 21:15:03 | zm167dc@jutal.com | 17-Jul-2026 21:58:27 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 22-Jul-2026 15:18:15 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 17:27:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:28:16 | 27-Jul-2026 03:07:16 | 0 |  |  | Approver | Locate
AO-000476 | MM-ASK-1A-WP01-ELE-LIS-0002 | ELECTRICAL CABLE SCHEDULE - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:10:00 | zm167dc@jutal.com | 13-Jun-2026 08:21:31 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 14:39:52 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:40:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:39:58 | 25-Jun-2026 02:53:41 | 0 |  |  | Approver | Locate
AO-000780 | MM-ASK-1A-WP01-ELE-LIS-0002 | ELECTRICAL CABLE SCHEDULE - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 16:09:23 | zm167dc@jutal.com | 26-Jul-2026 23:12:18 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:52:53 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:13:23 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:12:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:23:48 | 10-Aug-2026 06:13:48 | 0 |  |  | Approver | Locate
AO-001068 | MM-ASK-1A-WP01-ELE-LIS-0002 | ELECTRICAL CABLE SCHEDULE - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:41:01 | zm167dc@jutal.com | 24-Aug-2026 18:35:40 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:05:49 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 05-Sep-2026 23:59:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:23:03 | 06-Sep-2026 03:15:02 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP01-ELE-LIS-0003 | ELECTRICAL EQUIPMENT AND EXPLOSION PROOF EQUIPMENT SCHEDULE - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:17:38 | zm167dc@jutal.com | 03-Jul-2026 18:38:57 | Jumpol Sudjitjul | 14-Jul-2026 |  | Danai Chaisalee | 15-Jul-2026 | 09-Jul-2026 16:54:46 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 10-Jul-2026 00:51:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 10-Jul-2026 08:27:00 | 10-Jul-2026 02:25:16 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP01-ELE-LIS-0003 | ELECTRICAL EQUIPMENT AND EXPLOSION PROOF EQUIPMENT SCHEDULE - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:56:38 | zm167dc@jutal.com | 07-Aug-2026 11:02:28 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:14:46 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:41:32 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:48:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:53:01 | 21-Aug-2026 02:29:29 | 0 |  |  | Approver | Locate
AO-001146 | MM-ASK-1A-WP01-ELE-LIS-0003 | ELECTRICAL EQUIPMENT AND EXPLOSION PROOF EQUIPMENT SCHEDULE - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:50:03 | zm167dc@jutal.com | 02-Sep-2026 21:22:17 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:49:21 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 21:59:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 08:44:41 | 18-Sep-2026 02:09:47 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP01-ELE-LIS-0004-001 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:32:48 | zm167dc@jutal.com | 03-Jul-2026 13:36:20 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:42:22 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:44:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 08:14:25 | 10-Jul-2026 02:22:48 | 0 |  |  | Approver | Locate
AO-001304 | MM-ASK-1A-WP01-ELE-LIS-0004-001 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 09:08:01 | zm167dc@jutal.com | 11-Sep-2026 12:42:34 | Jumpol Sudjitjul | 21-Sep-2026 |  | Danai Chaisalee | 22-Sep-2026 | 16-Sep-2026 14:28:17 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 17-Sep-2026 22:01:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 18-Sep-2026 08:57:57 | 18-Sep-2026 02:44:46 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP01-ELE-LIS-0004-002 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:33:31 | zm167dc@jutal.com | 03-Jul-2026 13:36:09 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:43:25 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:44:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 08:27:47 | 10-Jul-2026 02:26:29 | 0 |  |  | Approver | Locate
AO-001304 | MM-ASK-1A-WP01-ELE-LIS-0004-002 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 09:08:42 | zm167dc@jutal.com | 11-Sep-2026 12:43:04 | Jumpol Sudjitjul | 21-Sep-2026 |  | Danai Chaisalee | 22-Sep-2026 | 16-Sep-2026 14:29:13 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 17-Sep-2026 22:05:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 18-Sep-2026 08:55:45 | 18-Sep-2026 02:41:59 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP01-ELE-LIS-0004-003 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:34:17 | zm167dc@jutal.com | 03-Jul-2026 13:36:22 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:47:10 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:48:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 08:24:07 | 10-Jul-2026 02:17:28 | 0 |  |  | Approver | Locate
AO-001304 | MM-ASK-1A-WP01-ELE-LIS-0004-003 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 09:09:22 | zm167dc@jutal.com | 11-Sep-2026 12:43:18 | Jumpol Sudjitjul | 21-Sep-2026 |  | Danai Chaisalee | 22-Sep-2026 | 16-Sep-2026 14:30:20 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 17-Sep-2026 22:10:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 18-Sep-2026 08:50:27 | 18-Sep-2026 02:12:32 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP01-ELE-LIS-0004-004 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:35:08 | zm167dc@jutal.com | 03-Jul-2026 13:36:17 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:44:28 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:45:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 08:15:15 | 10-Jul-2026 02:14:59 | 0 |  |  | Approver | Locate
AO-001304 | MM-ASK-1A-WP01-ELE-LIS-0004-004 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 09:09:53 | zm167dc@jutal.com | 11-Sep-2026 12:43:32 | Jumpol Sudjitjul | 21-Sep-2026 |  | Danai Chaisalee | 22-Sep-2026 | 16-Sep-2026 14:31:18 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 17-Sep-2026 22:41:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 18-Sep-2026 08:56:59 | 18-Sep-2026 02:43:27 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP01-ELE-LIS-0004-005 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:35:54 | zm167dc@jutal.com | 03-Jul-2026 13:36:15 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:45:23 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:45:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 08:13:42 | 10-Jul-2026 02:11:17 | 0 |  |  | Approver | Locate
AO-001312 | MM-ASK-1A-WP01-ELE-LIS-0004-005 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | In Review | VOID | Withdrawn or Superseded |  | 11-Sep-2026 19:40:26 | zm167dc@jutal.com | 11-Sep-2026 19:59:29 | Jumpol Sudjitjul |  |  | Danai Chaisalee |  |  | Pornlert Wanaphattharaphan | [8 empty] | 0 |  |  | For Info | Locate
AO-000599 | MM-ASK-1A-WP01-ELE-LIS-0004-006 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:36:32 | zm167dc@jutal.com | 03-Jul-2026 13:36:22 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:46:17 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:47:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 08:20:04 | 10-Jul-2026 02:16:12 | 0 |  |  | Approver | Locate
AO-001313 | MM-ASK-1A-WP01-ELE-LIS-0004-006 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE- WP01 |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | In Review | VOID | Withdrawn or Superseded |  | 11-Sep-2026 19:40:53 | zm167dc@jutal.com | 11-Sep-2026 19:59:41 | Jumpol Sudjitjul |  |  | Danai Chaisalee |  |  | Pornlert Wanaphattharaphan | [8 empty] | 0 |  |  | For Info | Locate
AO-000616 | MM-ASK-1A-WP01-ELE-LIS-0005-001 | ELECTRICAL DISTRIBUTION BOARD SCHEDULE - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:18:13 | zm167dc@jutal.com | 03-Jul-2026 18:39:11 | Jumpol Sudjitjul | 14-Jul-2026 |  | Danai Chaisalee | 15-Jul-2026 | 09-Jul-2026 16:55:39 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 10-Jul-2026 00:51:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 10-Jul-2026 08:19:14 | 10-Jul-2026 02:23:58 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP01-ELE-LIS-0005-001 | ELECTRICAL DISTRIBUTION BOARD SCHEDULE - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:57:10 | zm167dc@jutal.com | 07-Aug-2026 11:02:27 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:13:54 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:38:03 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:46:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:53:41 | 21-Aug-2026 02:30:50 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP01-ELE-LIS-0005-001 | ELECTRICAL DISTRIBUTION BOARD SCHEDULE - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:25:56 | zm167dc@jutal.com | 02-Sep-2026 21:23:33 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:50:42 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:41:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 08:59:12 | 18-Sep-2026 02:55:15 | 0 |  |  | Approver | Locate
AO-000659 | MM-ASK-1A-WP01-ELE-LIS-0005-002 | ELECTRICAL DC DISTRIBUTION BOARD SCHEDULE - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 08-Jul-2026 20:02:24 | zm167dc@jutal.com | 09-Jul-2026 10:18:28 | Jumpol Sudjitjul | 17-Jul-2026 | 14-Jul-2026 11:00:14 | Danai Chaisalee | 20-Jul-2026 | 17-Jul-2026 09:46:38 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 20-Jul-2026 02:56:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 20-Jul-2026 09:31:58 | 20-Jul-2026 03:04:13 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP01-ELE-LIS-0005-002 | ELECTRICAL DC DISTRIBUTION BOARD SCHEDULE - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:57:39 | zm167dc@jutal.com | 07-Aug-2026 11:02:27 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:14:12 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:39:28 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:47:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:54:23 | 21-Aug-2026 02:32:07 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP01-ELE-LIS-0005-002 | ELECTRICAL DC DISTRIBUTION BOARD SCHEDULE - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:26:32 | zm167dc@jutal.com | 02-Sep-2026 21:25:17 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:51:35 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:56:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 08:56:25 | 18-Sep-2026 02:53:52 | 0 |  |  | Approver | Locate
AO-000642 | MM-ASK-1A-WP01-ELE-LIS-0006 | ELECTRICAL I/O SUMMARY - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 00:10:38 | zm167dc@jutal.com | 07-Jul-2026 10:11:54 | Jumpol Sudjitjul | 15-Jul-2026 | 14-Jul-2026 10:54:30 | Danai Chaisalee | 16-Jul-2026 | 14-Jul-2026 14:58:27 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 19-Jul-2026 17:08:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Jul-2026 | 20-Jul-2026 09:43:17 | 20-Jul-2026 04:08:37 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP01-ELE-LIS-0006 | ELECTRICAL I/O SUMMARY - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:58:13 | zm167dc@jutal.com | 07-Aug-2026 11:02:28 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:13:36 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:37:01 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:45:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:54:56 | 21-Aug-2026 02:33:20 | 0 |  |  | Approver | Locate
AO-001198 | MM-ASK-1A-WP01-ELE-LIS-0006 | ELECTRICAL I/O SUMMARY - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 17:21:37 | zm167dc@jutal.com | 05-Sep-2026 18:18:05 | Jumpol Sudjitjul | 15-Sep-2026 |  | Danai Chaisalee | 16-Sep-2026 | 15-Sep-2026 15:49:39 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:12:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 15:51:13 | 20-Sep-2026 09:46:07 | 0 |  |  | Approver | Locate
AO-000091 | MM-ASK-1A-WP01-ELE-MR-0001 | MATERIAL REQUISITION FOR AC & DC DISTRIBUTION BOARDS / PANELS – WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 11:14:20 | zm167dc@jutal.com | 27-Apr-2026 13:49:05 | Jumpol Sudjitjul | 07-May-2026 | 13-May-2026 18:19:07 | Noppadol Iamtanasinchai | 08-May-2026 | 14-May-2026 09:17:29 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:55:55 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 08:40:31 | 15-May-2026 09:19:19 | 0 |  |  | Approver | Locate
AO-000448 | MM-ASK-1A-WP01-ELE-MR-0001 | MATERIAL REQUISITION FOR AC & DC DISTRIBUTION BOARDS / PANELS – WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 14:54:06 | zm167dc@jutal.com | 11-Jun-2026 15:15:16 | Jumpol Sudjitjul | 19-Jun-2026 | 16-Jun-2026 17:15:36 | Noppadol Iamtanasinchai | 22-Jun-2026 | 17-Jun-2026 08:55:35 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:27:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 10:48:40 | 19-Jun-2026 04:14:30 | 0 |  |  | Approver | Locate
AO-000885 | MM-ASK-1A-WP01-ELE-MR-0001 | MATERIAL REQUISITION FOR AC & DC DISTRIBUTION BOARDS / PANELS – WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 11:50:33 | zm167dc@jutal.com | 05-Aug-2026 11:56:19 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:28:14 | Danai Chaisalee | 17-Aug-2026 | 07-Aug-2026 13:56:21 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 10-Aug-2026 00:26:31 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 11:38:58 | 10-Aug-2026 06:06:21 | 0 |  |  | Approver | Locate
AO-000086 | MM-ASK-1A-WP01-ELE-MR-0002 | MATERIAL REQUISITION FOR SOLAR POWER SYSTEM – WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 11:14:54 | zm167dc@jutal.com | 27-Apr-2026 13:49:23 | Jumpol Sudjitjul | 07-May-2026 | 12-May-2026 14:24:11 | Noppadol Iamtanasinchai | 08-May-2026 | 14-May-2026 09:19:52 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:56:29 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 08:39:33 | 15-May-2026 09:18:20 | 0 |  |  | Approver | Locate
AO-000448 | MM-ASK-1A-WP01-ELE-MR-0002 | MATERIAL REQUISITION FOR SOLAR POWER SYSTEM – WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 14:54:41 | zm167dc@jutal.com | 11-Jun-2026 15:15:17 | Jumpol Sudjitjul | 19-Jun-2026 | 16-Jun-2026 17:17:50 | Noppadol Iamtanasinchai | 22-Jun-2026 | 17-Jun-2026 08:58:20 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:38:38 | APPR | Approved | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 10:42:11 | 19-Jun-2026 04:13:17 | 0 |  |  | Approver | Locate
AO-000885 | MM-ASK-1A-WP01-ELE-MR-0002 | MATERIAL REQUISITION FOR SOLAR POWER SYSTEM – WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 11:51:04 | zm167dc@jutal.com | 05-Aug-2026 11:56:22 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:29:00 | Danai Chaisalee | 17-Aug-2026 | 07-Aug-2026 13:57:21 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 10-Aug-2026 00:26:52 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 11:28:25 | 10-Aug-2026 06:00:16 | 0 |  |  | Approver | Locate
AO-000179 | MM-ASK-1A-WP01-ELE-MR-0003 | MATERIAL REQUISITION FOR NAVIGATION AID/ RED LANTERN, BEACON AND SIREN - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 21:26:15 | zm167dc@jutal.com | 08-May-2026 21:34:02 | Jumpol Sudjitjul | 19-May-2026 | 22-May-2026 13:06:23 | Noppadol Iamtanasinchai | 20-May-2026 | 23-May-2026 12:35:50 | Pornlert Wanaphattharaphan | 21-May-2026 | 24-May-2026 23:11:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 13:20:39 | 25-May-2026 13:33:24 | 0 |  |  | Approver | Locate
AO-000488 | MM-ASK-1A-WP01-ELE-MR-0003 | MATERIAL REQUISITION FOR NAVIGATION AID/ RED LANTERN, BEACON AND SIREN - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 16-Jun-2026 19:25:06 | zm167dc@jutal.com | 17-Jun-2026 08:49:14 | Jumpol Sudjitjul | 25-Jun-2026 |  | Danai Chaisalee | 26-Jun-2026 | 25-Jun-2026 14:06:11 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 28-Jun-2026 08:44:25 | APPR | Approved | Jumpol Sudjitjul | 30-Jun-2026 | 28-Jun-2026 08:48:52 | 28-Jun-2026 02:27:09 | 0 |  |  | Approver | Locate
AO-000958 | MM-ASK-1A-WP01-ELE-MR-0003 | MATERIAL REQUISITION FOR NAVIGATION AID/ RED LANTERN, BEACON AND SIREN - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 18:27:37 | zm167dc@jutal.com | 13-Aug-2026 13:13:36 | Jumpol Sudjitjul | 21-Aug-2026 |  | Danai Chaisalee | 24-Aug-2026 | 21-Aug-2026 09:31:57 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:15:17 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 13:19:51 | 24-Aug-2026 06:57:40 | 0 |  |  | Approver | Locate
AO-000087 | MM-ASK-1A-WP01-ELE-MR-0004 | MATERIAL REQUISITION FOR EXTERNAL BATTERY CHARGER – WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 11:15:23 | zm167dc@jutal.com | 27-Apr-2026 13:49:41 | Jumpol Sudjitjul | 07-May-2026 | 13-May-2026 18:20:26 | Noppadol Iamtanasinchai | 08-May-2026 | 14-May-2026 09:20:52 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:57:12 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:07:40 | 15-May-2026 10:54:09 | 0 |  |  | Approver | Locate
AO-000448 | MM-ASK-1A-WP01-ELE-MR-0004 | MATERIAL REQUISITION FOR EXTERNAL BATTERY CHARGER – WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 14:55:12 | zm167dc@jutal.com | 11-Jun-2026 15:15:18 | Jumpol Sudjitjul | 19-Jun-2026 | 16-Jun-2026 17:25:57 | Noppadol Iamtanasinchai | 22-Jun-2026 | 17-Jun-2026 08:57:38 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:37:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 10:49:31 | 19-Jun-2026 04:18:19 | 0 |  |  | Approver | Locate
AO-000885 | MM-ASK-1A-WP01-ELE-MR-0004 | MATERIAL REQUISITION FOR EXTERNAL BATTERY CHARGER – WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 11:51:34 | zm167dc@jutal.com | 05-Aug-2026 11:56:19 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:27:46 | Danai Chaisalee | 17-Aug-2026 | 07-Aug-2026 13:56:01 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 10-Aug-2026 00:27:19 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 11:43:45 | 10-Aug-2026 06:07:42 | 0 |  |  | Approver | Locate
AO-000900 | MM-ASK-1A-WP01-ELE-MR-0005 | MATERIAL REQUISITION FOR ELECTRICAL CABLES - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:58:47 | zm167dc@jutal.com | 07-Aug-2026 11:09:17 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:17:24 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:47:32 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:41:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:55:33 | 21-Aug-2026 02:34:31 | 0 |  |  | Approver | Locate
AO-001198 | MM-ASK-1A-WP01-ELE-MR-0006 | MATERIAL REQUISITION FOR ELECTRICAL BULK MATERIALS - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 17:22:05 | zm167dc@jutal.com | 05-Sep-2026 18:17:16 | Jumpol Sudjitjul | 15-Sep-2026 |  | Danai Chaisalee | 16-Sep-2026 | 15-Sep-2026 15:46:53 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 17-Sep-2026 22:38:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 18-Sep-2026 09:22:09 | 18-Sep-2026 03:04:25 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-ELE-MR-0007 | MATERIAL REQUISITION FOR FOG HORN - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 10:42:48 | zm167dc@jutal.com | 26-Jul-2026 22:18:08 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:37:48 | Danai Chaisalee | 07-Aug-2026 | 05-Aug-2026 09:09:58 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:15:59 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:26:54 | 10-Aug-2026 05:58:56 | 0 |  |  | Approver | Locate
AO-001134 | MM-ASK-1A-WP01-ELE-MTO-0001 | ELECTRICAL BULK MATERIALS TAKE OFF - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 28-Aug-2026 18:08:07 | zm167dc@jutal.com | 29-Aug-2026 13:36:24 | Jumpol Sudjitjul | 07-Sep-2026 |  | Danai Chaisalee | 08-Sep-2026 | 08-Sep-2026 13:15:16 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 10-Sep-2026 23:00:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 12:28:43 | 11-Sep-2026 06:05:36 | 0 |  |  | Approver | Locate
AO-000318 | MM-ASK-1A-WP01-ELE-SLD-0001 | ELECTRICAL KEY SINGLE LINE DIAGRAM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:42:52 | zm167dc@jutal.com | 23-May-2026 09:17:56 | Jumpol Sudjitjul | 02-Jun-2026 | 08-Jun-2026 14:12:43 | Noppadol Iamtanasinchai | 04-Jun-2026 | 08-Jun-2026 14:46:26 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:14:22 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:10:29 | 11-Jun-2026 02:34:11 | 0 |  |  | Approver | Locate
AO-000575 | MM-ASK-1A-WP01-ELE-SLD-0001 | ELECTRICAL KEY SINGLE LINE DIAGRAM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 22:03:07 | zm167dc@jutal.com | 30-Jun-2026 10:15:09 | Jumpol Sudjitjul | 08-Jul-2026 |  | Danai Chaisalee | 09-Jul-2026 | 02-Jul-2026 08:53:16 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:30:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 08:21:21 | 10-Jul-2026 01:56:35 | 0 |  |  | Approver | Locate
AO-000845 | MM-ASK-1A-WP01-ELE-SLD-0001 | ELECTRICAL KEY SINGLE LINE DIAGRAM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 21:58:57 | zm167dc@jutal.com | 01-Aug-2026 07:31:39 | Jumpol Sudjitjul | 10-Aug-2026 | 02-Aug-2026 13:08:04 | Danai Chaisalee | 11-Aug-2026 | 07-Aug-2026 13:17:19 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 10-Aug-2026 00:24:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 10-Aug-2026 11:45:29 | 10-Aug-2026 06:09:08 | 0 |  |  | Approver | Locate
AO-000318 | MM-ASK-1A-WP01-ELE-SLD-0002 | ELECTRICAL SINGLE LINE DIAGRAM - AC SYSTEM- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:43:15 | zm167dc@jutal.com | 23-May-2026 09:17:57 | Jumpol Sudjitjul | 02-Jun-2026 | 08-Jun-2026 14:13:13 | Noppadol Iamtanasinchai | 04-Jun-2026 | 08-Jun-2026 14:32:35 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:10:32 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:11:00 | 11-Jun-2026 02:35:18 | 0 |  |  | Approver | Locate
AO-000575 | MM-ASK-1A-WP01-ELE-SLD-0002 | ELECTRICAL SINGLE LINE DIAGRAM - AC SYSTEM- WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 22:03:34 | zm167dc@jutal.com | 30-Jun-2026 10:15:08 | Jumpol Sudjitjul | 08-Jul-2026 |  | Danai Chaisalee | 09-Jul-2026 | 02-Jul-2026 08:55:43 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:32:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 08:28:41 | 10-Jul-2026 02:06:01 | 0 |  |  | Approver | Locate
AO-000845 | MM-ASK-1A-WP01-ELE-SLD-0002 | ELECTRICAL SINGLE LINE DIAGRAM - AC SYSTEM- WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 21:59:32 | zm167dc@jutal.com | 01-Aug-2026 07:32:02 | Jumpol Sudjitjul | 10-Aug-2026 | 02-Aug-2026 13:08:23 | Danai Chaisalee | 11-Aug-2026 | 07-Aug-2026 13:18:12 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 10-Aug-2026 00:27:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 10-Aug-2026 11:35:20 | 10-Aug-2026 06:03:27 | 0 |  |  | Approver | Locate
AO-000318 | MM-ASK-1A-WP01-ELE-SLD-0003 | ELECTRICAL SINGLE LINE DIAGRAM - DC SYSTEM & NAVIGATION AIDS SYSTEM -WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:43:37 | zm167dc@jutal.com | 23-May-2026 09:17:54 | Jumpol Sudjitjul | 02-Jun-2026 | 08-Jun-2026 14:12:17 | Noppadol Iamtanasinchai | 04-Jun-2026 | 08-Jun-2026 14:45:35 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:11:15 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:11:36 | 11-Jun-2026 02:36:13 | 0 |  |  | Approver | Locate
AO-000575 | MM-ASK-1A-WP01-ELE-SLD-0003 | ELECTRICAL SINGLE LINE DIAGRAM - DC SYSTEM & NAVIGATION AIDS SYSTEM -WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 22:04:01 | zm167dc@jutal.com | 30-Jun-2026 10:15:10 | Jumpol Sudjitjul | 08-Jul-2026 |  | Danai Chaisalee | 09-Jul-2026 | 02-Jul-2026 08:59:22 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:33:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 08:27:51 | 10-Jul-2026 02:04:39 | 0 |  |  | Approver | Locate
AO-000845 | MM-ASK-1A-WP01-ELE-SLD-0003 | ELECTRICAL SINGLE LINE DIAGRAM - DC SYSTEM & NAVIGATION AIDS SYSTEM -WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 22:00:01 | zm167dc@jutal.com | 01-Aug-2026 07:32:18 | Jumpol Sudjitjul | 10-Aug-2026 | 02-Aug-2026 13:08:39 | Danai Chaisalee | 11-Aug-2026 | 07-Aug-2026 13:19:09 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 10-Aug-2026 00:29:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 10-Aug-2026 11:31:57 | 10-Aug-2026 06:01:58 | 0 |  |  | Approver | Locate
AO-000576 | MM-ASK-1A-WP01-ELE-SLD-0004 | SOLAR PV ARRAY PANEL ARRANGEMENT - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Jun-2026 22:04:32 | zm167dc@jutal.com | 30-Jun-2026 10:15:10 | Jumpol Sudjitjul | 08-Jul-2026 |  | Danai Chaisalee | 09-Jul-2026 | 02-Jul-2026 08:58:21 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:34:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 08:22:53 | 10-Jul-2026 01:59:07 | 0 |  |  | Approver | Locate
AO-000845 | MM-ASK-1A-WP01-ELE-SLD-0004 | SOLAR PV ARRAY PANEL ARRANGEMENT - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 22:00:32 | zm167dc@jutal.com | 01-Aug-2026 07:32:32 | Jumpol Sudjitjul | 10-Aug-2026 | 02-Aug-2026 13:09:02 | Danai Chaisalee | 11-Aug-2026 | 05-Aug-2026 14:43:20 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 10-Aug-2026 00:20:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 10-Aug-2026 11:38:22 | 10-Aug-2026 06:04:59 | 0 |  |  | Approver | Locate
AO-001201 | MM-ASK-1A-WP01-ELE-SLD-0004 | SOLAR PV ARRAY PANEL ARRANGEMENT - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 17:22:32 | zm167dc@jutal.com | 05-Sep-2026 18:14:29 | Jumpol Sudjitjul | 15-Sep-2026 |  | Danai Chaisalee | 16-Sep-2026 | 15-Sep-2026 15:43:29 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:09:23 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 15:51:58 | 20-Sep-2026 09:47:21 | 0 |  |  | Approver | Locate
AO-000631 | MM-ASK-1A-WP01-ELE-TBE-0001 | TECHNICAL BID EVALUATION FOR AC & DC DISTRIBUTION BOARDS/PANELS - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:23:16 | zm167dc@jutal.com | 04-Jul-2026 14:18:45 | Jumpol Sudjitjul | 13-Jul-2026 | 08-Jul-2026 13:43:13 | Danai Chaisalee | 14-Jul-2026 | 10-Jul-2026 13:00:11 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 13:07:33 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 13:23:43 | 10-Jul-2026 06:32:53 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-WP01-ELE-TBE-0001 | TECHNICAL BID EVALUATION FOR AC & DC DISTRIBUTION BOARDS/PANELS - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:53:37 | zm167dc@jutal.com | 20-Jul-2026 11:48:56 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 21-Jul-2026 10:20:31 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 21-Jul-2026 15:53:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 21-Jul-2026 16:12:35 | 21-Jul-2026 09:35:46 | 0 |  |  | Approver | Locate
AO-000804 | MM-ASK-1A-WP01-ELE-TBE-0001 | TECHNICAL BID EVALUATION FOR AC & DC DISTRIBUTION BOARDS/PANELS - WP01 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 18:23:04 | zm167dc@jutal.com | 28-Jul-2026 08:51:47 | Jumpol Sudjitjul | 06-Aug-2026 |  | Danai Chaisalee | 07-Aug-2026 | 30-Jul-2026 13:06:04 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 18:02:47 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 18:58:56 | 30-Jul-2026 12:18:56 | 0 |  |  | Approver | Locate
AO-000622 | MM-ASK-1A-WP01-ELE-TBE-0002 | TECHNICAL BID EVALUATION FOR SOLAR POWER SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:18:48 | zm167dc@jutal.com | 03-Jul-2026 18:43:57 | Jumpol Sudjitjul | 14-Jul-2026 |  | Danai Chaisalee | 15-Jul-2026 | 10-Jul-2026 13:01:17 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 10-Jul-2026 14:17:28 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Jul-2026 | 10-Jul-2026 14:41:41 | 10-Jul-2026 07:46:08 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-WP01-ELE-TBE-0002 | TECHNICAL BID EVALUATION FOR SOLAR POWER SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:54:07 | zm167dc@jutal.com | 20-Jul-2026 11:50:45 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 21-Jul-2026 10:22:42 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 21-Jul-2026 15:29:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 21-Jul-2026 15:35:20 | 21-Jul-2026 08:54:40 | 0 |  |  | Approver | Locate
AO-000809 | MM-ASK-1A-WP01-ELE-TBE-0002 | TECHNICAL BID EVALUATION FOR SOLAR POWER SYSTEM - WP01 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 28-Jul-2026 09:10:47 | zm167dc@jutal.com | 28-Jul-2026 20:21:50 | Jumpol Sudjitjul | 07-Aug-2026 |  | Danai Chaisalee | 10-Aug-2026 | 30-Jul-2026 13:04:55 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 30-Jul-2026 18:10:08 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 30-Jul-2026 18:59:37 | 30-Jul-2026 12:28:34 | 0 |  |  | Approver | Locate
AO-000690 | MM-ASK-1A-WP01-ELE-TBE-0003 | TECHNICAL BID EVALUATION FOR NAVIGATION AID SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 13-Jul-2026 14:41:44 | zm167dc@jutal.com | 13-Jul-2026 14:44:39 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:28:53 | Danai Chaisalee | 22-Jul-2026 | 20-Jul-2026 13:56:39 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 21-Jul-2026 00:43:43 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 24-Jul-2026 | 21-Jul-2026 07:37:33 | 21-Jul-2026 00:48:08 | 0 |  |  | Approver | Locate
AO-000883 | MM-ASK-1A-WP01-ELE-TBE-0003 | TECHNICAL BID EVALUATION FOR NAVIGATION AID SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 04-Aug-2026 17:34:51 | zm167dc@jutal.com | 05-Aug-2026 08:29:58 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:26:43 | Danai Chaisalee | 17-Aug-2026 | 06-Aug-2026 07:31:46 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 06-Aug-2026 23:49:47 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 07-Aug-2026 09:25:10 | 07-Aug-2026 03:18:44 | 0 |  |  | Approver | Locate
AO-000651 | MM-ASK-1A-WP01-ELE-TBE-0004 | TECHNICAL BID EVALUATION FOR EXTERNAL BATTERY CHARGER - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 18:43:00 | zm167dc@jutal.com | 07-Jul-2026 20:49:30 | Jumpol Sudjitjul | 16-Jul-2026 | 14-Jul-2026 10:58:40 | Danai Chaisalee | 17-Jul-2026 | 16-Jul-2026 16:26:30 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 16-Jul-2026 16:56:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 16-Jul-2026 16:59:37 | 16-Jul-2026 10:10:26 | 0 |  |  | Approver | Locate
AO-000846 | MM-ASK-1A-WP01-ELE-TBE-0004 | TECHNICAL BID EVALUATION FOR EXTERNAL BATTERY CHARGER - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 09:59:02 | zm167dc@jutal.com | 03-Aug-2026 11:15:13 | Jumpol Sudjitjul | 11-Aug-2026 | 04-Aug-2026 10:29:42 | Danai Chaisalee | 13-Aug-2026 | 05-Aug-2026 09:10:43 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 06-Aug-2026 23:51:51 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 09:25:35 | 07-Aug-2026 03:20:10 | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP01-ELE-WIR-0001-001 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:10:24 | zm167dc@jutal.com | 13-Jun-2026 08:24:23 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 14:29:22 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:39:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:42:04 | 25-Jun-2026 02:48:32 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP01-ELE-WIR-0001-001 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 09:54:43 | zm167dc@jutal.com | 20-Jul-2026 11:41:04 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:15:20 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 21:19:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:36:46 | 27-Jul-2026 02:58:13 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP01-ELE-WIR-0001-001 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:23:29 | zm167dc@jutal.com | 24-Aug-2026 20:04:30 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:06:45 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 00:06:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:23:44 | 06-Sep-2026 03:05:29 | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP01-ELE-WIR-0001-002 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:10:50 | zm167dc@jutal.com | 13-Jun-2026 08:24:37 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 14:25:54 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:38:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:44:06 | 25-Jun-2026 02:49:51 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP01-ELE-WIR-0001-002 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 09:55:13 | zm167dc@jutal.com | 20-Jul-2026 11:41:03 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:08:02 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 20:34:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:16:00 | 27-Jul-2026 02:31:10 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP01-ELE-WIR-0001-002 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:23:59 | zm167dc@jutal.com | 24-Aug-2026 20:05:03 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:07:41 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 00:19:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:24:20 | 06-Sep-2026 03:06:52 | 0 |  |  | Approver | Locate
AO-000735 | MM-ASK-1A-WP01-ELE-WIR-0001-003 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 12:09:22 | zm167dc@jutal.com | 20-Jul-2026 13:11:11 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:21:19 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 27-Jul-2026 00:24:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 10:36:17 | 27-Jul-2026 04:17:22 | 0 |  |  | Approver | Locate
AO-001069 | MM-ASK-1A-WP01-ELE-WIR-0001-003 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 18:38:37 | zm167dc@jutal.com | 24-Aug-2026 20:15:04 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:16:49 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 00:20:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:25:08 | 06-Sep-2026 03:16:19 | 0 |  |  | Approver | Locate
AO-001471 | MM-ASK-1A-WP01-ELE-WIR-0001-003 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 14:54:33 | zm167dc@jutal.com | 18-Sep-2026 17:09:34 | Jumpol Sudjitjul | 29-Sep-2026 |  | Danai Chaisalee | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP01-ELE-WIR-0002-001 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:11:14 | zm167dc@jutal.com | 13-Jun-2026 08:24:50 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 14:21:27 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:37:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 08:44:53 | 25-Jun-2026 02:51:06 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP01-ELE-WIR-0002-001 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 09:55:54 | zm167dc@jutal.com | 20-Jul-2026 11:41:00 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:03:08 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:52:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 10:44:31 | 27-Jul-2026 04:11:08 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP01-ELE-WIR-0002-001 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:24:24 | zm167dc@jutal.com | 24-Aug-2026 20:05:29 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:08:42 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 00:21:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:25:48 | 06-Sep-2026 03:08:12 | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP01-ELE-WIR-0002-002 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:11:40 | zm167dc@jutal.com | 13-Jun-2026 08:25:02 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 14:15:12 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:37:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 09:44:08 | 25-Jun-2026 02:52:22 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP01-ELE-WIR-0002-002 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 09:56:25 | zm167dc@jutal.com | 20-Jul-2026 11:41:08 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:13:37 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 21:03:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:58:30 | 27-Jul-2026 03:22:51 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP01-ELE-WIR-0002-002 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:24:55 | zm167dc@jutal.com | 24-Aug-2026 20:06:03 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:12:01 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 00:22:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:26:37 | 06-Sep-2026 03:09:32 | 0 |  |  | Approver | Locate
AO-000736 | MM-ASK-1A-WP01-ELE-WIR-0002-003 | ELECTRICAL WIRING INTERCONNECTION FOR SOLAR SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 12:09:48 | zm167dc@jutal.com | 20-Jul-2026 13:11:10 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:16:07 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 21:22:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 10:02:22 | 27-Jul-2026 03:27:42 | 0 |  |  | Approver | Locate
AO-001080 | MM-ASK-1A-WP01-ELE-WIR-0002-003 | ELECTRICAL WIRING INTERCONNECTION FOR SOLAR SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:28:51 | zm167dc@jutal.com | 24-Aug-2026 20:15:06 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:19:32 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 00:24:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:27:12 | 06-Sep-2026 02:57:34 | 0 |  |  | Approver | Locate
AO-001472 | MM-ASK-1A-WP01-ELE-WIR-0002-003 | ELECTRICAL WIRING INTERCONNECTION FOR SOLAR SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 14:55:08 | zm167dc@jutal.com | 18-Sep-2026 17:09:33 | Jumpol Sudjitjul | 29-Sep-2026 |  | Danai Chaisalee | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000737 | MM-ASK-1A-WP01-ELE-WIR-0002-004 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 12:10:16 | zm167dc@jutal.com | 20-Jul-2026 13:11:11 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:17:09 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 21:25:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 10:45:10 | 27-Jul-2026 04:21:45 | 0 |  |  | Approver | Locate
AO-001081 | MM-ASK-1A-WP01-ELE-WIR-0002-004 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:29:24 | zm167dc@jutal.com | 24-Aug-2026 20:15:06 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:17:42 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 00:25:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:28:03 | 06-Sep-2026 02:58:57 | 0 |  |  | Approver | Locate
AO-001473 | MM-ASK-1A-WP01-ELE-WIR-0002-004 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 14:55:37 | zm167dc@jutal.com | 18-Sep-2026 17:09:33 | Jumpol Sudjitjul | 29-Sep-2026 |  | Danai Chaisalee | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP01-ELE-WIR-0003 | ELECTRICAL WIRING INTERCONNECTION FOR NAVIGATION AID SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:12:06 | zm167dc@jutal.com | 13-Jun-2026 08:25:15 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 14:06:22 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:36:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 09:46:37 | 25-Jun-2026 03:27:31 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP01-ELE-WIR-0003 | ELECTRICAL WIRING INTERCONNECTION FOR NAVIGATION AID SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 09:56:55 | zm167dc@jutal.com | 20-Jul-2026 11:41:01 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:04:15 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:54:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 09:37:37 | 27-Jul-2026 02:59:33 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP01-ELE-WIR-0003 | ELECTRICAL WIRING INTERCONNECTION FOR NAVIGATION AID SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:25:24 | zm167dc@jutal.com | 24-Aug-2026 20:06:27 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:14:13 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 00:26:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 06-Sep-2026 09:28:41 | 06-Sep-2026 03:10:55 | 0 |  |  | Approver | Locate
AO-000093 | MM-ASK-1A-WP01-INS-DTS-0001 | DATASHEET FOR WELLHEAD CONTROL PANEL - WPA01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 28-Apr-2026 19:04:20 | zm167dc@jutal.com | 29-Apr-2026 10:05:01 | Jumpol Sudjitjul | 11-May-2026 | 11-May-2026 20:08:49 | Payut Phatdamrongdet | 12-May-2026 | 12-May-2026 21:48:53 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 22:58:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 19-May-2026 09:17:28 | 19-May-2026 10:55:36 | 0 |  |  | Approver | Locate
AO-000452 | MM-ASK-1A-WP01-INS-DTS-0001 | DATASHEET FOR WELLHEAD CONTROL PANEL - WPA01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 17:17:10 | zm167dc@jutal.com | 11-Jun-2026 17:47:27 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 16-Jun-2026 14:07:57 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 21-Jun-2026 08:43:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 10:39:56 | 22-Jun-2026 04:28:16 | 0 |  |  | Approver | Locate
AO-000655 | MM-ASK-1A-WP01-INS-DTS-0001 | DATASHEET FOR WELLHEAD CONTROL PANEL - WPA01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 16:58:52 | zm167dc@jutal.com | 08-Jul-2026 17:09:09 | Jumpol Sudjitjul | 17-Jul-2026 |  | Payut Phatdamrongdet | 20-Jul-2026 | 20-Jul-2026 23:40:01 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 23:01:26 | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 13:31:01 | 23-Jul-2026 07:11:24 | 0 |  |  | Approver | Locate
AO-000256 | MM-ASK-1A-WP01-INS-DTS-0002 | DATA SHEET FOR CONTROL VALVES-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 12:08:29 | zm167dc@jutal.com | 15-May-2026 17:44:45 | Jumpol Sudjitjul | 26-May-2026 | 26-May-2026 21:29:23 | Payut Phatdamrongdet | 27-May-2026 | 28-May-2026 14:19:53 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 01:10:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:53:41 | 10-Jun-2026 07:20:27 | 0 |  |  | Approver | Locate
AO-000635 | MM-ASK-1A-WP01-INS-DTS-0002 | DATA SHEET FOR CONTROL VALVES-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 00:11:28 | zm167dc@jutal.com | 07-Jul-2026 10:03:29 | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 11:30:28 | Payut Phatdamrongdet | 16-Jul-2026 | 21-Jul-2026 18:42:29 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 22-Jul-2026 22:57:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Jul-2026 | 23-Jul-2026 13:30:04 | 23-Jul-2026 07:05:02 | 0 |  |  | Approver | Locate
AO-000925 | MM-ASK-1A-WP01-INS-DTS-0002 | DATA SHEET FOR CONTROL VALVES-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 16:56:52 | zm167dc@jutal.com | 07-Aug-2026 17:09:10 | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 10:51:15 | Payut Phatdamrongdet | 20-Aug-2026 | 24-Aug-2026 16:45:06 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 27-Aug-2026 14:36:47 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 27-Aug-2026 14:44:15 | 27-Aug-2026 08:57:27 | 0 |  |  | Approver | Locate
AO-000270 | MM-ASK-1A-WP01-INS-DTS-0003 | DATA SHEET FOR SELF ACTUATED PCV-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 15:29:06 | zm167dc@jutal.com | 15-May-2026 17:44:45 | Jumpol Sudjitjul | 26-May-2026 | 26-May-2026 16:44:43 | Payut Phatdamrongdet | 27-May-2026 | 27-May-2026 13:48:22 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 01:03:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:51:40 | 10-Jun-2026 05:21:53 | 0 |  |  | Approver | Locate
AO-000597 | MM-ASK-1A-WP01-INS-DTS-0003 | DATA SHEET FOR SELF ACTUATED PCV-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 02-Jul-2026 16:06:53 | zm167dc@jutal.com | 02-Jul-2026 16:43:24 | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 16:32:35 | Payut Phatdamrongdet | 13-Jul-2026 | 20-Jul-2026 17:19:37 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 22-Jul-2026 22:40:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 23-Jul-2026 13:29:07 | 23-Jul-2026 06:53:20 | 0 |  |  | Approver | Locate
AO-000850 | MM-ASK-1A-WP01-INS-DTS-0003 | DATA SHEET FOR SELF ACTUATED PCV-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:03:12 | zm167dc@jutal.com | 03-Aug-2026 11:17:48 | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 00:37:31 | Payut Phatdamrongdet | 13-Aug-2026 | 10-Aug-2026 13:15:12 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:12:21 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 08:50:07 | 17-Aug-2026 02:08:24 | 0 |  |  | Approver | Locate
AO-000241 | MM-ASK-1A-WP01-INS-DTS-0004 | DATA SHEET FOR ACTUATED CHOKE VALVES-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:55:28 | zm167dc@jutal.com | 15-May-2026 17:44:44 | Jumpol Sudjitjul | 26-May-2026 | 20-May-2026 11:07:38 | Payut Phatdamrongdet | 27-May-2026 | 21-May-2026 16:28:50 | Pornlert Wanaphattharaphan | 28-May-2026 | 01-Jun-2026 18:32:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 01-Jun-2026 22:08:47 | 01-Jun-2026 15:25:00 | 0 |  |  | Approver | Locate
AO-000549 | MM-ASK-1A-WP01-INS-DTS-0004 | DATA SHEET FOR ACTUATED CHOKE VALVES-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:06:37 | zm167dc@jutal.com | 26-Jun-2026 08:18:48 | Jumpol Sudjitjul | 06-Jul-2026 | 06-Jul-2026 23:23:15 | Payut Phatdamrongdet | 07-Jul-2026 | 17-Jul-2026 14:03:59 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 19-Jul-2026 12:00:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 20-Jul-2026 09:29:56 | 20-Jul-2026 03:29:54 | 0 |  |  | Approver | Locate
AO-000829 | MM-ASK-1A-WP01-INS-DTS-0004 | DATA SHEET FOR ACTUATED CHOKE VALVES-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 16:44:31 | zm167dc@jutal.com | 31-Jul-2026 17:00:59 | Jumpol Sudjitjul | 10-Aug-2026 |  | Payut Phatdamrongdet | 11-Aug-2026 | 31-Jul-2026 21:19:51 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 10:03:34 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:30:10 | 13-Aug-2026 02:32:17 | 0 |  |  | Approver | Locate
AO-000402 | MM-ASK-1A-WP01-INS-DTS-0005 | DATA SHEETS FOR ACTUATED BALL VALVES-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 14:55:16 | zm167dc@jutal.com | 04-Jun-2026 16:56:47 | Jumpol Sudjitjul | 12-Jun-2026 | 10-Jun-2026 15:38:03 | Payut Phatdamrongdet | 15-Jun-2026 | 11-Jun-2026 15:46:15 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 13-Jun-2026 23:27:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 14-Jun-2026 21:44:35 | 14-Jun-2026 15:18:12 | 0 |  |  | Approver | Locate
AO-000637 | MM-ASK-1A-WP01-INS-DTS-0005 | DATA SHEETS FOR ACTUATED BALL VALVES-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 00:11:54 | zm167dc@jutal.com | 07-Jul-2026 10:03:48 | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 16:31:11 | Payut Phatdamrongdet | 16-Jul-2026 | 22-Jul-2026 08:56:59 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 22-Jul-2026 22:57:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Jul-2026 | 23-Jul-2026 13:28:11 | 23-Jul-2026 07:02:31 | 0 |  |  | Approver | Locate
AO-000923 | MM-ASK-1A-WP01-INS-DTS-0005 | DATA SHEETS FOR ACTUATED BALL VALVES-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 16:57:22 | zm167dc@jutal.com | 07-Aug-2026 17:09:27 | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 10:51:43 | Payut Phatdamrongdet | 20-Aug-2026 | 24-Aug-2026 16:51:12 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 27-Aug-2026 14:46:12 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 27-Aug-2026 14:54:43 | 27-Aug-2026 08:49:10 | 0 |  |  | Approver | Locate
AO-001253 | MM-ASK-1A-WP01-INS-DTS-0005 | DATA SHEETS FOR ACTUATED BALL VALVES-WP01 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 14:45:21 | zm167dc@jutal.com | 09-Sep-2026 16:50:18 | Jumpol Sudjitjul | 17-Sep-2026 |  | Payut Phatdamrongdet | 18-Sep-2026 | 11-Sep-2026 18:04:25 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 13-Sep-2026 22:47:02 | APPR | Approved | Jumpol Sudjitjul | 22-Sep-2026 | 13-Sep-2026 22:50:11 | 13-Sep-2026 17:02:28 | 0 |  |  | Approver | Locate
AO-000358 | MM-ASK-1A-WP01-INS-DTS-0006 | DATA SHEET FOR ACTUATED COMPACT BALL VALVES-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 27-May-2026 14:44:37 | zm167dc@jutal.com | 27-May-2026 14:58:49 | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 11:35:48 | Payut Phatdamrongdet | 09-Jun-2026 | 10-Jun-2026 13:54:35 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:28:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 09:18:29 | 11-Jun-2026 09:37:17 | 0 |  |  | Approver | Locate
AO-000517 | MM-ASK-1A-WP01-INS-DTS-0006 | DATA SHEET FOR ACTUATED COMPACT BALL VALVES-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 19-Jun-2026 17:24:56 | zm167dc@jutal.com | 19-Jun-2026 17:45:45 | Jumpol Sudjitjul | 30-Jun-2026 | 25-Jun-2026 14:49:17 | Payut Phatdamrongdet | 01-Jul-2026 | 30-Jun-2026 10:20:09 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 02-Jul-2026 00:59:47 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 02-Jul-2026 10:31:27 | 02-Jul-2026 04:39:10 | 0 |  |  | Approver | Locate
AO-000835 | MM-ASK-1A-WP01-INS-DTS-0006 | DATA SHEET FOR ACTUATED COMPACT BALL VALVES-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:19:11 | zm167dc@jutal.com | 31-Jul-2026 21:45:50 | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 00:37:00 | Payut Phatdamrongdet | 13-Aug-2026 | 10-Aug-2026 08:28:41 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 20:55:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 08:32:57 | 13-Aug-2026 02:13:54 | 0 |  |  | Approver | Locate
AO-000494 | MM-ASK-1A-WP01-INS-DTS-0007 | DATA SHEET FOR SAFETY RELIEF VALVES-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 17-Jun-2026 12:49:17 | zm167dc@jutal.com | 17-Jun-2026 16:06:27 | Jumpol Sudjitjul | 25-Jun-2026 | 24-Jun-2026 17:54:37 | Payut Phatdamrongdet | 26-Jun-2026 | 29-Jun-2026 13:32:47 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 30-Jun-2026 22:47:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 01-Jul-2026 08:39:56 | 01-Jul-2026 02:22:17 | 0 |  |  | Approver | Locate
AO-000685 | MM-ASK-1A-WP01-INS-DTS-0007 | DATA SHEET FOR SAFETY RELIEF VALVES-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:36:05 | zm167dc@jutal.com | 12-Jul-2026 11:52:38 | Jumpol Sudjitjul | 20-Jul-2026 | 14-Jul-2026 11:19:30 | Payut Phatdamrongdet | 21-Jul-2026 | 22-Jul-2026 11:31:59 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 13:42:46 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 13:45:59 | 24-Jul-2026 06:54:11 | 0 |  |  | Approver | Locate
AO-000924 | MM-ASK-1A-WP01-INS-DTS-0007 | DATA SHEET FOR SAFETY RELIEF VALVES-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 16:57:56 | zm167dc@jutal.com | 07-Aug-2026 17:09:43 | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 10:52:06 | Payut Phatdamrongdet | 20-Aug-2026 | 24-Aug-2026 17:13:47 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 27-Aug-2026 14:47:17 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 27-Aug-2026 15:24:03 | 27-Aug-2026 08:50:33 | 0 |  |  | Approver | Locate
AO-000538 | MM-ASK-1A-WP01-INS-DTS-0008 | DATA SHEET FOR CORIOLIS FLOW METERS-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jun-2026 13:15:20 | zm167dc@jutal.com | 24-Jun-2026 14:44:09 | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 14:46:34 | Payut Phatdamrongdet | 03-Jul-2026 | 07-Jul-2026 10:25:39 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 08-Jul-2026 00:51:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 08-Jul-2026 08:45:54 | 08-Jul-2026 02:42:46 | 0 |  |  | Approver | Locate
AO-000714 | MM-ASK-1A-WP01-INS-DTS-0008 | DATA SHEET FOR CORIOLIS FLOW METERS-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 17-Jul-2026 12:37:05 | zm167dc@jutal.com | 17-Jul-2026 12:51:21 | Jumpol Sudjitjul | 27-Jul-2026 | 23-Jul-2026 17:17:22 | Payut Phatdamrongdet | 30-Jul-2026 | 24-Jul-2026 08:25:15 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:15:30 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 09:59:16 | 27-Jul-2026 03:26:29 | 0 |  |  | Approver | Locate
AO-001038 | MM-ASK-1A-WP01-INS-DTS-0008 | DATA SHEET FOR CORIOLIS FLOW METERS-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 16:08:02 | zm167dc@jutal.com | 20-Aug-2026 17:04:41 | Jumpol Sudjitjul | 31-Aug-2026 |  | Payut Phatdamrongdet | 01-Sep-2026 | 26-Aug-2026 10:56:44 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 15:49:01 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 15:53:02 | 30-Aug-2026 09:43:31 | 0 |  |  | Approver | Locate
AO-000538 | MM-ASK-1A-WP01-INS-DTS-0009 | DATA SHEETS FOR VORTEX FLOW METERS-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jun-2026 13:15:49 | zm167dc@jutal.com | 24-Jun-2026 14:44:53 | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 14:45:42 | Payut Phatdamrongdet | 03-Jul-2026 | 07-Jul-2026 13:44:25 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 08-Jul-2026 00:53:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 08-Jul-2026 08:48:09 | 08-Jul-2026 02:44:05 | 0 |  |  | Approver | Locate
AO-000710 | MM-ASK-1A-WP01-INS-DTS-0009 | DATA SHEETS FOR VORTEX FLOW METERS-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 16:58:49 | zm167dc@jutal.com | 16-Jul-2026 20:46:15 | Jumpol Sudjitjul | 27-Jul-2026 |  | Payut Phatdamrongdet | 30-Jul-2026 | 22-Jul-2026 11:47:18 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:10:49 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:03:02 | 27-Jul-2026 03:35:48 | 0 |  |  | Approver | Locate
AO-001047 | MM-ASK-1A-WP01-INS-DTS-0009 | DATA SHEETS FOR VORTEX FLOW METERS-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 09:34:57 | zm167dc@jutal.com | 21-Aug-2026 13:43:23 | Jumpol Sudjitjul | 31-Aug-2026 |  | Payut Phatdamrongdet | 01-Sep-2026 | 26-Aug-2026 11:19:28 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 15:57:18 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:02:10 | 30-Aug-2026 09:45:58 | 0 |  |  | Approver | Locate
AO-000763 | MM-ASK-1A-WP01-INS-DTS-0011 | DATA SHEET FOR PRESSURE GAUGES-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 23-Jul-2026 12:48:58 | zm167dc@jutal.com | 23-Jul-2026 16:18:07 | Jumpol Sudjitjul | 04-Aug-2026 | 23-Jul-2026 17:36:39 | Payut Phatdamrongdet | 05-Aug-2026 | 31-Jul-2026 10:22:58 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 05-Aug-2026 23:15:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 06-Aug-2026 08:42:12 | 06-Aug-2026 02:55:04 | 0 |  |  | Approver | Locate
AO-001336 | MM-ASK-1A-WP01-INS-DTS-0011 | DATA SHEET FOR PRESSURE GAUGES-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:44:13 | zm167dc@jutal.com | 11-Sep-2026 20:36:36 | Jumpol Sudjitjul | 22-Sep-2026 |  | Payut Phatdamrongdet | 23-Sep-2026 | 18-Sep-2026 08:37:23 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:36:36 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 15:52:52 | 20-Sep-2026 09:22:12 | 0 |  |  | Approver | Locate
AO-000773 | MM-ASK-1A-WP01-INS-DTS-0012 | DATA SHEETS FOR PRESSURE TRANSMITTERS-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:06:54 | zm167dc@jutal.com | 26-Jul-2026 22:48:02 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 31-Jul-2026 13:26:17 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 21:56:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:08:55 | 08-Aug-2026 03:22:45 | 0 |  |  | Approver | Locate
AO-001485 | MM-ASK-1A-WP01-INS-DTS-0012 | DATA SHEETS FOR PRESSURE TRANSMITTERS-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:46:37 | zm167dc@jutal.com | 18-Sep-2026 17:17:17 | Jumpol Sudjitjul | 29-Sep-2026 |  | Payut Phatdamrongdet | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-INS-DTS-0013 | DATA SHEET FOR TEMPERATURE GAUGE AND THERMOWELL-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:55:35 | zm167dc@jutal.com | 26-Jul-2026 22:48:02 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 31-Jul-2026 18:35:46 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:00:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:12:39 | 08-Aug-2026 03:26:47 | 0 |  |  | Approver | Locate
AO-001493 | MM-ASK-1A-WP01-INS-DTS-0013 | DATA SHEET FOR TEMPERATURE GAUGE AND THERMOWELL-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:15:34 | zm167dc@jutal.com | 20-Sep-2026 14:17:26 | Jumpol Sudjitjul | 28-Sep-2026 |  | Payut Phatdamrongdet | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000773 | MM-ASK-1A-WP01-INS-DTS-0014 | DATA SHEET FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:07:17 | zm167dc@jutal.com | 26-Jul-2026 22:48:03 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 31-Jul-2026 15:11:16 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 21:57:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:18:22 | 08-Aug-2026 04:16:13 | 0 |  |  | Approver | Locate
AO-001466 | MM-ASK-1A-WP01-INS-DTS-0014 | DATA SHEET FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 14:56:12 | zm167dc@jutal.com | 18-Sep-2026 17:17:15 | Jumpol Sudjitjul | 29-Sep-2026 |  | Payut Phatdamrongdet | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-WP01-INS-DTS-0015 | DATA SHEETS FOR MAGNETIC LEVEL GAUGE AND TRANSMITTERS-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:51:17 | zm167dc@jutal.com | 27-Jun-2026 19:51:20 | Jumpol Sudjitjul | 07-Jul-2026 | 09-Jul-2026 15:25:14 | Payut Phatdamrongdet | 08-Jul-2026 | 19-Jul-2026 09:24:41 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 19-Jul-2026 12:15:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 20-Jul-2026 09:29:32 | 20-Jul-2026 03:28:38 | 0 |  |  | Approver | Locate
AO-000807 | MM-ASK-1A-WP01-INS-DTS-0015 | DATA SHEETS FOR MAGNETIC LEVEL GAUGE AND TRANSMITTERS-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-Jul-2026 09:11:15 | zm167dc@jutal.com | 28-Jul-2026 20:20:25 | Jumpol Sudjitjul | 07-Aug-2026 |  | Payut Phatdamrongdet | 10-Aug-2026 | 31-Jul-2026 21:22:33 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 12-Aug-2026 09:55:40 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 13-Aug-2026 08:39:11 | 13-Aug-2026 02:52:03 | 0 |  |  | Approver | Locate
AO-001115 | MM-ASK-1A-WP01-INS-DTS-0015 | DATA SHEETS FOR MAGNETIC LEVEL GAUGE AND TRANSMITTERS-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 27-Aug-2026 18:00:35 | zm167dc@jutal.com | 28-Aug-2026 13:34:02 | Jumpol Sudjitjul | 07-Sep-2026 |  | Payut Phatdamrongdet | 08-Sep-2026 | 28-Aug-2026 14:57:07 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 30-Aug-2026 18:36:59 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 30-Aug-2026 21:16:01 | 30-Aug-2026 14:22:56 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP01-INS-DTS-0017 | DATA SHEETS FOR LEVEL SWITCH-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 09:51:20 | zm167dc@jutal.com | 07-Aug-2026 15:24:32 | Jumpol Sudjitjul | 18-Aug-2026 | 18-Aug-2026 22:47:51 | Payut Phatdamrongdet | 19-Aug-2026 | 24-Aug-2026 16:31:37 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 27-Aug-2026 14:31:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 27-Aug-2026 14:45:40 | 27-Aug-2026 08:58:49 | 0 |  |  | Approver | Locate
AO-001198 | MM-ASK-1A-WP01-INS-DTS-0017 | DATA SHEETS FOR LEVEL SWITCH-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 17:24:19 | zm167dc@jutal.com | 05-Sep-2026 18:13:55 | Jumpol Sudjitjul | 15-Sep-2026 |  | Payut Phatdamrongdet | 16-Sep-2026 | 11-Sep-2026 18:13:20 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 22:29:37 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 22:39:04 | 13-Sep-2026 15:59:20 | 0 |  |  | Approver | Locate
AO-000780 | MM-ASK-1A-WP01-INS-DTS-0018 | DATA SHEETS FOR DP LEVEL TRANSMITTERS-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:11:37 | zm167dc@jutal.com | 26-Jul-2026 22:47:59 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 31-Jul-2026 17:06:08 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 21:59:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:18:45 | 08-Aug-2026 04:08:27 | 0 |  |  | Approver | Locate
AO-000626 | MM-ASK-1A-WP01-INS-DTS-0019 | DATA SHEETS FOR RESTRICTION ORIFICE- WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 19:09:23 | zm167dc@jutal.com | 04-Jul-2026 13:56:08 | Jumpol Sudjitjul | 13-Jul-2026 | 17-Jul-2026 09:59:10 | Payut Phatdamrongdet | 14-Jul-2026 | 20-Jul-2026 23:14:31 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:42:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 13:21:07 | 23-Jul-2026 07:08:29 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-WP01-INS-DTS-0019 | DATA SHEETS FOR RESTRICTION ORIFICE- WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:44:45 | zm167dc@jutal.com | 11-Sep-2026 20:37:08 | Jumpol Sudjitjul | 22-Sep-2026 |  | Payut Phatdamrongdet | 23-Sep-2026 | 18-Sep-2026 08:38:50 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:35:37 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 15:39:45 | 20-Sep-2026 09:12:45 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP01-INS-DTS-0020 | DATA SHEET FOR FIRE & GAS DETECTORS- WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 12:03:33 | zm167dc@jutal.com | 06-Aug-2026 13:51:34 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:08:24 | Payut Phatdamrongdet | 18-Aug-2026 | 10-Aug-2026 14:40:26 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 17-Aug-2026 00:07:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 08:43:16 | 17-Aug-2026 02:16:31 | 0 |  |  | Approver | Locate
AO-001127 | MM-ASK-1A-WP01-INS-DTS-0020 | DATA SHEET FOR FIRE & GAS DETECTORS- WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 16:47:40 | zm167dc@jutal.com | 28-Aug-2026 17:28:40 | Jumpol Sudjitjul | 08-Sep-2026 |  | Payut Phatdamrongdet | 09-Sep-2026 | 04-Sep-2026 10:48:15 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 06-Sep-2026 00:27:14 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 06-Sep-2026 09:29:16 | 06-Sep-2026 03:00:10 | 0 |  |  | Approver | Locate
AO-001481 | MM-ASK-1A-WP01-INS-DTS-0020 | DATA SHEET FOR FIRE & GAS DETECTORS- WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:47:13 | zm167dc@jutal.com | 18-Sep-2026 17:17:17 | Jumpol Sudjitjul | 29-Sep-2026 |  | Payut Phatdamrongdet | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-WP01-INS-DTS-0021 | DATA SHEETS FOR POSITION LIMIT SWITCHES- WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 05-Aug-2026 18:36:34 | zm167dc@jutal.com | 06-Aug-2026 13:52:06 | Jumpol Sudjitjul | 17-Aug-2026 | 16-Aug-2026 15:07:21 | Payut Phatdamrongdet | 18-Aug-2026 | 17-Aug-2026 15:43:15 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 20-Aug-2026 23:03:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 21-Aug-2026 08:56:10 | 21-Aug-2026 02:21:38 | 0 |  |  | Approver | Locate
AO-001115 | MM-ASK-1A-WP01-INS-DTS-0021 | DATA SHEETS FOR POSITION LIMIT SWITCHES- WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 18:01:03 | zm167dc@jutal.com | 28-Aug-2026 13:34:26 | Jumpol Sudjitjul | 07-Sep-2026 |  | Payut Phatdamrongdet | 08-Sep-2026 | 28-Aug-2026 15:00:42 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 30-Aug-2026 18:37:50 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 30-Aug-2026 21:16:58 | 30-Aug-2026 14:24:08 | 0 |  |  | Approver | Locate
AO-001367 | MM-ASK-1A-WP01-INS-DTS-0021 | DATA SHEETS FOR POSITION LIMIT SWITCHES- WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 15-Sep-2026 16:47:06 | zm167dc@jutal.com | 15-Sep-2026 17:28:37 | Jumpol Sudjitjul | 24-Sep-2026 |  | Payut Phatdamrongdet | 25-Sep-2026 | 18-Sep-2026 08:44:46 | Pornlert Wanaphattharaphan | 28-Sep-2026 | 20-Sep-2026 00:34:40 | APPR | Approved | Jumpol Sudjitjul | 29-Sep-2026 | 20-Sep-2026 15:40:37 | 20-Sep-2026 09:39:00 | 0 |  |  | Approver | Locate
AO-000757 | MM-ASK-1A-WP01-INS-DTS-0022 | DATA SHEETS FOR PIG SIGNALLER - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 14:35:37 | zm167dc@jutal.com | 22-Jul-2026 15:07:58 | Jumpol Sudjitjul | 03-Aug-2026 | 23-Jul-2026 17:35:46 | Payut Phatdamrongdet | 04-Aug-2026 | 30-Jul-2026 15:47:06 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 30-Jul-2026 18:30:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 30-Jul-2026 19:04:41 | 30-Jul-2026 12:29:51 | 0 |  |  | Approver | Locate
AO-001464 | MM-ASK-1A-WP01-INS-DTS-0022 | DATA SHEETS FOR PIG SIGNALLER - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:47:45 | zm167dc@jutal.com | 18-Sep-2026 17:17:15 | Jumpol Sudjitjul | 29-Sep-2026 |  | Payut Phatdamrongdet | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000466 | MM-ASK-1A-WP01-INS-DWG-0002 | CONTROL SYSTEM BLOCK DIAGRAM FOR-WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 14:46:36 | zm167dc@jutal.com | 12-Jun-2026 15:39:21 | Jumpol Sudjitjul | 22-Jun-2026 | 23-Jun-2026 10:16:24 | Payut Phatdamrongdet | 23-Jun-2026 | 26-Jun-2026 13:38:10 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 08:58:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 28-Jun-2026 09:26:11 | 28-Jun-2026 02:40:09 | 0 |  |  | Approver | Locate
AO-000662 | MM-ASK-1A-WP01-INS-DWG-0002 | CONTROL SYSTEM BLOCK DIAGRAM FOR-WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jul-2026 12:14:55 | zm167dc@jutal.com | 09-Jul-2026 13:20:10 | Jumpol Sudjitjul | 17-Jul-2026 | 28-Jul-2026 09:42:11 | Payut Phatdamrongdet | 20-Jul-2026 | 31-Jul-2026 21:42:06 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 01-Aug-2026 20:36:46 | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 02-Aug-2026 21:00:23 | 02-Aug-2026 14:41:01 | 0 |  |  | Approver | Locate
AO-000967 | MM-ASK-1A-WP01-INS-DWG-0002 | CONTROL SYSTEM BLOCK DIAGRAM FOR-WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 14:43:21 | zm167dc@jutal.com | 13-Aug-2026 16:31:13 | Jumpol Sudjitjul | 21-Aug-2026 | 28-Aug-2026 12:46:55 | Payut Phatdamrongdet | 24-Aug-2026 | 01-Sep-2026 11:35:05 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 23:09:32 | APPR | Approved | Soontaree Simpitak | 26-Aug-2026 | 03-Sep-2026 07:46:27 | 03-Sep-2026 00:55:22 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WP01-INS-DWG-0003 | INSTRUMENT CABLE BLOCK DIAGRAM PCS/ESD/FGS-WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 12:05:51 | zm167dc@jutal.com | 12-Jun-2026 12:51:24 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 22-Jun-2026 16:56:38 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:55:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 09:47:39 | 25-Jun-2026 03:29:15 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-WP01-INS-DWG-0003 | INSTRUMENT CABLE BLOCK DIAGRAM PCS/ESD/FGS-WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | Issued for Approval | Issued for Approval |  | 10-Jul-2026 16:52:33 | zm167dc@jutal.com | 10-Jul-2026 17:45:38 | Jumpol Sudjitjul | 22-Jun-2026 | 14-Jul-2026 11:24:34 | Payut Phatdamrongdet | 23-Jun-2026 | 31-Jul-2026 21:53:36 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 02-Aug-2026 08:04:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 02-Aug-2026 21:03:43 | 25-Jun-2026 03:29:15 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-WP01-INS-DWG-0003 | INSTRUMENT CABLE BLOCK DIAGRAM PCS/ESD/FGS-WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  |  | zm167dc@jutal.com |  |  | 21-Jul-2026 |  | Payut Phatdamrongdet | 22-Jul-2026 |  | Pornlert Wanaphattharaphan | 23-Jul-2026 |  | APPR | Approved |  | 24-Jul-2026 |  | 02-Aug-2026 14:29:51 | 0 |  |  | Approver | Locate
AO-001295 | MM-ASK-1A-WP01-INS-DWG-0005 | INSTRUMENT MULTI CABLE TRANSIT SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Sep-2026 18:04:44 | zm167dc@jutal.com | 10-Sep-2026 19:54:58 | Jumpol Sudjitjul | 21-Sep-2026 |  | Payut Phatdamrongdet | 22-Sep-2026 | 11-Sep-2026 18:37:56 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 12-Sep-2026 15:03:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 12-Sep-2026 19:51:02 | 12-Sep-2026 13:19:57 | 0 |  |  | Approver | Locate
AO-000625 | MM-ASK-1A-WP01-INS-DWG-0007 | INSTRUMENT HOOK-UP DRAWINGS- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:37:15 | zm167dc@jutal.com | 03-Jul-2026 19:06:22 | Jumpol Sudjitjul | 14-Jul-2026 | 14-Jul-2026 10:46:04 | Payut Phatdamrongdet | 15-Jul-2026 | 30-Jul-2026 15:22:38 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 30-Jul-2026 17:37:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 30-Jul-2026 19:05:45 | 30-Jul-2026 12:31:13 | 0 |  |  | Approver | Locate
AO-000620 | MM-ASK-1A-WP01-INS-LAY-0001 | INSTRUMENT CABLE TRAY LAYOUT- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:13:01 | zm167dc@jutal.com | 03-Jul-2026 18:26:19 | Jumpol Sudjitjul | 14-Jul-2026 | 14-Jul-2026 10:39:31 | Payut Phatdamrongdet | 15-Jul-2026 | 27-Jul-2026 11:19:39 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 28-Jul-2026 21:57:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 30-Jul-2026 08:47:11 | 30-Jul-2026 02:10:24 | 0 |  |  | Approver | Locate
AO-000773 | MM-ASK-1A-WP01-INS-LAY-0002 | INSTRUMENT CABLE ROUTING PLAN AND JUNCTION BOXES LAYOUT- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:07:43 | zm167dc@jutal.com | 26-Jul-2026 22:50:24 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:39:00 | Payut Phatdamrongdet | 07-Aug-2026 | 10-Aug-2026 15:29:01 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:01:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 08:42:22 | 13-Aug-2026 02:53:17 | 0 |  |  | Approver | Locate
AO-000616 | MM-ASK-1A-WP01-INS-LAY-0003 | INSTRUMENT TUBING TRAY LAYOUT - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:13:26 | zm167dc@jutal.com | 03-Jul-2026 18:26:37 | Jumpol Sudjitjul | 14-Jul-2026 | 14-Jul-2026 10:40:05 | Payut Phatdamrongdet | 15-Jul-2026 | 27-Jul-2026 11:19:52 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 28-Jul-2026 22:04:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 30-Jul-2026 08:45:38 | 30-Jul-2026 02:09:02 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-WP01-INS-LAY-0004 | INSTRUMENT LOCATION PLAN- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:08:47 | zm167dc@jutal.com | 13-Jun-2026 08:19:15 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 22-Jun-2026 16:05:30 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:41:42 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 09:51:15 | 25-Jun-2026 03:44:04 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-WP01-INS-LAY-0004 | INSTRUMENT LOCATION PLAN- WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 19:45:17 | zm167dc@jutal.com | 11-Sep-2026 20:37:47 | Jumpol Sudjitjul | 22-Sep-2026 |  | Payut Phatdamrongdet | 23-Sep-2026 | 18-Sep-2026 11:06:44 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:31:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 15:38:58 | 20-Sep-2026 09:11:31 | 0 |  |  | Approver | Locate
AO-000734 | MM-ASK-1A-WP01-INS-LAY-0005 | FUSIBLE PLUG AND F&G LAYOUT- WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 12:10:44 | zm167dc@jutal.com | 20-Jul-2026 12:52:01 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:33:55 | Payut Phatdamrongdet | 31-Jul-2026 | 10-Aug-2026 13:55:38 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 12-Aug-2026 00:21:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 13-Aug-2026 08:44:33 | 13-Aug-2026 02:54:37 | 0 |  |  | Approver | Locate
AO-000315 | MM-ASK-1A-WP01-INS-LIS-0002 | INSTRUMENT INDEX-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:41:42 | zm167dc@jutal.com | 23-May-2026 09:10:50 | Jumpol Sudjitjul | 02-Jun-2026 | 02-Jun-2026 15:38:51 | Payut Phatdamrongdet | 04-Jun-2026 | 08-Jun-2026 16:20:45 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:14:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:20:07 | 11-Jun-2026 09:38:26 | 0 |  |  | Approver | Locate
AO-000508 | MM-ASK-1A-WP01-INS-LIS-0002 | INSTRUMENT INDEX-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 19-Jun-2026 10:32:12 | zm167dc@jutal.com | 19-Jun-2026 10:37:00 | Jumpol Sudjitjul | 29-Jun-2026 | 29-Jun-2026 13:35:07 | Payut Phatdamrongdet | 30-Jun-2026 | 30-Jun-2026 10:07:20 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 00:08:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 10:52:44 | 02-Jul-2026 04:40:32 | 0 |  |  | Approver | Locate
AO-000900 | MM-ASK-1A-WP01-INS-LIS-0002 | INSTRUMENT INDEX-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:51:47 | zm167dc@jutal.com | 07-Aug-2026 10:46:49 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:11:53 | Payut Phatdamrongdet | 19-Aug-2026 | 24-Aug-2026 14:57:47 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 26-Aug-2026 00:22:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 26-Aug-2026 08:52:38 | 26-Aug-2026 02:40:06 | 0 |  |  | Approver | Locate
AO-000316 | MM-ASK-1A-WP01-INS-LIS-0003 | PLC INPUT/OUTPUT LIST-WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:42:04 | zm167dc@jutal.com | 23-May-2026 09:11:02 | Jumpol Sudjitjul | 02-Jun-2026 | 02-Jun-2026 16:07:14 | Payut Phatdamrongdet | 04-Jun-2026 | 08-Jun-2026 16:23:49 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:15:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:26:24 | 11-Jun-2026 09:39:33 | 0 |  |  | Approver | Locate
AO-000508 | MM-ASK-1A-WP01-INS-LIS-0003 | PLC INPUT/OUTPUT LIST-WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 19-Jun-2026 10:32:39 | zm167dc@jutal.com | 19-Jun-2026 10:37:16 | Jumpol Sudjitjul | 29-Jun-2026 | 29-Jun-2026 13:49:24 | Payut Phatdamrongdet | 30-Jun-2026 | 30-Jun-2026 10:10:09 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 00:11:27 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 10:53:51 | 02-Jul-2026 04:41:44 | 0 |  |  | Approver | Locate
AO-000900 | MM-ASK-1A-WP01-INS-LIS-0003 | PLC INPUT/OUTPUT LIST-WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:52:14 | zm167dc@jutal.com | 07-Aug-2026 10:47:14 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:12:12 | Payut Phatdamrongdet | 19-Aug-2026 | 24-Aug-2026 14:58:33 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 27-Aug-2026 14:23:15 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 27-Aug-2026 15:42:49 | 27-Aug-2026 10:14:20 | 0 |  |  | Approver | Locate
AO-001068 | MM-ASK-1A-WP01-INS-LIS-0004 | INSTRUMENT CABLE SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 18:39:13 | zm167dc@jutal.com | 24-Aug-2026 18:34:24 | Jumpol Sudjitjul | 02-Sep-2026 |  | Payut Phatdamrongdet | 03-Sep-2026 | 26-Aug-2026 12:52:23 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 22:03:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 13:41:12 | 31-Aug-2026 07:10:39 | 0 |  |  | Approver | Locate
AO-000794 | MM-ASK-1A-WP01-INS-LIS-0005 | INSTRUMENT TUBING SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 26-Jul-2026 22:33:48 | zm167dc@jutal.com | 27-Jul-2026 15:39:55 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:56:41 | Payut Phatdamrongdet | 07-Aug-2026 | 17-Aug-2026 09:40:39 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 17-Aug-2026 21:51:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 18-Aug-2026 08:09:33 | 18-Aug-2026 01:38:22 | 0 |  |  | Approver | Locate
AO-001100 | MM-ASK-1A-WP01-INS-LIS-0006 | INSTRUMENT EQUIPMENT AND EXPLOSION PROOF EQUIPMENT SCHEDULE- WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 26-Aug-2026 19:17:34 | zm167dc@jutal.com | 27-Aug-2026 11:33:34 | Jumpol Sudjitjul | 04-Sep-2026 |  | Payut Phatdamrongdet | 07-Sep-2026 | 27-Aug-2026 14:12:51 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 30-Aug-2026 22:12:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 31-Aug-2026 13:41:41 | 31-Aug-2026 07:01:43 | 0 |  |  | Approver | Locate
AO-000530 | MM-ASK-1A-WP01-INS-WIR-0001 | INSTRUMENT WIRING DIAGRAMS - WP01 (PCS ) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-Jun-2026 10:39:42 | zm167dc@jutal.com | 23-Jun-2026 12:57:04 | Jumpol Sudjitjul | 01-Jul-2026 | 03-Jul-2026 14:23:40 | Payut Phatdamrongdet | 02-Jul-2026 | 07-Jul-2026 08:01:24 | Pornlert Wanaphattharaphan | 03-Jul-2026 | 08-Jul-2026 00:41:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Jul-2026 | 08-Jul-2026 08:52:38 | 08-Jul-2026 02:34:21 | 0 |  |  | Approver | Locate
AO-000799 | MM-ASK-1A-WP01-INS-WIR-0001 | INSTRUMENT WIRING DIAGRAMS - WP01 (PCS ) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 26-Jul-2026 22:34:17 | zm167dc@jutal.com | 27-Jul-2026 15:41:08 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:57:26 | Payut Phatdamrongdet | 07-Aug-2026 | 17-Aug-2026 10:18:02 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 20-Aug-2026 16:25:43 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 20-Aug-2026 19:45:45 | 20-Aug-2026 13:13:42 | 0 |  |  | Approver | Locate
AO-001100 | MM-ASK-1A-WP01-INS-WIR-0001 | INSTRUMENT WIRING DIAGRAMS - WP01 (PCS ) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:18:04 | zm167dc@jutal.com | 27-Aug-2026 11:37:25 | Jumpol Sudjitjul | 04-Sep-2026 |  | Payut Phatdamrongdet | 07-Sep-2026 | 27-Aug-2026 14:00:14 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 30-Aug-2026 22:19:55 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 31-Aug-2026 13:42:16 | 31-Aug-2026 07:03:00 | 0 |  |  | Approver | Locate
AO-000546 | MM-ASK-1A-WP01-INS-WIR-0002 | INSTRUMENT WIRING DIAGRAMS - WP01 (SIS/FGS SYSTEM) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 25-Jun-2026 14:22:49 | zm167dc@jutal.com | 25-Jun-2026 15:23:09 | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 14:44:29 | Payut Phatdamrongdet | 06-Jul-2026 | 27-Jul-2026 10:59:18 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 28-Jul-2026 21:21:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jul-2026 | 30-Jul-2026 08:50:59 | 30-Jul-2026 02:17:05 | 0 |  |  | Approver | Locate
AO-000900 | MM-ASK-1A-WP01-INS-WIR-0002 | INSTRUMENT WIRING DIAGRAMS - WP01 (SIS/FGS SYSTEM) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:52:43 | zm167dc@jutal.com | 07-Aug-2026 10:20:36 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:11:21 | Payut Phatdamrongdet | 19-Aug-2026 | 24-Aug-2026 14:40:41 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 25-Aug-2026 22:38:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 26-Aug-2026 08:47:53 | 26-Aug-2026 02:15:15 | 0 |  |  | Approver | Locate
AO-001150 | MM-ASK-1A-WP01-INS-WIR-0002 | INSTRUMENT WIRING DIAGRAMS - WP01 (SIS/FGS SYSTEM) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:21:41 | zm167dc@jutal.com | 02-Sep-2026 21:27:42 | Soontaree Simpitak | 11-Sep-2026 |  | Payut Phatdamrongdet | 14-Sep-2026 | 04-Sep-2026 10:54:03 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 06-Sep-2026 22:18:16 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 07-Sep-2026 09:51:54 | 07-Sep-2026 03:04:21 | 0 |  |  | Approver | Locate
AO-000124 | MM-ASK-1A-WP01-MEC-DTS-0001 | WP01 MECHANICAL DATASHEET FOR TEST SEPARATOR (V-01001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 15:43:23 | zm167dc@jutal.com | 05-May-2026 16:39:43 | Jumpol Sudjitjul | 13-May-2026 | 08-May-2026 11:21:10 | Thanapat Sombatwattana | 14-May-2026 | 19-May-2026 10:52:23 | Pornlert Wanaphattharaphan | 15-May-2026 | 19-May-2026 22:15:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 09:14:44 | 20-May-2026 09:44:30 | 0 |  |  | Approver | Locate
AO-000419 | MM-ASK-1A-WP01-MEC-DTS-0001 | WP01 MECHANICAL DATASHEET FOR TEST SEPARATOR (V-01001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 17:55:31 | zm167dc@jutal.com | 05-Jun-2026 19:53:15 | Jumpol Sudjitjul | 16-Jun-2026 | 12-Jun-2026 15:41:45 | Thanapat Sombatwattana | 17-Jun-2026 | 17-Jun-2026 16:58:56 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 20:56:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 10:30:55 | 22-Jun-2026 04:42:11 | 0 |  |  | Approver | Locate
AO-000670 | MM-ASK-1A-WP01-MEC-DTS-0001 | WP01 MECHANICAL DATASHEET FOR TEST SEPARATOR (V-01001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 14:43:49 | zm167dc@jutal.com | 10-Jul-2026 16:29:48 | Jumpol Sudjitjul | 20-Jul-2026 | 14-Jul-2026 13:53:23 | Thanapat Sombatwattana | 21-Jul-2026 | 17-Jul-2026 13:46:22 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 19-Jul-2026 17:12:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:38:18 | 20-Jul-2026 04:39:22 | 0 |  |  | Approver | Locate
AO-000771 | MM-ASK-1A-WP01-MEC-DTS-0001 | WP01 MECHANICAL DATASHEET FOR TEST SEPARATOR (V-01001) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 14:59:32 | zm167dc@jutal.com | 26-Jul-2026 23:09:03 | Jumpol Sudjitjul | 06-Aug-2026 | 05-Aug-2026 23:25:56 | Thanapat Sombatwattana | 07-Aug-2026 | 06-Aug-2026 16:21:23 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:46:54 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:30:57 | 10-Aug-2026 06:25:26 | 0 |  |  | Approver | Locate
AO-000161 | MM-ASK-1A-WP01-MEC-DTS-0003 | WP01 MECHANICAL DATASHEET FOR CORROSION INHIBITOR INJECTION PUMP PACKAGE SK-09001 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:34:39 | zm167dc@jutal.com | 08-May-2026 13:51:31 | Jumpol Sudjitjul | 18-May-2026 | 18-May-2026 21:47:43 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 08:55:57 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 11:06:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 15:08:25 | 24-May-2026 15:27:18 | 0 |  |  | Approver | Locate
AO-000445 | MM-ASK-1A-WP01-MEC-DTS-0003 | WP01 MECHANICAL DATASHEET FOR CORROSION INHIBITOR INJECTION PUMP PACKAGE SK-09001 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 11:29:16 | zm167dc@jutal.com | 11-Jun-2026 12:47:37 | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 13:01:29 | Thanapat Sombatwattana | 22-Jun-2026 | 23-Jun-2026 15:48:14 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 24-Jun-2026 22:25:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 25-Jun-2026 09:52:00 | 25-Jun-2026 03:30:52 | 0 |  |  | Approver | Locate
AO-000648 | MM-ASK-1A-WP01-MEC-DTS-0003 | WP01 MECHANICAL DATASHEET FOR CORROSION INHIBITOR INJECTION PUMP PACKAGE SK-09001 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Jul-2026 16:49:09 | zm167dc@jutal.com | 07-Jul-2026 18:33:59 | Jumpol Sudjitjul | 16-Jul-2026 | 16-Jul-2026 11:47:46 | Thanapat Sombatwattana | 17-Jul-2026 | 16-Jul-2026 14:56:30 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 17-Jul-2026 00:10:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 17-Jul-2026 08:52:58 | 17-Jul-2026 02:49:13 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-MEC-DTS-0003 | WP01 MECHANICAL DATASHEET FOR CORROSION INHIBITOR INJECTION PUMP PACKAGE SK-09001 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 15:00:06 | zm167dc@jutal.com | 26-Jul-2026 23:09:23 | Jumpol Sudjitjul | 06-Aug-2026 | 05-Aug-2026 23:26:00 | Thanapat Sombatwattana | 07-Aug-2026 | 06-Aug-2026 16:34:03 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 11:04:40 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:41:05 | 10-Aug-2026 06:26:59 | 0 |  |  | Approver | Locate
AO-000167 | MM-ASK-1A-WP01-MEC-DTS-0005 | WP01 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP VESSEL (V-05001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 15:43:24 | zm167dc@jutal.com | 08-May-2026 17:16:14 | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 15:37:58 | Thanapat Sombatwattana | 20-May-2026 | 20-May-2026 11:18:20 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 08:11:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 27-May-2026 09:01:13 | 27-May-2026 02:30:07 | 0 |  |  | Approver | Locate
AO-000421 | MM-ASK-1A-WP01-MEC-DTS-0005 | WP01 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP VESSEL (V-05001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 17:55:59 | zm167dc@jutal.com | 05-Jun-2026 19:54:54 | Jumpol Sudjitjul | 16-Jun-2026 | 21-Jun-2026 10:41:17 | Thanapat Sombatwattana | 17-Jun-2026 | 23-Jun-2026 08:48:42 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 24-Jun-2026 00:48:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 24-Jun-2026 08:04:03 | 24-Jun-2026 01:18:47 | 0 |  |  | Approver | Locate
AO-000693 | MM-ASK-1A-WP01-MEC-DTS-0005 | WP01 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP VESSEL (V-05001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 14-Jul-2026 08:37:23 | zm167dc@jutal.com | 14-Jul-2026 08:57:46 | Jumpol Sudjitjul | 22-Jul-2026 | 17-Jul-2026 09:34:29 | Thanapat Sombatwattana | 23-Jul-2026 | 17-Jul-2026 14:32:27 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 19-Jul-2026 17:14:33 | APPR | Approved | Jumpol Sudjitjul | 27-Jul-2026 | 20-Jul-2026 09:36:48 | 20-Jul-2026 04:15:43 | 0 |  |  | Approver | Locate
AO-000187 | MM-ASK-1A-WP01-MEC-DTS-0006 | WP01 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP PUMP (P-05001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 10-May-2026 23:36:56 | zm167dc@jutal.com | 11-May-2026 09:18:26 | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 15:41:28 | Thanapat Sombatwattana | 20-May-2026 | 22-May-2026 07:49:25 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 22:12:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 28-May-2026 09:09:09 | 28-May-2026 09:39:51 | 0 |  |  | Approver | Locate
AO-000444 | MM-ASK-1A-WP01-MEC-DTS-0006 | WP01 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP PUMP (P-05001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 11:29:52 | zm167dc@jutal.com | 11-Jun-2026 12:44:56 | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 12:31:46 | Thanapat Sombatwattana | 22-Jun-2026 | 23-Jun-2026 13:03:33 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 24-Jun-2026 22:23:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 25-Jun-2026 09:52:54 | 25-Jun-2026 03:32:23 | 0 |  |  | Approver | Locate
AO-000714 | MM-ASK-1A-WP01-MEC-DTS-0006 | WP01 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP PUMP (P-05001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 12:37:40 | zm167dc@jutal.com | 17-Jul-2026 12:53:27 | Jumpol Sudjitjul | 27-Jul-2026 | 18-Jul-2026 07:35:55 | Thanapat Sombatwattana | 30-Jul-2026 | 22-Jul-2026 17:26:19 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:12:50 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:09:09 | 27-Jul-2026 03:31:05 | 0 |  |  | Approver | Locate
AO-000953 | MM-ASK-1A-WP01-MEC-DTS-0008 | WP01 MECHANICAL DATASHEET FOR BIOCIDE INJECTION PUMPS PACKAGE (SK-09002) (PROVISION FOR FUTURE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-Aug-2026 17:30:43 | zm167dc@jutal.com | 11-Aug-2026 17:40:21 | Jumpol Sudjitjul | 21-Aug-2026 | 25-Aug-2026 13:32:20 | Thanapat Sombatwattana | 24-Aug-2026 | 28-Aug-2026 15:55:10 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 29-Aug-2026 17:29:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 30-Aug-2026 15:40:30 | 30-Aug-2026 08:52:28 | 0 |  |  | Approver | Locate
AO-001322 | MM-ASK-1A-WP01-MEC-DTS-0008 | WP01 MECHANICAL DATASHEET FOR BIOCIDE INJECTION PUMPS PACKAGE (SK-09002) (PROVISION FOR FUTURE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:47:16 | zm167dc@jutal.com | 11-Sep-2026 20:38:53 | Jumpol Sudjitjul | 22-Sep-2026 | 20-Sep-2026 10:38:39 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000230 | MM-ASK-1A-WP01-MEC-LIS-0001 | WP01 MECHANICAL EQUIPMENT LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 16:14:12 | zm167dc@jutal.com | 14-May-2026 16:25:26 | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 09:28:44 | Thanapat Sombatwattana | 25-May-2026 | 27-May-2026 06:39:53 | Pornlert Wanaphattharaphan | 26-May-2026 | 01-Jun-2026 01:09:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-May-2026 | 01-Jun-2026 09:24:06 | 01-Jun-2026 03:02:29 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-WP01-MEC-LIS-0001 | WP01 MECHANICAL EQUIPMENT LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 21:15:35 | zm167dc@jutal.com | 17-Jul-2026 22:09:39 | Jumpol Sudjitjul | 30-Jul-2026 | 30-Jul-2026 07:57:40 | Thanapat Sombatwattana | 31-Jul-2026 | 05-Aug-2026 17:11:16 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 05-Aug-2026 20:56:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 06-Aug-2026 08:43:11 | 06-Aug-2026 02:44:25 | 0 |  |  | Approver | Locate
AO-001071 | MM-ASK-1A-WP01-MEC-LIS-0001 | WP01 MECHANICAL EQUIPMENT LIST |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | MEC | Mechanical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:41:54 | zm167dc@jutal.com | 24-Aug-2026 18:36:39 | Jumpol Sudjitjul | 02-Sep-2026 | 07-Sep-2026 16:23:03 | Thanapat Sombatwattana | 03-Sep-2026 | 07-Sep-2026 16:37:09 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 22:12:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 08-Sep-2026 12:54:55 | 08-Sep-2026 06:35:16 | 0 |  |  | Approver | Locate
AO-001348 | MM-ASK-1A-WP01-PIP-CAL-0001 | WP01 PIPING STRESS ANALYSIS REPORT (FLOWLINE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 14-Sep-2026 09:01:28 | zm167dc@jutal.com | 15-Sep-2026 13:41:40 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001468 | MM-ASK-1A-WP01-PIP-CAL-0002 | WP01 PIPING STRESS ANALYSIS REPORT (PIG LAUNCHER/RECEIVER) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 18-Sep-2026 14:47:59 | zm167dc@jutal.com | 18-Sep-2026 17:54:59 | Jumpol Sudjitjul | 29-Sep-2026 |  | Thanapat Sombatwattana | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001351 | MM-ASK-1A-WP01-PIP-CAL-0003 | WP01 PIPING STRESS ANALYSIS REPORT (OTHER GC LINES, IG LINES, AND HP VENT) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 14-Sep-2026 09:02:08 | zm167dc@jutal.com | 15-Sep-2026 13:42:28 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001492 | MM-ASK-1A-WP01-PIP-CAL-0004 | WP01 PIPING STRESS ANALYSIS REPORT (LP VENT AND DP LINES LEVEL 2) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 18-Sep-2026 20:14:09 | zm167dc@jutal.com | 20-Sep-2026 14:18:49 | Jumpol Sudjitjul | 28-Sep-2026 |  | Thanapat Sombatwattana | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001500 | MM-ASK-1A-WP01-PIP-ISO-0001 | WP01 PIPING ISOMETRIC DRAWINGS (LARGE BORE) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | ISO | Piping, Pipeline Isometric Drawing | 0 | In Review | IFR | Issued for Review |  | 18-Sep-2026 20:14:39 | zm167dc@jutal.com | 20-Sep-2026 14:19:58 | Jumpol Sudjitjul | 28-Sep-2026 |  | Thanapat Sombatwattana | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0001 | WP01 EQUIPMENT LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:38:53 | zm167dc@jutal.com | 08-May-2026 12:48:12 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 17:04:16 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 00:04:56 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 10:06:36 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 15:09:17 | 24-May-2026 08:34:35 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0001 | WP01 EQUIPMENT LAYOUT DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:20:54 | zm167dc@jutal.com | 12-Jul-2026 11:47:27 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:35:53 | Thanapat Sombatwattana | 21-Jul-2026 | 20-Jul-2026 11:58:56 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 22-Jul-2026 23:02:35 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 23-Jul-2026 13:13:03 | 23-Jul-2026 06:25:27 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0001 | WP01 EQUIPMENT LAYOUT DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:03:22 | zm167dc@jutal.com | 15-Sep-2026 08:37:27 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0002 | WP01 EQUIPMENT LAYOUT DRAWING UPPER DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:39:34 | zm167dc@jutal.com | 08-May-2026 12:48:56 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 17:04:35 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 01:05:33 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 10:19:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 15:10:05 | 24-May-2026 08:35:37 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0002 | WP01 EQUIPMENT LAYOUT DRAWING UPPER DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:21:23 | zm167dc@jutal.com | 12-Jul-2026 11:47:30 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:37:16 | Thanapat Sombatwattana | 21-Jul-2026 | 24-Jul-2026 11:45:07 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 02:28:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 10:11:18 | 27-Jul-2026 03:24:06 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0002 | WP01 EQUIPMENT LAYOUT DRAWING UPPER DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:04:03 | zm167dc@jutal.com | 15-Sep-2026 08:37:27 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0003 | WP01 EQUIPMENT LAYOUT DRAWING MEZZANINE DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:40:02 | zm167dc@jutal.com | 08-May-2026 12:49:17 | Jumpol Sudjitjul | 18-May-2026 | 13-May-2026 14:03:20 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 01:09:55 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 10:23:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 15:11:03 | 24-May-2026 08:36:39 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0003 | WP01 EQUIPMENT LAYOUT DRAWING MEZZANINE DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:21:52 | zm167dc@jutal.com | 12-Jul-2026 11:47:30 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:39:08 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 17:41:30 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:02:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:23:34 | 24-Jul-2026 04:19:14 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0003 | WP01 EQUIPMENT LAYOUT DRAWING MEZZANINE DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:04:41 | zm167dc@jutal.com | 15-Sep-2026 08:37:26 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0004 | WP01 EQUIPMENT LAYOUT DRAWING LOWER DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:40:32 | zm167dc@jutal.com | 08-May-2026 12:49:42 | Jumpol Sudjitjul | 18-May-2026 | 13-May-2026 14:07:15 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 01:27:33 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 10:30:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 15:07:35 | 24-May-2026 08:33:37 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0004 | WP01 EQUIPMENT LAYOUT DRAWING LOWER DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:22:21 | zm167dc@jutal.com | 12-Jul-2026 11:47:32 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:42:02 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 17:41:21 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:02:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:27:37 | 24-Jul-2026 04:20:37 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0004 | WP01 EQUIPMENT LAYOUT DRAWING LOWER DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:05:19 | zm167dc@jutal.com | 15-Sep-2026 08:37:28 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0005 | WP01 EQUIPMENT LAYOUT DRAWING SUMP DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:41:00 | zm167dc@jutal.com | 08-May-2026 12:54:41 | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 09:45:42 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 09:46:43 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 17:10:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 19:56:22 | 24-May-2026 13:34:45 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0005 | WP01 EQUIPMENT LAYOUT DRAWING SUMP DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:22:47 | zm167dc@jutal.com | 12-Jul-2026 11:47:33 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:43:47 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:06:53 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:09:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:28:11 | 24-Jul-2026 04:22:00 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0005 | WP01 EQUIPMENT LAYOUT DRAWING SUMP DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:05:46 | zm167dc@jutal.com | 15-Sep-2026 08:37:27 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0006 | WP01 EQUIPMENT LAYOUT DRAWING BOAT LANDING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:41:25 | zm167dc@jutal.com | 08-May-2026 12:55:01 | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 09:47:34 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 09:58:32 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 17:12:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:03:46 | 24-May-2026 13:36:39 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0006 | WP01 EQUIPMENT LAYOUT DRAWING BOAT LANDING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:23:14 | zm167dc@jutal.com | 12-Jul-2026 11:47:32 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:45:15 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 17:41:09 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 22-Jul-2026 23:08:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 23-Jul-2026 13:13:54 | 23-Jul-2026 06:54:51 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0006 | WP01 EQUIPMENT LAYOUT DRAWING BOAT LANDING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:06:14 | zm167dc@jutal.com | 15-Sep-2026 08:37:27 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0007 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:41:54 | zm167dc@jutal.com | 08-May-2026 12:55:21 | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 10:01:05 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 10:50:41 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 17:14:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:04:48 | 24-May-2026 13:37:38 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0007 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:23:41 | zm167dc@jutal.com | 12-Jul-2026 11:47:32 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:46:35 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:36:11 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:13:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:28:43 | 24-Jul-2026 04:23:20 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0007 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:06:44 | zm167dc@jutal.com | 15-Sep-2026 08:37:30 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0008 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:42:22 | zm167dc@jutal.com | 08-May-2026 12:55:38 | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 10:02:10 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 10:51:13 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 17:18:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:06:11 | 24-May-2026 13:38:39 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0008 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:24:07 | zm167dc@jutal.com | 12-Jul-2026 11:47:32 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:48:23 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:43:28 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:14:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:32:24 | 24-Jul-2026 04:24:42 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0008 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:07:20 | zm167dc@jutal.com | 15-Sep-2026 08:37:32 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0009 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:43:10 | zm167dc@jutal.com | 08-May-2026 12:59:14 | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 10:10:23 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 10:52:20 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 17:22:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:07:36 | 24-May-2026 13:39:41 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0009 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:24:34 | zm167dc@jutal.com | 12-Jul-2026 11:47:31 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:50:48 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:39:28 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:13:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:32:52 | 24-Jul-2026 04:26:04 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0009 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:07:52 | zm167dc@jutal.com | 15-Sep-2026 08:37:28 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP01-PIP-LAY-0010 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:43:42 | zm167dc@jutal.com | 08-May-2026 12:59:33 | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 10:12:22 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 10:52:56 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 17:25:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:09:24 | 24-May-2026 13:40:42 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-0010 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:25:00 | zm167dc@jutal.com | 12-Jul-2026 11:47:32 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:53:39 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:47:21 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:16:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:33:24 | 24-Jul-2026 04:27:26 | 0 |  |  | Approver | Locate
AO-001345 | MM-ASK-1A-WP01-PIP-LAY-0010 | WP01 EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:08:24 | zm167dc@jutal.com | 15-Sep-2026 08:37:30 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP01-PIP-LAY-1001 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT WELL CLEANUP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:29:25 | zm167dc@jutal.com | 08-May-2026 13:36:32 | Jumpol Sudjitjul | 18-May-2026 | 13-May-2026 14:47:14 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 09:32:13 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 16:44:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:11:31 | 24-May-2026 13:47:48 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-1001 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT WELL CLEANUP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:25:29 | zm167dc@jutal.com | 12-Jul-2026 11:47:36 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:42:06 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:12:13 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:10:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:33:52 | 24-Jul-2026 04:28:50 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP01-PIP-LAY-1001 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT WELL CLEANUP |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:08:55 | zm167dc@jutal.com | 15-Sep-2026 08:47:41 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP01-PIP-LAY-1002 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT ACID STIMULATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:29:54 | zm167dc@jutal.com | 08-May-2026 13:37:18 | Jumpol Sudjitjul | 18-May-2026 | 13-May-2026 14:50:00 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 09:32:44 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 16:50:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:13:21 | 24-May-2026 13:49:51 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-1002 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT ACID STIMULATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:25:55 | zm167dc@jutal.com | 12-Jul-2026 11:47:32 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:43:50 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:19:11 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:12:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:34:29 | 24-Jul-2026 04:30:19 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP01-PIP-LAY-1002 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT ACID STIMULATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:09:24 | zm167dc@jutal.com | 15-Sep-2026 08:48:05 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP01-PIP-LAY-1003 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT LIGHT WELL INTERVENTION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:30:22 | zm167dc@jutal.com | 08-May-2026 13:37:44 | Jumpol Sudjitjul | 18-May-2026 | 13-May-2026 14:53:07 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 09:33:07 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 16:53:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:12:26 | 24-May-2026 13:48:52 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-1003 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT LIGHT WELL INTERVENTION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:26:21 | zm167dc@jutal.com | 12-Jul-2026 11:47:34 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:45:31 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:16:22 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:11:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:37:22 | 24-Jul-2026 04:31:42 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP01-PIP-LAY-1003 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT LIGHT WELL INTERVENTION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:09:52 | zm167dc@jutal.com | 15-Sep-2026 08:48:35 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP01-PIP-LAY-1004 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT COILED TUBING CAMPAIGN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:30:49 | zm167dc@jutal.com | 08-May-2026 13:38:06 | Jumpol Sudjitjul | 18-May-2026 | 13-May-2026 14:56:06 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 09:34:18 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 16:59:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:10:31 | 24-May-2026 13:46:45 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-1004 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT COILED TUBING CAMPAIGN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:26:49 | zm167dc@jutal.com | 12-Jul-2026 11:47:36 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:47:05 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:07:04 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:10:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:38:05 | 24-Jul-2026 04:33:04 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP01-PIP-LAY-1004 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT COILED TUBING CAMPAIGN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:10:20 | zm167dc@jutal.com | 15-Sep-2026 08:49:01 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP01-PIP-LAY-1005 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT COILED TUBING CAMPAIGN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:31:16 | zm167dc@jutal.com | 08-May-2026 13:41:50 | Jumpol Sudjitjul | 18-May-2026 | 13-May-2026 15:04:35 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 09:33:40 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 16:56:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 20:02:40 | 24-May-2026 13:44:40 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP01-PIP-LAY-1005 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT COILED TUBING CAMPAIGN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:27:16 | zm167dc@jutal.com | 12-Jul-2026 11:47:36 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:48:36 | Thanapat Sombatwattana | 21-Jul-2026 | 21-Jul-2026 18:21:56 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:12:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:38:30 | 24-Jul-2026 04:34:26 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP01-PIP-LAY-1005 | WP01 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT COILED TUBING CAMPAIGN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:10:52 | zm167dc@jutal.com | 15-Sep-2026 08:49:24 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000333 | MM-ASK-1A-WP01-PIP-MTO-0001 | MATERIAL TAKE-OFF FOR MANUAL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 09:50:14 | zm167dc@jutal.com | 26-May-2026 09:20:40 | Jumpol Sudjitjul | 05-Jun-2026 | 09-Jun-2026 11:14:50 | Thanapat Sombatwattana | 08-Jun-2026 | 10-Jun-2026 00:33:32 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 10-Jun-2026 21:24:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 09:27:49 | 11-Jun-2026 03:19:34 | 0 |  |  | Approver | Locate
AO-000797 | MM-ASK-1A-WP01-PIP-MTO-0001 | MATERIAL TAKE-OFF FOR MANUAL VALVES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 26-Jul-2026 23:50:10 | zm167dc@jutal.com | 27-Jul-2026 09:33:52 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:55:55 | Thanapat Sombatwattana | 07-Aug-2026 | 13-Aug-2026 09:03:00 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 15-Aug-2026 13:36:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 15-Aug-2026 14:31:43 | 15-Aug-2026 08:07:40 | 0 |  |  | Approver | Locate
AO-001061 | MM-ASK-1A-WP01-PIP-MTO-0001 | MATERIAL TAKE-OFF FOR MANUAL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 17:26:51 | zm167dc@jutal.com | 21-Aug-2026 17:39:54 | Jumpol Sudjitjul | 01-Sep-2026 | 23-Aug-2026 22:25:54 | Thanapat Sombatwattana | 02-Sep-2026 | 02-Sep-2026 17:04:40 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:48:38 | APPR | Approved | Soontaree Simpitak | 04-Sep-2026 | 03-Sep-2026 07:47:40 | 03-Sep-2026 01:05:23 | 0 |  |  | Approver | Locate
AO-000801 | MM-ASK-1A-WP01-PIP-MTO-0002 | MATERIAL TAKE-OFF FOR PIPING BULK |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 26-Jul-2026 22:31:32 | zm167dc@jutal.com | 27-Jul-2026 09:36:44 | Jumpol Sudjitjul | 06-Aug-2026 |  | Thanapat Sombatwattana | 07-Aug-2026 | 13-Aug-2026 17:28:20 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 15-Aug-2026 13:39:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 15-Aug-2026 14:33:29 | 15-Aug-2026 08:10:15 | 0 |  |  | Approver | Locate
AO-001354 | MM-ASK-1A-WP01-PIP-MTO-0002 | MATERIAL TAKE-OFF FOR PIPING BULK |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PIP | Piping | MTO | Material Take Off | 0 | In Review | IFA | Issued for Approval |  | 14-Sep-2026 09:11:23 | zm167dc@jutal.com | 15-Sep-2026 12:03:18 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000611 | MM-ASK-1A-WP01-PLR-DWG-0007 | WP01 NPS 12 RISER HANGER FLANGE DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 14:13:54 | zm167dc@jutal.com | 03-Jul-2026 14:32:19 | Jumpol Sudjitjul | 13-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:10:20 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:23:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 08:54:12 | 17-Jul-2026 02:26:47 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP01-PLR-DWG-0007 | WP01 NPS 12 RISER HANGER FLANGE DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:44:24 | zm167dc@jutal.com | 07-Aug-2026 10:16:34 | Jumpol Sudjitjul | 18-Aug-2026 |  | Akkarapat Suntornsuttiwat | 19-Aug-2026 | 19-Aug-2026 09:10:52 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:44:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:56:39 | 21-Aug-2026 02:35:50 | 0 |  |  | Approver | Locate
AO-001206 | MM-ASK-1A-WP01-PLR-DWG-0007 | WP01 NPS 12 RISER HANGER FLANGE DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:18:11 | zm167dc@jutal.com | 08-Sep-2026 10:04:49 | Jumpol Sudjitjul | 16-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 17-Sep-2026 10:24:30 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 20-Sep-2026 00:33:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 15:38:12 | 20-Sep-2026 09:08:42 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP01-PLR-DWG-2001 | WP01 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:40:37 | zm167dc@jutal.com | 08-Jun-2026 09:52:41 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 10:53:14 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 13:44:52 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 16:45:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:03:32 | 22-Jun-2026 01:23:15 | 0 |  |  | Approver | Locate
AO-000614 | MM-ASK-1A-WP01-PLR-DWG-2001 | WP01 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:07:51 | zm167dc@jutal.com | 03-Jul-2026 16:19:20 | Jumpol Sudjitjul | 13-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:13:02 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:24:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:01:20 | 17-Jul-2026 02:22:39 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP01-PLR-DWG-2001 | WP01 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:44:53 | zm167dc@jutal.com | 07-Aug-2026 10:16:37 | Jumpol Sudjitjul | 18-Aug-2026 |  | Akkarapat Suntornsuttiwat | 19-Aug-2026 | 19-Aug-2026 09:12:19 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:45:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:58:00 | 21-Aug-2026 02:37:14 | 0 |  |  | Approver | Locate
AO-001207 | MM-ASK-1A-WP01-PLR-DWG-2001 | WP01 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:18:43 | zm167dc@jutal.com | 08-Sep-2026 10:05:30 | Jumpol Sudjitjul | 16-Sep-2026 | 14-Sep-2026 15:51:00 | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 17-Sep-2026 10:26:32 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 20-Sep-2026 00:30:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 15:53:52 | 20-Sep-2026 09:23:32 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP01-PLR-DWG-2002 | WP01 NPS 12 SLIDING CLAMP TYPE 1 DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:41:00 | zm167dc@jutal.com | 08-Jun-2026 09:53:01 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 10:55:13 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 13:46:25 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 16:48:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:04:08 | 22-Jun-2026 01:24:29 | 0 |  |  | Approver | Locate
AO-000614 | MM-ASK-1A-WP01-PLR-DWG-2002 | WP01 NPS 12 SLIDING CLAMP TYPE 1 DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:08:34 | zm167dc@jutal.com | 03-Jul-2026 16:19:33 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 09:05:11 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:14:33 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:25:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:04:14 | 17-Jul-2026 03:57:08 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP01-PLR-DWG-2002 | WP01 NPS 12 SLIDING CLAMP TYPE 1 DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:45:25 | zm167dc@jutal.com | 07-Aug-2026 10:16:30 | Jumpol Sudjitjul | 18-Aug-2026 | 15-Aug-2026 19:23:27 | Akkarapat Suntornsuttiwat | 19-Aug-2026 | 19-Aug-2026 09:12:50 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 07:57:34 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:58:31 | 21-Aug-2026 02:38:28 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP01-PLR-DWG-2003 | WP01 NPS 12 SLIDING CLAMP TYPE 2 DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:41:22 | zm167dc@jutal.com | 08-Jun-2026 09:53:18 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 10:57:05 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 13:48:37 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 16:51:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:05:25 | 22-Jun-2026 01:25:44 | 0 |  |  | Approver | Locate
AO-000614 | MM-ASK-1A-WP01-PLR-DWG-2003 | WP01 NPS 12 SLIDING CLAMP TYPE 2 DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:09:12 | zm167dc@jutal.com | 03-Jul-2026 16:19:36 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 09:06:47 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:16:50 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:25:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:04:52 | 17-Jul-2026 03:58:15 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP01-PLR-DWG-2003 | WP01 NPS 12 SLIDING CLAMP TYPE 2 DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:45:51 | zm167dc@jutal.com | 07-Aug-2026 10:16:32 | Jumpol Sudjitjul | 18-Aug-2026 | 15-Aug-2026 19:25:55 | Akkarapat Suntornsuttiwat | 19-Aug-2026 | 19-Aug-2026 09:14:12 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:41:15 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:25:30 | 24-Aug-2026 06:58:51 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP01-PLR-DWG-2004 | WP01 NPS 12 SLIDING CLAMP TYPE 3 DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:41:45 | zm167dc@jutal.com | 08-Jun-2026 09:53:31 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 11:01:24 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 13:50:54 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 16:56:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:06:14 | 22-Jun-2026 01:27:02 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP01-PLR-DWG-2004 | WP01 NPS 12 SLIDING CLAMP TYPE 3 DRAWING |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | In Review | VOID | Withdrawn or Superseded |  | 03-Jul-2026 18:05:53 | zm167dc@jutal.com | 03-Jul-2026 18:13:26 | Jumpol Sudjitjul |  | 24-Aug-2026 10:18:41 | Akkarapat Suntornsuttiwat |  |  | Pornlert Wanaphattharaphan | [8 empty] | 0 |  |  | For Info | Locate
AO-000767 | MM-ASK-1A-WP01-PLR-DWG-2005 | RISER GENERAL ARRANGEMENT AND DETAIL DRAWINGS AT WP01 - 20" EXPORT RISER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 10:39:53 | zm167dc@jutal.com | 26-Jul-2026 22:06:33 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:01:44 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:43:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:50:40 | 10-Aug-2026 06:22:39 | 0 |  |  | Approver | Locate
AO-001084 | MM-ASK-1A-WP01-PLR-DWG-2005 | RISER GENERAL ARRANGEMENT AND DETAIL DRAWINGS AT WP01 - 20" EXPORT RISER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:21:07 | zm167dc@jutal.com | 24-Aug-2026 20:11:44 | Jumpol Sudjitjul | 02-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 02-Sep-2026 14:50:35 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 22:04:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 09:53:56 | 07-Sep-2026 03:10:22 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-PLR-DWG-2006 | RISER GENERAL ARRANGEMENT AND DETAIL DRAWINGS AT WP01 - 12" PRE-INSTALLED RISER (FOR FUTURE) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 11:31:13 | zm167dc@jutal.com | 26-Jul-2026 22:07:03 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:03:06 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:48:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:27:21 | 10-Aug-2026 06:10:33 | 0 |  |  | Approver | Locate
AO-001084 | MM-ASK-1A-WP01-PLR-DWG-2006 | RISER GENERAL ARRANGEMENT AND DETAIL DRAWINGS AT WP01 - 12" PRE-INSTALLED RISER (FOR FUTURE) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:21:39 | zm167dc@jutal.com | 24-Aug-2026 20:12:18 | Jumpol Sudjitjul | 02-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 02-Sep-2026 14:51:40 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 22:07:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 09:54:42 | 07-Sep-2026 03:11:49 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-PLR-DWG-2007 | RISER GENERAL ARRANGEMENT AND DETAIL DRAWINGS AT WP01 - 12" IMPORT RISER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 11:31:37 | zm167dc@jutal.com | 26-Jul-2026 22:07:19 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:05:38 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:59:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:51:59 | 10-Aug-2026 06:12:15 | 0 |  |  | Approver | Locate
AO-001084 | MM-ASK-1A-WP01-PLR-DWG-2007 | RISER GENERAL ARRANGEMENT AND DETAIL DRAWINGS AT WP01 - 12" IMPORT RISER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:22:09 | zm167dc@jutal.com | 24-Aug-2026 20:12:40 | Jumpol Sudjitjul | 02-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 02-Sep-2026 14:38:08 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 22:07:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 09:55:23 | 07-Sep-2026 03:13:14 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-PLR-DWG-2008 | RISERS ISOMETRIC DRAWINGSAT WP01 - 20" EXPORT RISER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 11:32:05 | zm167dc@jutal.com | 26-Jul-2026 22:13:02 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:06:58 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:34:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 08:43:24 | 13-Aug-2026 02:34:58 | 0 |  |  | Approver | Locate
AO-001084 | MM-ASK-1A-WP01-PLR-DWG-2008 | RISERS ISOMETRIC DRAWINGSAT WP01 - 20" EXPORT RISER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:22:48 | zm167dc@jutal.com | 24-Aug-2026 20:13:03 | Jumpol Sudjitjul | 02-Sep-2026 | 02-Sep-2026 10:09:08 | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 02-Sep-2026 14:39:03 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 22:19:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 09:56:39 | 07-Sep-2026 03:15:34 | 0 |  |  | Approver | Locate
AO-000364 | MM-ASK-1A-WP01-PLR-RPT-2001 | WP01 RISER CLAMP DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 16:06:00 | zm167dc@jutal.com | 29-May-2026 08:20:26 | Jumpol Sudjitjul | 10-Jun-2026 | 10-Jun-2026 00:50:40 | Akkarapat Suntornsuttiwat | 11-Jun-2026 | 11-Jun-2026 08:37:10 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:15:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 09:05:37 | 12-Jun-2026 02:41:25 | 0 |  |  | Approver | Locate
AO-000600 | MM-ASK-1A-WP01-PLR-RPT-2001 | WP01 RISER CLAMP DESIGN REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:19:14 | zm167dc@jutal.com | 03-Jul-2026 13:18:05 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 09:14:06 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 09:16:34 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:31:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:28:46 | 17-Jul-2026 03:28:58 | 0 |  |  | Approver | Locate
AO-000919 | MM-ASK-1A-WP01-PLR-RPT-2001 | WP01 RISER CLAMP DESIGN REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:45:23 | zm167dc@jutal.com | 07-Aug-2026 16:40:55 | Jumpol Sudjitjul | 18-Aug-2026 | 15-Aug-2026 19:29:51 | Akkarapat Suntornsuttiwat | 19-Aug-2026 | 19-Aug-2026 09:18:53 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:42:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:26:17 | 24-Aug-2026 06:53:52 | 0 |  |  | Approver | Locate
AO-000734 | MM-ASK-1A-WP01-PLR-RPT-2003 | WP01 RISER HANGER FLANGE DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 12:08:56 | zm167dc@jutal.com | 20-Jul-2026 13:56:05 | Jumpol Sudjitjul | 30-Jul-2026 | 30-Jul-2026 09:55:57 | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 31-Jul-2026 10:19:19 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 12:35:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 21:05:05 | 02-Aug-2026 14:37:07 | 0 |  |  | Approver | Locate
AO-000977 | MM-ASK-1A-WP01-PLR-RPT-2003 | WP01 RISER HANGER FLANGE DESIGN REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 11:26:41 | zm167dc@jutal.com | 14-Aug-2026 12:48:04 | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:50:01 | Akkarapat Suntornsuttiwat | 25-Aug-2026 | 25-Aug-2026 09:34:22 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:53:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:01:08 | 28-Aug-2026 04:02:38 | 0 |  |  | Approver | Locate
AO-001300 | MM-ASK-1A-WP01-PLR-RPT-2003 | WP01 RISER HANGER FLANGE DESIGN REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | PLR | Pipeline | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 08:48:21 | zm167dc@jutal.com | 11-Sep-2026 19:49:16 | Jumpol Sudjitjul | 22-Sep-2026 | 14-Sep-2026 15:52:48 | Akkarapat Suntornsuttiwat | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP01-PRO-HMB-0001 | HEAT AND MATERIAL BALANCE FOR WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | HMB | Heat And Material Balance | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:44:08 | jumpols@pttep.com | 20-Apr-2026 17:11:28 | Jumpol Sudjitjul | 29-Apr-2026 |  | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 08:44:34 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 18:52:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 03-May-2026 16:10:54 | 03-May-2026 09:14:24 | 0 |  |  | Approver | Locate
AO-000844 | MM-ASK-1A-WP01-PRO-HMB-0001 | HEAT AND MATERIAL BALANCE FOR WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | HMB | Heat And Material Balance | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 22:01:07 | zm167dc@jutal.com | 01-Aug-2026 07:34:15 | Jumpol Sudjitjul | 10-Aug-2026 | 09-Aug-2026 23:59:03 | Naphat Nirotsinlapachai | 11-Aug-2026 | 10-Aug-2026 09:24:36 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 19:30:33 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:49:07 | 13-Aug-2026 02:36:11 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP01-PRO-PFD-0001 | PROCESS FLOW DIAGRAM HYDROCARBON PRODUCTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:44:40 | jumpols@pttep.com | 20-Apr-2026 17:15:30 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:15:21 | Naphat Nirotsinlapachai | 30-Apr-2026 | 29-Apr-2026 19:41:43 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 10:18:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 01-May-2026 10:41:21 | 01-May-2026 11:17:45 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP01-PRO-PFD-0001 | PROCESS FLOW DIAGRAM HYDROCARBON PRODUCTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:07:20 | zm167dc@jutal.com | 15-May-2026 18:33:01 | Jumpol Sudjitjul | 26-May-2026 | 27-May-2026 09:39:27 | Naphat Nirotsinlapachai | 27-May-2026 | 27-May-2026 09:45:42 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 11:42:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:43:38 | 10-Jun-2026 06:55:22 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP01-PRO-PFD-0001 | PROCESS FLOW DIAGRAM HYDROCARBON PRODUCTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:12:28 | zm167dc@jutal.com | 26-Jul-2026 23:15:38 | Jumpol Sudjitjul | 06-Aug-2026 | 05-Aug-2026 23:20:54 | Naphat Nirotsinlapachai | 07-Aug-2026 | 07-Aug-2026 15:36:06 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:45:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 08:47:10 | 13-Aug-2026 02:55:53 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP01-PRO-PID-0001 | PIPING & INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD (API 10000#) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:23:27 | zm167dc@jutal.com | 29-Apr-2026 10:17:06 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:34:14 | Naphat Nirotsinlapachai | 12-May-2026 | 11-May-2026 23:06:11 | Pornlert Wanaphattharaphan | 13-May-2026 | 15-May-2026 01:01:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 15-May-2026 10:11:03 | 15-May-2026 10:45:17 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0001 | PIPING & INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD (API 10000#) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:04:09 | zm167dc@jutal.com | 04-Jun-2026 09:13:27 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:42:04 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:29:14 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:29:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:07:00 | 22-Jun-2026 01:11:46 | 0 |  |  | Approver | Locate
AO-000719 | MM-ASK-1A-WP01-PRO-PID-0001 | PIPING & INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD (API 10000#) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 21:16:04 | zm167dc@jutal.com | 17-Jul-2026 21:55:38 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:18:22 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:56:55 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:06:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:38:20 | 03-Aug-2026 02:49:44 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP01-PRO-PID-0002 | PIPING & INSTRUMENTATION DIAGRAM WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:04:54 | zm167dc@jutal.com | 29-Apr-2026 10:17:53 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:35:10 | Naphat Nirotsinlapachai | 12-May-2026 | 11-May-2026 23:07:31 | Pornlert Wanaphattharaphan | 13-May-2026 | 15-May-2026 23:55:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 17-May-2026 00:02:50 | 17-May-2026 00:16:58 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0002 | PIPING & INSTRUMENTATION DIAGRAM WELLHEAD CONTROL PANEL |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:04:41 | zm167dc@jutal.com | 04-Jun-2026 09:13:25 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:41:34 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:30:18 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:36:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:07:38 | 22-Jun-2026 01:13:05 | 0 |  |  | Approver | Locate
AO-000725 | MM-ASK-1A-WP01-PRO-PID-0002 | PIPING & INSTRUMENTATION DIAGRAM WELLHEAD CONTROL PANEL |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:05:12 | zm167dc@jutal.com | 20-Jul-2026 10:55:58 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:20:39 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:57:18 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:07:55 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:51:24 | 03-Aug-2026 03:30:06 | 0 |  |  | Approver | Locate
AO-000097 | MM-ASK-1A-WP01-PRO-PID-0003 | PIPING & INSTRUMENT DIAGRAM PRODUCTION & TEST MANIFOLDS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:31:13 | zm167dc@jutal.com | 29-Apr-2026 10:18:12 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 14:02:05 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:24:25 | Pornlert Wanaphattharaphan | 13-May-2026 | 17-May-2026 22:41:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 18:59:40 | 18-May-2026 19:08:47 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0003 | PIPING & INSTRUMENT DIAGRAM PRODUCTION & TEST MANIFOLDS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:05:15 | zm167dc@jutal.com | 04-Jun-2026 09:13:24 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:41:04 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:31:14 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:43:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:08:57 | 22-Jun-2026 00:17:59 | 0 |  |  | Approver | Locate
AO-000719 | MM-ASK-1A-WP01-PRO-PID-0003 | PIPING & INSTRUMENT DIAGRAM PRODUCTION & TEST MANIFOLDS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 21:16:28 | zm167dc@jutal.com | 17-Jul-2026 21:56:05 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:18:44 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 22:04:40 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:40:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:37:20 | 03-Aug-2026 02:47:01 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP01-PRO-PID-0004 | PIPING & INSTRUMENTATION DIAGRAM PIG LAUNCHER AND EXPORT LINE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:05:25 | zm167dc@jutal.com | 29-Apr-2026 10:18:36 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 14:04:06 | Naphat Nirotsinlapachai | 12-May-2026 | 11-May-2026 23:12:49 | Pornlert Wanaphattharaphan | 13-May-2026 | 16-May-2026 00:20:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 17-May-2026 00:15:39 | 17-May-2026 01:11:27 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0004 | PIPING & INSTRUMENTATION DIAGRAM PIG LAUNCHER AND EXPORT LINE |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:05:46 | zm167dc@jutal.com | 04-Jun-2026 09:13:21 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:40:09 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:33:07 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:56:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:09:30 | 22-Jun-2026 00:20:27 | 0 |  |  | Approver | Locate
AO-000725 | MM-ASK-1A-WP01-PRO-PID-0004 | PIPING & INSTRUMENTATION DIAGRAM PIG LAUNCHER AND EXPORT LINE |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:05:45 | zm167dc@jutal.com | 20-Jul-2026 10:55:57 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:22:42 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:00:08 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:20:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:58:53 | 03-Aug-2026 03:35:33 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP01-PRO-PID-0005 | PIPING & INSTRUMENTATION DIAGRAM FUTURE PIG RECEIVER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:05:50 | zm167dc@jutal.com | 29-Apr-2026 10:23:40 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 16:47:19 | Naphat Nirotsinlapachai | 12-May-2026 | 11-May-2026 23:14:25 | Pornlert Wanaphattharaphan | 13-May-2026 | 16-May-2026 00:32:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 17-May-2026 00:04:34 | 17-May-2026 00:18:03 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0005 | PIPING & INSTRUMENTATION DIAGRAM FUTURE PIG RECEIVER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:06:18 | zm167dc@jutal.com | 04-Jun-2026 09:13:21 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:40:38 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:32:41 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:45:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:09:54 | 22-Jun-2026 00:19:14 | 0 |  |  | Approver | Locate
AO-000725 | MM-ASK-1A-WP01-PRO-PID-0005 | PIPING & INSTRUMENTATION DIAGRAM FUTURE PIG RECEIVER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:06:14 | zm167dc@jutal.com | 20-Jul-2026 10:55:53 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:22:00 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:45:57 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:28:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:53:01 | 03-Aug-2026 03:31:31 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP01-PRO-PID-0006 | PIPING & INSTRUMENTATION DIAGRAM TEST SEPARATOR |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:06:16 | zm167dc@jutal.com | 29-Apr-2026 10:23:57 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 16:48:18 | Naphat Nirotsinlapachai | 12-May-2026 | 11-May-2026 23:16:56 | Pornlert Wanaphattharaphan | 13-May-2026 | 16-May-2026 00:48:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 17-May-2026 00:14:07 | 17-May-2026 01:10:24 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0006 | PIPING & INSTRUMENTATION DIAGRAM TEST SEPARATOR |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:06:46 | zm167dc@jutal.com | 04-Jun-2026 09:13:26 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:37:31 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:34:52 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:59:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:10:47 | 22-Jun-2026 00:24:27 | 0 |  |  | Approver | Locate
AO-000719 | MM-ASK-1A-WP01-PRO-PID-0006 | PIPING & INSTRUMENTATION DIAGRAM TEST SEPARATOR |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 21:16:54 | zm167dc@jutal.com | 17-Jul-2026 21:56:22 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:19:07 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:47:19 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:36:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:40:05 | 03-Aug-2026 02:52:24 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP01-PRO-PID-0011-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:06:41 | zm167dc@jutal.com | 29-Apr-2026 10:24:15 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 17:55:52 | Naphat Nirotsinlapachai | 12-May-2026 | 11-May-2026 23:17:56 | Pornlert Wanaphattharaphan | 13-May-2026 | 16-May-2026 00:55:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 17-May-2026 00:07:40 | 17-May-2026 00:20:11 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0011-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:07:13 | zm167dc@jutal.com | 04-Jun-2026 09:16:40 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:07:31 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:00:03 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 18-Jun-2026 10:00:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 10:16:10 | 18-Jun-2026 03:51:22 | 0 |  |  | Approver | Locate
AO-000725 | MM-ASK-1A-WP01-PRO-PID-0011-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:06:42 | zm167dc@jutal.com | 20-Jul-2026 10:56:00 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:23:20 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:06:34 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 22:56:22 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:55:09 | 03-Aug-2026 03:34:11 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP01-PRO-PID-0011-002 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:07:08 | zm167dc@jutal.com | 29-Apr-2026 10:24:29 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 17:52:57 | Naphat Nirotsinlapachai | 12-May-2026 | 11-May-2026 23:19:02 | Pornlert Wanaphattharaphan | 13-May-2026 | 16-May-2026 13:14:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 17-May-2026 00:09:44 | 17-May-2026 00:21:15 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0011-002 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:07:46 | zm167dc@jutal.com | 04-Jun-2026 09:16:52 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:06:30 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:01:27 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 18-Jun-2026 10:04:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 10:18:04 | 18-Jun-2026 03:52:42 | 0 |  |  | Approver | Locate
AO-000725 | MM-ASK-1A-WP01-PRO-PID-0011-002 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:07:08 | zm167dc@jutal.com | 20-Jul-2026 10:55:55 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:23:38 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 22:06:07 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:48:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:43:58 | 03-Aug-2026 03:06:07 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP01-PRO-PID-0012 | PIPING & INSTRUMENTATION DIAGRAM OPEN AND CLOSED DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:07:33 | zm167dc@jutal.com | 29-Apr-2026 10:34:49 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 17:56:21 | Naphat Nirotsinlapachai | 12-May-2026 | 11-May-2026 23:20:10 | Pornlert Wanaphattharaphan | 13-May-2026 | 17-May-2026 22:28:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:04:57 | 18-May-2026 20:06:40 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0012 | PIPING & INSTRUMENTATION DIAGRAM OPEN AND CLOSED DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:08:24 | zm167dc@jutal.com | 04-Jun-2026 09:16:38 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:43:04 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:05:12 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 18-Jun-2026 10:05:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 10:22:14 | 18-Jun-2026 03:53:57 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP01-PRO-PID-0012 | PIPING & INSTRUMENTATION DIAGRAM OPEN AND CLOSED DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:07:37 | zm167dc@jutal.com | 20-Jul-2026 10:55:55 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:22:19 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:50:28 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 01:07:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:53:26 | 03-Aug-2026 03:32:53 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WP01-PRO-PID-0013 | PIPING & INSTRUMENT DIAGRAM DIESEL SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:31:43 | zm167dc@jutal.com | 27-Apr-2026 13:29:03 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:16:54 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:35:54 | Pornlert Wanaphattharaphan | 11-May-2026 | 13-May-2026 22:31:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 14-May-2026 08:30:51 | 14-May-2026 08:34:45 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0013 | PIPING & INSTRUMENT DIAGRAM DIESEL SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:08:52 | zm167dc@jutal.com | 04-Jun-2026 09:16:47 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:44:37 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:06:28 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 18-Jun-2026 10:12:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 10:23:30 | 18-Jun-2026 04:22:34 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP01-PRO-PID-0013 | PIPING & INSTRUMENT DIAGRAM DIESEL SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:08:03 | zm167dc@jutal.com | 20-Jul-2026 10:55:56 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:21:01 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 22:05:34 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:43:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:43:17 | 03-Aug-2026 03:04:29 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WP01-PRO-PID-0014 | PIPING & INSTRUMENT DIAGRAM UTILITY WATER SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:16:05 | zm167dc@jutal.com | 27-Apr-2026 13:29:19 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:18:22 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:38:00 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:03:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 08:49:33 | 15-May-2026 09:42:32 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0014 | PIPING & INSTRUMENT DIAGRAM UTILITY WATER SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:09:19 | zm167dc@jutal.com | 04-Jun-2026 09:16:44 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:08:50 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:07:22 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 22:07:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:11:25 | 22-Jun-2026 00:25:43 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP01-PRO-PID-0014 | PIPING & INSTRUMENT DIAGRAM UTILITY WATER SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:08:34 | zm167dc@jutal.com | 20-Jul-2026 10:56:03 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:26:43 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 22:03:31 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:37:18 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:41:22 | 03-Aug-2026 03:00:13 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP01-PRO-PID-0016 | PIPING & INSTRUMENTATION DIAGRAM CORROSION INHIBITOR INJECTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:07:59 | zm167dc@jutal.com | 29-Apr-2026 10:35:31 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 17:57:00 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:26:46 | Pornlert Wanaphattharaphan | 13-May-2026 | 17-May-2026 22:45:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:09:04 | 18-May-2026 20:07:50 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0016 | PIPING & INSTRUMENTATION DIAGRAM CORROSION INHIBITOR INJECTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:09:50 | zm167dc@jutal.com | 04-Jun-2026 09:16:46 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:08:09 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:10:50 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 22:11:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 10:40:41 | 22-Jun-2026 04:46:08 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP01-PRO-PID-0016 | PIPING & INSTRUMENTATION DIAGRAM CORROSION INHIBITOR INJECTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:09:02 | zm167dc@jutal.com | 20-Jul-2026 10:56:00 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:25:12 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 22:03:10 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 01:10:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:42:03 | 03-Aug-2026 03:01:43 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WP01-PRO-PID-0018 | PIPING & INSTRUMENT DIAGRAM BIOCIDE INJECTION SYSTEM (PROVISION) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:16:26 | zm167dc@jutal.com | 27-Apr-2026 13:29:35 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:20:58 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:41:37 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:32:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 09:01:59 | 15-May-2026 09:43:32 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0018 | PIPING & INSTRUMENT DIAGRAM BIOCIDE INJECTION SYSTEM (PROVISION) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:10:22 | zm167dc@jutal.com | 04-Jun-2026 09:16:49 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:45:56 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:12:44 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:09:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:12:01 | 22-Jun-2026 00:26:58 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP01-PRO-PID-0018 | PIPING & INSTRUMENT DIAGRAM BIOCIDE INJECTION SYSTEM (PROVISION) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:09:30 | zm167dc@jutal.com | 20-Jul-2026 10:56:01 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:25:50 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 22:00:39 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:51:12 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:38:45 | 03-Aug-2026 02:56:29 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WP01-PRO-PID-0019 | PIPING & INSTRUMENT DIAGRAM VENT SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:48:34 | zm167dc@jutal.com | 27-Apr-2026 13:29:52 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:22:19 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:43:57 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:39:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:12:54 | 15-May-2026 10:38:04 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0019 | PIPING & INSTRUMENT DIAGRAM VENT SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:10:50 | zm167dc@jutal.com | 04-Jun-2026 09:16:44 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:43:40 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:13:21 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:14:09 | APPR | Approved | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:12:50 | 22-Jun-2026 00:28:03 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP01-PRO-PID-0019 | PIPING & INSTRUMENT DIAGRAM VENT SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:10:05 | zm167dc@jutal.com | 20-Jul-2026 10:55:58 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:23:00 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:59:30 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:52:33 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:39:15 | 03-Aug-2026 02:57:40 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WP01-PRO-PID-0020 | PIPING & INSTRUMENT DIAGRAM NON-HAZARDOUS OPEN DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:16:47 | zm167dc@jutal.com | 27-Apr-2026 13:37:44 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:19:14 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:26:45 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:49:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 08:51:55 | 15-May-2026 09:13:23 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0020 | PIPING & INSTRUMENT DIAGRAM NON-HAZARDOUS OPEN DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:11:20 | zm167dc@jutal.com | 04-Jun-2026 09:16:48 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:44:09 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:14:31 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:17:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:13:12 | 22-Jun-2026 00:30:23 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP01-PRO-PID-0020 | PIPING & INSTRUMENT DIAGRAM NON-HAZARDOUS OPEN DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:10:35 | zm167dc@jutal.com | 20-Jul-2026 10:55:57 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:21:39 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:57:48 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:53:34 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:42:42 | 03-Aug-2026 03:03:01 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WP01-PRO-PID-0021 | PIPING & INSTRUMENT DIAGRAMBOOSTER COMPRESSOR MANIFOLD |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:48:56 | zm167dc@jutal.com | 27-Apr-2026 13:36:47 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:29:00 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:30:50 | Pornlert Wanaphattharaphan | 11-May-2026 | 15-May-2026 00:26:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:15:45 | 15-May-2026 10:40:21 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0021 | PIPING & INSTRUMENT DIAGRAMBOOSTER COMPRESSOR MANIFOLD |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:11:52 | zm167dc@jutal.com | 04-Jun-2026 09:16:48 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:05:53 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:15:23 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:21:23 | APPR | Approved | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:16:24 | 22-Jun-2026 00:29:10 | 0 |  |  | Approver | Locate
AO-000719 | MM-ASK-1A-WP01-PRO-PID-0021 | PIPING & INSTRUMENT DIAGRAMBOOSTER COMPRESSOR MANIFOLD |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 21:17:25 | zm167dc@jutal.com | 17-Jul-2026 21:56:38 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:19:28 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:56:49 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 01:02:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:47:29 | 03-Aug-2026 03:28:53 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WP01-PRO-PID-0022 | PIPING & INSTRUMENT DIAGRAM BOOSTER COMPRESSOR |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:17:08 | zm167dc@jutal.com | 27-Apr-2026 13:37:05 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:29:35 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:28:46 | Pornlert Wanaphattharaphan | 11-May-2026 | 15-May-2026 00:14:32 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 08:53:29 | 15-May-2026 09:14:19 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0022 | PIPING & INSTRUMENT DIAGRAM BOOSTER COMPRESSOR |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:12:26 | zm167dc@jutal.com | 04-Jun-2026 09:16:47 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:07:02 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:16:26 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:21:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 11:09:07 | 22-Jun-2026 04:47:32 | 0 |  |  | Approver | Locate
AO-000719 | MM-ASK-1A-WP01-PRO-PID-0022 | PIPING & INSTRUMENT DIAGRAM BOOSTER COMPRESSOR |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 21:18:04 | zm167dc@jutal.com | 17-Jul-2026 21:56:58 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:19:56 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:56:14 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:50:33 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:39:43 | 03-Aug-2026 02:51:00 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WP01-PRO-PID-0023 | PIPING & INSTRUMENT DIAGRAM POWER GENERATION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:17:44 | zm167dc@jutal.com | 27-Apr-2026 13:37:21 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:29:59 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:27:59 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:54:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:17:49 | 15-May-2026 10:46:22 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0023 | PIPING & INSTRUMENT DIAGRAM POWER GENERATION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:13:01 | zm167dc@jutal.com | 04-Jun-2026 09:16:44 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 07:46:28 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:17:21 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:25:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 11:11:48 | 22-Jun-2026 04:50:27 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP01-PRO-PID-0023 | PIPING & INSTRUMENT DIAGRAM POWER GENERATION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:11:02 | zm167dc@jutal.com | 20-Jul-2026 10:56:00 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:25:30 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:55:01 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:52:58 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:44:50 | 03-Aug-2026 03:07:33 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WP01-PRO-PID-0100 | PIPING & INSTRUMENT DIAGRAM WELLHEAD INSTRUMENT INDEX AND FLOWLINES |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:18:15 | zm167dc@jutal.com | 27-Apr-2026 13:35:23 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:27:54 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:44:49 | Pornlert Wanaphattharaphan | 11-May-2026 | 15-May-2026 00:37:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:19:29 | 15-May-2026 10:47:31 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP01-PRO-PID-0100 | PIPING & INSTRUMENT DIAGRAM WELLHEAD INSTRUMENT INDEX AND FLOWLINES |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:13:47 | zm167dc@jutal.com | 04-Jun-2026 09:39:42 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:40:28 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:18:35 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 19-Jun-2026 23:27:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:16:54 | 22-Jun-2026 00:43:49 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP01-PRO-PID-0100 | PIPING & INSTRUMENT DIAGRAM WELLHEAD INSTRUMENT INDEX AND FLOWLINES |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:11:30 | zm167dc@jutal.com | 20-Jul-2026 10:56:06 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:21:18 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 21:54:26 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:49:29 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:41:01 | 03-Aug-2026 02:58:51 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP01-PRO-UFD-0001 | PROCESS FLOW DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:45:08 | jumpols@pttep.com | 20-Apr-2026 17:21:16 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:19:27 | Naphat Nirotsinlapachai | 30-Apr-2026 | 29-Apr-2026 19:42:49 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 10:40:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 01-May-2026 10:41:48 | 01-May-2026 11:18:49 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP01-PRO-UFD-0001 | PROCESS FLOW DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:07:44 | zm167dc@jutal.com | 15-May-2026 18:38:39 | Jumpol Sudjitjul | 26-May-2026 | 27-May-2026 09:42:58 | Naphat Nirotsinlapachai | 27-May-2026 | 27-May-2026 09:46:57 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 15:06:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 15:16:23 | 10-Jun-2026 08:18:29 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP01-PRO-UFD-0001 | PROCESS FLOW DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:12:57 | zm167dc@jutal.com | 24-Jul-2026 16:32:00 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:19:00 | Naphat Nirotsinlapachai | 06-Aug-2026 | 06-Aug-2026 22:04:07 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 05:44:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:10:24 | 07-Aug-2026 04:59:16 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP01-PRO-UFD-0002 | PROCESS FLOW DIAGRAM DIESEL OIL, UTILITY WATER AND POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:45:32 | jumpols@pttep.com | 20-Apr-2026 17:21:31 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:21:36 | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 08:38:41 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 10:49:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 01-May-2026 11:00:34 | 01-May-2026 11:20:53 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP01-PRO-UFD-0002 | PROCESS FLOW DIAGRAM DIESEL OIL, UTILITY WATER AND POWER SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:08:10 | zm167dc@jutal.com | 15-May-2026 18:38:57 | Jumpol Sudjitjul | 26-May-2026 | 27-May-2026 09:43:38 | Naphat Nirotsinlapachai | 27-May-2026 | 27-May-2026 09:48:12 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 15:08:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 15:18:17 | 10-Jun-2026 08:46:36 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP01-PRO-UFD-0002 | PROCESS FLOW DIAGRAM DIESEL OIL, UTILITY WATER AND POWER SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:13:26 | zm167dc@jutal.com | 24-Jul-2026 16:32:37 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:19:33 | Naphat Nirotsinlapachai | 06-Aug-2026 | 06-Aug-2026 22:08:12 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 05:58:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:11:42 | 07-Aug-2026 05:00:39 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP01-PRO-UFD-0003 | PROCESS FLOW DIAGRAM CHEMICAL INJECTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:46:02 | jumpols@pttep.com | 20-Apr-2026 17:21:46 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:22:21 | Naphat Nirotsinlapachai | 30-Apr-2026 | 29-Apr-2026 19:44:29 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 11:12:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 01-May-2026 11:13:59 | 01-May-2026 11:21:52 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP01-PRO-UFD-0003 | PROCESS FLOW DIAGRAM CHEMICAL INJECTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:08:34 | zm167dc@jutal.com | 15-May-2026 18:39:14 | Jumpol Sudjitjul | 26-May-2026 | 27-May-2026 09:44:29 | Naphat Nirotsinlapachai | 27-May-2026 | 27-May-2026 09:49:21 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 15:08:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 15:19:01 | 10-Jun-2026 08:49:06 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP01-PRO-UFD-0003 | PROCESS FLOW DIAGRAM CHEMICAL INJECTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:13:51 | zm167dc@jutal.com | 24-Jul-2026 16:32:54 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:19:41 | Naphat Nirotsinlapachai | 06-Aug-2026 | 06-Aug-2026 22:26:06 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 06:00:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:12:33 | 07-Aug-2026 05:04:17 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP01-PRO-UFD-0004 | PROCESS FLOW DIAGRAM UTILITY FLOW DIAGRAM CLOSED DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:46:29 | jumpols@pttep.com | 20-Apr-2026 17:22:01 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:23:23 | Naphat Nirotsinlapachai | 30-Apr-2026 | 29-Apr-2026 19:45:29 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 11:21:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 01-May-2026 11:26:48 | 01-May-2026 12:11:12 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP01-PRO-UFD-0004 | PROCESS FLOW DIAGRAM UTILITY FLOW DIAGRAM CLOSED DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:08:58 | zm167dc@jutal.com | 15-May-2026 18:39:32 | Jumpol Sudjitjul | 26-May-2026 | 27-May-2026 09:45:15 | Naphat Nirotsinlapachai | 27-May-2026 | 27-May-2026 09:51:50 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 15:09:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 15:20:10 | 10-Jun-2026 08:51:47 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP01-PRO-UFD-0004 | PROCESS FLOW DIAGRAM UTILITY FLOW DIAGRAM CLOSED DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:14:15 | zm167dc@jutal.com | 24-Jul-2026 16:33:12 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:19:59 | Naphat Nirotsinlapachai | 06-Aug-2026 | 06-Aug-2026 22:11:23 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 06:00:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:12:08 | 07-Aug-2026 05:02:01 | 0 |  |  | Approver | Locate
AO-000578 | MM-ASK-1A-WP01-QAC-PDR-0011 | RT PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | WPA01 |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 15:01:07 | zm167dc@jutal.com | 30-Jun-2026 16:17:20 | Jumpol Sudjitjul | 08-Jul-2026 | 02-Jul-2026 14:29:06 | Poramate Kamlangkeng | 09-Jul-2026 | 03-Jul-2026 08:19:11 | Apisit Tangwashirakul | 10-Jul-2026 | 07-Jul-2026 15:32:14 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 15:37:46 | 07-Jul-2026 09:04:13 | 0 |  |  | Approver | Locate
AO-000579 | MM-ASK-1A-WP01-QAC-PDR-0012 | UT PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | WPA01 |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 15:01:49 | zm167dc@jutal.com | 30-Jun-2026 16:15:35 | Jumpol Sudjitjul | 08-Jul-2026 | 02-Jul-2026 14:29:53 | Poramate Kamlangkeng | 09-Jul-2026 | 03-Jul-2026 08:20:38 | Apisit Tangwashirakul | 10-Jul-2026 | 07-Jul-2026 15:32:37 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 15:38:09 | 07-Jul-2026 09:05:39 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0031 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:54:28 | zm167dc@jutal.com | 08-Jun-2026 18:03:28 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:31:24 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 17:59:04 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 00:49:56 | APPR | Approved | Jumpol Sudjitjul | 22-Jun-2026 | 24-Jun-2026 08:06:34 | 24-Jun-2026 01:14:27 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0031 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:00:28 | zm167dc@jutal.com | 30-Jul-2026 14:15:31 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 13:00:16 | Pongsakorn Monturat | 10-Aug-2026 | 19-Aug-2026 20:27:59 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 17:03:55 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 20-Aug-2026 19:46:05 | 20-Aug-2026 13:25:23 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0032 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:54:51 | zm167dc@jutal.com | 08-Jun-2026 18:04:07 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:34:42 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 17:57:11 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 20:55:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 25-Jun-2026 09:53:34 | 25-Jun-2026 03:33:57 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0032 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:00:59 | zm167dc@jutal.com | 30-Jul-2026 14:15:33 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 13:00:44 | Pongsakorn Monturat | 10-Aug-2026 | 19-Aug-2026 20:28:37 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 21:22:21 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 21-Aug-2026 08:59:22 | 21-Aug-2026 02:39:37 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0033 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:55:15 | zm167dc@jutal.com | 08-Jun-2026 18:04:24 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:35:38 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 18:19:03 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 21:02:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 25-Jun-2026 09:56:55 | 25-Jun-2026 03:35:42 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0033 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:01:29 | zm167dc@jutal.com | 30-Jul-2026 14:15:28 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 12:58:55 | Pongsakorn Monturat | 10-Aug-2026 | 18-Aug-2026 17:33:14 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 16:59:35 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 20-Aug-2026 19:46:29 | 20-Aug-2026 13:26:35 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0034 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:55:41 | zm167dc@jutal.com | 08-Jun-2026 18:04:41 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:37:17 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 18:24:38 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 21:09:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 25-Jun-2026 09:58:41 | 25-Jun-2026 03:37:20 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0034 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:01:59 | zm167dc@jutal.com | 30-Jul-2026 14:15:30 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 12:59:14 | Pongsakorn Monturat | 10-Aug-2026 | 18-Aug-2026 17:34:14 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 17:00:58 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 20-Aug-2026 19:47:02 | 20-Aug-2026 13:27:49 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0035 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:56:05 | zm167dc@jutal.com | 08-Jun-2026 18:07:56 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:38:42 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 18:27:54 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 21:37:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 25-Jun-2026 10:00:16 | 25-Jun-2026 03:38:35 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0035 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:02:27 | zm167dc@jutal.com | 30-Jul-2026 14:15:28 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 12:58:13 | Pongsakorn Monturat | 10-Aug-2026 | 18-Aug-2026 17:34:50 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 17:01:24 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 20-Aug-2026 19:47:28 | 20-Aug-2026 13:28:57 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0036 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:56:30 | zm167dc@jutal.com | 08-Jun-2026 18:08:15 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:39:42 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 18:30:10 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 21:37:40 | APPR | Approved | Jumpol Sudjitjul | 22-Jun-2026 | 25-Jun-2026 10:04:27 | 25-Jun-2026 03:39:48 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0036 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:02:53 | zm167dc@jutal.com | 30-Jul-2026 14:15:28 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 12:59:38 | Pongsakorn Monturat | 10-Aug-2026 | 18-Aug-2026 17:35:33 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 16:38:26 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 20-Aug-2026 19:48:01 | 20-Aug-2026 13:30:06 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0037 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:56:57 | zm167dc@jutal.com | 08-Jun-2026 18:08:46 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:43:39 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 18:34:10 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 21:38:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 25-Jun-2026 10:07:12 | 25-Jun-2026 03:41:14 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0037 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING EAST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:03:20 | zm167dc@jutal.com | 30-Jul-2026 14:15:33 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 13:01:07 | Pongsakorn Monturat | 10-Aug-2026 | 18-Aug-2026 17:36:58 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 16:50:42 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 20-Aug-2026 19:48:44 | 20-Aug-2026 13:32:31 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0038 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:57:20 | zm167dc@jutal.com | 08-Jun-2026 18:09:57 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:45:29 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 18:38:19 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 21:38:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 25-Jun-2026 10:07:54 | 25-Jun-2026 03:42:40 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0038 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING NORTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:03:52 | zm167dc@jutal.com | 30-Jul-2026 14:15:33 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 13:01:29 | Pongsakorn Monturat | 10-Aug-2026 | 18-Aug-2026 17:37:34 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 17:01:50 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 20-Aug-2026 19:48:21 | 20-Aug-2026 13:31:18 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0039 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:57:43 | zm167dc@jutal.com | 08-Jun-2026 18:10:15 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:49:38 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 18:40:39 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 21:40:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 25-Jun-2026 10:34:45 | 25-Jun-2026 04:36:02 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0039 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING WEST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:04:18 | zm167dc@jutal.com | 30-Jul-2026 14:15:29 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 12:59:56 | Pongsakorn Monturat | 10-Aug-2026 | 18-Aug-2026 17:38:26 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 17:02:18 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 20-Aug-2026 19:49:10 | 20-Aug-2026 13:33:42 | 0 |  |  | Approver | Locate
AO-000431 | MM-ASK-1A-WP01-SAF-DWG-0040 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 17:58:06 | zm167dc@jutal.com | 08-Jun-2026 18:10:32 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 13:50:51 | Warayut Ubolcharoen | 18-Jun-2026 | 21-Jun-2026 18:43:12 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 24-Jun-2026 21:51:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 25-Jun-2026 10:41:26 | 25-Jun-2026 04:37:26 | 0 |  |  | Approver | Locate
AO-000813 | MM-ASK-1A-WP01-SAF-DWG-0040 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING SOUTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jul-2026 14:04:46 | zm167dc@jutal.com | 30-Jul-2026 14:15:33 | Jumpol Sudjitjul | 07-Aug-2026 | 02-Aug-2026 13:01:47 | Pongsakorn Monturat | 10-Aug-2026 | 18-Aug-2026 17:39:02 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 20-Aug-2026 17:03:24 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 20-Aug-2026 19:49:33 | 20-Aug-2026 13:34:55 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0041 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:12:14 | zm167dc@jutal.com | 10-Jun-2026 08:45:13 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 13:54:51 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 18:46:04 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 21:59:27 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 10:45:46 | 25-Jun-2026 04:25:52 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-SAF-DWG-0041 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:06:13 | zm167dc@jutal.com | 31-Jul-2026 14:43:38 | Jumpol Sudjitjul | 10-Aug-2026 | 05-Aug-2026 13:58:09 | Pongsakorn Monturat | 11-Aug-2026 | 13-Aug-2026 12:51:48 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 16-Aug-2026 10:44:10 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 17-Aug-2026 08:51:06 | 17-Aug-2026 02:21:41 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0042 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:13:00 | zm167dc@jutal.com | 10-Jun-2026 08:45:49 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 13:55:51 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 18:51:19 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:20:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 10:34:40 | 25-Jun-2026 04:23:05 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-SAF-DWG-0042 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:06:44 | zm167dc@jutal.com | 31-Jul-2026 14:43:40 | Jumpol Sudjitjul | 10-Aug-2026 | 21-Aug-2026 13:54:59 | Pongsakorn Monturat | 11-Aug-2026 | 24-Aug-2026 16:36:02 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 25-Aug-2026 22:12:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 26-Aug-2026 08:46:27 | 26-Aug-2026 02:12:27 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0043 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:13:42 | zm167dc@jutal.com | 10-Jun-2026 08:46:06 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 13:56:34 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 18:48:11 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:20:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 10:49:54 | 25-Jun-2026 04:30:20 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-SAF-DWG-0043 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:07:10 | zm167dc@jutal.com | 31-Jul-2026 14:43:38 | Jumpol Sudjitjul | 10-Aug-2026 | 05-Aug-2026 13:58:14 | Pongsakorn Monturat | 11-Aug-2026 | 13-Aug-2026 11:41:22 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 16-Aug-2026 10:42:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 17-Aug-2026 08:44:07 | 17-Aug-2026 02:17:50 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0044 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:14:15 | zm167dc@jutal.com | 10-Jun-2026 08:46:25 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 13:57:41 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 18:54:26 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:21:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 10:46:16 | 25-Jun-2026 04:27:28 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-SAF-DWG-0044 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:07:42 | zm167dc@jutal.com | 31-Jul-2026 14:43:47 | Jumpol Sudjitjul | 10-Aug-2026 | 21-Aug-2026 13:56:12 | Pongsakorn Monturat | 11-Aug-2026 | 24-Aug-2026 16:37:44 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 25-Aug-2026 22:14:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 26-Aug-2026 08:50:22 | 26-Aug-2026 02:16:33 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0045 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:14:58 | zm167dc@jutal.com | 10-Jun-2026 08:46:43 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 13:58:45 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 18:58:43 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 21:59:52 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 10:51:09 | 25-Jun-2026 04:33:04 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-SAF-DWG-0045 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:08:10 | zm167dc@jutal.com | 31-Jul-2026 14:43:38 | Jumpol Sudjitjul | 10-Aug-2026 | 21-Aug-2026 13:53:09 | Pongsakorn Monturat | 11-Aug-2026 | 24-Aug-2026 16:32:44 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 25-Aug-2026 22:08:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 26-Aug-2026 08:47:08 | 26-Aug-2026 02:13:47 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0046 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:15:34 | zm167dc@jutal.com | 10-Jun-2026 08:55:25 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 14:03:46 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:09:16 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:15:34 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 10:47:12 | 25-Jun-2026 04:28:52 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-SAF-DWG-0046 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:08:36 | zm167dc@jutal.com | 31-Jul-2026 14:43:38 | Jumpol Sudjitjul | 10-Aug-2026 | 05-Aug-2026 13:57:03 | Pongsakorn Monturat | 11-Aug-2026 | 13-Aug-2026 12:53:10 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 16-Aug-2026 10:44:44 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 17-Aug-2026 08:45:06 | 17-Aug-2026 02:19:07 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0047 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:16:06 | zm167dc@jutal.com | 10-Jun-2026 08:55:07 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 14:02:51 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:07:36 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:01:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 10:41:30 | 25-Jun-2026 04:24:28 | 0 |  |  | Approver | Locate
AO-000828 | MM-ASK-1A-WP01-SAF-DWG-0047 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING EAST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:56:58 | zm167dc@jutal.com | 31-Jul-2026 15:01:06 | Jumpol Sudjitjul | 10-Aug-2026 | 05-Aug-2026 14:08:54 | Pongsakorn Monturat | 11-Aug-2026 | 24-Aug-2026 16:42:13 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 25-Aug-2026 22:21:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 26-Aug-2026 08:38:58 | 26-Aug-2026 02:17:53 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0048 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:16:35 | zm167dc@jutal.com | 10-Jun-2026 08:54:25 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 14:01:02 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:03:54 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:00:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 10:52:28 | 25-Jun-2026 04:34:31 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-SAF-DWG-0048 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING NORTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:09:02 | zm167dc@jutal.com | 31-Jul-2026 14:43:39 | Jumpol Sudjitjul | 10-Aug-2026 | 21-Aug-2026 13:54:01 | Pongsakorn Monturat | 11-Aug-2026 | 24-Aug-2026 16:34:57 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 25-Aug-2026 22:10:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 26-Aug-2026 08:38:23 | 26-Aug-2026 02:06:59 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0049 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:17:09 | zm167dc@jutal.com | 10-Jun-2026 08:54:48 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 14:01:57 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:05:52 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:01:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 12:10:39 | 25-Jun-2026 05:42:26 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-SAF-DWG-0049 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING WEST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:09:28 | zm167dc@jutal.com | 31-Jul-2026 14:43:41 | Jumpol Sudjitjul | 10-Aug-2026 | 21-Aug-2026 13:56:44 | Pongsakorn Monturat | 11-Aug-2026 | 24-Aug-2026 16:38:47 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 25-Aug-2026 22:16:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 26-Aug-2026 08:37:49 | 26-Aug-2026 02:05:31 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP01-SAF-DWG-0050 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:17:48 | zm167dc@jutal.com | 10-Jun-2026 08:54:04 | Jumpol Sudjitjul | 18-Jun-2026 | 20-Jun-2026 20:31:12 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:01:42 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:00:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 10:49:52 | 25-Jun-2026 04:31:42 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-SAF-DWG-0050 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING SOUTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 14:09:57 | zm167dc@jutal.com | 31-Jul-2026 14:43:40 | Jumpol Sudjitjul | 10-Aug-2026 | 21-Aug-2026 13:52:33 | Pongsakorn Monturat | 11-Aug-2026 | 24-Aug-2026 16:31:46 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 25-Aug-2026 22:05:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 26-Aug-2026 08:33:55 | 26-Aug-2026 02:01:51 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0125 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:52:18 | zm167dc@jutal.com | 18-Jun-2026 14:04:23 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:04:17 | Jumpol Sudjitjul | 29-Jun-2026 | 08-Jul-2026 10:42:09 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:22:18 | APPR | Approved | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 09:57:28 | 09-Jul-2026 03:44:05 | 0 |  |  | Approver | Locate
AO-000886 | MM-ASK-1A-WP01-SAF-DWG-0125 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:53:28 | zm167dc@jutal.com | 05-Aug-2026 12:04:47 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:30:36 | Pongsakorn Monturat | 17-Aug-2026 | 26-Aug-2026 15:53:03 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 27-Aug-2026 14:00:22 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 27-Aug-2026 14:23:07 | 27-Aug-2026 07:44:28 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0126 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:52:59 | zm167dc@jutal.com | 18-Jun-2026 14:05:11 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:06:01 | Jumpol Sudjitjul | 29-Jun-2026 | 08-Jul-2026 10:43:38 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:50:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 09:58:19 | 09-Jul-2026 03:46:33 | 0 |  |  | Approver | Locate
AO-000886 | MM-ASK-1A-WP01-SAF-DWG-0126 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:54:00 | zm167dc@jutal.com | 05-Aug-2026 12:04:49 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:31:35 | Pongsakorn Monturat | 17-Aug-2026 | 26-Aug-2026 15:57:51 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 27-Aug-2026 14:02:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 27-Aug-2026 14:18:14 | 27-Aug-2026 07:40:35 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0127 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:53:29 | zm167dc@jutal.com | 18-Jun-2026 14:05:31 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:06:49 | Jumpol Sudjitjul | 29-Jun-2026 | 08-Jul-2026 10:45:36 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:51:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 09:59:18 | 09-Jul-2026 03:49:23 | 0 |  |  | Approver | Locate
AO-000886 | MM-ASK-1A-WP01-SAF-DWG-0127 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:54:28 | zm167dc@jutal.com | 05-Aug-2026 12:04:48 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:30:54 | Pongsakorn Monturat | 17-Aug-2026 | 26-Aug-2026 15:55:31 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 27-Aug-2026 14:01:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 27-Aug-2026 14:19:48 | 27-Aug-2026 07:42:02 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0128 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:53:56 | zm167dc@jutal.com | 18-Jun-2026 14:05:52 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:07:40 | Jumpol Sudjitjul | 29-Jun-2026 | 08-Jul-2026 10:47:16 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:51:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 10:00:19 | 09-Jul-2026 03:52:02 | 0 |  |  | Approver | Locate
AO-000886 | MM-ASK-1A-WP01-SAF-DWG-0128 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:54:55 | zm167dc@jutal.com | 05-Aug-2026 12:04:47 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:31:10 | Pongsakorn Monturat | 17-Aug-2026 | 26-Aug-2026 15:56:56 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 27-Aug-2026 14:01:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 27-Aug-2026 14:27:56 | 27-Aug-2026 07:45:56 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0129 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:54:19 | zm167dc@jutal.com | 18-Jun-2026 14:06:12 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:09:23 | Jumpol Sudjitjul | 29-Jun-2026 | 08-Jul-2026 10:48:55 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:52:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 09:59:26 | 09-Jul-2026 03:50:41 | 0 |  |  | Approver | Locate
AO-000886 | MM-ASK-1A-WP01-SAF-DWG-0129 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:55:24 | zm167dc@jutal.com | 05-Aug-2026 12:04:50 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:32:11 | Pongsakorn Monturat | 17-Aug-2026 | 26-Aug-2026 16:12:15 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 27-Aug-2026 14:03:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 27-Aug-2026 14:20:50 | 27-Aug-2026 07:43:20 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0130 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:54:46 | zm167dc@jutal.com | 18-Jun-2026 14:21:32 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:15:30 | Warayut Ubolcharoen | 29-Jun-2026 | 08-Jul-2026 06:39:02 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:21:43 | NA | Not Approved | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 09:58:38 | 09-Jul-2026 03:47:50 | 0 |  |  | Approver | Locate
AO-000748 | MM-ASK-1A-WP01-SAF-DWG-0130 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) BOAT LANDING PLAN |  | A2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 15:16:32 | zm167dc@jutal.com | 21-Jul-2026 15:32:52 | Jumpol Sudjitjul | 31-Jul-2026 | 31-Jul-2026 13:28:24 | Pongsakorn Monturat | 03-Aug-2026 | 18-Aug-2026 12:43:58 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 18-Aug-2026 20:26:17 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 19-Aug-2026 09:53:49 | 19-Aug-2026 03:12:53 | 0 |  |  | Approver | Locate
AO-001043 | MM-ASK-1A-WP01-SAF-DWG-0130 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 21-Aug-2026 09:38:36 | zm167dc@jutal.com | 21-Aug-2026 13:46:05 | Jumpol Sudjitjul | 31-Aug-2026 | 10-Sep-2026 13:03:50 | Pongsakorn Monturat | 01-Sep-2026 |  | Pornlert Wanaphattharaphan | 02-Sep-2026 |  |  |  |  | 03-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0131 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:55:11 | zm167dc@jutal.com | 18-Jun-2026 14:10:58 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:10:27 | Jumpol Sudjitjul | 29-Jun-2026 | 08-Jul-2026 10:50:21 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:53:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 09:57:44 | 09-Jul-2026 03:45:18 | 0 |  |  | Approver | Locate
AO-000886 | MM-ASK-1A-WP01-SAF-DWG-0131 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING EAST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:55:51 | zm167dc@jutal.com | 05-Aug-2026 12:04:48 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:31:53 | Pongsakorn Monturat | 17-Aug-2026 | 26-Aug-2026 15:58:51 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 27-Aug-2026 14:02:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 27-Aug-2026 14:29:55 | 27-Aug-2026 07:47:28 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0132 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:55:37 | zm167dc@jutal.com | 18-Jun-2026 14:11:17 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:12:57 | Jumpol Sudjitjul | 29-Jun-2026 | 08-Jul-2026 10:52:13 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:53:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 09:56:32 | 09-Jul-2026 03:42:40 | 0 |  |  | Approver | Locate
AO-000886 | MM-ASK-1A-WP01-SAF-DWG-0132 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING NORTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:56:25 | zm167dc@jutal.com | 05-Aug-2026 12:04:51 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:32:53 | Pongsakorn Monturat | 17-Aug-2026 | 26-Aug-2026 16:13:16 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 27-Aug-2026 14:04:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 27-Aug-2026 14:30:53 | 27-Aug-2026 07:48:55 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0133 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:56:03 | zm167dc@jutal.com | 18-Jun-2026 14:11:39 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:13:52 | Jumpol Sudjitjul | 29-Jun-2026 | 08-Jul-2026 10:54:52 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:54:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 09:55:10 | 09-Jul-2026 04:00:49 | 0 |  |  | Approver | Locate
AO-000886 | MM-ASK-1A-WP01-SAF-DWG-0133 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING WEST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:57:01 | zm167dc@jutal.com | 05-Aug-2026 12:04:52 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:33:12 | Pongsakorn Monturat | 17-Aug-2026 | 26-Aug-2026 16:14:19 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 27-Aug-2026 14:05:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 27-Aug-2026 14:31:42 | 27-Aug-2026 07:50:24 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP01-SAF-DWG-0134 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:56:28 | zm167dc@jutal.com | 18-Jun-2026 14:11:59 | Jumpol Sudjitjul | 26-Jun-2026 | 07-Jul-2026 14:14:42 | Jumpol Sudjitjul | 29-Jun-2026 | 08-Jul-2026 10:42:29 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 08-Jul-2026 23:49:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 09-Jul-2026 09:54:22 | 09-Jul-2026 03:58:09 | 0 |  |  | Approver | Locate
AO-000886 | MM-ASK-1A-WP01-SAF-DWG-0134 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING SOUTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:57:29 | zm167dc@jutal.com | 05-Aug-2026 12:04:51 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:32:33 | Pongsakorn Monturat | 17-Aug-2026 | 26-Aug-2026 16:15:21 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 27-Aug-2026 14:10:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 27-Aug-2026 14:32:53 | 27-Aug-2026 07:51:53 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP01-SAF-LAY-0071 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:30:37 | zm167dc@jutal.com | 05-Jun-2026 14:40:16 | Jumpol Sudjitjul | 15-Jun-2026 | 10-Jun-2026 11:08:51 | Warayut Ubolcharoen | 16-Jun-2026 | 18-Jun-2026 17:17:17 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 16:41:13 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 22-Jun-2026 10:06:02 | 22-Jun-2026 03:51:14 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP01-SAF-LAY-0071 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:45:56 | zm167dc@jutal.com | 13-Aug-2026 13:43:56 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:39:09 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 01-Sep-2026 23:40:51 | APPR | Approved | Soontaree Simpitak | 26-Aug-2026 | 02-Sep-2026 08:33:25 | 02-Sep-2026 02:01:28 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP01-SAF-LAY-0072 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:31:08 | zm167dc@jutal.com | 05-Jun-2026 14:40:55 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:34:51 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 16:54:12 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 23-Jun-2026 00:49:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 23-Jun-2026 08:14:09 | 23-Jun-2026 01:44:30 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP01-SAF-LAY-0072 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:46:28 | zm167dc@jutal.com | 13-Aug-2026 13:43:59 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:56:34 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 23:05:04 | AWC | Approved with Comment | Soontaree Simpitak | 26-Aug-2026 | 03-Sep-2026 07:49:22 | 03-Sep-2026 01:26:35 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP01-SAF-LAY-0073 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:31:33 | zm167dc@jutal.com | 05-Jun-2026 14:41:25 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:35:17 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:02:25 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 23-Jun-2026 01:02:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 23-Jun-2026 08:15:27 | 23-Jun-2026 01:46:55 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP01-SAF-LAY-0073 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:46:56 | zm167dc@jutal.com | 13-Aug-2026 13:43:56 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:57:36 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 23:08:04 | AWC | Approved with Comment | Soontaree Simpitak | 26-Aug-2026 | 03-Sep-2026 07:55:42 | 03-Sep-2026 01:27:52 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP01-SAF-LAY-0074 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:32:01 | zm167dc@jutal.com | 05-Jun-2026 14:41:58 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:35:43 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:14:20 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 24-Jun-2026 00:06:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 24-Jun-2026 08:07:14 | 24-Jun-2026 01:21:13 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP01-SAF-LAY-0074 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:47:26 | zm167dc@jutal.com | 13-Aug-2026 13:44:04 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:54:26 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 23:02:00 | AWC | Approved with Comment | Soontaree Simpitak | 26-Aug-2026 | 03-Sep-2026 07:59:39 | 03-Sep-2026 01:31:02 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP01-SAF-LAY-0075 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:32:27 | zm167dc@jutal.com | 05-Jun-2026 14:42:23 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:36:07 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:21:34 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 24-Jun-2026 00:40:40 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 24-Jun-2026 08:07:52 | 24-Jun-2026 01:22:26 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP01-SAF-LAY-0075 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:47:59 | zm167dc@jutal.com | 13-Aug-2026 13:43:59 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:55:03 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 23:03:06 | APPR | Approved | Soontaree Simpitak | 26-Aug-2026 | 03-Sep-2026 08:07:33 | 03-Sep-2026 01:32:12 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP01-SAF-LAY-0076 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:32:52 | zm167dc@jutal.com | 05-Jun-2026 14:51:10 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:37:57 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:34:06 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 24-Jun-2026 00:21:52 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 24-Jun-2026 08:10:11 | 24-Jun-2026 01:42:34 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP01-SAF-LAY-0076 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:48:45 | zm167dc@jutal.com | 13-Aug-2026 13:43:56 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:38:35 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 01-Sep-2026 23:39:31 | APPR | Approved | Soontaree Simpitak | 26-Aug-2026 | 02-Sep-2026 10:23:32 | 02-Sep-2026 03:57:21 | 0 |  |  | Approver | Locate
AO-000436 | MM-ASK-1A-WP01-SAF-LAY-0083 | FIREFIGHTING EQUIPMENT LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 09:18:03 | zm167dc@jutal.com | 10-Jun-2026 09:39:29 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 11:08:53 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:29:58 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:19:22 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 12:17:03 | 25-Jun-2026 05:54:48 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP01-SAF-LAY-0083 | FIREFIGHTING EQUIPMENT LAYOUT DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:44:40 | zm167dc@jutal.com | 23-Jul-2026 17:02:50 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 13-Aug-2026 12:53:45 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 15-Aug-2026 12:35:50 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 15-Aug-2026 14:33:26 | 15-Aug-2026 08:28:27 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP01-SAF-LAY-0083 | FIREFIGHTING EQUIPMENT LAYOUT DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:16:55 | zm167dc@jutal.com | 20-Sep-2026 14:09:32 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000436 | MM-ASK-1A-WP01-SAF-LAY-0084 | FIREFIGHTING EQUIPMENT LAYOUT UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 09:18:57 | zm167dc@jutal.com | 10-Jun-2026 09:39:29 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 11:07:31 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:37:24 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:18:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 12:16:16 | 25-Jun-2026 05:53:25 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP01-SAF-LAY-0084 | FIREFIGHTING EQUIPMENT LAYOUT UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:45:07 | zm167dc@jutal.com | 23-Jul-2026 17:02:47 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 13-Aug-2026 12:54:13 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 15-Aug-2026 13:19:22 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Aug-2026 | 15-Aug-2026 14:36:18 | 15-Aug-2026 08:32:00 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP01-SAF-LAY-0084 | FIREFIGHTING EQUIPMENT LAYOUT UPPER DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:17:22 | zm167dc@jutal.com | 20-Sep-2026 14:09:33 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000436 | MM-ASK-1A-WP01-SAF-LAY-0085 | FIREFIGHTING EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 09:19:28 | zm167dc@jutal.com | 10-Jun-2026 09:39:29 | Jumpol Sudjitjul | 18-Jun-2026 | 12-Jun-2026 14:35:43 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:32:06 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:18:10 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 12:20:33 | 25-Jun-2026 05:56:06 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP01-SAF-LAY-0085 | FIREFIGHTING EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:45:34 | zm167dc@jutal.com | 23-Jul-2026 17:02:51 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 13-Aug-2026 12:54:35 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 15-Aug-2026 13:21:27 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 15-Aug-2026 14:34:41 | 15-Aug-2026 08:29:38 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP01-SAF-LAY-0085 | FIREFIGHTING EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:17:48 | zm167dc@jutal.com | 20-Sep-2026 14:09:34 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000436 | MM-ASK-1A-WP01-SAF-LAY-0086 | FIREFIGHTING EQUIPMENT LAYOUT LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 09:19:51 | zm167dc@jutal.com | 10-Jun-2026 09:39:29 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 11:14:09 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:34:21 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 21:58:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 12:21:30 | 25-Jun-2026 05:57:23 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP01-SAF-LAY-0086 | FIREFIGHTING EQUIPMENT LAYOUT LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:45:59 | zm167dc@jutal.com | 23-Jul-2026 17:02:48 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 13-Aug-2026 12:54:58 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 15-Aug-2026 13:24:09 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 15-Aug-2026 14:35:28 | 15-Aug-2026 08:30:46 | 0 |  |  | Approver | Locate
AO-000436 | MM-ASK-1A-WP01-SAF-LAY-0087 | FIREFIGHTING EQUIPMENT LAYOUT SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 09:20:14 | zm167dc@jutal.com | 10-Jun-2026 09:39:29 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 11:15:22 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:25:16 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:17:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 12:22:44 | 25-Jun-2026 05:58:45 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP01-SAF-LAY-0087 | FIREFIGHTING EQUIPMENT LAYOUT SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:46:25 | zm167dc@jutal.com | 23-Jul-2026 17:02:48 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 13-Aug-2026 12:55:25 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 15-Aug-2026 13:27:05 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 15-Aug-2026 14:36:47 | 15-Aug-2026 08:34:24 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP01-SAF-LAY-0087 | FIREFIGHTING EQUIPMENT LAYOUT SUMP DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:18:13 | zm167dc@jutal.com | 20-Sep-2026 14:09:37 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000436 | MM-ASK-1A-WP01-SAF-LAY-0088 | FIREFIGHTING EQUIPMENT LAYOUT BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 09:20:38 | zm167dc@jutal.com | 10-Jun-2026 09:39:29 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 11:17:42 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:23:34 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:19:46 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 12:23:28 | 25-Jun-2026 06:00:04 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP01-SAF-LAY-0088 | FIREFIGHTING EQUIPMENT LAYOUT BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:46:53 | zm167dc@jutal.com | 23-Jul-2026 17:02:50 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 13-Aug-2026 12:55:55 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 15-Aug-2026 13:27:34 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 15-Aug-2026 14:37:37 | 15-Aug-2026 08:36:37 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP01-SAF-LAY-0088 | FIREFIGHTING EQUIPMENT LAYOUT BOAT LANDING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:18:39 | zm167dc@jutal.com | 20-Sep-2026 14:09:37 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP01-SAF-LAY-0095 | SAFETY SIGNS LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 15:21:52 | zm167dc@jutal.com | 26-Jun-2026 16:26:47 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 14-Jul-2026 11:51:06 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 14-Jul-2026 19:15:54 | APPR | Approved | Jumpol Sudjitjul | 09-Jul-2026 | 14-Jul-2026 19:48:38 | 14-Jul-2026 12:54:47 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP01-SAF-LAY-0095 | SAFETY SIGNS LAYOUT DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:28:42 | zm167dc@jutal.com | 14-Aug-2026 15:39:03 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 11:19:22 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 20:28:00 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 12:55:21 | 08-Sep-2026 06:56:24 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP01-SAF-LAY-0096 | SAFETY SIGNS LAYOUT UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 15:22:28 | zm167dc@jutal.com | 26-Jun-2026 16:26:47 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 14-Jul-2026 11:50:18 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 14-Jul-2026 19:08:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 14-Jul-2026 19:50:21 | 14-Jul-2026 12:56:01 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP01-SAF-LAY-0096 | SAFETY SIGNS LAYOUT UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:29:09 | zm167dc@jutal.com | 14-Aug-2026 15:39:03 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 11:19:43 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 20:37:02 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 12:56:33 | 08-Sep-2026 06:57:44 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP01-SAF-LAY-0097 | SAFETY SIGNS LAYOUT MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 15:22:57 | zm167dc@jutal.com | 26-Jun-2026 16:26:50 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 14-Jul-2026 11:52:08 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 14-Jul-2026 20:00:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 15-Jul-2026 08:37:28 | 15-Jul-2026 02:04:49 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP01-SAF-LAY-0097 | SAFETY SIGNS LAYOUT MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:29:39 | zm167dc@jutal.com | 14-Aug-2026 15:39:10 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 11:17:32 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 20:22:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:00:00 | 08-Sep-2026 06:59:12 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP01-SAF-LAY-0098 | SAFETY SIGNS LAYOUT LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 15:23:31 | zm167dc@jutal.com | 26-Jun-2026 16:26:48 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 16-Jul-2026 14:41:49 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 16-Jul-2026 22:10:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 17-Jul-2026 09:29:32 | 17-Jul-2026 03:06:51 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP01-SAF-LAY-0098 | SAFETY SIGNS LAYOUT LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:30:10 | zm167dc@jutal.com | 14-Aug-2026 15:39:07 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 11:18:50 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 20:25:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:07:01 | 08-Sep-2026 07:01:53 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP01-SAF-LAY-0099 | SAFETY SIGNS LAYOUT SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 15:24:02 | zm167dc@jutal.com | 26-Jun-2026 16:26:53 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 14-Jul-2026 11:53:45 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 14-Jul-2026 20:01:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 15-Jul-2026 08:38:06 | 15-Jul-2026 02:06:11 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP01-SAF-LAY-0099 | SAFETY SIGNS LAYOUT SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:30:40 | zm167dc@jutal.com | 14-Aug-2026 15:39:03 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 11:20:03 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 21:17:10 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:08:51 | 08-Sep-2026 07:03:15 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP01-SAF-LAY-0100 | SAFETY SIGNS LAYOUT BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 14:42:54 | zm167dc@jutal.com | 26-Jun-2026 16:26:50 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 14-Jul-2026 11:54:26 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 14-Jul-2026 20:01:32 | APPR | Approved | Jumpol Sudjitjul | 09-Jul-2026 | 15-Jul-2026 08:38:53 | 15-Jul-2026 02:14:42 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP01-SAF-LAY-0100 | SAFETY SIGNS LAYOUT BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:31:07 | zm167dc@jutal.com | 14-Aug-2026 15:39:09 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 11:20:18 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 21:42:40 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:01:00 | 08-Sep-2026 07:00:30 | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP01-SAF-LAY-0107 | FIRE AND GAS DETECTOR LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 15:57:42 | zm167dc@jutal.com | 30-Jun-2026 16:19:48 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 16:55:08 | Pongsakorn Monturat | 09-Jul-2026 | 17-Jul-2026 18:15:09 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 19-Jul-2026 12:17:49 | APPR | Approved | Jumpol Sudjitjul | 13-Jul-2026 | 20-Jul-2026 09:28:58 | 20-Jul-2026 03:26:06 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-SAF-LAY-0107 | FIRE AND GAS DETECTOR LAYOUT DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 11:32:30 | zm167dc@jutal.com | 24-Jul-2026 11:41:20 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 12:53:51 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 18-Aug-2026 23:22:01 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 19-Aug-2026 09:51:44 | 19-Aug-2026 03:11:39 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP01-SAF-LAY-0107 | FIRE AND GAS DETECTOR LAYOUT DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:51:24 | zm167dc@jutal.com | 18-Sep-2026 16:50:01 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP01-SAF-LAY-0108 | FIRE AND GAS DETECTOR LAYOUT UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:54:21 | zm167dc@jutal.com | 30-Jun-2026 15:34:13 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:54:51 | Pongsakorn Monturat | 09-Jul-2026 | 17-Jul-2026 18:15:36 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 19-Jul-2026 12:25:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 20-Jul-2026 09:36:18 | 20-Jul-2026 04:02:16 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-SAF-LAY-0108 | FIRE AND GAS DETECTOR LAYOUT UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 11:32:57 | zm167dc@jutal.com | 24-Jul-2026 11:41:20 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 12:54:36 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 18-Aug-2026 23:34:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 19-Aug-2026 09:47:44 | 19-Aug-2026 03:08:50 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP01-SAF-LAY-0108 | FIRE AND GAS DETECTOR LAYOUT UPPER DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:51:57 | zm167dc@jutal.com | 18-Sep-2026 16:49:59 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP01-SAF-LAY-0109 | FIRE AND GAS DETECTOR LAYOUT MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:54:58 | zm167dc@jutal.com | 30-Jun-2026 15:35:17 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:55:13 | Pongsakorn Monturat | 09-Jul-2026 | 17-Jul-2026 18:16:07 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 19-Jul-2026 12:50:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 20-Jul-2026 09:28:27 | 20-Jul-2026 03:01:43 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-SAF-LAY-0109 | FIRE AND GAS DETECTOR LAYOUT MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 11:33:23 | zm167dc@jutal.com | 24-Jul-2026 11:41:20 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 12:57:14 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 19-Aug-2026 14:57:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 19-Aug-2026 17:22:32 | 19-Aug-2026 10:53:59 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP01-SAF-LAY-0109 | FIRE AND GAS DETECTOR LAYOUT MEZZANINE DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:52:28 | zm167dc@jutal.com | 18-Sep-2026 16:49:58 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP01-SAF-LAY-0110 | FIRE AND GAS DETECTOR LAYOUT LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:55:50 | zm167dc@jutal.com | 30-Jun-2026 15:35:41 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:54:29 | Pongsakorn Monturat | 09-Jul-2026 | 17-Jul-2026 18:17:09 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 19-Jul-2026 12:57:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 20-Jul-2026 09:34:56 | 20-Jul-2026 04:00:53 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-SAF-LAY-0110 | FIRE AND GAS DETECTOR LAYOUT LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 11:33:49 | zm167dc@jutal.com | 24-Jul-2026 11:41:21 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 13:00:08 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 15:04:46 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 15:12:03 | 20-Aug-2026 08:42:32 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP01-SAF-LAY-0110 | FIRE AND GAS DETECTOR LAYOUT LOWER DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:52:58 | zm167dc@jutal.com | 18-Sep-2026 16:50:04 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP01-SAF-LAY-0111 | FIRE AND GAS DETECTOR LAYOUT SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:56:29 | zm167dc@jutal.com | 30-Jun-2026 15:36:10 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:55:34 | Pongsakorn Monturat | 09-Jul-2026 | 17-Jul-2026 18:18:22 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 19-Jul-2026 13:00:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 20-Jul-2026 09:26:41 | 20-Jul-2026 03:00:13 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-SAF-LAY-0111 | FIRE AND GAS DETECTOR LAYOUT SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 11:34:15 | zm167dc@jutal.com | 24-Jul-2026 11:41:20 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 13:01:08 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:12:30 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:47:59 | 20-Aug-2026 13:36:05 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP01-SAF-LAY-0111 | FIRE AND GAS DETECTOR LAYOUT SUMP DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:53:31 | zm167dc@jutal.com | 18-Sep-2026 16:50:04 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP01-SAF-LAY-0112 | FIRE AND GAS DETECTOR LAYOUT BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:57:10 | zm167dc@jutal.com | 30-Jun-2026 15:36:36 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:55:57 | Pongsakorn Monturat | 09-Jul-2026 | 17-Jul-2026 18:19:07 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 19-Jul-2026 13:02:44 | APPR | Approved | Jumpol Sudjitjul | 13-Jul-2026 | 20-Jul-2026 09:25:29 | 20-Jul-2026 02:58:50 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP01-SAF-LAY-0112 | FIRE AND GAS DETECTOR LAYOUT BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 10:44:22 | zm167dc@jutal.com | 24-Jul-2026 11:41:24 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 13:02:17 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:13:40 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:49:55 | 20-Aug-2026 13:14:53 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP01-SAF-LAY-0112 | FIRE AND GAS DETECTOR LAYOUT BOAT LANDING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:53:56 | zm167dc@jutal.com | 18-Sep-2026 16:50:01 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WP01-STR-DWG-1001 | WP01 TOPSIDE DRAWING INDEX SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:33:09 | zm167dc@jutal.com | 14-Aug-2026 08:38:51 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 08:19:53 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:49:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:05:39 | 28-Aug-2026 03:54:57 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WP01-STR-DWG-1002 | WP01 TOPSIDE DRAWING INDEX SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:33:37 | zm167dc@jutal.com | 14-Aug-2026 08:39:31 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 08:23:04 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:49:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:06:13 | 28-Aug-2026 03:56:10 | 0 |  |  | Approver | Locate
AO-000294 | MM-ASK-1A-WP01-STR-DWG-1011 | WP01 TOPSIDE DECK LOADING DIAGRAMS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:39:19 | zm167dc@jutal.com | 20-May-2026 18:09:58 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 28-May-2026 09:38:37 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 15:05:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 16:37:56 | 31-May-2026 16:56:06 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1011 | WP01 TOPSIDE DECK LOADING DIAGRAMS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 07:56:57 | zm167dc@jutal.com | 13-Jun-2026 08:08:44 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 01:09:28 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 19:58:40 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 00:01:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 24-Jun-2026 08:13:09 | 12-Jul-2026 11:45:54 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1011 | WP01 TOPSIDE DECK LOADING DIAGRAMS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:29:01 | zm167dc@jutal.com | 17-Jul-2026 12:46:33 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:21:31 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:06:53 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:07:01 | 27-Jul-2026 03:29:58 | 0 |  |  | Approver | Locate
AO-000294 | MM-ASK-1A-WP01-STR-DWG-1101 | WP01 TOPSIDE - UPPER DECK PRIMARY STEEL FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:39:46 | zm167dc@jutal.com | 20-May-2026 18:09:51 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 28-May-2026 09:41:45 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 15:44:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 16:52:48 | 31-May-2026 17:18:34 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP01-STR-DWG-1101 | WP01 TOPSIDE - UPPER DECK PRIMARY STEEL FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:54:24 | zm167dc@jutal.com | 13-Jun-2026 07:10:42 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:45:52 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:00:24 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:46:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:15:53 | 23-Jun-2026 01:50:35 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1101 | WP01 TOPSIDE - UPPER DECK PRIMARY STEEL FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:29:40 | zm167dc@jutal.com | 17-Jul-2026 12:46:31 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:23:12 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 14:15:30 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 24-Jul-2026 14:19:12 | 24-Jul-2026 07:38:21 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP01-STR-DWG-1101 | WP01 TOPSIDE - UPPER DECK PRIMARY STEEL FRAMING PLAN |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:51:24 | zm167dc@jutal.com | 03-Sep-2026 16:10:11 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 10-Sep-2026 14:41:18 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 17:27:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:24:01 | 12-Sep-2026 14:06:51 | 0 |  |  | Approver | Locate
AO-001483 | MM-ASK-1A-WP01-STR-DWG-1101 | WP01 TOPSIDE - UPPER DECK PRIMARY STEEL FRAMING PLAN |  | C3 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:38:18 | zm167dc@jutal.com | 18-Sep-2026 16:55:19 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000294 | MM-ASK-1A-WP01-STR-DWG-1102 | WP01 TOPSIDE - LOWER DECK PRIMARY STEEL FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:40:13 | zm167dc@jutal.com | 20-May-2026 18:09:55 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 28-May-2026 09:43:21 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 15:43:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 16:57:36 | 31-May-2026 17:19:35 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP01-STR-DWG-1102 | WP01 TOPSIDE - LOWER DECK PRIMARY STEEL FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:54:48 | zm167dc@jutal.com | 13-Jun-2026 07:11:01 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:46:26 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:02:10 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 23-Jun-2026 23:59:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 24-Jun-2026 08:13:48 | 12-Jul-2026 11:40:13 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1102 | WP01 TOPSIDE - LOWER DECK PRIMARY STEEL FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:30:08 | zm167dc@jutal.com | 17-Jul-2026 12:46:30 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:29:44 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 14:15:57 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 24-Jul-2026 14:21:13 | 24-Jul-2026 07:40:34 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP01-STR-DWG-1102 | WP01 TOPSIDE - LOWER DECK PRIMARY STEEL FRAMING PLAN |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:51:57 | zm167dc@jutal.com | 03-Sep-2026 16:10:07 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 10-Sep-2026 14:45:07 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 17:29:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:26:47 | 12-Sep-2026 14:08:24 | 0 |  |  | Approver | Locate
AO-001483 | MM-ASK-1A-WP01-STR-DWG-1102 | WP01 TOPSIDE - LOWER DECK PRIMARY STEEL FRAMING PLAN |  | C3 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:38:48 | zm167dc@jutal.com | 18-Sep-2026 16:55:35 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000294 | MM-ASK-1A-WP01-STR-DWG-1103 | WP01 TOPSIDE - ELEVATION TRUSS ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:40:38 | zm167dc@jutal.com | 20-May-2026 18:09:52 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 28-May-2026 09:44:57 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 15:50:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 16:58:47 | 31-May-2026 17:20:35 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP01-STR-DWG-1103 | WP01 TOPSIDE - ELEVATION TRUSS ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:01:10 | zm167dc@jutal.com | 10-Jun-2026 12:03:35 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 15:44:34 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 21:22:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:21:51 | 19-Jun-2026 04:41:53 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1103 | WP01 TOPSIDE - ELEVATION TRUSS ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:30:44 | zm167dc@jutal.com | 17-Jul-2026 12:46:32 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:31:36 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 14:16:38 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 24-Jul-2026 14:29:05 | 24-Jul-2026 08:21:21 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP01-STR-DWG-1103 | WP01 TOPSIDE - ELEVATION TRUSS ROW 'A' |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:52:23 | zm167dc@jutal.com | 03-Sep-2026 16:10:15 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 10-Sep-2026 14:47:38 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 17:30:05 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:29:00 | 12-Sep-2026 14:09:49 | 0 |  |  | Approver | Locate
AO-000294 | MM-ASK-1A-WP01-STR-DWG-1104 | WP01 TOPSIDE - ELEVATION TRUSS ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:41:03 | zm167dc@jutal.com | 20-May-2026 18:09:51 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 28-May-2026 09:46:48 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:12:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 17:07:44 | 31-May-2026 17:21:37 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP01-STR-DWG-1104 | WP01 TOPSIDE - ELEVATION TRUSS ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:01:35 | zm167dc@jutal.com | 10-Jun-2026 12:03:55 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 15:46:22 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:11:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 10:51:37 | 19-Jun-2026 04:20:55 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1104 | WP01 TOPSIDE - ELEVATION TRUSS ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:31:16 | zm167dc@jutal.com | 17-Jul-2026 12:46:33 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:33:06 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 14:17:04 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 24-Jul-2026 14:33:23 | 24-Jul-2026 08:23:32 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP01-STR-DWG-1104 | WP01 TOPSIDE - ELEVATION TRUSS ROW 'B' |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:52:47 | zm167dc@jutal.com | 03-Sep-2026 16:10:14 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 10-Sep-2026 14:52:06 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 17:31:40 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:31:57 | 12-Sep-2026 14:11:13 | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1105 | WP01 TOPSIDE - ELEVATION TRUSS ROW '1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:28:50 | zm167dc@jutal.com | 18-May-2026 20:05:15 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 25-May-2026 08:12:33 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:09:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:50:44 | 28-May-2026 09:14:34 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP01-STR-DWG-1105 | WP01 TOPSIDE - ELEVATION TRUSS ROW '1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:02:01 | zm167dc@jutal.com | 10-Jun-2026 12:04:12 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 15:47:47 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:08:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:22:21 | 19-Jun-2026 04:43:12 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1105 | WP01 TOPSIDE - ELEVATION TRUSS ROW '1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:31:48 | zm167dc@jutal.com | 17-Jul-2026 12:46:33 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:34:35 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 14:59:49 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 24-Jul-2026 15:03:38 | 24-Jul-2026 08:24:41 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP01-STR-DWG-1105 | WP01 TOPSIDE - ELEVATION TRUSS ROW '1' |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:53:13 | zm167dc@jutal.com | 03-Sep-2026 16:10:16 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 10-Sep-2026 14:55:56 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 17:33:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:36:45 | 12-Sep-2026 14:15:38 | 0 |  |  | Approver | Locate
AO-001483 | MM-ASK-1A-WP01-STR-DWG-1105 | WP01 TOPSIDE - ELEVATION TRUSS ROW '1' |  | C3 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:39:22 | zm167dc@jutal.com | 18-Sep-2026 16:55:51 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1106 | WP01 TOPSIDE - ELEVATION TRUSS ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:29:17 | zm167dc@jutal.com | 18-May-2026 20:05:43 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 25-May-2026 08:14:49 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:10:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:51:30 | 28-May-2026 09:16:33 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP01-STR-DWG-1106 | WP01 TOPSIDE - ELEVATION TRUSS ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:02:25 | zm167dc@jutal.com | 10-Jun-2026 12:04:26 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 15:49:26 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:13:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:22:50 | 19-Jun-2026 04:44:35 | 0 |  |  | Approver | Locate
AO-000721 | MM-ASK-1A-WP01-STR-DWG-1106 | WP01 TOPSIDE - ELEVATION TRUSS ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:30:10 | zm167dc@jutal.com | 17-Jul-2026 21:51:56 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 09:59:08 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 15:20:14 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 10:46:13 | 27-Jul-2026 03:58:09 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP01-STR-DWG-1106 | WP01 TOPSIDE - ELEVATION TRUSS ROW '2' |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:53:39 | zm167dc@jutal.com | 03-Sep-2026 16:10:16 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 10-Sep-2026 14:59:10 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 17:35:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:31:54 | 12-Sep-2026 14:12:36 | 0 |  |  | Approver | Locate
AO-001483 | MM-ASK-1A-WP01-STR-DWG-1106 | WP01 TOPSIDE - ELEVATION TRUSS ROW '2' |  | C3 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:39:54 | zm167dc@jutal.com | 18-Sep-2026 16:56:05 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000294 | MM-ASK-1A-WP01-STR-DWG-1107 | WP01 TOPSIDE - SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:41:32 | zm167dc@jutal.com | 20-May-2026 18:09:53 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 28-May-2026 09:48:28 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:13:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 16:44:12 | 31-May-2026 16:58:07 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP01-STR-DWG-1107 | WP01 TOPSIDE - SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:02:53 | zm167dc@jutal.com | 10-Jun-2026 13:03:01 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 15:50:55 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:37:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:36:57 | 19-Jun-2026 04:45:54 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1107 | WP01 TOPSIDE - SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:32:53 | zm167dc@jutal.com | 17-Jul-2026 12:46:37 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:36:27 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:00:19 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:46:59 | 27-Jul-2026 03:59:19 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP01-STR-DWG-1107 | WP01 TOPSIDE - SECTIONS |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:54:05 | zm167dc@jutal.com | 03-Sep-2026 16:10:17 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 10-Sep-2026 15:03:49 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 17:37:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:35:16 | 12-Sep-2026 14:14:05 | 0 |  |  | Approver | Locate
AO-001483 | MM-ASK-1A-WP01-STR-DWG-1107 | WP01 TOPSIDE - SECTIONS |  | C3 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:40:25 | zm167dc@jutal.com | 18-Sep-2026 16:56:21 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1108 | WP01 TOPSIDE - SECTIONS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:29:41 | zm167dc@jutal.com | 18-May-2026 20:05:58 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 25-May-2026 08:16:53 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:19:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:49:49 | 28-May-2026 09:12:33 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP01-STR-DWG-1108 | WP01 TOPSIDE - SECTIONS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:55:12 | zm167dc@jutal.com | 13-Jun-2026 07:11:14 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:47:43 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:03:35 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:26:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:31:08 | 22-Jun-2026 07:55:35 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1108 | WP01 TOPSIDE - SECTIONS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:33:26 | zm167dc@jutal.com | 17-Jul-2026 12:46:31 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:38:07 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:00:48 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:48:24 | 27-Jul-2026 04:00:28 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP01-STR-DWG-1108 | WP01 TOPSIDE - SECTIONS SHEET 2 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:54:30 | zm167dc@jutal.com | 03-Sep-2026 16:10:19 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 10-Sep-2026 15:06:35 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:06:39 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:21:58 | 12-Sep-2026 17:13:59 | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1121 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:30:06 | zm167dc@jutal.com | 18-May-2026 20:06:11 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 07:33:50 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:28:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:56:31 | 28-May-2026 09:44:27 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP01-STR-DWG-1121 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:55:38 | zm167dc@jutal.com | 13-Jun-2026 07:11:59 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:49:03 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:05:20 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 23-Jun-2026 23:59:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 24-Jun-2026 08:15:26 | 12-Jul-2026 10:39:54 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1121 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:33:54 | zm167dc@jutal.com | 17-Jul-2026 12:46:33 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:40:15 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:01:43 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:05:56 | 27-Jul-2026 03:28:48 | 0 |  |  | Approver | Locate
AO-001333 | MM-ASK-1A-WP01-STR-DWG-1121 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 1 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:23:09 | zm167dc@jutal.com | 11-Sep-2026 20:06:05 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000294 | MM-ASK-1A-WP01-STR-DWG-1122 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:41:59 | zm167dc@jutal.com | 20-May-2026 18:09:51 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 28-May-2026 09:50:22 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:17:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 16:39:18 | 31-May-2026 16:57:07 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP01-STR-DWG-1122 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:56:03 | zm167dc@jutal.com | 13-Jun-2026 07:12:13 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:51:04 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:06:50 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:47:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:16:21 | 23-Jun-2026 01:54:07 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1122 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:34:25 | zm167dc@jutal.com | 17-Jul-2026 12:46:37 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:47:42 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:02:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:31:24 | 27-Jul-2026 03:57:01 | 0 |  |  | Approver | Locate
AO-001333 | MM-ASK-1A-WP01-STR-DWG-1122 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 2 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:23:41 | zm167dc@jutal.com | 11-Sep-2026 20:06:08 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1123 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:30:36 | zm167dc@jutal.com | 18-May-2026 20:06:25 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 07:36:54 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:34:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:46:48 | 28-May-2026 09:10:34 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP01-STR-DWG-1123 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:56:28 | zm167dc@jutal.com | 13-Jun-2026 07:12:27 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:52:24 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:08:11 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 23-Jun-2026 23:58:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 24-Jun-2026 08:16:00 | 12-Jul-2026 11:43:24 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1123 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:34:50 | zm167dc@jutal.com | 17-Jul-2026 12:46:37 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:49:39 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:02:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:49:33 | 27-Jul-2026 04:05:16 | 0 |  |  | Approver | Locate
AO-001333 | MM-ASK-1A-WP01-STR-DWG-1123 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 3 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:24:08 | zm167dc@jutal.com | 11-Sep-2026 20:06:08 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1124 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:31:09 | zm167dc@jutal.com | 18-May-2026 20:08:52 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 07:41:33 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:38:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 09:00:53 | 28-May-2026 09:45:30 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP01-STR-DWG-1124 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:56:52 | zm167dc@jutal.com | 13-Jun-2026 07:12:39 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:54:25 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:09:41 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 16:46:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 16:48:54 | 22-Jun-2026 10:04:42 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1124 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:35:26 | zm167dc@jutal.com | 17-Jul-2026 12:46:39 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:56:30 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:04:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:50:22 | 27-Jul-2026 04:07:21 | 0 |  |  | Approver | Locate
AO-001333 | MM-ASK-1A-WP01-STR-DWG-1124 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 4 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:24:38 | zm167dc@jutal.com | 11-Sep-2026 20:06:11 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000294 | MM-ASK-1A-WP01-STR-DWG-1125 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:42:29 | zm167dc@jutal.com | 20-May-2026 18:09:53 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 28-May-2026 09:52:02 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:17:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 17:15:29 | 31-May-2026 17:22:37 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP01-STR-DWG-1125 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:57:16 | zm167dc@jutal.com | 13-Jun-2026 07:12:53 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:58:28 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:11:00 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:36:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:38:24 | 12-Jul-2026 11:44:40 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1125 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 5 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 12:35:56 | zm167dc@jutal.com | 17-Jul-2026 12:46:34 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 08:58:51 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:09:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:51:18 | 27-Jul-2026 04:08:37 | 0 |  |  | Approver | Locate
AO-001333 | MM-ASK-1A-WP01-STR-DWG-1125 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 5 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:25:06 | zm167dc@jutal.com | 11-Sep-2026 20:06:08 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000294 | MM-ASK-1A-WP01-STR-DWG-1126 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:42:57 | zm167dc@jutal.com | 20-May-2026 18:09:59 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 28-May-2026 09:53:42 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:18:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 17:09:47 | 31-May-2026 17:24:41 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1126 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 07:57:20 | zm167dc@jutal.com | 13-Jun-2026 08:10:08 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:00:44 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:12:26 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:38:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:50:10 | 22-Jun-2026 09:28:36 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1126 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 6 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:52:50 | zm167dc@jutal.com | 17-Jul-2026 11:58:05 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 09:00:41 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:09:22 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:51:56 | 27-Jul-2026 04:22:52 | 0 |  |  | Approver | Locate
AO-001333 | MM-ASK-1A-WP01-STR-DWG-1126 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 6 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:25:35 | zm167dc@jutal.com | 11-Sep-2026 20:06:11 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1127 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:31:37 | zm167dc@jutal.com | 18-May-2026 20:08:07 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 07:43:52 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:39:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:45:46 | 28-May-2026 09:07:41 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1127 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 07:57:48 | zm167dc@jutal.com | 13-Jun-2026 08:10:21 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:01:17 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:13:56 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:39:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:51:37 | 22-Jun-2026 09:32:03 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1127 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:53:13 | zm167dc@jutal.com | 17-Jul-2026 11:58:05 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 09:04:44 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:11:34 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:43:28 | 27-Jul-2026 04:20:35 | 0 |  |  | Approver | Locate
AO-001361 | MM-ASK-1A-WP01-STR-DWG-1127 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 7 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 20:39:54 | zm167dc@jutal.com | 15-Sep-2026 13:55:05 | Jumpol Sudjitjul | 23-Sep-2026 |  | Washira Kaew-amatawong | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1128 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:32:05 | zm167dc@jutal.com | 18-May-2026 20:08:22 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 07:45:54 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:41:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:52:48 | 28-May-2026 09:17:34 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1128 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 07:58:12 | zm167dc@jutal.com | 13-Jun-2026 08:10:37 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:02:04 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:15:19 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:16:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:16:57 | 23-Jun-2026 01:38:38 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1128 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 8 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:53:37 | zm167dc@jutal.com | 17-Jul-2026 11:58:06 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 09:08:53 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:12:14 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:29:32 | 27-Jul-2026 04:15:05 | 0 |  |  | Approver | Locate
AO-001361 | MM-ASK-1A-WP01-STR-DWG-1128 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 8 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 20:40:23 | zm167dc@jutal.com | 15-Sep-2026 13:55:07 | Jumpol Sudjitjul | 23-Sep-2026 |  | Washira Kaew-amatawong | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1129 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:32:31 | zm167dc@jutal.com | 18-May-2026 20:08:35 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 07:48:05 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:42:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:51:28 | 28-May-2026 09:15:32 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1129 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 9 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 07:58:35 | zm167dc@jutal.com | 13-Jun-2026 08:10:51 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:26:30 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:16:38 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:45:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:54:22 | 22-Jun-2026 09:35:23 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1129 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 9 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:54:01 | zm167dc@jutal.com | 17-Jul-2026 11:58:09 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 09:16:23 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:12:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:52:36 | 27-Jul-2026 04:24:03 | 0 |  |  | Approver | Locate
AO-001361 | MM-ASK-1A-WP01-STR-DWG-1129 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 9 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 20:40:55 | zm167dc@jutal.com | 15-Sep-2026 13:55:09 | Jumpol Sudjitjul | 23-Sep-2026 |  | Washira Kaew-amatawong | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1130 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 10 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:32:57 | zm167dc@jutal.com | 18-May-2026 20:07:52 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 07:49:57 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:45:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:50:34 | 28-May-2026 09:13:35 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1130 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 10 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 07:58:58 | zm167dc@jutal.com | 13-Jun-2026 08:11:06 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:27:38 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:17:58 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:44:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:51:41 | 22-Jun-2026 09:33:33 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1130 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 10 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:54:25 | zm167dc@jutal.com | 17-Jul-2026 11:58:07 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 09:18:08 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:13:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:53:28 | 27-Jul-2026 04:25:16 | 0 |  |  | Approver | Locate
AO-001361 | MM-ASK-1A-WP01-STR-DWG-1130 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 10 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 20:41:24 | zm167dc@jutal.com | 15-Sep-2026 13:55:05 | Jumpol Sudjitjul | 23-Sep-2026 |  | Washira Kaew-amatawong | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1131 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 11 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:33:20 | zm167dc@jutal.com | 18-May-2026 20:07:38 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 07:53:35 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:50:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:44:11 | 28-May-2026 09:04:36 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1131 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 11 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 07:59:20 | zm167dc@jutal.com | 13-Jun-2026 08:11:04 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:26:56 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:19:17 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:43:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:50:20 | 22-Jun-2026 09:30:19 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1131 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 11 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:54:53 | zm167dc@jutal.com | 17-Jul-2026 11:58:10 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 09:19:45 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:14:03 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:36:44 | 27-Jul-2026 04:18:28 | 0 |  |  | Approver | Locate
AO-001361 | MM-ASK-1A-WP01-STR-DWG-1131 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 11 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 20:41:58 | zm167dc@jutal.com | 15-Sep-2026 13:55:05 | Jumpol Sudjitjul | 23-Sep-2026 |  | Washira Kaew-amatawong | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1132 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 12 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:33:43 | zm167dc@jutal.com | 18-May-2026 20:07:24 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 08:06:47 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:52:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:49:34 | 28-May-2026 09:11:35 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1132 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 12 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 07:59:43 | zm167dc@jutal.com | 13-Jun-2026 08:11:19 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:28:35 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:20:43 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:58:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 15:01:40 | 22-Jun-2026 09:36:52 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1132 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 12 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:55:23 | zm167dc@jutal.com | 17-Jul-2026 11:58:11 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 09:21:02 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:15:07 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:54:55 | 27-Jul-2026 04:26:20 | 0 |  |  | Approver | Locate
AO-001361 | MM-ASK-1A-WP01-STR-DWG-1132 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 12 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 20:42:30 | zm167dc@jutal.com | 15-Sep-2026 13:55:07 | Jumpol Sudjitjul | 23-Sep-2026 |  | Washira Kaew-amatawong | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1133 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 13 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:34:06 | zm167dc@jutal.com | 18-May-2026 20:07:09 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 08:10:36 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 23:56:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:46:56 | 28-May-2026 09:49:19 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1133 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 13 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:00:06 | zm167dc@jutal.com | 13-Jun-2026 08:11:35 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:29:17 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:23:03 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:24:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:26:56 | 22-Jun-2026 07:52:32 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1133 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 13 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:55:46 | zm167dc@jutal.com | 17-Jul-2026 11:58:07 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 09:54:33 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:16:09 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:35:58 | 27-Jul-2026 04:16:11 | 0 |  |  | Approver | Locate
AO-000283 | MM-ASK-1A-WP01-STR-DWG-1134 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:34:28 | zm167dc@jutal.com | 18-May-2026 20:06:52 | Jumpol Sudjitjul | 27-May-2026 |  | Washira Kaew-amatawong | 28-May-2026 | 26-May-2026 08:17:54 | Pornlert Wanaphattharaphan | 29-May-2026 | 28-May-2026 00:00:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 28-May-2026 08:45:50 | 28-May-2026 09:08:47 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP01-STR-DWG-1134 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 14 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:00:29 | zm167dc@jutal.com | 13-Jun-2026 08:11:48 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:29:53 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:24:56 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:17:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:23:29 | 22-Jun-2026 07:47:28 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WP01-STR-DWG-1134 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 14 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:56:10 | zm167dc@jutal.com | 17-Jul-2026 11:58:12 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 22-Jul-2026 10:01:04 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 15:17:55 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 10:55:34 | 27-Jul-2026 04:32:46 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP01-STR-DWG-1135 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 15 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:09:22 | zm167dc@jutal.com | 07-Jul-2026 18:24:39 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:34:12 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 09:43:17 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 00:59:06 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:27:54 | 20-Jul-2026 03:48:55 | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-WP01-STR-DWG-1135 | WP01 TOPSIDE JOINT CONNECTION DETAILS SHEET 15 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 18:32:29 | zm167dc@jutal.com | 06-Aug-2026 14:12:02 | Jumpol Sudjitjul | 17-Aug-2026 |  | Washira Kaew-amatawong | 18-Aug-2026 | 15-Aug-2026 20:29:25 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 17-Aug-2026 00:03:04 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 08:51:56 | 17-Aug-2026 02:36:07 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP01-STR-DWG-1136 | WP01 TOPSIDE PERSONNEL ACCESS RAMP (PAR) SUPPORT DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:09:47 | zm167dc@jutal.com | 07-Jul-2026 18:24:39 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:35:08 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 09:45:26 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 00:59:29 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:34:30 | 20-Jul-2026 04:13:27 | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-WP01-STR-DWG-1136 | WP01 TOPSIDE PERSONNEL ACCESS RAMP (PAR) SUPPORT DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 18:32:55 | zm167dc@jutal.com | 06-Aug-2026 14:11:55 | Jumpol Sudjitjul | 17-Aug-2026 |  | Washira Kaew-amatawong | 18-Aug-2026 | 15-Aug-2026 20:31:51 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 17-Aug-2026 00:09:10 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 09:19:09 | 17-Aug-2026 03:05:22 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1201 | WP01 TOPSIDE UPPER DECK SECONDARY STEEL FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:27:00 | zm167dc@jutal.com | 29-May-2026 12:51:47 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:20:48 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 12:56:23 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 06-Jun-2026 23:26:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:00:35 | 07-Jun-2026 17:09:58 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1201 | WP01 TOPSIDE UPPER DECK SECONDARY STEEL FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:54:37 | zm167dc@jutal.com | 22-Jun-2026 13:21:41 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 11:09:25 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:38:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 29-Jun-2026 09:19:13 | 29-Jun-2026 03:03:05 | 0 |  |  | Approver | Locate
AO-000833 | MM-ASK-1A-WP01-STR-DWG-1201 | WP01 TOPSIDE UPPER DECK SECONDARY STEEL FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:15:36 | zm167dc@jutal.com | 31-Jul-2026 17:19:15 | Jumpol Sudjitjul | 11-Aug-2026 |  | Washira Kaew-amatawong | 13-Aug-2026 | 13-Aug-2026 09:27:18 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 14-Aug-2026 00:02:43 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 08:12:51 | 14-Aug-2026 01:19:14 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1202 | WP01 TOPSIDE LOWER DECK SECONDARY STEEL FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:27:25 | zm167dc@jutal.com | 29-May-2026 12:52:13 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:21:30 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:00:21 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 06-Jun-2026 23:57:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:01:10 | 07-Jun-2026 17:11:11 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1202 | WP01 TOPSIDE LOWER DECK SECONDARY STEEL FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:55:01 | zm167dc@jutal.com | 22-Jun-2026 13:22:12 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 11:11:50 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:42:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 29-Jun-2026 20:35:00 | 29-Jun-2026 13:38:22 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-STR-DWG-1202 | WP01 TOPSIDE LOWER DECK SECONDARY STEEL FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 13:57:27 | zm167dc@jutal.com | 31-Jul-2026 13:58:54 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 10:42:41 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:06:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:50:24 | 13-Aug-2026 02:15:09 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1203 | WP01 TOPSIDE MEZZANINE DECK FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:27:55 | zm167dc@jutal.com | 29-May-2026 12:54:30 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:22:52 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:03:28 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 00:13:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:01:49 | 07-Jun-2026 17:12:16 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1203 | WP01 TOPSIDE MEZZANINE DECK FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:55:25 | zm167dc@jutal.com | 22-Jun-2026 13:22:30 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 11:13:48 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:45:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 29-Jun-2026 11:27:51 | 29-Jun-2026 04:59:30 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-STR-DWG-1203 | WP01 TOPSIDE MEZZANINE DECK FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 13:57:54 | zm167dc@jutal.com | 31-Jul-2026 13:59:20 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 10:45:07 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:06:29 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:51:40 | 13-Aug-2026 02:16:16 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1204 | WP01 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:28:27 | zm167dc@jutal.com | 29-May-2026 12:54:58 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:25:05 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:05:21 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 00:27:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:02:23 | 07-Jun-2026 17:13:20 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1204 | WP01 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:55:49 | zm167dc@jutal.com | 22-Jun-2026 13:22:51 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 11:19:21 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:46:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 29-Jun-2026 20:36:01 | 29-Jun-2026 13:39:43 | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-WP01-STR-DWG-1204 | WP01 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 18:33:24 | zm167dc@jutal.com | 06-Aug-2026 14:11:55 | Jumpol Sudjitjul | 17-Aug-2026 |  | Washira Kaew-amatawong | 18-Aug-2026 | 15-Aug-2026 20:34:53 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 17-Aug-2026 00:09:57 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 09:20:54 | 17-Aug-2026 03:08:00 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1205 | WP01 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:28:51 | zm167dc@jutal.com | 29-May-2026 12:54:44 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:23:49 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:10:26 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:16:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:03:03 | 07-Jun-2026 17:14:25 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1205 | WP01 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:56:12 | zm167dc@jutal.com | 22-Jun-2026 13:23:17 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:04:55 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:48:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:43:51 | 30-Jun-2026 06:49:38 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-STR-DWG-1205 | WP01 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 13:58:22 | zm167dc@jutal.com | 31-Jul-2026 14:24:37 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 10:49:17 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:07:17 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:52:34 | 13-Aug-2026 02:17:23 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1221 | WP01 TOPSIDE SUMP DECK FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:29:22 | zm167dc@jutal.com | 29-May-2026 12:57:12 | Jumpol Sudjitjul | 10-Jun-2026 |  | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:18:37 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:18:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:03:36 | 07-Jun-2026 17:15:29 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1221 | WP01 TOPSIDE SUMP DECK FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:56:36 | zm167dc@jutal.com | 22-Jun-2026 13:27:52 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:23:22 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:49:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:44:14 | 30-Jun-2026 06:51:00 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-STR-DWG-1221 | WP01 TOPSIDE SUMP DECK FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 13:58:48 | zm167dc@jutal.com | 31-Jul-2026 14:24:36 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 10:54:03 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:06:50 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:54:11 | 13-Aug-2026 02:19:31 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1222 | WP01 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:29:48 | zm167dc@jutal.com | 29-May-2026 12:57:26 | Jumpol Sudjitjul | 10-Jun-2026 |  | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:20:14 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:25:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:04:53 | 07-Jun-2026 17:16:35 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1222 | WP01 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:56:59 | zm167dc@jutal.com | 22-Jun-2026 13:28:16 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:25:36 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:49:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:44:56 | 30-Jun-2026 06:32:13 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-STR-DWG-1222 | WP01 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 13:59:17 | zm167dc@jutal.com | 31-Jul-2026 14:24:37 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 11:21:58 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:07:40 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:54:56 | 13-Aug-2026 02:20:41 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1223 | WP01 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:30:10 | zm167dc@jutal.com | 29-May-2026 12:57:44 | Jumpol Sudjitjul | 10-Jun-2026 |  | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:22:34 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:21:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:05:35 | 07-Jun-2026 17:17:38 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1223 | WP01 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:57:22 | zm167dc@jutal.com | 22-Jun-2026 13:28:38 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:39:57 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:50:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:46:55 | 30-Jun-2026 06:33:43 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-STR-DWG-1223 | WP01 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 13:59:51 | zm167dc@jutal.com | 31-Jul-2026 14:24:36 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 11:27:57 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:07:59 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:55:54 | 13-Aug-2026 02:21:47 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1224 | WP01 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:30:32 | zm167dc@jutal.com | 29-May-2026 12:57:57 | Jumpol Sudjitjul | 10-Jun-2026 |  | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:25:19 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:26:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:06:13 | 07-Jun-2026 17:18:52 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1224 | WP01 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:57:47 | zm167dc@jutal.com | 22-Jun-2026 13:28:58 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:42:06 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 02-Jul-2026 00:16:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 02-Jul-2026 11:00:32 | 02-Jul-2026 04:43:08 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-STR-DWG-1224 | WP01 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:00:24 | zm167dc@jutal.com | 31-Jul-2026 14:24:37 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 12:29:37 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:08:26 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 08:59:01 | 13-Aug-2026 02:24:56 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1231 | WP01 TOPSIDE STANDARD JOINT DETAILS FOR SECONDARY BEAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:31:01 | zm167dc@jutal.com | 29-May-2026 13:08:28 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:38:19 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:27:11 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:27:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:06:52 | 07-Jun-2026 17:20:08 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1231 | WP01 TOPSIDE STANDARD JOINT DETAILS FOR SECONDARY BEAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:58:11 | zm167dc@jutal.com | 22-Jun-2026 13:49:14 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:43:57 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:51:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:47:30 | 30-Jun-2026 06:36:25 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP01-STR-DWG-1231 | WP01 TOPSIDE STANDARD JOINT DETAILS FOR SECONDARY BEAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:00:52 | zm167dc@jutal.com | 31-Jul-2026 14:24:37 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 12:35:24 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:09:57 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 09:00:56 | 13-Aug-2026 02:26:02 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1241 | WP01 TOPSIDE VENT BOOM PLAN AND ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:31:27 | zm167dc@jutal.com | 29-May-2026 13:04:37 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:32:18 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:31:04 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:30:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:08:27 | 07-Jun-2026 18:13:18 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1241 | WP01 TOPSIDE VENT BOOM PLAN AND ELEVATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:58:38 | zm167dc@jutal.com | 22-Jun-2026 13:33:31 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:45:48 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:52:25 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:43:22 | 30-Jun-2026 06:26:16 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP01-STR-DWG-1241 | WP01 TOPSIDE VENT BOOM PLAN AND ELEVATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:45:50 | zm167dc@jutal.com | 07-Aug-2026 15:03:45 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 15:17:29 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:34:02 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:00:16 | 21-Aug-2026 02:40:44 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1242 | WP01 TOPSIDE VENT BOOM SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:31:52 | zm167dc@jutal.com | 29-May-2026 13:04:37 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:35:21 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:33:04 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:34:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:07:51 | 07-Jun-2026 17:21:15 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1242 | WP01 TOPSIDE VENT BOOM SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:59:03 | zm167dc@jutal.com | 22-Jun-2026 13:33:34 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:50:44 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:52:53 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:48:20 | 30-Jun-2026 06:38:57 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP01-STR-DWG-1242 | WP01 TOPSIDE VENT BOOM SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:46:15 | zm167dc@jutal.com | 07-Aug-2026 15:03:44 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 15:20:26 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:34:34 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:00:51 | 21-Aug-2026 02:41:50 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1243 | WP01 TOPSIDE VENT BOOM WALKWAY PLAN AND SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:32:15 | zm167dc@jutal.com | 29-May-2026 13:04:37 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:31:09 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:34:39 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:40:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:08:59 | 07-Jun-2026 18:14:24 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1243 | WP01 TOPSIDE VENT BOOM WALKWAY PLAN AND SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:59:27 | zm167dc@jutal.com | 22-Jun-2026 13:33:30 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:53:21 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:00:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:50:42 | 30-Jun-2026 06:41:34 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP01-STR-DWG-1243 | WP01 TOPSIDE VENT BOOM WALKWAY PLAN AND SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:46:42 | zm167dc@jutal.com | 07-Aug-2026 15:03:44 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 15:22:46 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:35:06 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:01:39 | 21-Aug-2026 02:42:55 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1244 | WP01 TOPSIDE VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:32:51 | zm167dc@jutal.com | 29-May-2026 13:04:36 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:29:42 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:36:16 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:45:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:09:27 | 07-Jun-2026 18:15:30 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1244 | WP01 TOPSIDE VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 21:59:52 | zm167dc@jutal.com | 22-Jun-2026 13:33:32 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:55:04 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:01:32 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:53:01 | 30-Jun-2026 06:42:47 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP01-STR-DWG-1244 | WP01 TOPSIDE VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:47:10 | zm167dc@jutal.com | 07-Aug-2026 15:03:47 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 15:25:38 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:36:25 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:02:17 | 21-Aug-2026 02:44:02 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1245 | WP01 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:33:16 | zm167dc@jutal.com | 29-May-2026 13:04:37 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:36:25 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:37:40 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:42:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:10:10 | 07-Jun-2026 18:16:35 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1245 | WP01 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:00:24 | zm167dc@jutal.com | 22-Jun-2026 13:33:36 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:56:58 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:02:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:48:24 | 30-Jun-2026 06:40:17 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP01-STR-DWG-1245 | WP01 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:47:37 | zm167dc@jutal.com | 07-Aug-2026 15:03:50 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 15:29:20 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:36:54 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:02:53 | 21-Aug-2026 02:45:10 | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1246 | WP01 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:33:53 | zm167dc@jutal.com | 29-May-2026 13:04:37 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:33:57 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:39:06 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:47:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:10:50 | 07-Jun-2026 18:17:41 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP01-STR-DWG-1246 | WP01 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:00:57 | zm167dc@jutal.com | 22-Jun-2026 13:33:30 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 14:59:01 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:02:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:47:36 | 30-Jun-2026 06:37:45 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP01-STR-DWG-1246 | WP01 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:48:04 | zm167dc@jutal.com | 07-Aug-2026 15:03:50 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 15:35:24 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:37:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:03:33 | 21-Aug-2026 02:46:25 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP01-STR-DWG-1251 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:47:22 | zm167dc@jutal.com | 11-Jun-2026 15:08:39 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:32:46 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:30:15 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 22:55:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:38:41 | 19-Jun-2026 04:47:05 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP01-STR-DWG-1251 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:06:42 | zm167dc@jutal.com | 05-Sep-2026 18:28:17 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:07:47 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 22:38:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 09:54:09 | 16-Sep-2026 02:59:42 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP01-STR-DWG-1252 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:47:51 | zm167dc@jutal.com | 11-Jun-2026 15:09:10 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:33:41 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:32:16 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 22:59:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:39:24 | 19-Jun-2026 04:48:22 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP01-STR-DWG-1252 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:07:20 | zm167dc@jutal.com | 05-Sep-2026 18:28:16 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:10:39 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 22:39:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 10:36:03 | 16-Sep-2026 04:37:15 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP01-STR-DWG-1253 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:48:26 | zm167dc@jutal.com | 11-Jun-2026 15:09:28 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:34:14 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:37:04 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:08:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:39:48 | 19-Jun-2026 05:18:52 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP01-STR-DWG-1253 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:07:47 | zm167dc@jutal.com | 05-Sep-2026 18:28:16 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:14:41 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 22:41:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 09:56:28 | 16-Sep-2026 03:01:25 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP01-STR-DWG-1254 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:48:55 | zm167dc@jutal.com | 11-Jun-2026 15:09:47 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:35:17 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:39:25 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:06:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:40:08 | 19-Jun-2026 05:20:07 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP01-STR-DWG-1254 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:08:17 | zm167dc@jutal.com | 05-Sep-2026 18:28:17 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:17:57 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 22:42:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 09:58:12 | 16-Sep-2026 03:39:59 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP01-STR-DWG-1255 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:49:31 | zm167dc@jutal.com | 11-Jun-2026 15:10:20 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:36:18 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:42:30 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:06:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 10:49:09 | 19-Jun-2026 04:16:58 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP01-STR-DWG-1255 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:08:44 | zm167dc@jutal.com | 05-Sep-2026 18:28:21 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:21:16 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 22:43:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 10:11:11 | 16-Sep-2026 03:41:28 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP01-STR-DWG-1256 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:49:58 | zm167dc@jutal.com | 11-Jun-2026 15:11:23 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:42:26 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:45:50 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:14:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:40:52 | 19-Jun-2026 05:21:18 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP01-STR-DWG-1256 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:09:11 | zm167dc@jutal.com | 05-Sep-2026 18:28:16 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:24:16 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 22:44:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 10:47:11 | 16-Sep-2026 04:38:34 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP01-STR-DWG-1257 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:50:24 | zm167dc@jutal.com | 11-Jun-2026 15:11:22 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:38:32 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:48:29 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:11:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:41:57 | 19-Jun-2026 05:22:28 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP01-STR-DWG-1257 | WP01 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:09:40 | zm167dc@jutal.com | 05-Sep-2026 18:28:18 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:28:03 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 22:58:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 10:13:48 | 16-Sep-2026 03:42:56 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP01-STR-DWG-1301 | WP01 TOPSIDE UPPER DECK FLOORING & HANDRAIL LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:34:20 | zm167dc@jutal.com | 10-Jul-2026 17:31:55 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:07:19 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 15:39:06 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:09:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 10:41:25 | 27-Jul-2026 04:09:51 | 0 |  |  | Approver | Locate
AO-001085 | MM-ASK-1A-WP01-STR-DWG-1301 | WP01 TOPSIDE UPPER DECK FLOORING & HANDRAIL LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 12:32:12 | zm167dc@jutal.com | 24-Aug-2026 20:30:28 | Jumpol Sudjitjul | 02-Sep-2026 |  | Washira Kaew-amatawong | 03-Sep-2026 | 03-Sep-2026 15:43:22 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 22:37:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 09:57:46 | 07-Sep-2026 03:16:54 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP01-STR-DWG-1302 | WP01 TOPSIDE LOWER DECK FLOORING & HANDRAIL LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:34:49 | zm167dc@jutal.com | 10-Jul-2026 17:31:56 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:06:35 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 15:40:31 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:09:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 10:56:12 | 27-Jul-2026 04:33:56 | 0 |  |  | Approver | Locate
AO-001085 | MM-ASK-1A-WP01-STR-DWG-1302 | WP01 TOPSIDE LOWER DECK FLOORING & HANDRAIL LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 13:57:33 | zm167dc@jutal.com | 24-Aug-2026 20:30:33 | Jumpol Sudjitjul | 02-Sep-2026 |  | Washira Kaew-amatawong | 03-Sep-2026 | 03-Sep-2026 15:45:33 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 22:55:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 09:58:38 | 07-Sep-2026 03:39:29 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP01-STR-DWG-1303 | WP01 TOPSIDE MEZZANINE DECK FLOORING & HANDRAIL LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:35:13 | zm167dc@jutal.com | 10-Jul-2026 17:36:40 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:09:16 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 15:41:50 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:10:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 10:54:08 | 27-Jul-2026 04:13:56 | 0 |  |  | Approver | Locate
AO-001085 | MM-ASK-1A-WP01-STR-DWG-1303 | WP01 TOPSIDE MEZZANINE DECK FLOORING & HANDRAIL LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 13:58:08 | zm167dc@jutal.com | 24-Aug-2026 20:30:34 | Jumpol Sudjitjul | 02-Sep-2026 |  | Washira Kaew-amatawong | 03-Sep-2026 | 03-Sep-2026 15:47:27 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:03:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 09:59:30 | 07-Sep-2026 03:40:57 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP01-STR-DWG-1304 | WP01 TOPSIDE SUMP DECK FLOORING & HANDRAIL LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:35:41 | zm167dc@jutal.com | 10-Jul-2026 17:31:55 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:02:18 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 15:43:05 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:12:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 10:57:06 | 27-Jul-2026 04:36:01 | 0 |  |  | Approver | Locate
AO-001117 | MM-ASK-1A-WP01-STR-DWG-1304 | WP01 TOPSIDE SUMP DECK FLOORING & HANDRAIL LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 12:02:28 | zm167dc@jutal.com | 28-Aug-2026 13:37:27 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 08:41:54 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 22:20:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 08-Sep-2026 13:09:20 | 08-Sep-2026 07:04:42 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP01-STR-DWG-1305 | WP01 TOPSIDE FLOORING SECTIONS & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:36:10 | zm167dc@jutal.com | 10-Jul-2026 17:40:05 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:19:36 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 15:44:24 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:13:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 10:57:55 | 27-Jul-2026 04:37:15 | 0 |  |  | Approver | Locate
AO-001085 | MM-ASK-1A-WP01-STR-DWG-1305 | WP01 TOPSIDE FLOORING SECTIONS & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 12:32:41 | zm167dc@jutal.com | 24-Aug-2026 20:30:27 | Jumpol Sudjitjul | 02-Sep-2026 |  | Washira Kaew-amatawong | 03-Sep-2026 | 03-Sep-2026 15:49:50 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:13:32 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:00:41 | 07-Sep-2026 03:42:14 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP01-STR-DWG-1306 | WP01 TOPSIDE FLOORING SECTIONS & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:36:44 | zm167dc@jutal.com | 10-Jul-2026 17:40:18 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:20:08 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 15:45:42 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:13:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 10:59:17 | 27-Jul-2026 04:38:25 | 0 |  |  | Approver | Locate
AO-001117 | MM-ASK-1A-WP01-STR-DWG-1306 | WP01 TOPSIDE FLOORING SECTIONS & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 12:02:53 | zm167dc@jutal.com | 28-Aug-2026 13:37:30 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 08:43:47 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 22:21:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 08-Sep-2026 13:09:59 | 08-Sep-2026 07:06:10 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1311 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:02:50 | zm167dc@jutal.com | 19-Jun-2026 16:12:30 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:23:58 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:30:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:16:41 | 24-Jun-2026 01:43:44 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1311 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:06:39 | zm167dc@jutal.com | 20-Aug-2026 14:19:16 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 13:53:21 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:35:34 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 15:54:30 | 30-Aug-2026 09:55:14 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1312 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:03:19 | zm167dc@jutal.com | 19-Jun-2026 16:13:00 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:25:55 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:31:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:19:50 | 24-Jun-2026 01:44:56 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1312 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:07:25 | zm167dc@jutal.com | 20-Aug-2026 14:20:11 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 13:54:50 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:35:55 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 15:56:39 | 30-Aug-2026 09:56:22 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1313 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:03:44 | zm167dc@jutal.com | 19-Jun-2026 16:13:30 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:29:15 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:34:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:20:21 | 24-Jun-2026 01:46:09 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1313 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:08:04 | zm167dc@jutal.com | 20-Aug-2026 14:20:43 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 13:56:19 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:36:14 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 15:58:40 | 30-Aug-2026 09:57:27 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1314 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:04:11 | zm167dc@jutal.com | 19-Jun-2026 16:13:46 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:30:53 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:34:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:21:19 | 24-Jun-2026 01:47:23 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1314 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:08:35 | zm167dc@jutal.com | 20-Aug-2026 14:21:22 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 13:57:51 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:36:37 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:03:31 | 30-Aug-2026 09:58:33 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1315 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:04:39 | zm167dc@jutal.com | 19-Jun-2026 16:14:02 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:32:46 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:36:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:21:49 | 24-Jun-2026 01:48:35 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1315 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:09:06 | zm167dc@jutal.com | 20-Aug-2026 14:21:55 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 13:59:36 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:37:14 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:04:41 | 30-Aug-2026 09:28:09 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1316 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:05:04 | zm167dc@jutal.com | 19-Jun-2026 16:18:18 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:35:23 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:40:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:22:26 | 24-Jun-2026 01:49:45 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1316 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:09:38 | zm167dc@jutal.com | 20-Aug-2026 14:24:41 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:02:07 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:38:02 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:09:37 | 30-Aug-2026 09:31:36 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1317 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:05:31 | zm167dc@jutal.com | 19-Jun-2026 16:18:57 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:39:26 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:41:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:23:00 | 24-Jun-2026 01:50:58 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1317 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:10:16 | zm167dc@jutal.com | 20-Aug-2026 14:25:03 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:03:48 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:38:39 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:07:36 | 30-Aug-2026 09:29:20 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1318 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:05:56 | zm167dc@jutal.com | 19-Jun-2026 16:19:34 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:42:16 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:43:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:23:30 | 24-Jun-2026 01:52:10 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1318 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:11:00 | zm167dc@jutal.com | 20-Aug-2026 14:25:23 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:05:41 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:39:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 15:48:13 | 30-Aug-2026 09:23:22 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1319 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:06:21 | zm167dc@jutal.com | 19-Jun-2026 16:20:13 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:44:13 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:43:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:24:00 | 24-Jun-2026 01:55:37 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1319 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 9 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:11:40 | zm167dc@jutal.com | 20-Aug-2026 14:25:49 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:07:53 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:39:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:11:44 | 30-Aug-2026 09:35:02 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1320 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 10 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:06:46 | zm167dc@jutal.com | 19-Jun-2026 16:23:23 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:46:11 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:44:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:24:32 | 24-Jun-2026 01:56:51 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1320 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 10 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:12:17 | zm167dc@jutal.com | 20-Aug-2026 14:26:16 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:10:23 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:44:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 15:55:39 | 30-Aug-2026 09:27:02 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP01-STR-DWG-1321 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 11 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:07:11 | zm167dc@jutal.com | 19-Jun-2026 16:23:38 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 13:48:59 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:45:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:25:02 | 24-Jun-2026 02:04:12 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-1321 | WP01 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 11 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:12:49 | zm167dc@jutal.com | 20-Aug-2026 14:29:51 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:12:25 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:44:37 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 15:51:26 | 30-Aug-2026 09:24:33 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1401 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 11:30:08 | zm167dc@jutal.com | 22-Jul-2026 13:41:02 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 13:17:23 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:06:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 08:44:02 | 06-Aug-2026 02:32:28 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP01-STR-DWG-1401 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:20:46 | zm167dc@jutal.com | 08-Sep-2026 10:04:06 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 15:16:08 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 21:53:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 09:25:00 | 18-Sep-2026 02:48:23 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1402 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:36:45 | zm167dc@jutal.com | 22-Jul-2026 10:51:06 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 13:20:23 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:08:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 08:52:45 | 06-Aug-2026 02:56:21 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP01-STR-DWG-1402 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:21:12 | zm167dc@jutal.com | 08-Sep-2026 10:04:16 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 15:18:55 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 23:01:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 09:25:33 | 18-Sep-2026 02:49:47 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1403 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:37:10 | zm167dc@jutal.com | 22-Jul-2026 10:51:41 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 13:26:37 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:09:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 08:53:26 | 06-Aug-2026 02:57:37 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP01-STR-DWG-1403 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:21:40 | zm167dc@jutal.com | 08-Sep-2026 10:04:06 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 15:21:58 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 23:01:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 09:26:24 | 18-Sep-2026 02:51:09 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1404 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 11:30:31 | zm167dc@jutal.com | 22-Jul-2026 13:41:26 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 13:29:27 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:09:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 08:53:52 | 06-Aug-2026 02:39:47 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-STR-DWG-1404 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 08:50:13 | zm167dc@jutal.com | 11-Sep-2026 12:34:20 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 16-Sep-2026 15:25:56 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 15:45:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 15:54:47 | 20-Sep-2026 09:48:42 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1405 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:37:33 | zm167dc@jutal.com | 22-Jul-2026 10:52:06 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 13:55:33 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:11:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 08:55:02 | 06-Aug-2026 02:58:55 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP01-STR-DWG-1405 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:22:08 | zm167dc@jutal.com | 08-Sep-2026 10:04:06 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 15:29:44 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 23:05:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 09:33:06 | 18-Sep-2026 02:52:31 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1406 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:37:57 | zm167dc@jutal.com | 22-Jul-2026 10:52:20 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 14:08:50 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:12:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 08:56:23 | 06-Aug-2026 03:00:16 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP01-STR-DWG-1406 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:22:37 | zm167dc@jutal.com | 08-Sep-2026 10:04:06 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 15:34:05 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 12:45:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 15:55:43 | 20-Sep-2026 09:29:51 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1407 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:38:25 | zm167dc@jutal.com | 22-Jul-2026 10:52:34 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 14:12:45 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:12:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 08:58:00 | 06-Aug-2026 03:01:40 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-STR-DWG-1407 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 08:50:56 | zm167dc@jutal.com | 11-Sep-2026 12:34:21 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 16-Sep-2026 15:38:28 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 15:46:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 15:56:30 | 20-Sep-2026 09:50:02 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1408 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 11:30:56 | zm167dc@jutal.com | 22-Jul-2026 13:41:47 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 14:14:56 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:13:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 08:57:19 | 06-Aug-2026 02:41:02 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP01-STR-DWG-1408 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:23:09 | zm167dc@jutal.com | 08-Sep-2026 10:04:06 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 15:40:59 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 12:46:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 15:57:19 | 21-Sep-2026 00:28:21 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1409 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:38:51 | zm167dc@jutal.com | 22-Jul-2026 10:47:08 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 14:17:01 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:13:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 08:59:02 | 06-Aug-2026 03:04:22 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-STR-DWG-1409 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 9 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 08:51:29 | zm167dc@jutal.com | 11-Sep-2026 12:34:21 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 16-Sep-2026 15:45:16 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 15:47:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 15:58:21 | 20-Sep-2026 09:51:20 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1410 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 10 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:39:24 | zm167dc@jutal.com | 22-Jul-2026 10:46:36 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 14:19:47 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:13:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:03:44 | 06-Aug-2026 03:05:44 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP01-STR-DWG-1411 | WP01 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 11 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 11:31:26 | zm167dc@jutal.com | 22-Jul-2026 13:35:08 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 14:22:40 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:14:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:05:52 | 06-Aug-2026 02:42:19 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP01-STR-DWG-1420 | WP01 TOPSIDE MONORAIL LAYOUT AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:07:43 | zm167dc@jutal.com | 03-Jul-2026 18:22:25 | Jumpol Sudjitjul | 14-Jul-2026 |  | Washira Kaew-amatawong | 15-Jul-2026 | 14-Jul-2026 16:16:22 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 14-Jul-2026 23:26:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 08:39:28 | 15-Jul-2026 01:59:22 | 0 |  |  | Approver | Locate
AO-001490 | MM-ASK-1A-WP01-STR-DWG-1420 | WP01 TOPSIDE MONORAIL LAYOUT AND DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 17:18:09 | zm167dc@jutal.com | 18-Sep-2026 17:30:03 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-STR-DWG-1531 | WP01 TOPSIDE CONDENSATE BURNER BOOM SUPPORT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:46:02 | zm167dc@jutal.com | 26-Jul-2026 22:23:21 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 07-Aug-2026 17:31:09 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:37:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:41:55 | 10-Aug-2026 06:28:29 | 0 |  |  | Approver | Locate
AO-001158 | MM-ASK-1A-WP01-STR-DWG-1531 | WP01 TOPSIDE CONDENSATE BURNER BOOM SUPPORT DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:16:21 | zm167dc@jutal.com | 02-Sep-2026 21:35:19 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 11:59:25 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 13-Sep-2026 22:56:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 22:58:45 | 13-Sep-2026 16:33:43 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-STR-DWG-1532 | WP01 TOPSIDE CONDENSATE BURNER BOOM SUPPORT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:46:31 | zm167dc@jutal.com | 26-Jul-2026 22:23:52 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 07-Aug-2026 17:33:36 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:39:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:54:06 | 10-Aug-2026 06:31:27 | 0 |  |  | Approver | Locate
AO-001158 | MM-ASK-1A-WP01-STR-DWG-1532 | WP01 TOPSIDE CONDENSATE BURNER BOOM SUPPORT DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:16:53 | zm167dc@jutal.com | 02-Sep-2026 21:45:26 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 12:02:10 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 14-Sep-2026 23:51:08 | AWC | Approved with Comment | Soontaree Simpitak | 16-Sep-2026 | 15-Sep-2026 08:23:47 | 15-Sep-2026 02:20:45 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP01-STR-DWG-1551 | WP01 TOPSIDE HELIDECK MARKING AND SAFETY NETTING LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:08:10 | zm167dc@jutal.com | 03-Jul-2026 18:20:39 | Jumpol Sudjitjul | 14-Jul-2026 |  | Washira Kaew-amatawong | 15-Jul-2026 | 14-Jul-2026 17:41:03 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 14-Jul-2026 23:27:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 08:55:39 | 15-Jul-2026 02:29:45 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-STR-DWG-1551 | WP01 TOPSIDE HELIDECK MARKING AND SAFETY NETTING LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 08:52:15 | zm167dc@jutal.com | 11-Sep-2026 12:34:20 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP01-STR-DWG-1552 | WP01 TOPSIDE HELIDECK MARKING AND SAFETY NETTING DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:08:38 | zm167dc@jutal.com | 03-Jul-2026 18:20:39 | Jumpol Sudjitjul | 14-Jul-2026 |  | Washira Kaew-amatawong | 15-Jul-2026 | 14-Jul-2026 17:42:48 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 14-Jul-2026 23:29:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 08:57:12 | 15-Jul-2026 02:31:01 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-STR-DWG-1552 | WP01 TOPSIDE HELIDECK MARKING AND SAFETY NETTING DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 08:52:50 | zm167dc@jutal.com | 11-Sep-2026 12:34:20 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP01-STR-DWG-1553 | WP01 TOPSIDE HELIDECK MARKING AND SAFETY NETTING DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:09:05 | zm167dc@jutal.com | 03-Jul-2026 18:20:40 | Jumpol Sudjitjul | 14-Jul-2026 |  | Washira Kaew-amatawong | 15-Jul-2026 | 14-Jul-2026 17:44:21 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 14-Jul-2026 23:28:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 09:15:17 | 15-Jul-2026 02:41:06 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-STR-DWG-1553 | WP01 TOPSIDE HELIDECK MARKING AND SAFETY NETTING DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 08:53:20 | zm167dc@jutal.com | 11-Sep-2026 12:34:25 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001274 | MM-ASK-1A-WP01-STR-DWG-1554 | WP01 TOPSIDE HELIDECK LANDING NET LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFR | Issued for Review |  | 10-Sep-2026 13:15:49 | zm167dc@jutal.com | 10-Sep-2026 15:36:20 | Jumpol Sudjitjul | 18-Sep-2026 |  | Washira Kaew-amatawong | 21-Sep-2026 |  | Pornlert Wanaphattharaphan | 22-Sep-2026 |  |  |  |  | 23-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP01-STR-DWG-1601 | WP01 TOPSIDE UPPER DECK EQUIPMENT SUPPORT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:10:14 | zm167dc@jutal.com | 07-Jul-2026 18:24:42 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:36:00 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 15:52:00 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 01:06:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:34:06 | 20-Jul-2026 04:22:56 | 0 |  |  | Approver | Locate
AO-001139 | MM-ASK-1A-WP01-STR-DWG-1601 | WP01 TOPSIDE UPPER DECK EQUIPMENT SUPPORT LOCATION PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 13:58:59 | zm167dc@jutal.com | 29-Aug-2026 14:03:03 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 15:59:05 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 22:33:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 08-Sep-2026 13:12:06 | 08-Sep-2026 06:40:49 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP01-STR-DWG-1602 | WP01 TOPSIDE LOWER DECK EQUIPMENT SUPPORT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:10:39 | zm167dc@jutal.com | 07-Jul-2026 18:24:41 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:36:44 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 15:53:34 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 01:14:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:33:27 | 20-Jul-2026 04:21:43 | 0 |  |  | Approver | Locate
AO-001139 | MM-ASK-1A-WP01-STR-DWG-1602 | WP01 TOPSIDE LOWER DECK EQUIPMENT SUPPORT LOCATION PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 13:59:23 | zm167dc@jutal.com | 29-Aug-2026 14:03:23 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 16:00:45 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 22:44:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 08-Sep-2026 13:11:31 | 08-Sep-2026 06:39:23 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP01-STR-DWG-1603 | WP01 TOPSIDE MEZZANINE DECK EQUIPMENT SUPPORT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:11:03 | zm167dc@jutal.com | 07-Jul-2026 18:24:39 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:33:38 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 15:58:03 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 01:24:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:33:04 | 20-Jul-2026 03:32:29 | 0 |  |  | Approver | Locate
AO-001139 | MM-ASK-1A-WP01-STR-DWG-1603 | WP01 TOPSIDE MEZZANINE DECK EQUIPMENT SUPPORT LOCATION PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 13:59:48 | zm167dc@jutal.com | 29-Aug-2026 14:03:42 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 16:02:15 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 23:19:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 08-Sep-2026 13:12:54 | 08-Sep-2026 06:43:50 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP01-STR-DWG-1604 | WP01 TOPSIDE SUMP DECK EQUIPMENT SUPPORT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:11:27 | zm167dc@jutal.com | 07-Jul-2026 18:24:41 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:37:40 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 16:00:20 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 02:57:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:32:27 | 20-Jul-2026 04:18:13 | 0 |  |  | Approver | Locate
AO-001139 | MM-ASK-1A-WP01-STR-DWG-1604 | WP01 TOPSIDE SUMP DECK EQUIPMENT SUPPORT LOCATION PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 14:00:12 | zm167dc@jutal.com | 29-Aug-2026 14:03:59 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 16:03:51 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 23:34:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 08-Sep-2026 13:13:23 | 08-Sep-2026 06:45:12 | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP01-STR-DWG-1611 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:02:40 | zm167dc@jutal.com | 26-Jul-2026 22:36:23 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:17:26 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:40:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:28:44 | 10-Aug-2026 06:15:08 | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP01-STR-DWG-1612 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:03:06 | zm167dc@jutal.com | 26-Jul-2026 22:36:39 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:20:04 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:40:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:58:09 | 10-Aug-2026 06:24:03 | 0 |  |  | Approver | Locate
AO-001366 | MM-ASK-1A-WP01-STR-DWG-1612 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 15-Sep-2026 16:43:57 | zm167dc@jutal.com | 15-Sep-2026 17:24:16 | Jumpol Sudjitjul | 24-Sep-2026 |  | Washira Kaew-amatawong | 25-Sep-2026 |  | Pornlert Wanaphattharaphan | 28-Sep-2026 |  |  |  |  | 29-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP01-STR-DWG-1613 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:03:33 | zm167dc@jutal.com | 26-Jul-2026 22:36:55 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:22:09 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:40:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:42:42 | 10-Aug-2026 06:19:24 | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP01-STR-DWG-1614 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:04:00 | zm167dc@jutal.com | 26-Jul-2026 22:37:13 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:24:00 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:41:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:06:02 | 10-Aug-2026 08:07:23 | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP01-STR-DWG-1615 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:04:24 | zm167dc@jutal.com | 26-Jul-2026 22:37:28 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:26:41 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:41:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:39:55 | 10-Aug-2026 06:18:00 | 0 |  |  | Approver | Locate
AO-000916 | MM-ASK-1A-WP01-STR-DWG-1616 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:48:33 | zm167dc@jutal.com | 07-Aug-2026 15:03:52 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 19-Aug-2026 08:08:59 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:41:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:04:00 | 21-Aug-2026 02:47:38 | 0 |  |  | Approver | Locate
AO-000916 | MM-ASK-1A-WP01-STR-DWG-1617 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:49:02 | zm167dc@jutal.com | 07-Aug-2026 15:03:53 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 19-Aug-2026 08:12:37 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:42:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:04:31 | 21-Aug-2026 02:48:56 | 0 |  |  | Approver | Locate
AO-000916 | MM-ASK-1A-WP01-STR-DWG-1618 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:49:31 | zm167dc@jutal.com | 07-Aug-2026 15:03:55 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 19-Aug-2026 08:22:49 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:42:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:05:09 | 21-Aug-2026 02:22:58 | 0 |  |  | Approver | Locate
AO-000916 | MM-ASK-1A-WP01-STR-DWG-1619 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:49:59 | zm167dc@jutal.com | 07-Aug-2026 15:03:51 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 19-Aug-2026 08:27:07 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:42:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:05:38 | 21-Aug-2026 02:24:08 | 0 |  |  | Approver | Locate
AO-000916 | MM-ASK-1A-WP01-STR-DWG-1620 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 10 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:50:28 | zm167dc@jutal.com | 07-Aug-2026 15:03:54 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 19-Aug-2026 08:30:27 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:43:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:06:04 | 21-Aug-2026 02:19:10 | 0 |  |  | Approver | Locate
AO-000916 | MM-ASK-1A-WP01-STR-DWG-1621 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 11 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:50:53 | zm167dc@jutal.com | 07-Aug-2026 15:03:53 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 19-Aug-2026 08:35:46 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:43:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:18:52 | 21-Aug-2026 03:05:19 | 0 |  |  | Approver | Locate
AO-000916 | MM-ASK-1A-WP01-STR-DWG-1622 | WP01 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 12 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:51:18 | zm167dc@jutal.com | 07-Aug-2026 15:15:55 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 19-Aug-2026 08:39:40 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:44:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:19:37 | 21-Aug-2026 03:08:53 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-STR-DWG-1721 | WP01 TOPSIDE PLATFORM NAME PLATE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:47:02 | zm167dc@jutal.com | 26-Jul-2026 22:33:41 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 08-Aug-2026 14:36:15 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:44:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:46:07 | 10-Aug-2026 06:29:58 | 0 |  |  | Approver | Locate
AO-001490 | MM-ASK-1A-WP01-STR-DWG-1721 | WP01 TOPSIDE PLATFORM NAME PLATE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 17:18:45 | zm167dc@jutal.com | 18-Sep-2026 17:30:22 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1801 | WP01 TOPSIDE LIFTING CONFIGURATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:34:22 | zm167dc@jutal.com | 29-May-2026 13:10:22 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:42:00 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:41:44 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:53:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:11:34 | 07-Jun-2026 11:18:48 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP01-STR-DWG-1801 | WP01 TOPSIDE LIFTING CONFIGURATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 15:40:57 | zm167dc@jutal.com | 18-Sep-2026 16:57:00 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1802 | WP01 TOPSIDE LIFTING PADEYE DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 11:35:04 | zm167dc@jutal.com | 29-May-2026 13:10:41 | Jumpol Sudjitjul | 10-Jun-2026 | 04-Jun-2026 07:56:38 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:44:43 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 01:58:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:12:07 | 07-Jun-2026 11:28:58 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP01-STR-DWG-1802 | WP01 TOPSIDE LIFTING PADEYE DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 14:48:43 | zm167dc@jutal.com | 18-Sep-2026 16:57:16 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1803 | WP01 TOPSIDE LIFTING PADEYE DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 10:48:03 | zm167dc@jutal.com | 29-May-2026 11:20:44 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:08:21 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:46:06 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 02:01:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:13:07 | 07-Jun-2026 10:42:53 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP01-STR-DWG-1803 | WP01 TOPSIDE LIFTING PADEYE DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 15:41:24 | zm167dc@jutal.com | 18-Sep-2026 16:57:30 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1804 | WP01 TOPSIDE LIFTING PADEYE DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 10:48:34 | zm167dc@jutal.com | 29-May-2026 11:21:15 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:09:36 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:47:34 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 17:23:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:49:25 | 07-Jun-2026 12:06:36 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP01-STR-DWG-1804 | WP01 TOPSIDE LIFTING PADEYE DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 15:41:56 | zm167dc@jutal.com | 18-Sep-2026 16:57:51 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000378 | MM-ASK-1A-WP01-STR-DWG-1805 | WP01 TOPSIDE LIFTING PADEYE DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 10:49:02 | zm167dc@jutal.com | 29-May-2026 11:21:38 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:15:07 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:50:04 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 17:39:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:49:51 | 07-Jun-2026 12:07:42 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP01-STR-DWG-1805 | WP01 TOPSIDE LIFTING PADEYE DETAILS SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 15:42:22 | zm167dc@jutal.com | 18-Sep-2026 16:58:07 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2001 | WP01 JACKET - DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:46:52 | zm167dc@jutal.com | 29-May-2026 08:24:24 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 16:50:46 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:51:45 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 17:39:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:49:34 | 07-Jun-2026 12:28:03 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP01-STR-DWG-2001 | WP01 JACKET - DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:51:28 | zm167dc@jutal.com | 06-Aug-2026 17:17:07 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 11:05:02 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:07:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:34:24 | 24-Aug-2026 07:00:09 | 0 |  |  | Approver | Locate
AO-001179 | MM-ASK-1A-WP01-STR-DWG-2001 | WP01 JACKET - DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 17:25:20 | zm167dc@jutal.com | 03-Sep-2026 17:34:22 | Jumpol Sudjitjul | 14-Sep-2026 |  | Washira Kaew-amatawong | 15-Sep-2026 | 14-Sep-2026 15:15:33 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 14-Sep-2026 23:58:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 15-Sep-2026 16:56:28 | 15-Sep-2026 10:29:37 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2101 | WP01 JACKET - ELEVATION ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:47:22 | zm167dc@jutal.com | 29-May-2026 08:28:50 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 16:54:54 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:53:10 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 17:48:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:51:58 | 07-Jun-2026 12:08:49 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP01-STR-DWG-2101 | WP01 JACKET - ELEVATION ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 17:33:06 | zm167dc@jutal.com | 07-Aug-2026 09:41:26 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 11:07:51 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:08:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:36:16 | 24-Aug-2026 07:01:38 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP01-STR-DWG-2101 | WP01 JACKET - ELEVATION ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:40:30 | zm167dc@jutal.com | 02-Sep-2026 21:36:59 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:04:06 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:38:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:19:24 | 12-Sep-2026 16:59:07 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2102 | WP01 JACKET - ELEVATION ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:47:51 | zm167dc@jutal.com | 29-May-2026 08:29:32 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 16:55:56 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:54:42 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 17:50:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:53:03 | 07-Jun-2026 12:09:58 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP01-STR-DWG-2102 | WP01 JACKET - ELEVATION ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 17:33:31 | zm167dc@jutal.com | 07-Aug-2026 09:41:20 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 11:11:11 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:08:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:38:15 | 24-Aug-2026 07:03:04 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP01-STR-DWG-2102 | WP01 JACKET - ELEVATION ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:41:05 | zm167dc@jutal.com | 02-Sep-2026 21:46:44 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:06:07 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:43:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:20:27 | 12-Sep-2026 17:00:35 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2103 | WP01 JACKET - ELEVATION ROW '1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:48:19 | zm167dc@jutal.com | 29-May-2026 08:30:03 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 16:56:37 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:56:17 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 17:51:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:54:25 | 07-Jun-2026 12:11:04 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP01-STR-DWG-2103 | WP01 JACKET - ELEVATION ROW '1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 17:33:55 | zm167dc@jutal.com | 07-Aug-2026 09:41:20 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 11:20:05 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:09:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:39:47 | 24-Aug-2026 07:09:57 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP01-STR-DWG-2103 | WP01 JACKET - ELEVATION ROW '1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:41:38 | zm167dc@jutal.com | 02-Sep-2026 21:38:33 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:08:08 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:47:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:31:57 | 12-Sep-2026 17:04:42 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2104 | WP01 JACKET - ELEVATION ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:48:48 | zm167dc@jutal.com | 29-May-2026 08:30:41 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 16:57:47 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:57:55 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 17:53:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:55:28 | 07-Jun-2026 12:13:08 | 0 |  |  | Approver | Locate
AO-000922 | MM-ASK-1A-WP01-STR-DWG-2104 | WP01 JACKET - ELEVATION ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 16:07:17 | zm167dc@jutal.com | 07-Aug-2026 16:49:08 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 11:30:08 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:09:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:15:09 | 24-Aug-2026 06:48:17 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP01-STR-DWG-2104 | WP01 JACKET - ELEVATION ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:42:11 | zm167dc@jutal.com | 02-Sep-2026 21:48:25 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:10:18 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:50:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:28:52 | 12-Sep-2026 17:01:59 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2111 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:49:16 | zm167dc@jutal.com | 29-May-2026 08:44:26 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 16:59:34 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 13:59:41 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:29:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 19:50:15 | 07-Jun-2026 13:14:27 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP01-STR-DWG-2111 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (+) 8000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 17:34:20 | zm167dc@jutal.com | 07-Aug-2026 09:41:23 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 11:34:52 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:09:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:45:08 | 24-Aug-2026 07:11:15 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP01-STR-DWG-2111 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (+) 8000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:42:46 | zm167dc@jutal.com | 02-Sep-2026 21:50:23 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:12:52 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:51:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:31:13 | 12-Sep-2026 17:03:19 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2112 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (±) 0000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:49:42 | zm167dc@jutal.com | 29-May-2026 08:44:47 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:00:56 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 14:01:08 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:34:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 19:51:22 | 07-Jun-2026 13:15:32 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP01-STR-DWG-2112 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (±) 0000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 17:34:46 | zm167dc@jutal.com | 07-Aug-2026 09:41:22 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 12:21:30 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:10:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:17:16 | 24-Aug-2026 07:07:12 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP01-STR-DWG-2112 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (±) 0000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:43:19 | zm167dc@jutal.com | 02-Sep-2026 21:42:30 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:18:04 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:52:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:36:59 | 12-Sep-2026 17:12:45 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2113 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (-) 9000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:50:08 | zm167dc@jutal.com | 29-May-2026 08:45:00 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:02:38 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 14:02:59 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:43:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 19:55:45 | 07-Jun-2026 13:17:44 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP01-STR-DWG-2113 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (-) 9000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 17:35:13 | zm167dc@jutal.com | 07-Aug-2026 09:41:24 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 12:23:52 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:10:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:16:11 | 24-Aug-2026 06:49:38 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP01-STR-DWG-2113 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (-) 9000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:43:53 | zm167dc@jutal.com | 02-Sep-2026 21:40:33 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:21:39 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:53:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:34:35 | 12-Sep-2026 17:10:04 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2114 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (-) 17400 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:50:37 | zm167dc@jutal.com | 29-May-2026 08:45:13 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:03:22 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 14:04:18 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:53:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:01:27 | 07-Jun-2026 13:19:56 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP01-STR-DWG-2114 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (-) 17400 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:51:58 | zm167dc@jutal.com | 06-Aug-2026 17:17:07 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 12:26:10 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:11:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:43:12 | 24-Aug-2026 07:04:28 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP01-STR-DWG-2114 | WP01 JACKET - HORIZONTAL FRAMING PLAN EL (-) 17400 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:44:25 | zm167dc@jutal.com | 02-Sep-2026 21:43:47 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:24:47 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:54:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:36:13 | 12-Sep-2026 17:11:24 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-STR-DWG-2115 | WP01 JACKET - SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:47:29 | zm167dc@jutal.com | 26-Jul-2026 22:32:06 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 06-Aug-2026 15:32:32 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:45:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:10:55 | 10-Aug-2026 07:55:49 | 0 |  |  | Approver | Locate
AO-001109 | MM-ASK-1A-WP01-STR-DWG-2115 | WP01 JACKET - SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 15:00:27 | zm167dc@jutal.com | 27-Aug-2026 17:37:18 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 07:15:52 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:52:34 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:26:45 | 09-Sep-2026 01:53:36 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP01-STR-DWG-2115 | WP01 JACKET - SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:42:52 | zm167dc@jutal.com | 18-Sep-2026 17:07:11 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2121 | WP01 JACKET - PILE MAKE UP & DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:51:03 | zm167dc@jutal.com | 29-May-2026 09:10:46 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:11:32 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 20:11:23 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 16:57:55 | NA | Not Approved | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:13:47 | 07-Jun-2026 10:44:04 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-STR-DWG-2121 | WP01 JACKET - PILE MAKE UP & DETAILS - SHEET 1 |  | A2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 08:53:54 | zm167dc@jutal.com | 11-Sep-2026 12:37:12 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 14-Sep-2026 12:53:16 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 15-Sep-2026 00:00:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 15-Sep-2026 17:00:02 | 15-Sep-2026 11:17:16 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP01-STR-DWG-2121 | WP01 JACKET - PILE MAKE UP & DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 14:49:30 | zm167dc@jutal.com | 18-Sep-2026 17:05:07 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2122 | WP01 JACKET - PILE MAKE UP & DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:51:31 | zm167dc@jutal.com | 29-May-2026 09:10:50 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:08:58 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 20:14:18 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 17:00:40 | NA | Not Approved | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:14:29 | 07-Jun-2026 10:45:12 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-STR-DWG-2122 | WP01 JACKET - PILE MAKE UP & DETAILS - SHEET 2 |  | A2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 08:54:28 | zm167dc@jutal.com | 11-Sep-2026 12:37:08 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 14-Sep-2026 12:58:01 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 15-Sep-2026 00:00:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 15-Sep-2026 16:57:32 | 15-Sep-2026 10:19:43 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP01-STR-DWG-2122 | WP01 JACKET - PILE MAKE UP & DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 15:43:25 | zm167dc@jutal.com | 18-Sep-2026 17:06:38 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP01-STR-DWG-2123 | WP01 JACKET - PILE MARKING DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:51:59 | zm167dc@jutal.com | 29-May-2026 09:10:45 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:05:11 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 20:17:06 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 17:10:54 | NA | Not Approved | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:17:32 | 07-Jun-2026 10:46:18 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-STR-DWG-2123 | WP01 JACKET - PILE MARKING DETAILS |  | A2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 08:55:01 | zm167dc@jutal.com | 11-Sep-2026 12:37:09 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 14-Sep-2026 13:12:29 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 15-Sep-2026 23:15:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 16-Sep-2026 10:16:58 | 16-Sep-2026 03:38:29 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP01-STR-DWG-2123 | WP01 JACKET - PILE MARKING DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 15:43:54 | zm167dc@jutal.com | 18-Sep-2026 17:06:54 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001306 | MM-ASK-1A-WP01-STR-DWG-2124 | WP01 JACKET - PILE MAKE UP & DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 12:33:42 | zm167dc@jutal.com | 11-Sep-2026 20:06:08 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 | 14-Sep-2026 14:23:10 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 15-Sep-2026 23:14:33 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 16-Sep-2026 10:16:08 | 16-Sep-2026 03:33:44 | 0 |  |  | Approver | Locate
AO-000983 | MM-ASK-1A-WP01-STR-DWG-2201 | WP01 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 13:58:28 | zm167dc@jutal.com | 14-Aug-2026 14:16:57 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:22:45 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:54:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:07:19 | 28-Aug-2026 03:35:22 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP01-STR-DWG-2201 | WP01 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:26:06 | zm167dc@jutal.com | 11-Sep-2026 20:06:12 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000983 | MM-ASK-1A-WP01-STR-DWG-2202 | WP01 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 13:58:52 | zm167dc@jutal.com | 14-Aug-2026 14:17:00 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:26:57 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:54:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:06:42 | 28-Aug-2026 03:41:15 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP01-STR-DWG-2202 | WP01 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:26:34 | zm167dc@jutal.com | 11-Sep-2026 20:06:09 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000983 | MM-ASK-1A-WP01-STR-DWG-2203 | WP01 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 13:59:19 | zm167dc@jutal.com | 14-Aug-2026 14:16:57 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:29:05 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:55:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:07:49 | 28-Aug-2026 03:42:28 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP01-STR-DWG-2203 | WP01 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:27:01 | zm167dc@jutal.com | 11-Sep-2026 20:06:14 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000983 | MM-ASK-1A-WP01-STR-DWG-2211 | WP01 JACKET - ANODE LAYOUT & DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 13:59:45 | zm167dc@jutal.com | 14-Aug-2026 15:06:30 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:32:20 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:56:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:08:16 | 28-Aug-2026 03:43:41 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP01-STR-DWG-2211 | WP01 JACKET - ANODE LAYOUT & DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:27:39 | zm167dc@jutal.com | 11-Sep-2026 20:16:25 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000926 | MM-ASK-1A-WP01-STR-DWG-2221 | WP01 JACKET - MUDMAT LAYOUT & DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 17:24:08 | zm167dc@jutal.com | 07-Aug-2026 17:28:33 | Jumpol Sudjitjul | 19-Aug-2026 |  | Washira Kaew-amatawong | 20-Aug-2026 | 20-Aug-2026 14:59:44 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:57:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 13:55:48 | 24-Aug-2026 07:35:42 | 0 |  |  | Approver | Locate
AO-001181 | MM-ASK-1A-WP01-STR-DWG-2221 | WP01 JACKET - MUDMAT LAYOUT & DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 17:25:52 | zm167dc@jutal.com | 03-Sep-2026 17:34:22 | Jumpol Sudjitjul | 14-Sep-2026 |  | Washira Kaew-amatawong | 15-Sep-2026 | 14-Sep-2026 14:58:39 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 14-Sep-2026 23:55:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 15-Sep-2026 16:57:01 | 15-Sep-2026 10:31:04 | 0 |  |  | Approver | Locate
AO-000926 | MM-ASK-1A-WP01-STR-DWG-2222 | WP01 JACKET - MUDMAT LAYOUT & DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 17:24:35 | zm167dc@jutal.com | 07-Aug-2026 17:28:52 | Jumpol Sudjitjul | 19-Aug-2026 |  | Washira Kaew-amatawong | 20-Aug-2026 | 20-Aug-2026 15:05:43 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:58:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 13:45:50 | 24-Aug-2026 07:12:31 | 0 |  |  | Approver | Locate
AO-001181 | MM-ASK-1A-WP01-STR-DWG-2222 | WP01 JACKET - MUDMAT LAYOUT & DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 17:26:22 | zm167dc@jutal.com | 03-Sep-2026 17:34:23 | Jumpol Sudjitjul | 14-Sep-2026 |  | Washira Kaew-amatawong | 15-Sep-2026 | 14-Sep-2026 15:02:39 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 14-Sep-2026 23:55:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 15-Sep-2026 16:59:36 | 15-Sep-2026 10:39:20 | 0 |  |  | Approver | Locate
AO-000979 | MM-ASK-1A-WP01-STR-DWG-2301 | WP01 JACKET - LIFTING CONFIGURATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 13:23:14 | zm167dc@jutal.com | 14-Aug-2026 14:35:34 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:34:37 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:57:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:09:26 | 28-Aug-2026 03:36:35 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP01-STR-DWG-2301 | WP01 JACKET - LIFTING CONFIGURATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:28:08 | zm167dc@jutal.com | 11-Sep-2026 20:16:40 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000975 | MM-ASK-1A-WP01-STR-DWG-2302 | WP01 JACKET - LIFTING PADEYE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 11:27:38 | zm167dc@jutal.com | 14-Aug-2026 12:56:12 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:37:05 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:57:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:08:45 | 28-Aug-2026 04:04:44 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP01-STR-DWG-2302 | WP01 JACKET - LIFTING PADEYE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:28:46 | zm167dc@jutal.com | 11-Sep-2026 20:17:41 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP01-STR-DWG-2411 | WP01 JACKET - LOWERING SEQUENCE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Aug-2026 14:13:18 | zm167dc@jutal.com | 20-Aug-2026 14:30:00 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 28-Aug-2026 15:46:36 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:34:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 15:54:05 | 30-Aug-2026 09:25:46 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP01-STR-DWG-2411 | WP01 JACKET - LOWERING SEQUENCE |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:29:24 | zm167dc@jutal.com | 11-Sep-2026 20:17:56 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000352 | MM-ASK-1A-WP01-STR-MTO-1001 | WP01 TOPSIDE PRIMARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Review |  | 26-May-2026 16:44:41 | zm167dc@jutal.com | 27-May-2026 09:09:23 | Jumpol Sudjitjul | 08-Jun-2026 |  | Washira Kaew-amatawong | 09-Jun-2026 | 05-Jun-2026 15:06:14 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 06-Jun-2026 22:11:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 07-Jun-2026 17:15:27 | 07-Jun-2026 11:29:19 | 0 |  |  | Approver | Locate
AO-000670 | MM-ASK-1A-WP01-STR-MTO-1001 | WP01 TOPSIDE PRIMARY STEEL MTO REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 14:37:30 | zm167dc@jutal.com | 10-Jul-2026 14:48:10 | Jumpol Sudjitjul | 20-Jul-2026 |  | Washira Kaew-amatawong | 21-Jul-2026 | 20-Jul-2026 15:36:49 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 22-Jul-2026 23:03:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 23-Jul-2026 08:52:36 | 23-Jul-2026 02:39:17 | 0 |  |  | Approver | Locate
AO-001008 | MM-ASK-1A-WP01-STR-MTO-1001 | WP01 TOPSIDE PRIMARY STEEL MTO REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 12:47:15 | zm167dc@jutal.com | 17-Aug-2026 13:33:41 | Jumpol Sudjitjul | 25-Aug-2026 |  | Washira Kaew-amatawong | 26-Aug-2026 | 26-Aug-2026 16:48:44 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 23:02:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 15:43:39 | 30-Aug-2026 08:56:17 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP01-STR-MTO-1002 | WP01 TOPSIDE SECONDARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:51:44 | zm167dc@jutal.com | 29-May-2026 16:58:58 | Jumpol Sudjitjul | 10-Jun-2026 |  | Washira Kaew-amatawong | 11-Jun-2026 | 10-Jun-2026 10:26:42 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:31:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:32:48 | 11-Jun-2026 03:39:11 | 0 |  |  | Approver | Locate
AO-000670 | MM-ASK-1A-WP01-STR-MTO-1002 | WP01 TOPSIDE SECONDARY STEEL MTO REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 14:38:25 | zm167dc@jutal.com | 10-Jul-2026 14:48:46 | Jumpol Sudjitjul | 20-Jul-2026 |  | Washira Kaew-amatawong | 21-Jul-2026 | 20-Jul-2026 15:39:00 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 22-Jul-2026 23:03:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 23-Jul-2026 08:52:15 | 23-Jul-2026 02:36:20 | 0 |  |  | Approver | Locate
AO-001101 | MM-ASK-1A-WP01-STR-MTO-1002 | WP01 TOPSIDE SECONDARY STEEL MTO REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:16:09 | zm167dc@jutal.com | 27-Aug-2026 09:17:47 | Jumpol Sudjitjul | 04-Sep-2026 |  | Washira Kaew-amatawong | 07-Sep-2026 | 07-Sep-2026 07:18:09 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 07-Sep-2026 23:37:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 08-Sep-2026 13:14:14 | 08-Sep-2026 06:46:39 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP01-STR-MTO-2001 | WP01 JACKET PRIMARY AND SECONDARY STEEL MTO |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:44:53 | zm167dc@jutal.com | 07-Jun-2026 19:28:32 | Jumpol Sudjitjul | 16-Jun-2026 |  | Washira Kaew-amatawong | 17-Jun-2026 | 16-Jun-2026 14:51:15 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 20:44:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 19-Jun-2026 11:42:22 | 19-Jun-2026 05:38:44 | 0 |  |  | Approver | Locate
AO-000677 | MM-ASK-1A-WP01-STR-MTO-2001 | WP01 JACKET PRIMARY AND SECONDARY STEEL MTO |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 17:23:12 | zm167dc@jutal.com | 10-Jul-2026 17:54:00 | Jumpol Sudjitjul | 21-Jul-2026 |  | Washira Kaew-amatawong | 22-Jul-2026 | 24-Jul-2026 07:50:04 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 23:18:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 11:00:50 | 27-Jul-2026 04:53:55 | 0 |  |  | Approver | Locate
AO-000839 | MM-ASK-1A-WP01-STR-MTO-2001 | WP01 JACKET PRIMARY AND SECONDARY STEEL MTO |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:16:10 | zm167dc@jutal.com | 31-Jul-2026 21:52:39 | Jumpol Sudjitjul | 11-Aug-2026 |  | Washira Kaew-amatawong | 13-Aug-2026 | 13-Aug-2026 09:59:55 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 14-Aug-2026 00:05:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 08:13:55 | 14-Aug-2026 02:27:50 | 0 |  |  | Approver | Locate
AO-000837 | MM-ASK-1A-WP01-STR-MTO-2002 | WP01 JACKET SECONDARY STEEL MTO |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 16:43:25 | zm167dc@jutal.com | 31-Jul-2026 17:03:58 | Jumpol Sudjitjul | 11-Aug-2026 |  | Washira Kaew-amatawong | 13-Aug-2026 | 13-Aug-2026 10:35:01 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 14-Aug-2026 00:09:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 08:13:28 | 14-Aug-2026 01:16:54 | 0 |  |  | Approver | Locate
AO-001146 | MM-ASK-1A-WP01-STR-MTO-2002 | WP01 JACKET SECONDARY STEEL MTO |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 20:45:08 | zm167dc@jutal.com | 02-Sep-2026 22:27:23 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 13-Sep-2026 07:06:07 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 13-Sep-2026 11:19:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:23:03 | 13-Sep-2026 05:12:20 | 0 |  |  | Approver | Locate
AO-000429 | MM-ASK-1A-WP01-STR-RPT-1001 | WP01 TOPSIDE COMPUTER MODELING AND LOAD FORMULATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:17:06 | zm167dc@jutal.com | 08-Jun-2026 11:02:06 | Jumpol Sudjitjul | 16-Jun-2026 |  | Washira Kaew-amatawong | 17-Jun-2026 | 15-Jun-2026 20:42:04 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 23:19:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 19-Jun-2026 11:42:44 | 19-Jun-2026 05:17:34 | 0 |  |  | Approver | Locate
AO-001277 | MM-ASK-1A-WP01-STR-RPT-1001 | WP01 TOPSIDE COMPUTER MODELING AND LOAD FORMULATION REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 10-Sep-2026 13:16:32 | zm167dc@jutal.com | 10-Sep-2026 17:24:25 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000514 | MM-ASK-1A-WP01-STR-RPT-1002 | WP01 TOPSIDE IN-PLACE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:07:43 | zm167dc@jutal.com | 19-Jun-2026 16:46:36 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 26-Jun-2026 14:55:33 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 28-Jun-2026 23:38:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 30-Jun-2026 12:46:58 | 30-Jun-2026 06:35:05 | 0 |  |  | Approver | Locate
AO-001326 | MM-ASK-1A-WP01-STR-RPT-1002 | WP01 TOPSIDE IN-PLACE ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:30:08 | zm167dc@jutal.com | 11-Sep-2026 20:26:33 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000510 | MM-ASK-1A-WP01-STR-RPT-1003 | WP01 TOPSIDE LOADOUT ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 11:48:48 | zm167dc@jutal.com | 19-Jun-2026 13:17:56 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 26-Jun-2026 16:58:10 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 29-Jun-2026 00:29:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 30-Jun-2026 12:44:54 | 30-Jun-2026 06:56:11 | 0 |  |  | Approver | Locate
AO-000607 | MM-ASK-1A-WP01-STR-RPT-1004 | WP01 TOPSIDE TRANSPORTATION ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 11:55:45 | zm167dc@jutal.com | 03-Jul-2026 13:21:51 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 13-Jul-2026 13:19:28 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:44:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:30:04 | 17-Jul-2026 03:30:22 | 0 |  |  | Approver | Locate
AO-000630 | MM-ASK-1A-WP01-STR-RPT-1005 | WP01 TOPSIDE VIBRATION ANAYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 23:22:45 | zm167dc@jutal.com | 04-Jul-2026 14:22:43 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 13-Jul-2026 13:28:43 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:48:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:30:37 | 20-Jul-2026 02:11:32 | 0 |  |  | Approver | Locate
AO-000520 | MM-ASK-1A-WP01-STR-RPT-1006 | WP01 TOPSIDE LIFTING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 18:10:50 | zm167dc@jutal.com | 19-Jun-2026 21:11:28 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 28-Jun-2026 07:48:17 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:17:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:44:04 | 30-Jun-2026 06:30:40 | 0 |  |  | Approver | Locate
AO-001073 | MM-ASK-1A-WP01-STR-RPT-1009 | WP01 TOPSIDE MISCELLANEOUS DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 18:37:24 | zm167dc@jutal.com | 24-Aug-2026 18:30:48 | Jumpol Sudjitjul | 02-Sep-2026 |  | Washira Kaew-amatawong | 03-Sep-2026 | 04-Sep-2026 13:11:42 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 05-Sep-2026 18:18:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 05-Sep-2026 18:32:29 | 09-Sep-2026 05:27:52 | 0 |  |  | Approver | Locate
AO-000998 | MM-ASK-1A-WP01-STR-RPT-1010 | WP01 TOPSIDE VIBRATION ANAYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 18:09:58 | zm167dc@jutal.com | 15-Aug-2026 14:58:10 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 27-Aug-2026 16:13:35 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 22:25:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:09:53 | 28-Aug-2026 03:44:58 | 0 |  |  | Approver | Locate
AO-000135 | MM-ASK-1A-WP01-STR-RPT-2001 | WP01 JACKET COMPUTER MODELLING & LOAD FORMULATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:00:44 | zm167dc@jutal.com | 06-May-2026 10:48:09 | Jumpol Sudjitjul | 14-May-2026 |  | Washira Kaew-amatawong | 15-May-2026 | 14-May-2026 14:06:47 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 22:01:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 20-May-2026 08:15:36 | 20-May-2026 01:46:43 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WP01-STR-RPT-2001 | WP01 JACKET COMPUTER MODELLING & LOAD FORMULATION REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:20:50 | zm167dc@jutal.com | 03-Jul-2026 13:23:06 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 14-Jul-2026 15:38:19 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:31:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 08:54:56 | 15-Jul-2026 02:28:31 | 0 |  |  | Approver | Locate
AO-000174 | MM-ASK-1A-WP01-STR-RPT-2002 | WP01 JACKET IN-PLACE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 18:10:10 | zm167dc@jutal.com | 08-May-2026 20:17:53 | Jumpol Sudjitjul | 19-May-2026 |  | Washira Kaew-amatawong | 20-May-2026 | 19-May-2026 15:50:36 | Pornlert Wanaphattharaphan | 21-May-2026 | 22-May-2026 00:11:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 08:20:27 | 22-May-2026 01:32:58 | 0 |  |  | Approver | Locate
AO-001125 | MM-ASK-1A-WP01-STR-RPT-2002 | WP01 JACKET IN-PLACE ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 14:44:40 | zm167dc@jutal.com | 28-Aug-2026 17:57:52 | Jumpol Sudjitjul | 08-Sep-2026 |  | Washira Kaew-amatawong | 09-Sep-2026 | 09-Sep-2026 16:08:23 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:55:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:26:50 | 12-Sep-2026 13:53:43 | 0 |  |  | Approver | Locate
AO-000268 | MM-ASK-1A-WP01-STR-RPT-2003 | WP01 JACKET DYNAMIC ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 14:13:49 | zm167dc@jutal.com | 15-May-2026 18:09:55 | Jumpol Sudjitjul | 26-May-2026 |  | Washira Kaew-amatawong | 27-May-2026 | 24-May-2026 20:15:40 | Pornlert Wanaphattharaphan | 28-May-2026 | 28-May-2026 00:30:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 28-May-2026 08:44:33 | 28-May-2026 01:58:30 | 0 |  |  | Approver | Locate
AO-001177 | MM-ASK-1A-WP01-STR-RPT-2003 | WP01 JACKET DYNAMIC ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 16:40:15 | zm167dc@jutal.com | 03-Sep-2026 16:43:57 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 13-Sep-2026 14:43:42 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 13-Sep-2026 16:53:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 22:40:14 | 13-Sep-2026 15:55:17 | 0 |  |  | Approver | Locate
AO-001192 | MM-ASK-1A-WP01-STR-RPT-2004 | WP01 PLATFORM SPECTRAL FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Sep-2026 12:39:28 | zm167dc@jutal.com | 05-Sep-2026 18:31:28 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 18-Sep-2026 10:54:32 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:14:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 15:59:41 | 20-Sep-2026 09:52:43 | 0 |  |  | Approver | Locate
AO-000901 | MM-ASK-1A-WP01-STR-RPT-2005 | WP01 JACKET LOADOUT ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 11:32:45 | zm167dc@jutal.com | 07-Aug-2026 15:21:03 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 21-Aug-2026 19:39:07 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 22-Aug-2026 12:54:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:57:56 | 24-Aug-2026 07:37:03 | 0 |  |  | Approver | Locate
AO-001202 | MM-ASK-1A-WP01-STR-RPT-2005 | WP01 JACKET LOADOUT ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 17:19:02 | zm167dc@jutal.com | 05-Sep-2026 18:21:36 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 18-Sep-2026 15:09:26 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:16:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 16:04:17 | 20-Sep-2026 10:26:35 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WP01-STR-RPT-2006 | WP01 JACKET TRANSPORTATION ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 16:43:00 | zm167dc@jutal.com | 21-Aug-2026 17:22:35 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 03-Sep-2026 08:50:19 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 05-Sep-2026 18:10:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 05-Sep-2026 18:11:51 | 05-Sep-2026 12:12:30 | 0 |  |  | Approver | Locate
AO-000512 | MM-ASK-1A-WP01-STR-RPT-2007 | WP01 JACKET LIFTING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 15:16:50 | zm167dc@jutal.com | 19-Jun-2026 16:38:39 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 29-Jun-2026 15:47:05 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 01-Jul-2026 23:38:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 11:19:14 | 02-Jul-2026 04:44:37 | 0 |  |  | Approver | Locate
AO-000775 | MM-ASK-1A-WP01-STR-RPT-2007 | WP01 JACKET LIFTING ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 16:04:59 | zm167dc@jutal.com | 26-Jul-2026 23:11:19 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 15:22:12 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:46:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:11:37 | 10-Aug-2026 08:09:01 | 0 |  |  | Approver | Locate
AO-000309 | MM-ASK-1A-WP01-STR-RPT-2008 | WP01 PILE FATIGUE ANALYSIS , PILE STICK-UP AND HANDLING ANALYSIS AND PILE DRIVABILITY ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 16:59:17 | zm167dc@jutal.com | 21-May-2026 17:28:16 | Jumpol Sudjitjul | 02-Jun-2026 | 29-May-2026 17:35:05 | Washira Kaew-amatawong | 04-Jun-2026 | 03-Jun-2026 19:31:50 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 06-Jun-2026 21:45:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 07-Jun-2026 17:18:10 | 07-Jun-2026 10:47:33 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-WP01-STR-RPT-2008 | WP01 PILE FATIGUE ANALYSIS , PILE STICK-UP AND HANDLING ANALYSIS AND PILE DRIVABILITY ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:29:52 | zm167dc@jutal.com | 27-Jun-2026 19:36:56 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 09-Jul-2026 11:02:09 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:57:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 08:27:04 | 10-Jul-2026 02:03:17 | 0 |  |  | Approver | Locate
AO-000456 | MM-ASK-1A-WP01-STR-RPT-2009 | WP01 JACKET ON-BOTTOM STABILITY ANALYSIS & MUDMAT DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:07:52 | zm167dc@jutal.com | 12-Jun-2026 09:33:27 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 01:21:39 | Washira Kaew-amatawong | 23-Jun-2026 | 22-Jun-2026 08:09:28 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:14:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:18:07 | 23-Jun-2026 01:51:50 | 0 |  |  | Approver | Locate
AO-000660 | MM-ASK-1A-WP01-STR-RPT-2009 | WP01 JACKET ON-BOTTOM STABILITY ANALYSIS & MUDMAT DESIGN REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 08-Jul-2026 20:00:05 | zm167dc@jutal.com | 09-Jul-2026 10:26:29 | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 17:25:46 | Washira Kaew-amatawong | 20-Jul-2026 | 20-Jul-2026 14:28:15 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 23:00:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 13:12:26 | 23-Jul-2026 06:16:41 | 0 |  |  | Approver | Locate
AO-000903 | MM-ASK-1A-WP01-STR-RPT-2009 | WP01 JACKET ON-BOTTOM STABILITY ANALYSIS & MUDMAT DESIGN REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 11:33:23 | zm167dc@jutal.com | 07-Aug-2026 15:18:26 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 21-Aug-2026 18:47:06 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 22-Aug-2026 12:32:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:50:26 | 24-Aug-2026 07:34:28 | 0 |  |  | Approver | Locate
AO-000956 | MM-ASK-1A-WP01-STR-RPT-2012 | WP01 JACKET CATHODIC PROTECTION DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 11-Aug-2026 17:29:20 | zm167dc@jutal.com | 11-Aug-2026 17:47:19 | Jumpol Sudjitjul | 21-Aug-2026 |  | Washira Kaew-amatawong | 24-Aug-2026 | 24-Aug-2026 17:28:18 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 27-Aug-2026 14:55:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 27-Aug-2026 15:44:22 | 27-Aug-2026 10:30:41 | 0 |  |  | Approver | Locate
AO-001352 | MM-ASK-1A-WP01-STR-RPT-2012 | WP01 JACKET CATHODIC PROTECTION DESIGN REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 14-Sep-2026 09:21:21 | zm167dc@jutal.com | 15-Sep-2026 13:45:08 | Jumpol Sudjitjul | 23-Sep-2026 |  | Washira Kaew-amatawong | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP01-STR-RPT-2013 | WP01 JACKET MISCELLANEOUS DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:09:41 | zm167dc@jutal.com | 03-Jul-2026 18:24:26 | Jumpol Sudjitjul | 14-Jul-2026 | 15-Jul-2026 15:25:32 | Washira Kaew-amatawong | 15-Jul-2026 | 16-Jul-2026 09:26:59 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 19-Jul-2026 15:59:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 20-Jul-2026 09:31:49 | 20-Jul-2026 04:35:06 | 0 |  |  | Approver | Locate
AO-000990 | MM-ASK-1A-WP01-STR-RPT-2014 | WP01 JACKET TRANSPORTATION FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 15:27:44 | zm167dc@jutal.com | 14-Aug-2026 15:33:17 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 28-Aug-2026 13:44:35 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 29-Aug-2026 19:55:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 30-Aug-2026 15:57:06 | 30-Aug-2026 09:44:51 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WP01-STR-RPT-2015 | WP01 JACKET LEVELING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 16:43:31 | zm167dc@jutal.com | 21-Aug-2026 17:19:53 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 03-Sep-2026 11:11:44 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 05-Sep-2026 17:54:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 05-Sep-2026 17:57:56 | 05-Sep-2026 11:49:40 | 0 |  |  | Approver | Locate
AO-000560 | MM-ASK-1A-WP01-STR-RPT-2021 | WP01 JACKET SEISMIC ANALYSIS REPORT- ELE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:34:14 | zm167dc@jutal.com | 26-Jun-2026 16:43:56 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 13:54:33 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 04-Jul-2026 19:37:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 05-Jul-2026 10:27:57 | 05-Jul-2026 03:48:59 | 0 |  |  | Approver | Locate
AO-001215 | MM-ASK-1A-WP01-STR-RPT-2021 | WP01 JACKET SEISMIC ANALYSIS REPORT- ELE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:23:50 | zm167dc@jutal.com | 08-Sep-2026 10:24:17 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 18-Sep-2026 15:24:01 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 15:12:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:05:24 | 20-Sep-2026 10:04:05 | 0 |  |  | Approver | Locate
AO-000791 | MM-ASK-1A-WP01-STR-RPT-2022 | WP01 JACKET SEISMIC ANALYSIS REPORT - ALE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 26-Jul-2026 23:50:44 | zm167dc@jutal.com | 27-Jul-2026 15:43:55 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 10-Aug-2026 19:35:33 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:03:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 09:01:53 | 13-Aug-2026 02:43:28 | 0 |  |  | Approver | Locate
AO-000730 | MM-ASK-1A-WP01-STR-RPT-2031 | WP01 BOAT IMPACT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 09:48:49 | zm167dc@jutal.com | 20-Jul-2026 13:18:49 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 31-Jul-2026 14:24:37 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 13:08:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 21:05:46 | 02-Aug-2026 14:50:32 | 0 |  |  | Approver | Locate
AO-001059 | MM-ASK-1A-WP01-STR-RPT-2031 | WP01 BOAT IMPACT ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 17:28:13 | zm167dc@jutal.com | 21-Aug-2026 17:31:28 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 03-Sep-2026 13:33:10 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 04-Sep-2026 23:57:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 05-Sep-2026 17:58:20 | 05-Sep-2026 11:26:21 | 0 |  |  | Approver | Locate
AO-001344 | MM-ASK-1A-WP01-STR-RPT-2031 | WP01 BOAT IMPACT ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:30:47 | zm167dc@jutal.com | 11-Sep-2026 20:26:53 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000993 | MM-ASK-1A-WP01-STR-RPT-2032 | WP01 NON-LINEAR STATIC PUSHOVER ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 17:23:45 | zm167dc@jutal.com | 14-Aug-2026 17:28:43 | Jumpol Sudjitjul | 25-Aug-2026 |  | Washira Kaew-amatawong | 26-Aug-2026 | 28-Aug-2026 15:09:53 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 23:06:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 16:20:31 | 30-Aug-2026 09:36:20 | 0 |  |  | Approver | Locate
AO-000638 | MM-ASK-1A-WP01-STR-WCR-1001 | WP01 TOPSIDE WEIGHT CONTROL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 00:09:06 | zm167dc@jutal.com | 07-Jul-2026 10:16:38 | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 15:29:47 | Washira Kaew-amatawong | 16-Jul-2026 | 16-Jul-2026 12:45:25 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 19-Jul-2026 17:11:03 | NA | Not Approved | Jumpol Sudjitjul | 20-Jul-2026 | 20-Jul-2026 09:24:30 | 20-Jul-2026 02:43:05 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-STR-WCR-1001 | WP01 TOPSIDE WEIGHT CONTROL REPORT |  | A2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:48:06 | zm167dc@jutal.com | 24-Jul-2026 14:57:15 | Jumpol Sudjitjul | 05-Aug-2026 | 24-Jul-2026 16:19:01 | Washira Kaew-amatawong | 06-Aug-2026 | 06-Aug-2026 14:32:59 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 05:35:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:13:43 | 07-Aug-2026 05:14:08 | 0 |  |  | Approver | Locate
AO-001341 | MM-ASK-1A-WP01-STR-WCR-2001 | WP01 JACKET WEIGHT CONTROL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | STR | Structural | WCR | Weight Control Report | 0 | In Review | IFR | Issued for Review |  | 11-Sep-2026 19:31:25 | zm167dc@jutal.com | 11-Sep-2026 20:29:12 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-WP01-TEL-DTS-0001 | DATA SHEET FOR WIMAX RADIO - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 15:29:31 | zm167dc@jutal.com | 10-Jun-2026 13:56:08 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 13:35:18 | Noppadol Iamtanasinchai | 19-Jun-2026 | 17-Jun-2026 08:46:57 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 06:38:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 11:12:53 | 22-Jun-2026 04:34:27 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP01-TEL-DTS-0001 | DATA SHEET FOR WIMAX RADIO - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 02-Jul-2026 16:02:09 | zm167dc@jutal.com | 02-Jul-2026 16:38:57 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:32:25 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:33:49 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:01:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 08:53:30 | 15-Jul-2026 02:27:03 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP01-TEL-DTS-0001 | DATA SHEET FOR WIMAX RADIO - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 14:50:47 | zm167dc@jutal.com | 26-Jul-2026 22:57:48 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:43:00 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 14:51:12 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 17:27:56 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 09-Aug-2026 18:16:40 | 09-Aug-2026 11:32:51 | 0 |  |  | Approver | Locate
AO-000246 | MM-ASK-1A-WP01-TEL-DTS-0002 | DATA SHEET FOR RADAR BEACON - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 17:41:38 | zm167dc@jutal.com | 15-May-2026 11:51:53 | Jumpol Sudjitjul | 25-May-2026 |  | Noppadol Iamtanasinchai | 26-May-2026 | 23-May-2026 12:43:17 | Pornlert Wanaphattharaphan | 27-May-2026 | 01-Jun-2026 17:47:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 01-Jun-2026 22:08:20 | 01-Jun-2026 22:23:49 | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-WP01-TEL-DTS-0002 | DATA SHEET FOR RADAR BEACON - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 13:45:50 | zm167dc@jutal.com | 10-Jun-2026 13:56:08 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 13:19:11 | Noppadol Iamtanasinchai | 19-Jun-2026 | 17-Jun-2026 08:43:17 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 06:25:27 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 11:13:33 | 22-Jun-2026 04:35:45 | 0 |  |  | Approver | Locate
AO-000560 | MM-ASK-1A-WP01-TEL-DTS-0002 | DATA SHEET FOR RADAR BEACON - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 16:36:39 | zm167dc@jutal.com | 26-Jun-2026 16:58:32 | Jumpol Sudjitjul | 06-Jul-2026 | 03-Jul-2026 14:58:23 | Danai Chaisalee | 07-Jul-2026 | 06-Jul-2026 10:31:01 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 08-Jul-2026 01:00:55 | APPR | Approved | Jumpol Sudjitjul | 09-Jul-2026 | 08-Jul-2026 08:55:15 | 08-Jul-2026 02:35:40 | 0 |  |  | Approver | Locate
AO-000247 | MM-ASK-1A-WP01-TEL-DTS-0003 | DATA SHEET FOR AUTOMATIC IDENTIFICATION SYSTEM - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 17:42:03 | zm167dc@jutal.com | 15-May-2026 11:52:11 | Jumpol Sudjitjul | 25-May-2026 |  | Noppadol Iamtanasinchai | 26-May-2026 | 23-May-2026 12:44:12 | Pornlert Wanaphattharaphan | 27-May-2026 | 01-Jun-2026 15:55:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 01-Jun-2026 22:09:34 | 01-Jun-2026 22:26:04 | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-WP01-TEL-DTS-0003 | DATA SHEET FOR AUTOMATIC IDENTIFICATION SYSTEM - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 13:46:18 | zm167dc@jutal.com | 10-Jun-2026 13:56:10 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 13:20:25 | Noppadol Iamtanasinchai | 19-Jun-2026 | 17-Jun-2026 08:43:55 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 06:28:14 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 11:11:45 | 22-Jun-2026 04:33:09 | 0 |  |  | Approver | Locate
AO-000560 | MM-ASK-1A-WP01-TEL-DTS-0003 | DATA SHEET FOR AUTOMATIC IDENTIFICATION SYSTEM - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 16:37:14 | zm167dc@jutal.com | 26-Jun-2026 16:59:28 | Jumpol Sudjitjul | 06-Jul-2026 | 03-Jul-2026 14:58:51 | Danai Chaisalee | 07-Jul-2026 | 06-Jul-2026 10:32:19 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 11-Jul-2026 11:42:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 12-Jul-2026 11:22:13 | 12-Jul-2026 04:43:55 | 0 |  |  | Approver | Locate
AO-000829 | MM-ASK-1A-WP01-TEL-DTS-0003 | DATA SHEET FOR AUTOMATIC IDENTIFICATION SYSTEM - WP01 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:17:09 | zm167dc@jutal.com | 31-Jul-2026 21:43:24 | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 13:09:39 | Danai Chaisalee | 13-Aug-2026 | 05-Aug-2026 09:14:56 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 19:38:38 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 09:06:40 | 13-Aug-2026 02:27:11 | 0 |  |  | Approver | Locate
AO-000248 | MM-ASK-1A-WP01-TEL-DTS-0004 | DATA SHEET FOR VHF-DMR - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 17:42:27 | zm167dc@jutal.com | 15-May-2026 17:40:00 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 19:33:19 | Noppadol Iamtanasinchai | 27-May-2026 | 26-May-2026 10:12:28 | Pornlert Wanaphattharaphan | 28-May-2026 | 09-Jun-2026 23:51:54 | APPR | Approved | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:51:02 | 10-Jun-2026 16:18:54 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-WP01-TEL-DTS-0004 | DATA SHEET FOR VHF-DMR - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:05:16 | zm167dc@jutal.com | 13-Jun-2026 08:16:46 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 23-Jun-2026 10:35:32 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:04:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:47:25 | 25-Jun-2026 06:26:15 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP01-TEL-DTS-0004 | DATA SHEET FOR VHF-DMR - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 02-Jul-2026 16:02:42 | zm167dc@jutal.com | 02-Jul-2026 16:38:56 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:33:36 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:34:40 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:02:13 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:14:15 | 15-Jul-2026 02:38:39 | 0 |  |  | Approver | Locate
AO-000249 | MM-ASK-1A-WP01-TEL-DTS-0005 | DATA SHEET FOR VHF-FM - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 17:42:52 | zm167dc@jutal.com | 15-May-2026 17:40:03 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 19:43:27 | Noppadol Iamtanasinchai | 27-May-2026 | 26-May-2026 10:20:40 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 00:48:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:50:26 | 10-Jun-2026 14:22:57 | 0 |  |  | Approver | Locate
AO-000476 | MM-ASK-1A-WP01-TEL-DTS-0005 | DATA SHEET FOR VHF-FM - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:05:41 | zm167dc@jutal.com | 13-Jun-2026 08:16:59 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 23-Jun-2026 10:38:34 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:04:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:48:25 | 25-Jun-2026 06:29:46 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP01-TEL-DTS-0005 | DATA SHEET FOR VHF-FM - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 02-Jul-2026 16:03:28 | zm167dc@jutal.com | 02-Jul-2026 16:38:55 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:30:28 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:31:57 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 14-Jul-2026 23:59:46 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:16:21 | 15-Jul-2026 02:43:36 | 0 |  |  | Approver | Locate
AO-000277 | MM-ASK-1A-WP01-TEL-DTS-0006 | DATA SHEET FOR TELEPHONE - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 18:49:57 | zm167dc@jutal.com | 17-May-2026 10:35:28 | Jumpol Sudjitjul | 25-May-2026 |  | Noppadol Iamtanasinchai | 26-May-2026 | 23-May-2026 12:46:58 | Pornlert Wanaphattharaphan | 27-May-2026 | 01-Jun-2026 15:47:54 | APPR | Approved | Jumpol Sudjitjul | 28-May-2026 | 01-Jun-2026 22:10:00 | 01-Jun-2026 22:26:58 | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-WP01-TEL-DTS-0006 | DATA SHEET FOR TELEPHONE - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 13:46:45 | zm167dc@jutal.com | 10-Jun-2026 13:56:11 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 14:08:05 | Noppadol Iamtanasinchai | 19-Jun-2026 | 17-Jun-2026 08:48:37 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 06:44:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 11:14:10 | 22-Jun-2026 04:37:59 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP01-TEL-DTS-0006 | DATA SHEET FOR TELEPHONE - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 02-Jul-2026 16:04:09 | zm167dc@jutal.com | 02-Jul-2026 16:38:53 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:29:29 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:31:01 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 14-Jul-2026 23:57:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:16:49 | 15-Jul-2026 02:45:02 | 0 |  |  | Approver | Locate
AO-000714 | MM-ASK-1A-WP01-TEL-DTS-0006 | DATA SHEET FOR TELEPHONE - WP01 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:56:58 | zm167dc@jutal.com | 17-Jul-2026 12:00:24 | Jumpol Sudjitjul | 27-Jul-2026 |  | Danai Chaisalee | 30-Jul-2026 | 22-Jul-2026 15:17:05 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:11:51 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 11:01:52 | 27-Jul-2026 04:39:31 | 0 |  |  | Approver | Locate
AO-000250 | MM-ASK-1A-WP01-TEL-DTS-0007 | DATA SHEET FOR BULK MATERIAL - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 12:07:15 | zm167dc@jutal.com | 15-May-2026 17:40:01 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 20:17:03 | Noppadol Iamtanasinchai | 27-May-2026 | 26-May-2026 10:18:44 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 00:25:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:49:54 | 10-Jun-2026 14:24:05 | 0 |  |  | Approver | Locate
AO-000476 | MM-ASK-1A-WP01-TEL-DTS-0007 | DATA SHEET FOR BULK MATERIAL - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:06:05 | zm167dc@jutal.com | 13-Jun-2026 08:17:16 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 23-Jun-2026 10:39:25 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:05:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:49:03 | 25-Jun-2026 06:31:34 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-WP01-TEL-DTS-0007 | DATA SHEET FOR BULK MATERIAL - WP01 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 16:50:22 | zm167dc@jutal.com | 10-Jul-2026 17:26:13 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:23:54 | Danai Chaisalee | 22-Jul-2026 | 17-Jul-2026 09:51:20 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:34:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 09:30:04 | 20-Jul-2026 03:31:17 | 0 |  |  | Approver | Locate
AO-000912 | MM-ASK-1A-WP01-TEL-DTS-0007 | DATA SHEET FOR BULK MATERIAL - WP01 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:56:34 | zm167dc@jutal.com | 07-Aug-2026 16:42:55 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:48:50 | Danai Chaisalee | 19-Aug-2026 | 19-Aug-2026 13:09:59 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:47:19 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 13:59:08 | 24-Aug-2026 07:38:12 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-TEL-DWG-0001 | TELECOMMUNICTION INSTALLATION AND MOUNTING DETAIL - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 09:00:30 | zm167dc@jutal.com | 11-Sep-2026 19:53:39 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 | 17-Sep-2026 14:57:48 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:25:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 16:06:52 | 20-Sep-2026 10:57:24 | 0 |  |  | Approver | Locate
AO-001146 | MM-ASK-1A-WP01-TEL-LAY-0001 | TELECOMMUNICTION CABLE ROUTING PLAN - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 02-Sep-2026 20:49:25 | zm167dc@jutal.com | 02-Sep-2026 21:32:24 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:53:05 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 18-Sep-2026 20:15:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 20-Sep-2026 16:08:02 | 20-Sep-2026 10:47:03 | 0 |  |  | Approver | Locate
AO-000949 | MM-ASK-1A-WP01-TEL-LAY-0002 | TELECOMMUNICTION EQUIPMENT LAYOUT - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Aug-2026 10:42:18 | zm167dc@jutal.com | 11-Aug-2026 11:46:46 | Jumpol Sudjitjul | 20-Aug-2026 | 13-Aug-2026 12:11:18 | Danai Chaisalee | 21-Aug-2026 | 20-Aug-2026 14:19:14 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 21-Aug-2026 20:05:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Aug-2026 | 24-Aug-2026 14:00:01 | 24-Aug-2026 07:53:58 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP01-TEL-LAY-0002 | TELECOMMUNICTION EQUIPMENT LAYOUT - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 09:01:21 | zm167dc@jutal.com | 11-Sep-2026 19:54:35 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP01-TEL-LIS-0001 | TELECOMMUNICTION DOCUMENT INDEX - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 02-Jul-2026 16:04:49 | zm167dc@jutal.com | 02-Jul-2026 16:40:44 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:35:40 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:38:47 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:26:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:00:26 | 15-Jul-2026 02:32:19 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WP01-TEL-LIS-0001 | TELECOMMUNICTION DOCUMENT INDEX - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:36:20 | zm167dc@jutal.com | 14-Aug-2026 08:44:10 | Jumpol Sudjitjul | 24-Aug-2026 |  | Danai Chaisalee | 25-Aug-2026 | 21-Aug-2026 10:55:11 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 13:07:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 14:00:50 | 24-Aug-2026 07:56:14 | 0 |  |  | Approver | Locate
AO-001304 | MM-ASK-1A-WP01-TEL-LIS-0001 | TELECOMMUNICTION DOCUMENT INDEX - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 09:02:11 | zm167dc@jutal.com | 11-Sep-2026 12:40:46 | Jumpol Sudjitjul | 21-Sep-2026 |  | Danai Chaisalee | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000704 | MM-ASK-1A-WP01-TEL-LIS-0002 | TELECOMMUNICTION EQUIPMENT LIST - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 15-Jul-2026 17:57:58 | zm167dc@jutal.com | 15-Jul-2026 18:02:48 | Jumpol Sudjitjul | 24-Jul-2026 |  | Danai Chaisalee | 27-Jul-2026 | 22-Jul-2026 15:09:30 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 09:18:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 11:02:39 | 27-Jul-2026 04:40:45 | 0 |  |  | Approver | Locate
AO-000887 | MM-ASK-1A-WP01-TEL-LIS-0002 | TELECOMMUNICTION EQUIPMENT LIST - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:49:00 | zm167dc@jutal.com | 05-Aug-2026 11:59:38 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:29:45 | Danai Chaisalee | 17-Aug-2026 | 07-Aug-2026 13:54:15 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 12-Aug-2026 23:47:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 09:07:58 | 13-Aug-2026 02:28:26 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WP01-TEL-LIS-0003 | TELECOMMUNICTION CABLE SCHEDULE - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 12:10:40 | zm167dc@jutal.com | 16-Jul-2026 14:42:17 | Jumpol Sudjitjul | 24-Jul-2026 |  | Danai Chaisalee | 27-Jul-2026 | 22-Jul-2026 15:11:26 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 09:55:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 11:03:32 | 27-Jul-2026 04:41:59 | 0 |  |  | Approver | Locate
AO-001317 | MM-ASK-1A-WP01-TEL-LIS-0003 | TELECOMMUNICTION CABLE SCHEDULE - WP01 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:36:36 | zm167dc@jutal.com | 11-Sep-2026 20:30:47 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001052 | MM-ASK-1A-WP01-TEL-LIS-0004 | TELECOMMUNICTION POWER CPNSTRUCTION AND HEAT DISSIPATION LIST - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 11:30:38 | zm167dc@jutal.com | 21-Aug-2026 14:15:37 | Jumpol Sudjitjul | 31-Aug-2026 |  | Danai Chaisalee | 01-Sep-2026 | 01-Sep-2026 08:01:30 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 02-Sep-2026 23:36:46 | AWC | Approved with Comment | Soontaree Simpitak | 03-Sep-2026 | 03-Sep-2026 08:10:00 | 03-Sep-2026 01:20:41 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP01-TEL-LIS-0005 | TELECOMMUNICTION DRAWING INDEX - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 02-Jul-2026 16:05:18 | zm167dc@jutal.com | 02-Jul-2026 16:40:59 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:36:03 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:39:38 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:27:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:17:23 | 15-Jul-2026 02:46:24 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WP01-TEL-LIS-0005 | TELECOMMUNICTION DRAWING INDEX - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:36:46 | zm167dc@jutal.com | 14-Aug-2026 08:44:29 | Jumpol Sudjitjul | 24-Aug-2026 |  | Danai Chaisalee | 25-Aug-2026 | 21-Aug-2026 10:56:22 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 13:01:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 13:57:03 | 24-Aug-2026 07:52:45 | 0 |  |  | Approver | Locate
AO-001304 | MM-ASK-1A-WP01-TEL-LIS-0005 | TELECOMMUNICTION DRAWING INDEX - WP01 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 09:02:45 | zm167dc@jutal.com | 11-Sep-2026 12:41:03 | Jumpol Sudjitjul | 21-Sep-2026 |  | Danai Chaisalee | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001318 | MM-ASK-1A-WP01-TEL-MTO-0001 | TELECOMMUNICTION BULK MATERIAL TAKE -OFF - WP01 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA01 |  |  | TEL | Telecommunication | MTO | Material Take Off | 0 | In Review | IFR | Issued for Review |  | 11-Sep-2026 19:37:09 | zm167dc@jutal.com | 11-Sep-2026 20:32:10 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001184 | MM-ASK-1A-WP01-TEL-SCH-0001 | TELECOMMUNICTION SCHEMATIC DIAGRAM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | SCH | Schematic | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 18:06:11 | zm167dc@jutal.com | 04-Sep-2026 11:27:13 | Jumpol Sudjitjul | 14-Sep-2026 |  | Danai Chaisalee | 15-Sep-2026 | 14-Sep-2026 11:04:51 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 18-Sep-2026 22:49:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 20-Sep-2026 16:09:00 | 20-Sep-2026 10:27:50 | 0 |  |  | Approver | Locate
AO-000829 | MM-ASK-1A-WP01-TEL-SLD-0001 | TELECOMMUNICTION SYSTEM BLOCK DIAGRAM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 17:17:38 | zm167dc@jutal.com | 31-Jul-2026 21:56:17 | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 13:10:31 | Danai Chaisalee | 13-Aug-2026 | 05-Aug-2026 14:34:08 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 19:47:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 09:08:35 | 13-Aug-2026 02:29:41 | 0 |  |  | Approver | Locate
AO-001171 | MM-ASK-1A-WP01-TEL-SLD-0001 | TELECOMMUNICTION SYSTEM BLOCK DIAGRAM - WP01 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 14:56:23 | zm167dc@jutal.com | 03-Sep-2026 16:28:34 | Jumpol Sudjitjul | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:43:00 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:54:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 09:37:39 | 18-Sep-2026 03:00:47 | 0 |  |  | Approver | Locate
AO-001321 | MM-ASK-1A-WP01-TEL-WIR-0001 | TELECOMMUNICTION SYSTEM WIRING DIAGRAM - WP01 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | TEL | Telecommunication | WIR | Wiring Diagram | 0 | In Review | IFR | Issued for Review |  | 11-Sep-2026 19:37:44 | zm167dc@jutal.com | 11-Sep-2026 20:33:05 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:19:30 | zm167dc@jutal.com | 03-Jul-2026 18:35:26 | Jumpol Sudjitjul | 14-Jul-2026 |  | Danai Chaisalee | 15-Jul-2026 | 14-Jul-2026 10:27:35 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 19-Jul-2026 15:48:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 20-Jul-2026 09:29:19 | 20-Jul-2026 03:27:19 | 0 |  |  | Approver | Locate
AO-000893 | MM-ASK-1A-WP02-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 08:53:43 | zm167dc@jutal.com | 06-Aug-2026 10:09:09 | Jumpol Sudjitjul | 17-Aug-2026 | 06-Aug-2026 10:53:53 | Danai Chaisalee | 18-Aug-2026 | 13-Aug-2026 08:12:54 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 20-Aug-2026 23:00:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 21-Aug-2026 09:20:07 | 21-Aug-2026 03:10:12 | 0 |  |  | Approver | Locate
AO-001158 | MM-ASK-1A-WP02-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:27:06 | zm167dc@jutal.com | 02-Sep-2026 22:06:04 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:54:05 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:40:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 18:02:41 | 18-Sep-2026 11:38:26 | 0 |  |  | Approver | Locate
AO-000115 | MM-ASK-1A-WP02-ELE-CAL-0001 | ELECTRICAL EQUIPMENT SIZING CALCULATIONS - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 01-May-2026 10:30:41 | zm167dc@jutal.com | 01-May-2026 10:58:33 | Jumpol Sudjitjul | 12-May-2026 | 19-May-2026 11:33:14 | Noppadol Iamtanasinchai | 13-May-2026 | 19-May-2026 13:20:21 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 21:33:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 09:15:16 | 20-May-2026 09:45:53 | 0 |  |  | Approver | Locate
AO-000476 | MM-ASK-1A-WP02-ELE-CAL-0001 | ELECTRICAL EQUIPMENT SIZING CALCULATIONS - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:12:33 | zm167dc@jutal.com | 13-Jun-2026 08:20:58 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 14:34:28 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:39:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:50:25 | 25-Jun-2026 06:40:26 | 0 |  |  | Approver | Locate
AO-000741 | MM-ASK-1A-WP02-ELE-CAL-0001 | ELECTRICAL EQUIPMENT SIZING CALCULATIONS - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 15:01:23 | zm167dc@jutal.com | 20-Jul-2026 15:48:27 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:34:40 | Danai Chaisalee | 31-Jul-2026 | 24-Jul-2026 09:28:10 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 27-Jul-2026 00:49:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 11:04:29 | 27-Jul-2026 04:43:18 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WP02-ELE-CAL-0002 | ELECTRICAL CABLE SIZING CALCULATIONS - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 11:58:44 | zm167dc@jutal.com | 12-Jun-2026 12:46:18 | Jumpol Sudjitjul | 22-Jun-2026 | 23-Jun-2026 08:53:50 | Noppadol Iamtanasinchai | 23-Jun-2026 | 23-Jun-2026 11:07:16 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:09:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:14:42 | 25-Jun-2026 05:43:45 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-WP02-ELE-CAL-0002 | ELECTRICAL CABLE SIZING CALCULATIONS - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 20:40:38 | zm167dc@jutal.com | 17-Jul-2026 22:00:21 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 21-Jul-2026 16:01:20 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 12:35:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 11:05:41 | 27-Jul-2026 04:44:36 | 0 |  |  | Approver | Locate
AO-000914 | MM-ASK-1A-WP02-ELE-CAL-0002 | ELECTRICAL CABLE SIZING CALCULATIONS - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:57:30 | zm167dc@jutal.com | 07-Aug-2026 16:44:40 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:49:53 | Danai Chaisalee | 19-Aug-2026 | 19-Aug-2026 14:35:09 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:48:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 14:03:25 | 24-Aug-2026 07:39:34 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-WP02-ELE-CAL-0003 | ELECTRICAL CABLE TRAY / CABLE LADDER SIZING - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 16:52:06 | zm167dc@jutal.com | 10-Jul-2026 17:49:42 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:26:37 | Danai Chaisalee | 22-Jul-2026 | 20-Jul-2026 15:22:59 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 03:01:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 11:11:29 | 27-Jul-2026 04:45:49 | 0 |  |  | Approver | Locate
AO-001246 | MM-ASK-1A-WP02-ELE-CAL-0003 | ELECTRICAL CABLE TRAY / CABLE LADDER SIZING - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 08-Sep-2026 12:34:12 | zm167dc@jutal.com | 08-Sep-2026 14:15:38 | Jumpol Sudjitjul | 16-Sep-2026 |  | Danai Chaisalee | 17-Sep-2026 | 16-Sep-2026 10:16:30 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 00:24:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:09:49 | 20-Sep-2026 10:29:12 | 0 |  |  | Approver | Locate
AO-000682 | MM-ASK-1A-WP02-ELE-CAL-0004 | ILLUMINATION CALCULATIONS - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 18:09:16 | zm167dc@jutal.com | 10-Jul-2026 18:21:56 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:28:15 | Danai Chaisalee | 22-Jul-2026 | 20-Jul-2026 16:08:28 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 03:12:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 11:12:23 | 27-Jul-2026 04:50:08 | 0 |  |  | Approver | Locate
AO-000915 | MM-ASK-1A-WP02-ELE-CAL-0004 | ILLUMINATION CALCULATIONS - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 14:58:05 | zm167dc@jutal.com | 07-Aug-2026 16:44:57 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:50:14 | Danai Chaisalee | 19-Aug-2026 | 19-Aug-2026 14:36:18 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:48:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 14:04:14 | 24-Aug-2026 07:40:55 | 0 |  |  | Approver | Locate
AO-001119 | MM-ASK-1A-WP02-ELE-CAL-0004 | ILLUMINATION CALCULATIONS - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 09:16:49 | zm167dc@jutal.com | 28-Aug-2026 14:33:42 | Jumpol Sudjitjul | 07-Sep-2026 |  | Danai Chaisalee | 08-Sep-2026 | 08-Sep-2026 13:14:06 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 10-Sep-2026 22:58:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 12:29:11 | 11-Sep-2026 06:17:39 | 0 |  |  | Approver | Locate
AO-000072 | MM-ASK-1A-WP02-ELE-DTS-0001 | DATA SHEET FOR AC AND DC DISTRIBTUTION BOARDS/PANELS – WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:01:57 | zm167dc@jutal.com | 25-Apr-2026 09:13:50 | Jumpol Sudjitjul | 06-May-2026 | 07-May-2026 17:19:59 | Noppadol Iamtanasinchai | 07-May-2026 | 14-May-2026 09:08:59 | Pornlert Wanaphattharaphan | 08-May-2026 | 15-May-2026 22:18:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 17-May-2026 00:11:25 | 17-May-2026 00:22:21 | 0 |  |  | Approver | Locate
AO-000375 | MM-ASK-1A-WP02-ELE-DTS-0001 | DATA SHEET FOR AC AND DC DISTRIBTUTION BOARDS/PANELS – WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 21:01:57 | zm167dc@jutal.com | 29-May-2026 09:59:19 | Jumpol Sudjitjul | 10-Jun-2026 | 09-Jun-2026 10:47:50 | Noppadol Iamtanasinchai | 11-Jun-2026 | 10-Jun-2026 14:38:16 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:32:00 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:34:36 | 11-Jun-2026 03:31:10 | 0 |  |  | Approver | Locate
AO-000710 | MM-ASK-1A-WP02-ELE-DTS-0001 | DATA SHEET FOR AC AND DC DISTRIBTUTION BOARDS/PANELS – WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 16:58:12 | zm167dc@jutal.com | 16-Jul-2026 20:45:03 | Jumpol Sudjitjul | 27-Jul-2026 |  | Danai Chaisalee | 30-Jul-2026 | 22-Jul-2026 15:15:51 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:11:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 11:13:41 | 27-Jul-2026 04:51:22 | 0 |  |  | Approver | Locate
AO-001035 | MM-ASK-1A-WP02-ELE-DTS-0001 | DATA SHEET FOR AC AND DC DISTRIBTUTION BOARDS/PANELS – WP02 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 14:19:08 | zm167dc@jutal.com | 20-Aug-2026 14:36:29 | Jumpol Sudjitjul | 28-Aug-2026 |  | Danai Chaisalee | 31-Aug-2026 | 31-Aug-2026 09:37:23 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 02-Sep-2026 23:30:47 | AWC | Approved with Comment | Soontaree Simpitak | 02-Sep-2026 | 03-Sep-2026 08:10:32 | 03-Sep-2026 01:25:12 | 0 |  |  | Approver | Locate
AO-000073 | MM-ASK-1A-WP02-ELE-DTS-0002 | DATA SHEET FOR SOLAR POWER SYSTEM – WPA02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:02:21 | zm167dc@jutal.com | 25-Apr-2026 09:14:03 | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 09:31:42 | Noppadol Iamtanasinchai | 07-May-2026 | 14-May-2026 09:10:59 | Pornlert Wanaphattharaphan | 08-May-2026 | 15-May-2026 22:19:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 17-May-2026 00:13:09 | 17-May-2026 01:09:21 | 0 |  |  | Approver | Locate
AO-000380 | MM-ASK-1A-WP02-ELE-DTS-0002 | DATA SHEET FOR SOLAR POWER SYSTEM – WPA02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 14:06:07 | zm167dc@jutal.com | 29-May-2026 15:10:28 | Jumpol Sudjitjul | 10-Jun-2026 | 09-Jun-2026 16:26:01 | Noppadol Iamtanasinchai | 11-Jun-2026 | 10-Jun-2026 15:05:42 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:33:00 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:43:36 | 11-Jun-2026 03:33:13 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-WP02-ELE-DTS-0002 | DATA SHEET FOR SOLAR POWER SYSTEM – WPA02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:48:21 | zm167dc@jutal.com | 27-Jun-2026 19:46:49 | Jumpol Sudjitjul | 07-Jul-2026 |  | Danai Chaisalee | 08-Jul-2026 | 02-Jul-2026 11:12:00 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:28:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 08:54:54 | 10-Jul-2026 02:31:30 | 0 |  |  | Approver | Locate
AO-001035 | MM-ASK-1A-WP02-ELE-DTS-0002 | DATA SHEET FOR SOLAR POWER SYSTEM – WPA02 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 14:19:55 | zm167dc@jutal.com | 20-Aug-2026 14:36:49 | Jumpol Sudjitjul | 28-Aug-2026 |  | Danai Chaisalee | 31-Aug-2026 | 31-Aug-2026 09:38:11 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 02-Sep-2026 23:31:46 | AWC | Approved with Comment | Soontaree Simpitak | 02-Sep-2026 | 03-Sep-2026 08:49:10 | 03-Sep-2026 02:01:06 | 0 |  |  | Approver | Locate
AO-000177 | MM-ASK-1A-WP02-ELE-DTS-0003 | DATASHEET FOR NAVIGATION AID SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 18:11:33 | zm167dc@jutal.com | 08-May-2026 20:24:13 | Jumpol Sudjitjul | 19-May-2026 | 21-May-2026 14:04:15 | Noppadol Iamtanasinchai | 20-May-2026 | 23-May-2026 10:40:46 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 22:40:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 28-May-2026 09:10:03 | 28-May-2026 09:40:29 | 0 |  |  | Approver | Locate
AO-000416 | MM-ASK-1A-WP02-ELE-DTS-0003 | DATASHEET FOR NAVIGATION AID SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 17:53:57 | zm167dc@jutal.com | 05-Jun-2026 19:47:32 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 10:21:27 | Noppadol Iamtanasinchai | 17-Jun-2026 | 17-Jun-2026 08:29:32 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 18:02:49 | APPR | Approved | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:17:22 | 22-Jun-2026 01:10:45 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-WP02-ELE-DTS-0003 | DATASHEET FOR NAVIGATION AID SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:57:32 | zm167dc@jutal.com | 20-Jul-2026 11:44:37 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 22-Jul-2026 15:20:16 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:26:56 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 11:05:06 | 27-Jul-2026 04:47:44 | 0 |  |  | Approver | Locate
AO-000075 | MM-ASK-1A-WP02-ELE-DTS-0004 | DATA SHEET FOR EXTERNAL BATTERY CHARGER - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 25-Apr-2026 09:02:43 | zm167dc@jutal.com | 25-Apr-2026 09:14:14 | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 10:04:40 | Noppadol Iamtanasinchai | 07-May-2026 | 14-May-2026 09:12:48 | Pornlert Wanaphattharaphan | 08-May-2026 | 15-May-2026 23:38:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 17-May-2026 00:05:45 | 17-May-2026 00:19:06 | 0 |  |  | Approver | Locate
AO-000376 | MM-ASK-1A-WP02-ELE-DTS-0004 | DATA SHEET FOR EXTERNAL BATTERY CHARGER - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 21:02:31 | zm167dc@jutal.com | 29-May-2026 09:59:45 | Jumpol Sudjitjul | 10-Jun-2026 | 09-Jun-2026 10:51:55 | Noppadol Iamtanasinchai | 11-Jun-2026 | 10-Jun-2026 15:01:53 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:32:30 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 09:45:41 | 11-Jun-2026 03:34:18 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-WP02-ELE-DTS-0004 | DATA SHEET FOR EXTERNAL BATTERY CHARGER - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:58:06 | zm167dc@jutal.com | 20-Jul-2026 11:44:51 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 22-Jul-2026 15:21:56 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:37:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 11:14:23 | 27-Jul-2026 04:52:38 | 0 |  |  | Approver | Locate
AO-001025 | MM-ASK-1A-WP02-ELE-DTS-0004 | DATA SHEET FOR EXTERNAL BATTERY CHARGER - WP02 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 15:56:22 | zm167dc@jutal.com | 19-Aug-2026 16:12:10 | Jumpol Sudjitjul | 27-Aug-2026 |  | Danai Chaisalee | 28-Aug-2026 | 28-Aug-2026 08:02:09 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 29-Aug-2026 23:30:03 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 15:58:44 | 30-Aug-2026 09:38:52 | 0 |  |  | Approver | Locate
AO-000708 | MM-ASK-1A-WP02-ELE-DTS-0005 | DATASHEET FOR ELECTRICAL CABLES - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 15:34:28 | zm167dc@jutal.com | 16-Jul-2026 15:37:32 | Jumpol Sudjitjul | 24-Jul-2026 |  | Danai Chaisalee | 27-Jul-2026 | 22-Jul-2026 15:14:01 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 09:59:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 11:15:01 | 27-Jul-2026 04:55:05 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP02-ELE-DTS-0005 | DATASHEET FOR ELECTRICAL CABLES - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:59:19 | zm167dc@jutal.com | 07-Aug-2026 11:06:14 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:16:50 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:45:33 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:40:20 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:38:44 | 21-Aug-2026 03:14:46 | 0 |  |  | Approver | Locate
AO-001163 | MM-ASK-1A-WP02-ELE-DTS-0006 | DATASHEET FOR ELECTRICAL BULK MATERIALS - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 02-Sep-2026 20:02:02 | zm167dc@jutal.com | 02-Sep-2026 22:08:53 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:55:03 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:43:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 09:24:18 | 18-Sep-2026 03:14:22 | 0 |  |  | Approver | Locate
AO-000723 | MM-ASK-1A-WP02-ELE-DTS-0007 | DATASHEET FOR FOG HORN - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 09:58:36 | zm167dc@jutal.com | 20-Jul-2026 11:47:04 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 22-Jul-2026 15:23:54 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:42:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 13:52:51 | 27-Jul-2026 07:24:34 | 0 |  |  | Approver | Locate
AO-000958 | MM-ASK-1A-WP02-ELE-DTS-0007 | DATASHEET FOR FOG HORN - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Aug-2026 18:28:06 | zm167dc@jutal.com | 13-Aug-2026 13:17:20 | Jumpol Sudjitjul | 21-Aug-2026 |  | Danai Chaisalee | 24-Aug-2026 | 20-Aug-2026 14:21:29 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:10:39 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 14:06:31 | 24-Aug-2026 07:42:04 | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-WP02-ELE-DTS-0008 | DATASHEET FOR MOTOR CONTROL CENTER - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 05-Aug-2026 18:37:28 | zm167dc@jutal.com | 06-Aug-2026 14:13:54 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:09:35 | Danai Chaisalee | 18-Aug-2026 | 18-Aug-2026 10:34:36 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 20-Aug-2026 23:26:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 21-Aug-2026 09:43:17 | 21-Aug-2026 03:21:27 | 0 |  |  | Approver | Locate
AO-001120 | MM-ASK-1A-WP02-ELE-DTS-0008 | DATASHEET FOR MOTOR CONTROL CENTER - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 08:31:47 | zm167dc@jutal.com | 28-Aug-2026 14:25:17 | Jumpol Sudjitjul | 07-Sep-2026 |  | Danai Chaisalee | 08-Sep-2026 | 08-Sep-2026 15:11:43 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 10-Sep-2026 23:20:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 12:31:23 | 11-Sep-2026 06:23:10 | 0 |  |  | Approver | Locate
AO-000938 | MM-ASK-1A-WP02-ELE-DTS-0009 | DATASHEET FOR AC GENERATOR - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:27:15 | zm167dc@jutal.com | 10-Aug-2026 15:56:53 | Jumpol Sudjitjul | 19-Aug-2026 |  | Danai Chaisalee | 20-Aug-2026 | 20-Aug-2026 09:44:25 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:56:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 13:53:31 | 24-Aug-2026 08:09:36 | 0 |  |  | Approver | Locate
AO-001149 | MM-ASK-1A-WP02-ELE-DTS-0009 | DATASHEET FOR AC GENERATOR - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:27:52 | zm167dc@jutal.com | 02-Sep-2026 22:10:08 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:56:01 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 16:19:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 17-Sep-2026 16:23:54 | 17-Sep-2026 10:18:36 | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-WP02-ELE-DTS-0010 | DATASHEET FOR INDUCTION MOTOR - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 05-Aug-2026 18:37:54 | zm167dc@jutal.com | 06-Aug-2026 14:14:18 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:09:56 | Danai Chaisalee | 18-Aug-2026 | 18-Aug-2026 10:35:55 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 20-Aug-2026 23:28:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 21-Aug-2026 09:45:36 | 21-Aug-2026 03:24:12 | 0 |  |  | Approver | Locate
AO-001122 | MM-ASK-1A-WP02-ELE-DTS-0010 | DATASHEET FOR INDUCTION MOTOR - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 11:35:29 | zm167dc@jutal.com | 28-Aug-2026 14:25:48 | Jumpol Sudjitjul | 07-Sep-2026 |  | Danai Chaisalee | 08-Sep-2026 | 08-Sep-2026 15:12:37 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 10-Sep-2026 23:33:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 12:29:52 | 11-Sep-2026 06:14:08 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-ELE-DWG-0001 | ELECTRICAL DRAWING INDEX - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:53:10 | zm167dc@jutal.com | 26-Jul-2026 23:07:05 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:51:53 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:12:37 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:08:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:12:18 | 10-Aug-2026 07:58:12 | 0 |  |  | Approver | Locate
AO-000565 | MM-ASK-1A-WP02-ELE-DWG-0002 | EQUIPMENT LOCATION PLAN - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:48:58 | zm167dc@jutal.com | 27-Jun-2026 19:49:07 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 15:05:35 | Danai Chaisalee | 08-Jul-2026 | 07-Jul-2026 10:37:52 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:09:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 08:22:10 | 10-Jul-2026 01:57:54 | 0 |  |  | Approver | Locate
AO-000935 | MM-ASK-1A-WP02-ELE-DWG-0002 | EQUIPMENT LOCATION PLAN - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:27:53 | zm167dc@jutal.com | 10-Aug-2026 15:49:37 | Jumpol Sudjitjul | 19-Aug-2026 |  | Danai Chaisalee | 20-Aug-2026 | 20-Aug-2026 09:33:06 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:48:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:07:27 | 24-Aug-2026 08:13:10 | 0 |  |  | Approver | Locate
AO-001205 | MM-ASK-1A-WP02-ELE-DWG-0002 | EQUIPMENT LOCATION PLAN - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:28:23 | zm167dc@jutal.com | 08-Sep-2026 10:29:06 | Jumpol Sudjitjul | 16-Sep-2026 |  | Danai Chaisalee | 17-Sep-2026 | 15-Sep-2026 13:33:03 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 22:13:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 17:59:06 | 18-Sep-2026 11:52:50 | 0 |  |  | Approver | Locate
AO-000565 | MM-ASK-1A-WP02-ELE-DWG-0003 | EQUIPMENT LOCATION PLAN - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:49:43 | zm167dc@jutal.com | 27-Jun-2026 19:49:08 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 15:06:09 | Danai Chaisalee | 08-Jul-2026 | 07-Jul-2026 10:39:00 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:15:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 08:56:43 | 10-Jul-2026 02:32:44 | 0 |  |  | Approver | Locate
AO-000935 | MM-ASK-1A-WP02-ELE-DWG-0003 | EQUIPMENT LOCATION PLAN - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:28:27 | zm167dc@jutal.com | 10-Aug-2026 15:49:38 | Jumpol Sudjitjul | 19-Aug-2026 |  | Danai Chaisalee | 20-Aug-2026 | 20-Aug-2026 09:35:40 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:51:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 13:55:52 | 24-Aug-2026 08:10:56 | 0 |  |  | Approver | Locate
AO-001204 | MM-ASK-1A-WP02-ELE-DWG-0003 | EQUIPMENT LOCATION PLAN - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:28:49 | zm167dc@jutal.com | 08-Sep-2026 10:29:44 | Jumpol Sudjitjul | 16-Sep-2026 |  | Danai Chaisalee | 17-Sep-2026 | 15-Sep-2026 13:34:01 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 22:26:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 17:59:59 | 18-Sep-2026 11:54:16 | 0 |  |  | Approver | Locate
AO-000565 | MM-ASK-1A-WP02-ELE-DWG-0004 | EQUIPMENT LOCATION PLAN - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:50:34 | zm167dc@jutal.com | 27-Jun-2026 19:49:08 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 15:08:03 | Danai Chaisalee | 08-Jul-2026 | 07-Jul-2026 10:39:57 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:15:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 08:58:11 | 10-Jul-2026 02:33:59 | 0 |  |  | Approver | Locate
AO-000935 | MM-ASK-1A-WP02-ELE-DWG-0004 | EQUIPMENT LOCATION PLAN - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:29:01 | zm167dc@jutal.com | 10-Aug-2026 15:49:41 | Jumpol Sudjitjul | 19-Aug-2026 |  | Danai Chaisalee | 20-Aug-2026 | 20-Aug-2026 09:39:14 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:53:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:09:15 | 24-Aug-2026 08:14:26 | 0 |  |  | Approver | Locate
AO-001204 | MM-ASK-1A-WP02-ELE-DWG-0004 | EQUIPMENT LOCATION PLAN - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:29:16 | zm167dc@jutal.com | 08-Sep-2026 10:30:04 | Jumpol Sudjitjul | 16-Sep-2026 |  | Danai Chaisalee | 17-Sep-2026 | 15-Sep-2026 13:34:48 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 22:28:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 18:01:34 | 18-Sep-2026 11:55:39 | 0 |  |  | Approver | Locate
AO-000603 | MM-ASK-1A-WP02-ELE-DWG-0005-001 | LIGHTING AND SMALL POWER LOOP DIAGRAM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:37:12 | zm167dc@jutal.com | 03-Jul-2026 13:33:35 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:15:30 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:30:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:33:08 | 17-Jul-2026 03:19:21 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-WP02-ELE-DWG-0005-001 | LIGHTING AND SMALL POWER LOOP DIAGRAM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:22:59 | zm167dc@jutal.com | 03-Sep-2026 16:04:46 | Jumpol Sudjitjul | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:39:54 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:29:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 09:25:15 | 18-Sep-2026 03:05:53 | 0 |  |  | Approver | Locate
AO-000603 | MM-ASK-1A-WP02-ELE-DWG-0005-002 | LIGHTING AND SMALL POWER LOOP DIAGRAM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:37:46 | zm167dc@jutal.com | 03-Jul-2026 13:33:44 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:33:18 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:50:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:37:20 | 17-Jul-2026 03:20:32 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-WP02-ELE-DWG-0005-002 | LIGHTING AND SMALL POWER LOOP DIAGRAM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:23:25 | zm167dc@jutal.com | 03-Sep-2026 16:05:14 | Jumpol Sudjitjul | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:41:02 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:27:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 09:25:56 | 18-Sep-2026 03:07:15 | 0 |  |  | Approver | Locate
AO-000603 | MM-ASK-1A-WP02-ELE-DWG-0005-003 | LIGHTING AND SMALL POWER LOOP DIAGRAM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:38:22 | zm167dc@jutal.com | 03-Jul-2026 13:33:42 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:31:24 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:50:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:38:49 | 17-Jul-2026 03:21:41 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-WP02-ELE-DWG-0005-003 | LIGHTING AND SMALL POWER LOOP DIAGRAM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:02:37 | zm167dc@jutal.com | 02-Sep-2026 22:11:40 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:56:52 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:26:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 09:24:44 | 18-Sep-2026 03:15:45 | 0 |  |  | Approver | Locate
AO-000606 | MM-ASK-1A-WP02-ELE-DWG-0006-001 | LIGHTING AND SMALL POWER PLAN - WP02 MEZZANINE DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 14:20:57 | zm167dc@jutal.com | 03-Jul-2026 14:38:39 | Jumpol Sudjitjul | 13-Jul-2026 | 03-Jul-2026 14:53:54 | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:35:28 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:51:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:39:14 | 17-Jul-2026 03:31:35 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP02-ELE-DWG-0006-001 | LIGHTING AND SMALL POWER PLAN - WP02 MEZZANINE DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:28:24 | zm167dc@jutal.com | 02-Sep-2026 22:16:51 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 11:00:02 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:25:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 17:56:33 | 18-Sep-2026 11:37:04 | 0 |  |  | Approver | Locate
AO-000606 | MM-ASK-1A-WP02-ELE-DWG-0006-002 | LIGHTING AND SMALL POWER PLAN - WP02 LOWER DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 14:22:01 | zm167dc@jutal.com | 03-Jul-2026 14:38:37 | Jumpol Sudjitjul | 13-Jul-2026 | 03-Jul-2026 14:53:31 | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:34:12 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 22:50:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:39:39 | 17-Jul-2026 03:33:00 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP02-ELE-DWG-0006-002 | LIGHTING AND SMALL POWER PLAN - WP02 LOWER DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:28:57 | zm167dc@jutal.com | 02-Sep-2026 22:13:10 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:58:03 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:22:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 18:03:02 | 18-Sep-2026 11:39:49 | 0 |  |  | Approver | Locate
AO-000606 | MM-ASK-1A-WP02-ELE-DWG-0006-003 | LIGHTING AND SMALL POWER PLAN - WP02 SUMP DECK AND BOAT LANDING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 14:23:17 | zm167dc@jutal.com | 03-Jul-2026 14:38:45 | Jumpol Sudjitjul | 13-Jul-2026 | 03-Jul-2026 14:54:45 | Danai Chaisalee | 14-Jul-2026 | 13-Jul-2026 13:37:11 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:07:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:40:34 | 17-Jul-2026 03:41:08 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP02-ELE-DWG-0006-003 | LIGHTING AND SMALL POWER PLAN - WP02 SUMP DECK AND BOAT LANDING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:29:31 | zm167dc@jutal.com | 02-Sep-2026 22:15:06 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:59:00 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:12:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 18:06:56 | 18-Sep-2026 11:42:12 | 0 |  |  | Approver | Locate
AO-000629 | MM-ASK-1A-WP02-ELE-DWG-0007 | ELECTRICAL OVERALL EARTHING AND BONDING DIAGRAMS- WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 20:30:12 | zm167dc@jutal.com | 04-Jul-2026 14:08:36 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:59:37 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:43:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 09:00:08 | 10-Jul-2026 02:55:32 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP02-ELE-DWG-0007 | ELECTRICAL OVERALL EARTHING AND BONDING DIAGRAMS- WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:59:53 | zm167dc@jutal.com | 07-Aug-2026 11:04:14 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:16:14 | Danai Chaisalee | 19-Aug-2026 | 13-Aug-2026 08:14:49 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 17-Aug-2026 00:10:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 17-Aug-2026 09:26:54 | 17-Aug-2026 03:27:30 | 0 |  |  | Approver | Locate
AO-001156 | MM-ASK-1A-WP02-ELE-DWG-0007 | ELECTRICAL OVERALL EARTHING AND BONDING DIAGRAMS- WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:30:06 | zm167dc@jutal.com | 02-Sep-2026 22:18:56 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 11:01:00 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:18:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 09:31:01 | 18-Sep-2026 02:56:40 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP02-ELE-LAY-0001 | SOLAR PANEL LAYOUT - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:46:04 | zm167dc@jutal.com | 07-Jun-2026 19:32:01 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 13:15:51 | Noppadol Iamtanasinchai | 17-Jun-2026 | 17-Jun-2026 08:34:30 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 18:17:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:17:54 | 22-Jun-2026 01:12:02 | 0 |  |  | Approver | Locate
AO-000801 | MM-ASK-1A-WP02-ELE-LAY-0001 | SOLAR PANEL LAYOUT - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Jul-2026 22:35:35 | zm167dc@jutal.com | 26-Jul-2026 23:05:25 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:47:59 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:02:59 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 23:04:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 11:47:11 | 10-Aug-2026 06:21:08 | 0 |  |  | Approver | Locate
AO-001470 | MM-ASK-1A-WP02-ELE-LAY-0001 | SOLAR PANEL LAYOUT - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 14:57:18 | zm167dc@jutal.com | 18-Sep-2026 17:12:27 | Jumpol Sudjitjul | 29-Sep-2026 |  | Danai Chaisalee | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000573 | MM-ASK-1A-WP02-ELE-LAY-0002-001 | E&I ROOM EQUIPMENT LAYOUT PLAN - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-Jun-2026 12:11:12 | zm167dc@jutal.com | 30-Jun-2026 10:10:34 | Jumpol Sudjitjul | 08-Jul-2026 | 03-Jul-2026 15:17:57 | Danai Chaisalee | 09-Jul-2026 | 07-Jul-2026 10:46:27 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:40:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 09:04:56 | 10-Jul-2026 02:35:11 | 0 |  |  | Approver | Locate
AO-000984 | MM-ASK-1A-WP02-ELE-LAY-0002-001 | E&I ROOM EQUIPMENT LAYOUT PLAN - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 14:48:49 | zm167dc@jutal.com | 14-Aug-2026 15:22:41 | Jumpol Sudjitjul | 24-Aug-2026 |  | Danai Chaisalee | 25-Aug-2026 | 19-Aug-2026 13:14:06 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 08:53:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 14:10:12 | 24-Aug-2026 08:15:44 | 0 |  |  | Approver | Locate
AO-000573 | MM-ASK-1A-WP02-ELE-LAY-0002-002 | E&I ROOM EQUIPMENT LAYOUT PLAN - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-Jun-2026 12:11:40 | zm167dc@jutal.com | 30-Jun-2026 10:10:56 | Jumpol Sudjitjul | 08-Jul-2026 | 03-Jul-2026 15:18:46 | Danai Chaisalee | 09-Jul-2026 | 07-Jul-2026 10:47:13 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:42:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 09:17:33 | 10-Jul-2026 02:38:59 | 0 |  |  | Approver | Locate
AO-000984 | MM-ASK-1A-WP02-ELE-LAY-0002-002 | E&I ROOM EQUIPMENT LAYOUT PLAN - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 14:49:25 | zm167dc@jutal.com | 14-Aug-2026 15:22:59 | Jumpol Sudjitjul | 24-Aug-2026 |  | Danai Chaisalee | 25-Aug-2026 | 19-Aug-2026 13:15:01 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 09:01:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 14:10:54 | 24-Aug-2026 08:17:04 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-ELE-LAY-0003-001 | CABLE TRAYS/LADDERS LAYOUT DRAWINGS - WP02 UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:53:36 | zm167dc@jutal.com | 26-Jul-2026 23:05:24 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:46:48 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:01:32 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 22:55:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:12:53 | 10-Aug-2026 07:59:36 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-ELE-LAY-0003-002 | CABLE TRAYS/LADDERS LAYOUT DRAWINGS - WP02 LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:54:12 | zm167dc@jutal.com | 26-Jul-2026 23:05:25 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:48:30 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:04:07 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 23:09:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:10:06 | 10-Aug-2026 07:53:04 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-ELE-LAY-0003-003 | CABLE TRAYS/LADDERS LAYOUT DRAWINGS - WP02 SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:54:40 | zm167dc@jutal.com | 26-Jul-2026 23:05:26 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:49:22 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:06:16 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 23:36:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:19:33 | 10-Aug-2026 08:00:59 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-ELE-LAY-0003-004 | CABLE TRAYS/LADDERS LAYOUT DRAWINGS - WP02 E&I ROOM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:55:06 | zm167dc@jutal.com | 26-Jul-2026 23:05:29 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:50:45 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:09:45 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 23:58:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:23:13 | 10-Aug-2026 08:02:21 | 0 |  |  | Approver | Locate
AO-000779 | MM-ASK-1A-WP02-ELE-LAY-0004-001 | CABLES ROUTING PLAN/LAYOUT DRAWINGS - WP02 UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:09:57 | zm167dc@jutal.com | 26-Jul-2026 23:05:26 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:48:56 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:05:01 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 23:20:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:24:05 | 10-Aug-2026 08:12:01 | 0 |  |  | Approver | Locate
AO-000779 | MM-ASK-1A-WP02-ELE-LAY-0004-002 | CABLES ROUTING PLAN/LAYOUT DRAWINGS - WP02 LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:10:23 | zm167dc@jutal.com | 26-Jul-2026 23:05:27 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:50:17 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:08:49 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 23:57:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:26:31 | 10-Aug-2026 08:13:22 | 0 |  |  | Approver | Locate
AO-000779 | MM-ASK-1A-WP02-ELE-LAY-0004-003 | CABLES ROUTING PLAN/LAYOUT DRAWINGS - WP02 SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:10:47 | zm167dc@jutal.com | 26-Jul-2026 23:05:26 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:49:58 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:07:35 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 09-Aug-2026 23:51:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:28:42 | 11-Aug-2026 02:10:05 | 0 |  |  | Approver | Locate
AO-000779 | MM-ASK-1A-WP02-ELE-LAY-0004-004 | CABLES ROUTING PLAN/LAYOUT DRAWINGS - WP02 E&I ROOM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:11:11 | zm167dc@jutal.com | 26-Jul-2026 23:05:28 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:51:08 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:10:42 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:05:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:28:04 | 11-Aug-2026 02:08:45 | 0 |  |  | Approver | Locate
AO-000120 | MM-ASK-1A-WP02-ELE-LIS-0001 | ELECTRICAL LOAD LIST & LOAD ANALYSIS – WPA02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 01-May-2026 11:00:16 | zm167dc@jutal.com | 01-May-2026 11:12:31 | Jumpol Sudjitjul | 12-May-2026 | 19-May-2026 12:09:02 | Noppadol Iamtanasinchai | 13-May-2026 | 19-May-2026 13:27:11 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 22:00:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:19:51 | 20-May-2026 01:54:55 | 0 |  |  | Approver | Locate
AO-000452 | MM-ASK-1A-WP02-ELE-LIS-0001 | ELECTRICAL LOAD LIST & LOAD ANALYSIS – WPA02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 17:16:37 | zm167dc@jutal.com | 11-Jun-2026 17:46:20 | Jumpol Sudjitjul |  | 16-Jun-2026 17:01:30 | Noppadol Iamtanasinchai |  | 17-Jun-2026 08:42:13 | Pornlert Wanaphattharaphan |  | 21-Jun-2026 00:20:51 | AWC | Approved with Comment | Jumpol Sudjitjul |  | 22-Jun-2026 11:14:57 | 22-Jun-2026 04:40:45 | 0 |  |  | For Info | Locate
AO-000718 | MM-ASK-1A-WP02-ELE-LIS-0001 | ELECTRICAL LOAD LIST & LOAD ANALYSIS – WPA02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:41:02 | zm167dc@jutal.com | 17-Jul-2026 21:58:42 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 22-Jul-2026 15:19:03 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:15:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 13:30:20 | 27-Jul-2026 07:23:18 | 0 |  |  | Approver | Locate
AO-000476 | MM-ASK-1A-WP02-ELE-LIS-0002 | ELECTRICAL CABLE SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:13:00 | zm167dc@jutal.com | 13-Jun-2026 08:22:14 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 14:50:24 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:40:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:51:25 | 25-Jun-2026 06:42:40 | 0 |  |  | Approver | Locate
AO-000782 | MM-ASK-1A-WP02-ELE-LIS-0002 | ELECTRICAL CABLE SCHEDULE - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 17:34:51 | zm167dc@jutal.com | 26-Jul-2026 23:22:14 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:55:07 | Danai Chaisalee | 07-Aug-2026 | 04-Aug-2026 15:14:22 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:15:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:25:37 | 10-Aug-2026 07:26:38 | 0 |  |  | Approver | Locate
AO-001068 | MM-ASK-1A-WP02-ELE-LIS-0002 | ELECTRICAL CABLE SCHEDULE - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:41:27 | zm167dc@jutal.com | 24-Aug-2026 18:35:14 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:05:00 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:15:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:02:11 | 07-Sep-2026 03:49:51 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-ELE-LIS-0003 | ELECTRICAL EQUIPMENT AND EXPLOSION PROOF EQUIPMENT SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:20:08 | zm167dc@jutal.com | 03-Jul-2026 18:39:25 | Jumpol Sudjitjul | 14-Jul-2026 |  | Danai Chaisalee | 15-Jul-2026 | 09-Jul-2026 16:56:32 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 10-Jul-2026 00:52:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 10-Jul-2026 09:26:12 | 10-Jul-2026 02:50:58 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP02-ELE-LIS-0003 | ELECTRICAL EQUIPMENT AND EXPLOSION PROOF EQUIPMENT SCHEDULE - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 10:00:35 | zm167dc@jutal.com | 07-Aug-2026 11:02:30 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:15:37 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:44:48 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:39:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:41:14 | 21-Aug-2026 03:16:06 | 0 |  |  | Approver | Locate
AO-001146 | MM-ASK-1A-WP02-ELE-LIS-0003 | ELECTRICAL EQUIPMENT AND EXPLOSION PROOF EQUIPMENT SCHEDULE - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:50:33 | zm167dc@jutal.com | 02-Sep-2026 22:22:05 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 11:02:56 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:24:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 17:56:05 | 18-Sep-2026 11:47:27 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP02-ELE-LIS-0004-001 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:38:59 | zm167dc@jutal.com | 03-Jul-2026 13:41:56 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:48:12 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:48:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 09:29:15 | 10-Jul-2026 03:32:04 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-WP02-ELE-LIS-0004-001 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:41:22 | zm167dc@jutal.com | 11-Sep-2026 20:02:29 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 | 16-Sep-2026 14:27:11 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 17-Sep-2026 22:24:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 18-Sep-2026 17:57:28 | 18-Sep-2026 11:51:27 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP02-ELE-LIS-0004-002 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:39:54 | zm167dc@jutal.com | 03-Jul-2026 13:42:13 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:52:01 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:50:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 09:32:54 | 10-Jul-2026 03:33:22 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-WP02-ELE-LIS-0004-002 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:41:52 | zm167dc@jutal.com | 11-Sep-2026 20:02:45 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 | 16-Sep-2026 14:32:22 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 17-Sep-2026 22:31:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 18-Sep-2026 17:56:58 | 18-Sep-2026 11:50:06 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP02-ELE-LIS-0004-003 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:40:42 | zm167dc@jutal.com | 03-Jul-2026 13:42:08 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:50:12 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:49:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 09:57:56 | 10-Jul-2026 03:34:35 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-WP02-ELE-LIS-0004-003 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:42:21 | zm167dc@jutal.com | 11-Sep-2026 20:03:00 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 | 16-Sep-2026 14:33:19 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:18:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 16:10:31 | 20-Sep-2026 10:48:26 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP02-ELE-LIS-0004-004 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:41:40 | zm167dc@jutal.com | 03-Jul-2026 13:42:03 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:51:09 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:49:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 09:59:58 | 10-Jul-2026 03:35:49 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-WP02-ELE-LIS-0004-004 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:42:47 | zm167dc@jutal.com | 11-Sep-2026 20:03:14 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 | 16-Sep-2026 14:34:52 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:15:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 16:11:12 | 20-Sep-2026 10:49:47 | 0 |  |  | Approver | Locate
AO-000599 | MM-ASK-1A-WP02-ELE-LIS-0004-005 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:42:27 | zm167dc@jutal.com | 03-Jul-2026 13:42:09 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:49:09 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:49:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 10:01:25 | 10-Jul-2026 03:37:00 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-WP02-ELE-LIS-0004-005 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | In Review | VOID | Withdrawn or Superseded |  | 11-Sep-2026 19:43:15 | zm167dc@jutal.com | 11-Sep-2026 19:59:53 | Jumpol Sudjitjul |  |  | Danai Chaisalee |  |  | Pornlert Wanaphattharaphan | [8 empty] | 0 |  |  | For Info | Locate
AO-000599 | MM-ASK-1A-WP02-ELE-LIS-0004-006 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:43:16 | zm167dc@jutal.com | 03-Jul-2026 13:42:16 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 09-Jul-2026 16:53:02 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 00:50:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 08:57:30 | 10-Jul-2026 02:41:26 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-WP02-ELE-LIS-0004-006 | ELECTRICAL MULTI CABLE TRANSIT SCHEDULE - WP02 |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | In Review | VOID | Withdrawn or Superseded |  | 11-Sep-2026 19:43:43 | zm167dc@jutal.com | 11-Sep-2026 20:00:08 | Jumpol Sudjitjul |  |  | Danai Chaisalee |  |  | Pornlert Wanaphattharaphan | [8 empty] | 0 |  |  | For Info | Locate
AO-000616 | MM-ASK-1A-WP02-ELE-LIS-0005-001 | ELECTRICAL AC DISTRIBUTION BOARD SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:20:52 | zm167dc@jutal.com | 03-Jul-2026 18:39:40 | Jumpol Sudjitjul | 14-Jul-2026 |  | Danai Chaisalee | 15-Jul-2026 | 09-Jul-2026 16:57:31 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 10-Jul-2026 00:52:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 10-Jul-2026 08:56:15 | 10-Jul-2026 02:40:12 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP02-ELE-LIS-0005-001 | ELECTRICAL AC DISTRIBUTION BOARD SCHEDULE - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 10:01:14 | zm167dc@jutal.com | 07-Aug-2026 11:02:29 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:15:20 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:43:39 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:39:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:42:27 | 21-Aug-2026 03:18:38 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP02-ELE-LIS-0005-001 | ELECTRICAL AC DISTRIBUTION BOARD SCHEDULE - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:30:39 | zm167dc@jutal.com | 02-Sep-2026 22:20:15 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 11:02:00 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 18-Sep-2026 20:22:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 20-Sep-2026 16:12:37 | 20-Sep-2026 11:00:11 | 0 |  |  | Approver | Locate
AO-000658 | MM-ASK-1A-WP02-ELE-LIS-0005-002 | ELECTRICAL DC DISTRIBUTION BOARD SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 08-Jul-2026 20:02:59 | zm167dc@jutal.com | 09-Jul-2026 10:19:09 | Jumpol Sudjitjul | 17-Jul-2026 | 14-Jul-2026 11:01:01 | Danai Chaisalee | 20-Jul-2026 | 17-Jul-2026 09:47:27 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 20-Jul-2026 02:56:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 20-Jul-2026 09:28:46 | 20-Jul-2026 03:02:58 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP02-ELE-LIS-0005-002 | ELECTRICAL DC DISTRIBUTION BOARD SCHEDULE - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 10:01:56 | zm167dc@jutal.com | 07-Aug-2026 11:02:28 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:14:28 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:40:34 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:47:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:47:02 | 21-Aug-2026 03:27:06 | 0 |  |  | Approver | Locate
AO-001157 | MM-ASK-1A-WP02-ELE-LIS-0005-002 | ELECTRICAL DC DISTRIBUTION BOARD SCHEDULE - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:31:16 | zm167dc@jutal.com | 02-Sep-2026 22:23:33 | Soontaree Simpitak | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 11:03:46 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:34:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 09:33:01 | 18-Sep-2026 02:58:06 | 0 |  |  | Approver | Locate
AO-000643 | MM-ASK-1A-WP02-ELE-LIS-0006 | ELECTRICAL I/O SUMMARY - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 00:11:01 | zm167dc@jutal.com | 07-Jul-2026 10:12:13 | Jumpol Sudjitjul | 15-Jul-2026 | 14-Jul-2026 10:54:55 | Danai Chaisalee | 16-Jul-2026 | 14-Jul-2026 14:59:29 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 19-Jul-2026 17:11:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Jul-2026 | 20-Jul-2026 09:26:50 | 20-Jul-2026 02:44:22 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP02-ELE-LIS-0006 | ELECTRICAL I/O SUMMARY - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 10:02:30 | zm167dc@jutal.com | 07-Aug-2026 11:02:34 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:15:04 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:42:38 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:38:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:51:23 | 21-Aug-2026 03:29:49 | 0 |  |  | Approver | Locate
AO-001198 | MM-ASK-1A-WP02-ELE-LIS-0006 | ELECTRICAL I/O SUMMARY - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | In Review | AFC | Approved for Construction |  | 04-Sep-2026 17:22:58 | zm167dc@jutal.com | 05-Sep-2026 18:18:37 | Jumpol Sudjitjul | 15-Sep-2026 |  | Danai Chaisalee | 16-Sep-2026 | 15-Sep-2026 15:51:47 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:13:11 | AWC |  |  | 18-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000088 | MM-ASK-1A-WP02-ELE-MR-0001 | MATERIAL REQUISITION FOR AC & DC DISTRIBUTION BOARDS / PANELS – WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 11:15:51 | zm167dc@jutal.com | 27-Apr-2026 13:52:37 | Jumpol Sudjitjul | 07-May-2026 | 12-May-2026 13:33:22 | Noppadol Iamtanasinchai | 08-May-2026 | 14-May-2026 09:22:08 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:57:41 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 09:05:39 | 15-May-2026 09:25:50 | 0 |  |  | Approver | Locate
AO-000448 | MM-ASK-1A-WP02-ELE-MR-0001 | MATERIAL REQUISITION FOR AC & DC DISTRIBUTION BOARDS / PANELS – WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 14:55:45 | zm167dc@jutal.com | 11-Jun-2026 15:15:15 | Jumpol Sudjitjul | 19-Jun-2026 | 16-Jun-2026 17:14:36 | Noppadol Iamtanasinchai | 22-Jun-2026 | 17-Jun-2026 08:56:12 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:32:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:43:07 | 19-Jun-2026 05:24:54 | 0 |  |  | Approver | Locate
AO-000885 | MM-ASK-1A-WP02-ELE-MR-0001 | MATERIAL REQUISITION FOR AC & DC DISTRIBUTION BOARDS / PANELS – WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 11:52:01 | zm167dc@jutal.com | 05-Aug-2026 11:56:19 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:27:29 | Danai Chaisalee | 17-Aug-2026 | 07-Aug-2026 13:55:40 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 10-Aug-2026 00:31:09 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 13:10:34 | 10-Aug-2026 07:54:25 | 0 |  |  | Approver | Locate
AO-000089 | MM-ASK-1A-WP02-ELE-MR-0002 | MATERIAL REQUISITION FOR SOLAR POWER SYSTEM – WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 11:16:16 | zm167dc@jutal.com | 27-Apr-2026 13:52:53 | Jumpol Sudjitjul | 07-May-2026 | 12-May-2026 13:51:22 | Noppadol Iamtanasinchai | 08-May-2026 | 14-May-2026 09:23:06 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:58:23 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 09:18:39 | 15-May-2026 09:40:30 | 0 |  |  | Approver | Locate
AO-000448 | MM-ASK-1A-WP02-ELE-MR-0002 | MATERIAL REQUISITION FOR SOLAR POWER SYSTEM – WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 14:56:15 | zm167dc@jutal.com | 11-Jun-2026 15:15:18 | Jumpol Sudjitjul | 19-Jun-2026 | 16-Jun-2026 17:21:29 | Noppadol Iamtanasinchai | 22-Jun-2026 | 17-Jun-2026 08:56:58 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:33:40 | APPR | Approved | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:39:50 | 19-Jun-2026 04:49:29 | 0 |  |  | Approver | Locate
AO-000885 | MM-ASK-1A-WP02-ELE-MR-0002 | MATERIAL REQUISITION FOR SOLAR POWER SYSTEM – WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 11:52:27 | zm167dc@jutal.com | 05-Aug-2026 11:56:21 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:28:29 | Danai Chaisalee | 17-Aug-2026 | 07-Aug-2026 13:56:39 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 10-Aug-2026 00:31:50 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 11-Aug-2026 08:23:08 | 11-Aug-2026 02:17:40 | 0 |  |  | Approver | Locate
AO-000180 | MM-ASK-1A-WP02-ELE-MR-0003 | MATERIAL REQUISITION FOR NAVIGATION AID/ RED LANTERN, BEACON AND SIREN - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 21:26:47 | zm167dc@jutal.com | 08-May-2026 21:34:24 | Jumpol Sudjitjul | 19-May-2026 | 22-May-2026 13:07:05 | Noppadol Iamtanasinchai | 20-May-2026 | 23-May-2026 12:37:50 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 22:47:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 28-May-2026 09:13:40 | 28-May-2026 09:32:32 | 0 |  |  | Approver | Locate
AO-000489 | MM-ASK-1A-WP02-ELE-MR-0003 | MATERIAL REQUISITION FOR NAVIGATION AID/ RED LANTERN, BEACON AND SIREN - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 16-Jun-2026 19:25:34 | zm167dc@jutal.com | 17-Jun-2026 08:49:48 | Jumpol Sudjitjul | 25-Jun-2026 |  | Danai Chaisalee | 26-Jun-2026 | 25-Jun-2026 14:06:33 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 28-Jun-2026 08:45:17 | APPR | Approved | Jumpol Sudjitjul | 30-Jun-2026 | 28-Jun-2026 08:49:58 | 28-Jun-2026 02:28:17 | 0 |  |  | Approver | Locate
AO-000958 | MM-ASK-1A-WP02-ELE-MR-0003 | MATERIAL REQUISITION FOR NAVIGATION AID/ RED LANTERN, BEACON AND SIREN - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 18:28:38 | zm167dc@jutal.com | 13-Aug-2026 13:14:09 | Jumpol Sudjitjul | 21-Aug-2026 |  | Danai Chaisalee | 24-Aug-2026 | 21-Aug-2026 09:32:26 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:23:15 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 14:11:46 | 24-Aug-2026 07:44:27 | 0 |  |  | Approver | Locate
AO-000090 | MM-ASK-1A-WP02-ELE-MR-0004 | MATERIAL REQUISITION FOR EXTERNAL BATTERY CHARGER – WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 11:16:40 | zm167dc@jutal.com | 27-Apr-2026 13:53:07 | Jumpol Sudjitjul | 07-May-2026 | 13-May-2026 18:15:53 | Noppadol Iamtanasinchai | 08-May-2026 | 14-May-2026 09:24:30 | Pornlert Wanaphattharaphan | 11-May-2026 | 15-May-2026 00:00:49 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:20:44 | 15-May-2026 10:49:20 | 0 |  |  | Approver | Locate
AO-000448 | MM-ASK-1A-WP02-ELE-MR-0004 | MATERIAL REQUISITION FOR EXTERNAL BATTERY CHARGER – WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 14:56:46 | zm167dc@jutal.com | 11-Jun-2026 15:15:16 | Jumpol Sudjitjul | 19-Jun-2026 | 16-Jun-2026 17:24:24 | Noppadol Iamtanasinchai | 22-Jun-2026 | 17-Jun-2026 08:54:48 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:21:49 | APPR | Approved | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 10:51:22 | 19-Jun-2026 04:19:36 | 0 |  |  | Approver | Locate
AO-000885 | MM-ASK-1A-WP02-ELE-MR-0004 | MATERIAL REQUISITION FOR EXTERNAL BATTERY CHARGER – WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 11:52:55 | zm167dc@jutal.com | 05-Aug-2026 11:56:20 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:28:44 | Danai Chaisalee | 17-Aug-2026 | 07-Aug-2026 13:56:57 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 10-Aug-2026 00:32:31 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 11-Aug-2026 08:17:56 | 11-Aug-2026 01:37:14 | 0 |  |  | Approver | Locate
AO-000900 | MM-ASK-1A-WP02-ELE-MR-0005 | MATERIAL REQUISITION FOR ELECTRICAL CABLES - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 10:03:03 | zm167dc@jutal.com | 07-Aug-2026 11:09:39 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:17:43 | Danai Chaisalee | 19-Aug-2026 | 18-Aug-2026 10:48:42 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 06:41:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:49:46 | 21-Aug-2026 03:28:25 | 0 |  |  | Approver | Locate
AO-001198 | MM-ASK-1A-WP02-ELE-MR-0006 | MATERIAL REQUISITION FOR ELECTRICAL BULK MATERIALS - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 17:23:24 | zm167dc@jutal.com | 05-Sep-2026 18:17:43 | Jumpol Sudjitjul | 15-Sep-2026 |  | Danai Chaisalee | 16-Sep-2026 | 15-Sep-2026 15:48:19 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:11:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 16:13:34 | 20-Sep-2026 10:30:27 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP02-ELE-MR-0007 | MATERIAL REQUISITION FOR FOG HORN - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 10:43:20 | zm167dc@jutal.com | 26-Jul-2026 22:18:37 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:38:06 | Danai Chaisalee | 07-Aug-2026 | 05-Aug-2026 09:10:21 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:16:41 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:17:30 | 11-Aug-2026 01:27:58 | 0 |  |  | Approver | Locate
AO-000939 | MM-ASK-1A-WP02-ELE-MR-0008 | MATERIAL REQUISITION FOR MOTOR CONTROL CENTER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:29:36 | zm167dc@jutal.com | 10-Aug-2026 15:53:28 | Jumpol Sudjitjul | 19-Aug-2026 |  | Danai Chaisalee | 20-Aug-2026 | 20-Aug-2026 09:42:22 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:54:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:12:31 | 24-Aug-2026 08:19:48 | 0 |  |  | Approver | Locate
AO-001135 | MM-ASK-1A-WP02-ELE-MTO-0001 | ELECTRICAL BULK MATERIALS TAKE OFF - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 28-Aug-2026 18:08:33 | zm167dc@jutal.com | 29-Aug-2026 13:36:43 | Jumpol Sudjitjul | 07-Sep-2026 |  | Danai Chaisalee | 08-Sep-2026 | 08-Sep-2026 13:16:07 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 10-Sep-2026 23:05:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 12:30:20 | 11-Sep-2026 06:09:04 | 0 |  |  | Approver | Locate
AO-000686 | MM-ASK-1A-WP02-ELE-RPT-0001 | ELECTRICAL POWER GENERATION SELECTION REPORT - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jul-2026 11:36:35 | zm167dc@jutal.com | 12-Jul-2026 11:54:54 | Jumpol Sudjitjul | 20-Jul-2026 | 14-Jul-2026 11:22:32 | Danai Chaisalee | 21-Jul-2026 | 20-Jul-2026 13:58:25 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 22-Jul-2026 23:02:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 23-Jul-2026 13:11:57 | 23-Jul-2026 06:21:00 | 0 |  |  | Approver | Locate
AO-000318 | MM-ASK-1A-WP02-ELE-SLD-0001 | ELECTRICAL KEY SINGLE LINE DIAGRAM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:44:03 | zm167dc@jutal.com | 23-May-2026 09:17:59 | Jumpol Sudjitjul | 02-Jun-2026 | 08-Jun-2026 14:14:01 | Noppadol Iamtanasinchai | 04-Jun-2026 | 08-Jun-2026 14:46:44 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:14:39 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:46:50 | 11-Jun-2026 03:22:56 | 0 |  |  | Approver | Locate
AO-000575 | MM-ASK-1A-WP02-ELE-SLD-0001 | ELECTRICAL KEY SINGLE LINE DIAGRAM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 22:04:58 | zm167dc@jutal.com | 30-Jun-2026 10:15:07 | Jumpol Sudjitjul | 08-Jul-2026 |  | Danai Chaisalee | 09-Jul-2026 | 02-Jul-2026 08:54:43 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:30:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 10:05:41 | 10-Jul-2026 03:27:28 | 0 |  |  | Approver | Locate
AO-000848 | MM-ASK-1A-WP02-ELE-SLD-0001 | ELECTRICAL KEY SINGLE LINE DIAGRAM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 09:59:42 | zm167dc@jutal.com | 03-Aug-2026 11:12:00 | Jumpol Sudjitjul | 11-Aug-2026 | 04-Aug-2026 10:28:28 | Danai Chaisalee | 13-Aug-2026 | 07-Aug-2026 13:19:57 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 19:55:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 09:02:51 | 13-Aug-2026 02:44:46 | 0 |  |  | Approver | Locate
AO-000318 | MM-ASK-1A-WP02-ELE-SLD-0002 | ELECTRICAL SINGLE LINE DIAGRAM - AC SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:44:24 | zm167dc@jutal.com | 23-May-2026 09:17:55 | Jumpol Sudjitjul | 02-Jun-2026 |  | Noppadol Iamtanasinchai | 04-Jun-2026 | 08-Jun-2026 14:09:49 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:09:45 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:48:29 | 11-Jun-2026 03:23:57 | 0 |  |  | Approver | Locate
AO-000575 | MM-ASK-1A-WP02-ELE-SLD-0002 | ELECTRICAL SINGLE LINE DIAGRAM - AC SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 12:44:28 | zm167dc@jutal.com | 30-Jun-2026 10:15:16 | Jumpol Sudjitjul | 08-Jul-2026 |  | Danai Chaisalee | 09-Jul-2026 | 02-Jul-2026 09:01:40 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:34:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 10:07:34 | 10-Jul-2026 03:39:32 | 0 |  |  | Approver | Locate
AO-000848 | MM-ASK-1A-WP02-ELE-SLD-0002 | ELECTRICAL SINGLE LINE DIAGRAM - AC SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:00:26 | zm167dc@jutal.com | 03-Aug-2026 11:12:27 | Jumpol Sudjitjul | 11-Aug-2026 | 04-Aug-2026 10:28:53 | Danai Chaisalee | 13-Aug-2026 | 07-Aug-2026 13:20:46 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 19:56:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 09:05:54 | 13-Aug-2026 02:46:07 | 0 |  |  | Approver | Locate
AO-000318 | MM-ASK-1A-WP02-ELE-SLD-0003 | ELECTRICAL SINGLE LINE DIAGRAM - DC SYSTEM & NAVIGATION AIDS SYSTEM -WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:44:47 | zm167dc@jutal.com | 23-May-2026 09:17:59 | Jumpol Sudjitjul | 02-Jun-2026 | 08-Jun-2026 14:13:39 | Noppadol Iamtanasinchai | 04-Jun-2026 | 08-Jun-2026 14:45:57 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:12:12 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:49:57 | 11-Jun-2026 03:25:03 | 0 |  |  | Approver | Locate
AO-000575 | MM-ASK-1A-WP02-ELE-SLD-0003 | ELECTRICAL SINGLE LINE DIAGRAM - DC SYSTEM & NAVIGATION AIDS SYSTEM -WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 12:44:55 | zm167dc@jutal.com | 30-Jun-2026 10:15:12 | Jumpol Sudjitjul | 08-Jul-2026 |  | Danai Chaisalee | 09-Jul-2026 | 02-Jul-2026 09:00:34 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:33:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 10:01:48 | 10-Jul-2026 03:38:15 | 0 |  |  | Approver | Locate
AO-000848 | MM-ASK-1A-WP02-ELE-SLD-0003 | ELECTRICAL SINGLE LINE DIAGRAM - DC SYSTEM & NAVIGATION AIDS SYSTEM -WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:01:00 | zm167dc@jutal.com | 03-Aug-2026 11:12:47 | Jumpol Sudjitjul | 11-Aug-2026 | 04-Aug-2026 10:29:11 | Danai Chaisalee | 13-Aug-2026 | 07-Aug-2026 13:21:43 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 19:58:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 09:10:00 | 13-Aug-2026 03:31:11 | 0 |  |  | Approver | Locate
AO-000577 | MM-ASK-1A-WP02-ELE-SLD-0004 | SOLAR PV ARRAY PANEL ARRANGEMENT - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Jun-2026 21:10:49 | zm167dc@jutal.com | 30-Jun-2026 10:15:09 | Jumpol Sudjitjul | 08-Jul-2026 |  | Danai Chaisalee | 09-Jul-2026 | 02-Jul-2026 08:57:27 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:32:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 09:04:00 | 10-Jul-2026 02:56:43 | 0 |  |  | Approver | Locate
AO-000848 | MM-ASK-1A-WP02-ELE-SLD-0004 | SOLAR PV ARRAY PANEL ARRANGEMENT - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:01:40 | zm167dc@jutal.com | 03-Aug-2026 11:13:02 | Jumpol Sudjitjul | 11-Aug-2026 | 04-Aug-2026 10:29:28 | Danai Chaisalee | 13-Aug-2026 | 05-Aug-2026 14:44:19 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 19:53:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 10:04:37 | 13-Aug-2026 03:39:23 | 0 |  |  | Approver | Locate
AO-001201 | MM-ASK-1A-WP02-ELE-SLD-0004 | SOLAR PV ARRAY PANEL ARRANGEMENT - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 17:23:51 | zm167dc@jutal.com | 05-Sep-2026 18:14:53 | Jumpol Sudjitjul | 15-Sep-2026 |  | Danai Chaisalee | 16-Sep-2026 | 15-Sep-2026 15:45:44 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:10:04 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 16:14:22 | 20-Sep-2026 10:31:41 | 0 |  |  | Approver | Locate
AO-000681 | MM-ASK-1A-WP02-ELE-STU-0001 | MOTOR STARTING STUDY - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | STU | Study Report | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 18:09:44 | zm167dc@jutal.com | 10-Jul-2026 18:21:08 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:27:56 | Danai Chaisalee | 22-Jul-2026 | 20-Jul-2026 13:57:37 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 02:59:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 13:53:43 | 27-Jul-2026 07:19:38 | 0 |  |  | Approver | Locate
AO-000965 | MM-ASK-1A-WP02-ELE-STU-0001 | MOTOR STARTING STUDY - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | STU | Study Report | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:53:43 | zm167dc@jutal.com | 13-Aug-2026 14:00:48 | Jumpol Sudjitjul | 21-Aug-2026 |  | Danai Chaisalee | 24-Aug-2026 | 21-Aug-2026 08:54:37 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:11:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 14:13:17 | 24-Aug-2026 07:49:25 | 0 |  |  | Approver | Locate
AO-000631 | MM-ASK-1A-WP02-ELE-TBE-0001 | TECHNICAL BID EVALUATION FOR AC & DC DISTRIBUTION BOARDS/PANELS - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:23:48 | zm167dc@jutal.com | 04-Jul-2026 14:19:04 | Jumpol Sudjitjul | 13-Jul-2026 | 08-Jul-2026 13:45:20 | Danai Chaisalee | 14-Jul-2026 | 10-Jul-2026 13:02:23 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 13:14:53 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 13:25:11 | 10-Jul-2026 06:34:16 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-WP02-ELE-TBE-0001 | TECHNICAL BID EVALUATION FOR AC & DC DISTRIBUTION BOARDS/PANELS - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:59:10 | zm167dc@jutal.com | 20-Jul-2026 11:49:24 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 21-Jul-2026 10:19:22 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 21-Jul-2026 15:52:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 21-Jul-2026 16:11:07 | 21-Jul-2026 09:44:28 | 0 |  |  | Approver | Locate
AO-000805 | MM-ASK-1A-WP02-ELE-TBE-0001 | TECHNICAL BID EVALUATION FOR AC & DC DISTRIBUTION BOARDS/PANELS - WP02 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 18:23:32 | zm167dc@jutal.com | 28-Jul-2026 08:52:16 | Jumpol Sudjitjul | 06-Aug-2026 |  | Danai Chaisalee | 07-Aug-2026 | 30-Jul-2026 13:05:43 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 18:04:07 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 19:00:17 | 30-Jul-2026 12:20:17 | 0 |  |  | Approver | Locate
AO-000631 | MM-ASK-1A-WP02-ELE-TBE-0002 | TECHNICAL BID EVALUATION FOR SOLAR POWER SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:24:18 | zm167dc@jutal.com | 04-Jul-2026 14:20:04 | Jumpol Sudjitjul | 13-Jul-2026 |  | Danai Chaisalee | 14-Jul-2026 | 10-Jul-2026 13:03:17 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 13:37:58 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 13:51:22 | 10-Jul-2026 07:56:10 | 0 |  |  | Approver | Locate
AO-000732 | MM-ASK-1A-WP02-ELE-TBE-0002 | TECHNICAL BID EVALUATION FOR SOLAR POWER SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:59:41 | zm167dc@jutal.com | 20-Jul-2026 11:50:30 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 21-Jul-2026 10:21:39 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 21-Jul-2026 15:45:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 21-Jul-2026 16:08:34 | 21-Jul-2026 09:42:58 | 0 |  |  | Approver | Locate
AO-000806 | MM-ASK-1A-WP02-ELE-TBE-0002 | TECHNICAL BID EVALUATION FOR SOLAR POWER SYSTEM - WP02 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 17:08:02 | zm167dc@jutal.com | 28-Jul-2026 08:52:33 | Jumpol Sudjitjul | 06-Aug-2026 |  | Danai Chaisalee | 07-Aug-2026 | 30-Jul-2026 13:05:20 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 18:06:49 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 19:08:10 | 30-Jul-2026 12:40:20 | 0 |  |  | Approver | Locate
AO-000687 | MM-ASK-1A-WP02-ELE-TBE-0003 | TECHNICAL BID EVALUATION FOR NAVIGATION AID SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:37:08 | zm167dc@jutal.com | 12-Jul-2026 11:56:42 | Jumpol Sudjitjul | 20-Jul-2026 | 14-Jul-2026 11:23:04 | Danai Chaisalee | 21-Jul-2026 | 20-Jul-2026 13:52:42 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 21-Jul-2026 00:51:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 21-Jul-2026 07:35:11 | 21-Jul-2026 00:53:17 | 0 |  |  | Approver | Locate
AO-000884 | MM-ASK-1A-WP02-ELE-TBE-0003 | TECHNICAL BID EVALUATION FOR NAVIGATION AID SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 04-Aug-2026 17:35:22 | zm167dc@jutal.com | 05-Aug-2026 08:30:32 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:27:11 | Danai Chaisalee | 17-Aug-2026 | 06-Aug-2026 07:32:08 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 06-Aug-2026 23:54:22 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 07-Aug-2026 09:26:34 | 07-Aug-2026 03:23:03 | 0 |  |  | Approver | Locate
AO-000652 | MM-ASK-1A-WP02-ELE-TBE-0004 | TECHNICAL BID EVALUATION FOR EXTERNAL BATTERY CHARGER - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 18:43:29 | zm167dc@jutal.com | 07-Jul-2026 20:49:46 | Jumpol Sudjitjul | 16-Jul-2026 | 14-Jul-2026 10:59:24 | Danai Chaisalee | 17-Jul-2026 | 16-Jul-2026 16:30:56 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 16-Jul-2026 17:00:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 16-Jul-2026 17:02:33 | 17-Jul-2026 07:27:39 | 0 |  |  | Approver | Locate
AO-000847 | MM-ASK-1A-WP02-ELE-TBE-0004 | TECHNICAL BID EVALUATION FOR EXTERNAL BATTERY CHARGER - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:02:26 | zm167dc@jutal.com | 03-Aug-2026 11:15:35 | Jumpol Sudjitjul | 11-Aug-2026 | 04-Aug-2026 10:30:02 | Danai Chaisalee | 13-Aug-2026 | 05-Aug-2026 09:11:05 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 06-Aug-2026 21:03:53 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 09:25:46 | 07-Aug-2026 03:21:37 | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP02-ELE-WIR-0001-001 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:13:23 | zm167dc@jutal.com | 13-Jun-2026 08:25:26 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 13:48:08 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:35:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:53:17 | 25-Jun-2026 06:45:38 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP02-ELE-WIR-0001-001 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:00:31 | zm167dc@jutal.com | 20-Jul-2026 11:41:01 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:05:17 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 20:13:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 13:54:38 | 27-Jul-2026 07:11:27 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP02-ELE-WIR-0001-001 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:25:57 | zm167dc@jutal.com | 24-Aug-2026 20:05:35 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:09:48 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:18:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:03:42 | 07-Sep-2026 03:51:15 | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP02-ELE-WIR-0001-002 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:13:47 | zm167dc@jutal.com | 13-Jun-2026 08:25:39 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 13:56:14 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:36:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:14:58 | 25-Jun-2026 05:46:21 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP02-ELE-WIR-0001-002 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:01:12 | zm167dc@jutal.com | 20-Jul-2026 11:41:01 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:12:14 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 21:01:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:00:11 | 27-Jul-2026 07:13:42 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP02-ELE-WIR-0001-002 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:26:26 | zm167dc@jutal.com | 24-Aug-2026 20:06:02 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:10:55 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:19:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:05:03 | 07-Sep-2026 03:52:40 | 0 |  |  | Approver | Locate
AO-000738 | MM-ASK-1A-WP02-ELE-WIR-0001-003 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 11:14:39 | zm167dc@jutal.com | 20-Jul-2026 13:11:10 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:20:22 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 21:30:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:01:37 | 27-Jul-2026 07:18:21 | 0 |  |  | Approver | Locate
AO-001070 | MM-ASK-1A-WP02-ELE-WIR-0001-003 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 18:40:04 | zm167dc@jutal.com | 24-Aug-2026 20:15:07 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:20:33 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:21:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:06:06 | 07-Sep-2026 03:53:59 | 0 |  |  | Approver | Locate
AO-001474 | MM-ASK-1A-WP02-ELE-WIR-0001-003 | ELECTRICAL WIRING INTERCONNECTION FOR AC AND DISTRIBUTION SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:48:18 | zm167dc@jutal.com | 18-Sep-2026 17:09:33 | Jumpol Sudjitjul | 29-Sep-2026 |  | Danai Chaisalee | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP02-ELE-WIR-0002-001 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:14:18 | zm167dc@jutal.com | 13-Jun-2026 08:25:52 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 13:41:13 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:34:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:11:24 | 25-Jun-2026 05:45:03 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP02-ELE-WIR-0002-001 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:01:50 | zm167dc@jutal.com | 20-Jul-2026 11:41:01 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:06:15 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 20:15:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 13:52:08 | 27-Jul-2026 07:08:59 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP02-ELE-WIR-0002-001 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:26:53 | zm167dc@jutal.com | 24-Aug-2026 20:06:27 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:13:17 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:24:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:06:53 | 07-Sep-2026 03:55:22 | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP02-ELE-WIR-0002-002 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:14:44 | zm167dc@jutal.com | 13-Jun-2026 08:26:05 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 13:28:36 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:34:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:52:19 | 25-Jun-2026 06:44:12 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP02-ELE-WIR-0002-002 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:02:23 | zm167dc@jutal.com | 20-Jul-2026 11:41:03 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:07:10 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 20:25:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:07:37 | 27-Jul-2026 08:05:13 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP02-ELE-WIR-0002-002 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:27:22 | zm167dc@jutal.com | 24-Aug-2026 20:06:59 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:15:10 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:25:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:07:41 | 07-Sep-2026 03:43:33 | 0 |  |  | Approver | Locate
AO-000739 | MM-ASK-1A-WP02-ELE-WIR-0002-003 | ELECTRICAL WIRING INTERCONNECTION FOR SOLAR SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 11:15:05 | zm167dc@jutal.com | 20-Jul-2026 13:11:11 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:19:14 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 21:27:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 13:49:45 | 27-Jul-2026 07:17:07 | 0 |  |  | Approver | Locate
AO-001082 | MM-ASK-1A-WP02-ELE-WIR-0002-003 | ELECTRICAL WIRING INTERCONNECTION FOR SOLAR SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:30:01 | zm167dc@jutal.com | 24-Aug-2026 20:15:09 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:18:38 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:27:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:08:33 | 07-Sep-2026 03:44:53 | 0 |  |  | Approver | Locate
AO-001475 | MM-ASK-1A-WP02-ELE-WIR-0002-003 | ELECTRICAL WIRING INTERCONNECTION FOR SOLAR SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:48:57 | zm167dc@jutal.com | 18-Sep-2026 17:09:34 | Jumpol Sudjitjul | 29-Sep-2026 |  | Danai Chaisalee | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000740 | MM-ASK-1A-WP02-ELE-WIR-0002-004 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 11:15:29 | zm167dc@jutal.com | 20-Jul-2026 13:11:10 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:17:59 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 21:26:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 13:30:13 | 27-Jul-2026 07:15:50 | 0 |  |  | Approver | Locate
AO-001083 | MM-ASK-1A-WP02-ELE-WIR-0002-004 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:30:44 | zm167dc@jutal.com | 24-Aug-2026 20:15:11 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:21:47 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:29:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:09:43 | 07-Sep-2026 03:47:17 | 0 |  |  | Approver | Locate
AO-001476 | MM-ASK-1A-WP02-ELE-WIR-0002-004 | ELECTRICAL WIRING INTERCONNECTION FOR DC DISTRIBUTION SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:49:29 | zm167dc@jutal.com | 18-Sep-2026 17:09:36 | Jumpol Sudjitjul | 29-Sep-2026 |  | Danai Chaisalee | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000474 | MM-ASK-1A-WP02-ELE-WIR-0003 | ELECTRICAL WIRING INTERCONNECTION FOR NAVIGATION AID SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:15:08 | zm167dc@jutal.com | 13-Jun-2026 08:26:18 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 13:08:47 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:32:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:54:04 | 25-Jun-2026 06:47:11 | 0 |  |  | Approver | Locate
AO-000729 | MM-ASK-1A-WP02-ELE-WIR-0003 | ELECTRICAL WIRING INTERCONNECTION FOR NAVIGATION AID SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:02:59 | zm167dc@jutal.com | 20-Jul-2026 11:41:04 | Jumpol Sudjitjul | 30-Jul-2026 |  | Danai Chaisalee | 31-Jul-2026 | 23-Jul-2026 13:14:37 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 21:07:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 13:37:07 | 27-Jul-2026 07:06:40 | 0 |  |  | Approver | Locate
AO-001079 | MM-ASK-1A-WP02-ELE-WIR-0003 | ELECTRICAL WIRING INTERCONNECTION FOR NAVIGATION AID SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:28:10 | zm167dc@jutal.com | 24-Aug-2026 20:07:20 | Jumpol Sudjitjul | 02-Sep-2026 |  | Danai Chaisalee | 03-Sep-2026 | 03-Sep-2026 11:15:57 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 06-Sep-2026 23:38:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:38:29 | 07-Sep-2026 04:42:25 | 0 |  |  | Approver | Locate
AO-000094 | MM-ASK-1A-WP02-INS-DTS-0001 | DATASHEET FOR WELLHEAD CONTROL PANEL - WPA02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 28-Apr-2026 19:04:45 | zm167dc@jutal.com | 29-Apr-2026 10:05:20 | Jumpol Sudjitjul | 11-May-2026 | 11-May-2026 20:09:58 | Payut Phatdamrongdet | 12-May-2026 | 12-May-2026 22:14:37 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 23:00:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 19-May-2026 09:20:09 | 19-May-2026 14:23:02 | 0 |  |  | Approver | Locate
AO-000452 | MM-ASK-1A-WP02-INS-DTS-0001 | DATASHEET FOR WELLHEAD CONTROL PANEL - WPA02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 17:18:07 | zm167dc@jutal.com | 11-Jun-2026 17:47:44 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 16-Jun-2026 14:09:52 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 21-Jun-2026 08:47:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 11:29:05 | 22-Jun-2026 04:55:16 | 0 |  |  | Approver | Locate
AO-000656 | MM-ASK-1A-WP02-INS-DTS-0001 | DATASHEET FOR WELLHEAD CONTROL PANEL - WPA02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 16:59:17 | zm167dc@jutal.com | 08-Jul-2026 17:09:28 | Jumpol Sudjitjul | 17-Jul-2026 |  | Payut Phatdamrongdet | 20-Jul-2026 | 20-Jul-2026 23:40:13 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 23:02:11 | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 08:46:59 | 23-Jul-2026 02:24:18 | 0 |  |  | Approver | Locate
AO-000257 | MM-ASK-1A-WP02-INS-DTS-0002 | DATA SHEET FOR CONTROL VALVES-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 12:08:53 | zm167dc@jutal.com | 15-May-2026 17:44:48 | Jumpol Sudjitjul | 26-May-2026 | 26-May-2026 21:31:01 | Payut Phatdamrongdet | 27-May-2026 | 28-May-2026 14:57:25 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 01:13:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:49:18 | 10-Jun-2026 07:21:44 | 0 |  |  | Approver | Locate
AO-000674 | MM-ASK-1A-WP02-INS-DTS-0002 | DATA SHEET FOR CONTROL VALVES-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 16:53:01 | zm167dc@jutal.com | 10-Jul-2026 17:47:30 | Jumpol Sudjitjul | 21-Jul-2026 | 21-Jul-2026 23:36:22 | Payut Phatdamrongdet | 22-Jul-2026 | 22-Jul-2026 11:25:46 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 03:13:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 13:28:46 | 27-Jul-2026 07:21:57 | 0 |  |  | Approver | Locate
AO-000929 | MM-ASK-1A-WP02-INS-DTS-0002 | DATA SHEET FOR CONTROL VALVES-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 17:26:32 | zm167dc@jutal.com | 07-Aug-2026 17:30:33 | Jumpol Sudjitjul | 19-Aug-2026 | 19-Aug-2026 22:48:34 | Payut Phatdamrongdet | 20-Aug-2026 | 24-Aug-2026 16:47:43 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 27-Aug-2026 14:44:31 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 27-Aug-2026 14:47:26 | 27-Aug-2026 08:44:11 | 0 |  |  | Approver | Locate
AO-000271 | MM-ASK-1A-WP02-INS-DTS-0003 | DATA SHEET FOR SELF ACTUATED PCV-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 15:29:40 | zm167dc@jutal.com | 15-May-2026 17:44:48 | Jumpol Sudjitjul | 26-May-2026 | 26-May-2026 16:45:38 | Payut Phatdamrongdet | 27-May-2026 | 28-May-2026 08:16:49 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 01:06:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:48:48 | 10-Jun-2026 05:20:46 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-INS-DTS-0003 | DATA SHEET FOR SELF ACTUATED PCV-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 18:13:55 | zm167dc@jutal.com | 03-Jul-2026 18:27:57 | Jumpol Sudjitjul | 14-Jul-2026 | 14-Jul-2026 20:43:21 | Payut Phatdamrongdet | 15-Jul-2026 | 20-Jul-2026 17:27:13 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 22-Jul-2026 22:55:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 23-Jul-2026 13:10:30 | 23-Jul-2026 06:28:37 | 0 |  |  | Approver | Locate
AO-000851 | MM-ASK-1A-WP02-INS-DTS-0003 | DATA SHEET FOR SELF ACTUATED PCV-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:03:55 | zm167dc@jutal.com | 03-Aug-2026 11:18:11 | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 00:37:24 | Payut Phatdamrongdet | 13-Aug-2026 | 10-Aug-2026 13:21:10 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:14:54 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 09:33:09 | 17-Aug-2026 03:33:06 | 0 |  |  | Approver | Locate
AO-000242 | MM-ASK-1A-WP02-INS-DTS-0004 | DATA SHEET FOR ACTUATED CHOKE VALVES-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:55:55 | zm167dc@jutal.com | 15-May-2026 17:44:45 | Jumpol Sudjitjul | 26-May-2026 | 26-May-2026 07:58:29 | Payut Phatdamrongdet | 27-May-2026 | 27-May-2026 13:28:23 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 00:57:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:47:44 | 10-Jun-2026 07:27:34 | 0 |  |  | Approver | Locate
AO-000550 | MM-ASK-1A-WP02-INS-DTS-0004 | DATA SHEET FOR ACTUATED CHOKE VALVES-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:07:04 | zm167dc@jutal.com | 26-Jun-2026 08:20:18 | Jumpol Sudjitjul | 06-Jul-2026 | 06-Jul-2026 23:22:02 | Payut Phatdamrongdet | 07-Jul-2026 | 17-Jul-2026 14:06:46 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 19-Jul-2026 11:53:34 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 09-Jul-2026 | 20-Jul-2026 09:28:20 | 20-Jul-2026 03:24:10 | 0 |  |  | Approver | Locate
AO-000829 | MM-ASK-1A-WP02-INS-DTS-0004 | DATA SHEET FOR ACTUATED CHOKE VALVES-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:19:50 | zm167dc@jutal.com | 31-Jul-2026 21:46:12 | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 00:38:04 | Payut Phatdamrongdet | 13-Aug-2026 | 10-Aug-2026 12:29:13 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 13-Aug-2026 00:05:43 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 10:11:50 | 13-Aug-2026 04:09:25 | 0 |  |  | Approver | Locate
AO-000410 | MM-ASK-1A-WP02-INS-DTS-0005 | DATA SHEETS FOR ACTUATED BALL VALVES-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:48:09 | zm167dc@jutal.com | 05-Jun-2026 13:58:32 | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 21:25:51 | Payut Phatdamrongdet | 16-Jun-2026 | 15-Jun-2026 10:31:47 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 15-Jun-2026 23:19:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 16-Jun-2026 09:41:24 | 16-Jun-2026 03:38:39 | 0 |  |  | Approver | Locate
AO-000666 | MM-ASK-1A-WP02-INS-DTS-0005 | DATA SHEETS FOR ACTUATED BALL VALVES-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 09-Jul-2026 16:57:11 | zm167dc@jutal.com | 09-Jul-2026 17:07:49 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 23:58:46 | Payut Phatdamrongdet | 21-Jul-2026 | 22-Jul-2026 11:23:58 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:42:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 10:24:29 | 24-Jul-2026 04:06:15 | 0 |  |  | Approver | Locate
AO-000927 | MM-ASK-1A-WP02-INS-DTS-0005 | DATA SHEETS FOR ACTUATED BALL VALVES-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 17:27:06 | zm167dc@jutal.com | 07-Aug-2026 17:30:51 | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 10:53:27 | Payut Phatdamrongdet | 20-Aug-2026 | 24-Aug-2026 17:00:58 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 27-Aug-2026 14:46:47 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 27-Aug-2026 15:35:16 | 27-Aug-2026 08:53:27 | 0 |  |  | Approver | Locate
AO-001254 | MM-ASK-1A-WP02-INS-DTS-0005 | DATA SHEETS FOR ACTUATED BALL VALVES-WP02 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 14:45:49 | zm167dc@jutal.com | 09-Sep-2026 16:50:54 | Jumpol Sudjitjul | 17-Sep-2026 |  | Payut Phatdamrongdet | 18-Sep-2026 | 11-Sep-2026 18:05:05 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 13-Sep-2026 22:47:58 | APPR | Approved | Jumpol Sudjitjul | 22-Sep-2026 | 13-Sep-2026 22:50:44 | 13-Sep-2026 17:03:45 | 0 |  |  | Approver | Locate
AO-000359 | MM-ASK-1A-WP02-INS-DTS-0006 | DATA SHEET FOR ACTUATED COMPACT BALL VALVES-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 27-May-2026 14:45:03 | zm167dc@jutal.com | 27-May-2026 14:59:20 | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 11:36:50 | Payut Phatdamrongdet | 09-Jun-2026 | 10-Jun-2026 14:16:58 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:28:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 09:52:25 | 11-Jun-2026 10:35:35 | 0 |  |  | Approver | Locate
AO-000517 | MM-ASK-1A-WP02-INS-DTS-0006 | DATA SHEET FOR ACTUATED COMPACT BALL VALVES-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 19-Jun-2026 17:25:25 | zm167dc@jutal.com | 19-Jun-2026 17:46:10 | Jumpol Sudjitjul | 30-Jun-2026 | 30-Jun-2026 13:19:53 | Payut Phatdamrongdet | 01-Jul-2026 | 30-Jun-2026 16:11:17 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:33:49 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 16:02:45 | 03-Jul-2026 09:51:41 | 0 |  |  | Approver | Locate
AO-000831 | MM-ASK-1A-WP02-INS-DTS-0006 | DATA SHEET FOR ACTUATED COMPACT BALL VALVES-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:20:23 | zm167dc@jutal.com | 31-Jul-2026 21:46:34 | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 00:36:31 | Payut Phatdamrongdet | 13-Aug-2026 | 10-Aug-2026 08:31:36 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 23:53:33 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 09:10:53 | 13-Aug-2026 03:40:31 | 0 |  |  | Approver | Locate
AO-000495 | MM-ASK-1A-WP02-INS-DTS-0007 | DATA SHEET FOR SAFETY RELIEF VALVES-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 17-Jun-2026 12:49:41 | zm167dc@jutal.com | 17-Jun-2026 16:06:50 | Jumpol Sudjitjul | 25-Jun-2026 | 24-Jun-2026 17:55:40 | Payut Phatdamrongdet | 26-Jun-2026 | 29-Jun-2026 15:45:36 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 30-Jun-2026 22:59:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 01-Jul-2026 08:39:38 | 01-Jul-2026 02:20:55 | 0 |  |  | Approver | Locate
AO-000684 | MM-ASK-1A-WP02-INS-DTS-0007 | DATA SHEET FOR SAFETY RELIEF VALVES-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 18:45:17 | zm167dc@jutal.com | 10-Jul-2026 20:38:27 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:28:33 | Payut Phatdamrongdet | 22-Jul-2026 | 22-Jul-2026 11:27:48 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 03:22:39 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 11:06:12 | 27-Jul-2026 04:48:50 | 0 |  |  | Approver | Locate
AO-000937 | MM-ASK-1A-WP02-INS-DTS-0007 | DATA SHEET FOR SAFETY RELIEF VALVES-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:24:56 | zm167dc@jutal.com | 10-Aug-2026 15:58:35 | Jumpol Sudjitjul | 19-Aug-2026 |  | Payut Phatdamrongdet | 20-Aug-2026 | 24-Aug-2026 17:30:18 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 27-Aug-2026 14:47:47 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 27-Aug-2026 15:51:39 | 27-Aug-2026 10:16:45 | 0 |  |  | Approver | Locate
AO-000538 | MM-ASK-1A-WP02-INS-DTS-0008 | DATA SHEET FOR CORIOLIS FLOW METERS-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jun-2026 13:16:22 | zm167dc@jutal.com | 24-Jun-2026 14:45:17 | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 14:42:32 | Payut Phatdamrongdet | 03-Jul-2026 | 07-Jul-2026 11:15:08 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 08-Jul-2026 00:52:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 08-Jul-2026 08:59:19 | 08-Jul-2026 02:47:42 | 0 |  |  | Approver | Locate
AO-000714 | MM-ASK-1A-WP02-INS-DTS-0008 | DATA SHEET FOR CORIOLIS FLOW METERS-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 17-Jul-2026 11:58:33 | zm167dc@jutal.com | 17-Jul-2026 12:51:49 | Jumpol Sudjitjul | 27-Jul-2026 | 23-Jul-2026 17:17:42 | Payut Phatdamrongdet | 30-Jul-2026 | 24-Jul-2026 08:30:14 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:15:51 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 13:34:53 | 27-Jul-2026 07:05:19 | 0 |  |  | Approver | Locate
AO-001038 | MM-ASK-1A-WP02-INS-DTS-0008 | DATA SHEET FOR CORIOLIS FLOW METERS-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 16:08:37 | zm167dc@jutal.com | 20-Aug-2026 17:05:14 | Jumpol Sudjitjul | 31-Aug-2026 |  | Payut Phatdamrongdet | 01-Sep-2026 | 26-Aug-2026 11:00:46 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 15:50:46 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:12:52 | 30-Aug-2026 09:49:36 | 0 |  |  | Approver | Locate
AO-000538 | MM-ASK-1A-WP02-INS-DTS-0009 | DATA SHEETS FOR VORTEX FLOW METERS-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jun-2026 13:16:52 | zm167dc@jutal.com | 24-Jun-2026 14:45:40 | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 14:35:12 | Payut Phatdamrongdet | 03-Jul-2026 | 07-Jul-2026 14:38:11 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 08-Jul-2026 00:54:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 08-Jul-2026 09:13:55 | 08-Jul-2026 02:52:39 | 0 |  |  | Approver | Locate
AO-000710 | MM-ASK-1A-WP02-INS-DTS-0009 | DATA SHEETS FOR VORTEX FLOW METERS-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 16:59:18 | zm167dc@jutal.com | 16-Jul-2026 20:46:40 | Jumpol Sudjitjul | 27-Jul-2026 | 23-Jul-2026 22:59:13 | Payut Phatdamrongdet | 30-Jul-2026 | 24-Jul-2026 08:21:08 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:14:47 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 14:08:25 | 27-Jul-2026 08:06:22 | 0 |  |  | Approver | Locate
AO-001047 | MM-ASK-1A-WP02-INS-DTS-0009 | DATA SHEETS FOR VORTEX FLOW METERS-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 09:35:31 | zm167dc@jutal.com | 21-Aug-2026 13:42:51 | Jumpol Sudjitjul | 31-Aug-2026 |  | Payut Phatdamrongdet | 01-Sep-2026 | 26-Aug-2026 11:18:20 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 15:55:33 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:14:54 | 30-Aug-2026 09:51:49 | 0 |  |  | Approver | Locate
AO-000764 | MM-ASK-1A-WP02-INS-DTS-0011 | DATA SHEET FOR PRESSURE GAUGES-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 23-Jul-2026 12:49:27 | zm167dc@jutal.com | 23-Jul-2026 16:18:28 | Jumpol Sudjitjul | 04-Aug-2026 | 23-Jul-2026 17:37:01 | Payut Phatdamrongdet | 05-Aug-2026 | 31-Jul-2026 10:24:47 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 05-Aug-2026 23:25:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 06-Aug-2026 09:05:16 | 06-Aug-2026 03:08:20 | 0 |  |  | Approver | Locate
AO-001337 | MM-ASK-1A-WP02-INS-DTS-0011 | DATA SHEET FOR PRESSURE GAUGES-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:45:45 | zm167dc@jutal.com | 11-Sep-2026 20:37:23 | Jumpol Sudjitjul | 22-Sep-2026 |  | Payut Phatdamrongdet | 23-Sep-2026 | 18-Sep-2026 08:41:12 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:16:25 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 16:15:27 | 20-Sep-2026 10:09:24 | 0 |  |  | Approver | Locate
AO-000773 | MM-ASK-1A-WP02-INS-DTS-0012 | DATA SHEETS FOR PRESSURE TRANSMITTERS-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:08:07 | zm167dc@jutal.com | 26-Jul-2026 22:47:59 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 31-Jul-2026 13:22:17 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 21:55:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:19:11 | 08-Aug-2026 04:17:29 | 0 |  |  | Approver | Locate
AO-001486 | MM-ASK-1A-WP02-INS-DTS-0012 | DATA SHEETS FOR PRESSURE TRANSMITTERS-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:49:59 | zm167dc@jutal.com | 18-Sep-2026 17:17:20 | Jumpol Sudjitjul | 29-Sep-2026 |  | Payut Phatdamrongdet | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-INS-DTS-0013 | DATA SHEET FOR TEMPERATURE GAUGE AND THERMOWELL-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:56:01 | zm167dc@jutal.com | 26-Jul-2026 22:48:04 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 31-Jul-2026 19:17:50 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:01:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:23:04 | 08-Aug-2026 04:35:29 | 0 |  |  | Approver | Locate
AO-001495 | MM-ASK-1A-WP02-INS-DTS-0013 | DATA SHEET FOR TEMPERATURE GAUGE AND THERMOWELL-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:16:00 | zm167dc@jutal.com | 20-Sep-2026 14:17:41 | Jumpol Sudjitjul | 28-Sep-2026 |  | Payut Phatdamrongdet | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000773 | MM-ASK-1A-WP02-INS-DTS-0014 | DATA SHEET FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:08:34 | zm167dc@jutal.com | 26-Jul-2026 22:48:00 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 31-Jul-2026 15:12:15 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 21:59:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:23:28 | 08-Aug-2026 04:22:29 | 0 |  |  | Approver | Locate
AO-001467 | MM-ASK-1A-WP02-INS-DTS-0014 | DATA SHEET FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:50:28 | zm167dc@jutal.com | 18-Sep-2026 17:17:21 | Jumpol Sudjitjul | 29-Sep-2026 |  | Payut Phatdamrongdet | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP02-INS-DTS-0015 | DATA SHEETS FOR MAGNETIC LEVEL GAUGE AND TRANSMITTERS-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:53:36 | zm167dc@jutal.com | 30-Jun-2026 16:13:30 | Jumpol Sudjitjul | 08-Jul-2026 | 09-Jul-2026 15:26:06 | Payut Phatdamrongdet | 09-Jul-2026 | 20-Jul-2026 08:43:46 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 22-Jul-2026 12:38:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 22-Jul-2026 13:15:25 | 22-Jul-2026 06:20:37 | 0 |  |  | Approver | Locate
AO-000808 | MM-ASK-1A-WP02-INS-DTS-0015 | DATA SHEETS FOR MAGNETIC LEVEL GAUGE AND TRANSMITTERS-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-Jul-2026 09:11:44 | zm167dc@jutal.com | 28-Jul-2026 20:20:52 | Jumpol Sudjitjul | 07-Aug-2026 |  | Payut Phatdamrongdet | 10-Aug-2026 | 31-Jul-2026 21:23:34 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 12-Aug-2026 10:01:36 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 13-Aug-2026 09:09:23 | 13-Aug-2026 02:57:08 | 0 |  |  | Approver | Locate
AO-001115 | MM-ASK-1A-WP02-INS-DTS-0015 | DATA SHEETS FOR MAGNETIC LEVEL GAUGE AND TRANSMITTERS-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 27-Aug-2026 18:01:32 | zm167dc@jutal.com | 28-Aug-2026 13:34:44 | Jumpol Sudjitjul | 07-Sep-2026 |  | Payut Phatdamrongdet | 08-Sep-2026 | 28-Aug-2026 14:58:44 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 30-Aug-2026 22:41:24 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 31-Aug-2026 13:42:49 | 31-Aug-2026 07:04:18 | 0 |  |  | Approver | Locate
AO-000898 | MM-ASK-1A-WP02-INS-DTS-0017 | DATA SHEETS FOR LEVEL SWITCH-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 09:53:07 | zm167dc@jutal.com | 07-Aug-2026 15:24:50 | Jumpol Sudjitjul | 18-Aug-2026 | 18-Aug-2026 22:48:38 | Payut Phatdamrongdet | 19-Aug-2026 | 24-Aug-2026 16:36:27 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 27-Aug-2026 14:32:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 27-Aug-2026 17:32:20 | 27-Aug-2026 11:27:30 | 0 |  |  | Approver | Locate
AO-001198 | MM-ASK-1A-WP02-INS-DTS-0017 | DATA SHEETS FOR LEVEL SWITCH-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 17:24:45 | zm167dc@jutal.com | 05-Sep-2026 18:14:29 | Jumpol Sudjitjul | 15-Sep-2026 |  | Payut Phatdamrongdet | 16-Sep-2026 | 11-Sep-2026 18:13:55 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 22:31:16 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 22:41:06 | 13-Sep-2026 16:00:36 | 0 |  |  | Approver | Locate
AO-000590 | MM-ASK-1A-WP02-INS-DTS-0018 | DATA SHEET FOR GUIDED WAVE RADAR LEVEL TRANSMITTER - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 01-Jul-2026 18:34:46 | zm167dc@jutal.com | 02-Jul-2026 14:24:04 | Jumpol Sudjitjul | 10-Jul-2026 | 15-Jul-2026 17:24:22 | Payut Phatdamrongdet | 13-Jul-2026 | 20-Jul-2026 14:53:51 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 22-Jul-2026 22:39:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 23-Jul-2026 13:09:31 | 23-Jul-2026 06:19:19 | 0 |  |  | Approver | Locate
AO-000842 | MM-ASK-1A-WP02-INS-DTS-0018 | DATA SHEET FOR GUIDED WAVE RADAR LEVEL TRANSMITTER - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 18:14:41 | zm167dc@jutal.com | 31-Jul-2026 21:47:07 | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 00:37:55 | Payut Phatdamrongdet | 13-Aug-2026 | 10-Aug-2026 13:36:36 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:15:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 09:41:30 | 17-Aug-2026 03:18:42 | 0 |  |  | Approver | Locate
AO-001100 | MM-ASK-1A-WP02-INS-DTS-0018 | DATA SHEET FOR GUIDED WAVE RADAR LEVEL TRANSMITTER - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:18:35 | zm167dc@jutal.com | 27-Aug-2026 10:54:48 | Jumpol Sudjitjul | 04-Sep-2026 |  | Payut Phatdamrongdet | 07-Sep-2026 | 27-Aug-2026 13:54:46 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 30-Aug-2026 22:53:42 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 31-Aug-2026 13:43:15 | 31-Aug-2026 07:06:45 | 0 |  |  | Approver | Locate
AO-000780 | MM-ASK-1A-WP02-INS-DTS-0019 | DATA SHEETS FOR DP LEVEL TRANSMITTERS-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:12:02 | zm167dc@jutal.com | 26-Jul-2026 22:48:00 | Jumpol Sudjitjul | 06-Aug-2026 |  | Payut Phatdamrongdet | 07-Aug-2026 | 31-Jul-2026 19:37:22 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:02:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:23:35 | 08-Aug-2026 04:12:22 | 0 |  |  | Approver | Locate
AO-000618 | MM-ASK-1A-WP02-INS-DTS-0020 | DATA SHEETS FOR RESTRICTION ORIFICE- WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:14:24 | zm167dc@jutal.com | 04-Jul-2026 13:56:35 | Jumpol Sudjitjul | 13-Jul-2026 | 17-Jul-2026 10:05:11 | Payut Phatdamrongdet | 14-Jul-2026 | 21-Jul-2026 09:26:33 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:45:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 13:03:25 | 23-Jul-2026 06:27:00 | 0 |  |  | Approver | Locate
AO-001324 | MM-ASK-1A-WP02-INS-DTS-0020 | DATA SHEETS FOR RESTRICTION ORIFICE- WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 19:46:14 | zm167dc@jutal.com | 11-Sep-2026 20:37:39 | Jumpol Sudjitjul | 22-Sep-2026 |  | Payut Phatdamrongdet | 23-Sep-2026 | 18-Sep-2026 08:42:41 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:13:54 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 16:17:28 | 20-Sep-2026 10:10:38 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-INS-DTS-0021 | DATA SHEET FOR FIRE & GAS DETECTORS- WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 12:03:58 | zm167dc@jutal.com | 06-Aug-2026 13:52:22 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:09:00 | Payut Phatdamrongdet | 18-Aug-2026 | 17-Aug-2026 17:19:38 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 20-Aug-2026 23:05:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 21-Aug-2026 09:51:58 | 21-Aug-2026 03:32:14 | 0 |  |  | Approver | Locate
AO-001127 | MM-ASK-1A-WP02-INS-DTS-0021 | DATA SHEET FOR FIRE & GAS DETECTORS- WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 16:48:08 | zm167dc@jutal.com | 28-Aug-2026 17:29:05 | Jumpol Sudjitjul | 08-Sep-2026 |  | Payut Phatdamrongdet | 09-Sep-2026 | 04-Sep-2026 10:49:33 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 06-Sep-2026 23:43:15 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 10:39:18 | 07-Sep-2026 04:43:34 | 0 |  |  | Approver | Locate
AO-001482 | MM-ASK-1A-WP02-INS-DTS-0021 | DATA SHEET FOR FIRE & GAS DETECTORS- WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:50:55 | zm167dc@jutal.com | 18-Sep-2026 17:17:23 | Jumpol Sudjitjul | 29-Sep-2026 |  | Payut Phatdamrongdet | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-WP02-INS-DTS-0022 | DATA SHEETS FOR POSITION LIMIT SWITCHES- WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 05-Aug-2026 18:37:01 | zm167dc@jutal.com | 06-Aug-2026 13:52:39 | Jumpol Sudjitjul | 17-Aug-2026 | 16-Aug-2026 15:41:36 | Payut Phatdamrongdet | 18-Aug-2026 | 24-Aug-2026 09:42:58 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 25-Aug-2026 22:29:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 26-Aug-2026 08:33:01 | 26-Aug-2026 01:53:07 | 0 |  |  | Approver | Locate
AO-001198 | MM-ASK-1A-WP02-INS-DTS-0022 | DATA SHEETS FOR POSITION LIMIT SWITCHES- WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 17:25:13 | zm167dc@jutal.com | 05-Sep-2026 18:15:02 | Jumpol Sudjitjul | 15-Sep-2026 |  | Payut Phatdamrongdet | 16-Sep-2026 | 11-Sep-2026 18:15:38 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 22:34:13 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 22:43:28 | 13-Sep-2026 16:01:52 | 0 |  |  | Approver | Locate
AO-001494 | MM-ASK-1A-WP02-INS-DTS-0022 | DATA SHEETS FOR POSITION LIMIT SWITCHES- WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:16:27 | zm167dc@jutal.com | 20-Sep-2026 14:17:10 | Jumpol Sudjitjul | 28-Sep-2026 |  | Payut Phatdamrongdet | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000584 | MM-ASK-1A-WP02-INS-DTS-0023 | DATA SHEET FOR OIL IN WATER ANALYZER - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 01-Jul-2026 13:54:37 | zm167dc@jutal.com | 01-Jul-2026 14:37:42 | Jumpol Sudjitjul | 09-Jul-2026 | 03-Jul-2026 15:24:30 | Payut Phatdamrongdet | 10-Jul-2026 | 20-Jul-2026 12:11:28 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 22-Jul-2026 22:36:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 23-Jul-2026 13:02:03 | 23-Jul-2026 06:15:06 | 0 |  |  | Approver | Locate
AO-000857 | MM-ASK-1A-WP02-INS-DTS-0023 | DATA SHEET FOR OIL IN WATER ANALYZER - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 17:29:17 | zm167dc@jutal.com | 04-Aug-2026 08:00:48 | Jumpol Sudjitjul | 13-Aug-2026 | 04-Aug-2026 10:31:23 | Payut Phatdamrongdet | 14-Aug-2026 | 10-Aug-2026 13:37:25 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 16-Aug-2026 23:22:16 | APPR | Approved | Jumpol Sudjitjul | 18-Aug-2026 | 17-Aug-2026 09:36:27 | 17-Aug-2026 03:39:28 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WP02-INS-DTS-0023 | DATA SHEET FOR OIL IN WATER ANALYZER - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 15:24:19 | zm167dc@jutal.com | 21-Aug-2026 17:08:45 | Jumpol Sudjitjul | 01-Sep-2026 |  | Payut Phatdamrongdet | 02-Sep-2026 | 26-Aug-2026 11:26:08 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 30-Aug-2026 16:13:22 | APPR | Approved | Jumpol Sudjitjul | 04-Sep-2026 | 30-Aug-2026 16:18:13 | 30-Aug-2026 09:41:07 | 0 |  |  | Approver | Locate
AO-000469 | MM-ASK-1A-WP02-INS-DWG-0002 | CONTROL SYSTEM BLOCK DIAGRAM FOR-WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 15:52:00 | zm167dc@jutal.com | 16-Jun-2026 11:53:16 | Jumpol Sudjitjul | 22-Jun-2026 | 26-Jun-2026 09:01:09 | Payut Phatdamrongdet | 23-Jun-2026 | 29-Jun-2026 09:24:46 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 29-Jun-2026 23:46:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 30-Jun-2026 12:42:30 | 30-Jun-2026 06:48:10 | 0 |  |  | Approver | Locate
AO-000662 | MM-ASK-1A-WP02-INS-DWG-0002 | CONTROL SYSTEM BLOCK DIAGRAM FOR-WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jul-2026 12:15:22 | zm167dc@jutal.com | 09-Jul-2026 13:20:37 | Jumpol Sudjitjul | 17-Jul-2026 | 28-Jul-2026 09:47:27 | Payut Phatdamrongdet | 20-Jul-2026 | 31-Jul-2026 21:42:35 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 01-Aug-2026 20:42:53 | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 02-Aug-2026 21:01:13 | 02-Aug-2026 14:42:14 | 0 |  |  | Approver | Locate
AO-000968 | MM-ASK-1A-WP02-INS-DWG-0002 | CONTROL SYSTEM BLOCK DIAGRAM FOR-WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 14:43:49 | zm167dc@jutal.com | 13-Aug-2026 16:31:33 | Jumpol Sudjitjul | 21-Aug-2026 | 28-Aug-2026 13:15:34 | Payut Phatdamrongdet | 24-Aug-2026 | 01-Sep-2026 11:35:32 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 23:11:53 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 03-Sep-2026 09:29:07 | 03-Sep-2026 03:05:52 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WP02-INS-DWG-0003 | INSTRUMENT CABLE BLOCK DIAGRAM PCS/ESD/FGS-WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 12:06:15 | zm167dc@jutal.com | 12-Jun-2026 12:51:36 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 22-Jun-2026 17:11:21 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:56:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:55:33 | 25-Jun-2026 06:33:11 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-WP02-INS-DWG-0003 | INSTRUMENT CABLE BLOCK DIAGRAM PCS/ESD/FGS-WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 16:53:26 | zm167dc@jutal.com | 10-Jul-2026 17:45:51 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:25:01 | Payut Phatdamrongdet | 22-Jul-2026 | 31-Jul-2026 21:55:23 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 02-Aug-2026 08:10:16 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 02-Aug-2026 21:04:35 | 02-Aug-2026 14:31:26 | 0 |  |  | Approver | Locate
AO-000964 | MM-ASK-1A-WP02-INS-DWG-0003 | INSTRUMENT CABLE BLOCK DIAGRAM PCS/ESD/FGS-WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 10:48:11 | zm167dc@jutal.com | 13-Aug-2026 14:22:59 | Jumpol Sudjitjul | 21-Aug-2026 |  | Payut Phatdamrongdet | 24-Aug-2026 | 26-Aug-2026 08:59:23 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 27-Aug-2026 14:58:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 27-Aug-2026 17:34:42 | 27-Aug-2026 11:35:54 | 0 |  |  | Approver | Locate
AO-001286 | MM-ASK-1A-WP02-INS-DWG-0005 | INSTRUMENT MULTI CABLE TRANSIT SCHEDULE- WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Sep-2026 13:20:04 | zm167dc@jutal.com | 10-Sep-2026 16:22:40 | Jumpol Sudjitjul | 18-Sep-2026 |  | Payut Phatdamrongdet | 21-Sep-2026 | 11-Sep-2026 18:28:39 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 13-Sep-2026 22:52:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 13-Sep-2026 22:54:22 | 13-Sep-2026 17:07:28 | 0 |  |  | Approver | Locate
AO-000623 | MM-ASK-1A-WP02-INS-DWG-0007 | INSTRUMENT HOOK-UP DRAWINGS- WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:14:53 | zm167dc@jutal.com | 03-Jul-2026 18:29:12 | Jumpol Sudjitjul | 14-Jul-2026 | 14-Jul-2026 10:44:47 | Payut Phatdamrongdet | 15-Jul-2026 | 30-Jul-2026 15:21:14 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 30-Jul-2026 17:35:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 30-Jul-2026 19:07:15 | 30-Jul-2026 12:39:01 | 0 |  |  | Approver | Locate
AO-000621 | MM-ASK-1A-WP02-INS-LAY-0001 | INSTRUMENT CABLE TRAY LAYOUT- WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:15:19 | zm167dc@jutal.com | 03-Jul-2026 18:26:53 | Jumpol Sudjitjul | 14-Jul-2026 | 14-Jul-2026 10:40:49 | Payut Phatdamrongdet | 15-Jul-2026 | 27-Jul-2026 11:20:54 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 28-Jul-2026 22:18:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 30-Jul-2026 08:53:08 | 30-Jul-2026 02:34:47 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-INS-LAY-0002 | INSTRUMENT CABLE ROUTING PLAN AND JUNCTION BOXES LAYOUT- WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:56:29 | zm167dc@jutal.com | 26-Jul-2026 22:50:10 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:38:43 | Payut Phatdamrongdet | 07-Aug-2026 | 10-Aug-2026 14:51:35 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:00:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:13:07 | 13-Aug-2026 04:10:43 | 0 |  |  | Approver | Locate
AO-000616 | MM-ASK-1A-WP02-INS-LAY-0003 | INSTRUMENT TUBING TRAY LAYOUT - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:15:46 | zm167dc@jutal.com | 03-Jul-2026 18:27:07 | Jumpol Sudjitjul | 14-Jul-2026 | 14-Jul-2026 10:43:42 | Payut Phatdamrongdet | 15-Jul-2026 | 27-Jul-2026 11:21:36 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 28-Jul-2026 22:25:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 30-Jul-2026 09:14:16 | 30-Jul-2026 02:38:00 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-WP02-INS-LAY-0004 | INSTRUMENT LOCATION PLAN- WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:09:11 | zm167dc@jutal.com | 13-Jun-2026 08:19:27 | Jumpol Sudjitjul | 22-Jun-2026 |  | Payut Phatdamrongdet | 23-Jun-2026 | 22-Jun-2026 16:05:46 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:42:26 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 12:47:18 | 25-Jun-2026 06:24:47 | 0 |  |  | Approver | Locate
AO-001331 | MM-ASK-1A-WP02-INS-LAY-0004 | INSTRUMENT LOCATION PLAN- WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 19:46:44 | zm167dc@jutal.com | 11-Sep-2026 20:38:02 | Jumpol Sudjitjul | 22-Sep-2026 |  | Payut Phatdamrongdet | 23-Sep-2026 | 18-Sep-2026 11:08:48 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 20-Sep-2026 00:11:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 16:10:39 | 20-Sep-2026 10:08:11 | 0 |  |  | Approver | Locate
AO-000734 | MM-ASK-1A-WP02-INS-LAY-0005 | FUSIBLE PLUG AND F&G LAYOUT- WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 11:15:56 | zm167dc@jutal.com | 20-Jul-2026 12:52:19 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:34:10 | Payut Phatdamrongdet | 31-Jul-2026 | 10-Aug-2026 14:05:33 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 12-Aug-2026 00:26:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 13-Aug-2026 10:22:32 | 13-Aug-2026 04:06:00 | 0 |  |  | Approver | Locate
AO-000299 | MM-ASK-1A-WP02-INS-LIS-0002 | INSTRUMENT INDEX-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:37:11 | zm167dc@jutal.com | 21-May-2026 13:50:21 | Jumpol Sudjitjul | 29-May-2026 | 27-May-2026 11:04:40 | Payut Phatdamrongdet | 02-Jun-2026 | 05-Jun-2026 10:08:08 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 10-Jun-2026 21:02:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 11-Jun-2026 09:53:31 | 11-Jun-2026 10:36:47 | 0 |  |  | Approver | Locate
AO-000519 | MM-ASK-1A-WP02-INS-LIS-0002 | INSTRUMENT INDEX-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 19-Jun-2026 17:25:58 | zm167dc@jutal.com | 19-Jun-2026 17:47:01 | Jumpol Sudjitjul | 30-Jun-2026 | 29-Jun-2026 13:31:11 | Payut Phatdamrongdet | 01-Jul-2026 | 01-Jul-2026 22:11:09 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:45:53 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 16:03:09 | 03-Jul-2026 09:52:58 | 0 |  |  | Approver | Locate
AO-000900 | MM-ASK-1A-WP02-INS-LIS-0002 | INSTRUMENT INDEX-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:53:34 | zm167dc@jutal.com | 07-Aug-2026 10:47:33 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:12:42 | Payut Phatdamrongdet | 19-Aug-2026 | 24-Aug-2026 14:59:14 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 27-Aug-2026 14:24:08 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 27-Aug-2026 14:42:32 | 27-Aug-2026 08:56:11 | 0 |  |  | Approver | Locate
AO-000317 | MM-ASK-1A-WP02-INS-LIS-0003 | PLC INPUT/OUTPUT LIST-WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:42:26 | zm167dc@jutal.com | 23-May-2026 09:11:20 | Jumpol Sudjitjul | 02-Jun-2026 | 02-Jun-2026 16:08:32 | Payut Phatdamrongdet | 04-Jun-2026 | 05-Jun-2026 10:26:05 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:08:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:54:53 | 11-Jun-2026 10:26:14 | 0 |  |  | Approver | Locate
AO-000519 | MM-ASK-1A-WP02-INS-LIS-0003 | PLC INPUT/OUTPUT LIST-WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 19-Jun-2026 17:26:27 | zm167dc@jutal.com | 19-Jun-2026 17:47:14 | Jumpol Sudjitjul | 30-Jun-2026 | 29-Jun-2026 13:48:54 | Payut Phatdamrongdet | 01-Jul-2026 | 01-Jul-2026 22:12:46 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 02-Jul-2026 00:40:55 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 02-Jul-2026 13:00:46 | 02-Jul-2026 06:23:49 | 0 |  |  | Approver | Locate
AO-000900 | MM-ASK-1A-WP02-INS-LIS-0003 | PLC INPUT/OUTPUT LIST-WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:54:05 | zm167dc@jutal.com | 07-Aug-2026 10:47:52 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:12:59 | Payut Phatdamrongdet | 19-Aug-2026 | 24-Aug-2026 15:01:17 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 27-Aug-2026 14:25:12 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 27-Aug-2026 14:46:46 | 27-Aug-2026 09:00:11 | 0 |  |  | Approver | Locate
AO-001068 | MM-ASK-1A-WP02-INS-LIS-0004 | INSTRUMENT CABLE SCHEDULE- WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 18:40:34 | zm167dc@jutal.com | 24-Aug-2026 18:34:39 | Jumpol Sudjitjul | 02-Sep-2026 |  | Payut Phatdamrongdet | 03-Sep-2026 | 26-Aug-2026 12:54:32 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 22:55:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 13:43:46 | 31-Aug-2026 07:11:55 | 0 |  |  | Approver | Locate
AO-000796 | MM-ASK-1A-WP02-INS-LIS-0005 | INSTRUMENT TUBING SCHEDULE- WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 26-Jul-2026 23:11:05 | zm167dc@jutal.com | 27-Jul-2026 15:40:19 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:57:04 | Payut Phatdamrongdet | 07-Aug-2026 | 17-Aug-2026 09:44:23 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 17-Aug-2026 23:01:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 18-Aug-2026 08:13:01 | 18-Aug-2026 01:26:51 | 0 |  |  | Approver | Locate
AO-001100 | MM-ASK-1A-WP02-INS-LIS-0006 | INSTRUMENT EQUIPMENT AND EXPLOSION PROOF EQUIPMENT SCHEDULE- WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 26-Aug-2026 19:19:00 | zm167dc@jutal.com | 27-Aug-2026 11:34:04 | Jumpol Sudjitjul | 04-Sep-2026 |  | Payut Phatdamrongdet | 07-Sep-2026 | 27-Aug-2026 14:16:18 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 30-Aug-2026 22:57:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 31-Aug-2026 13:43:36 | 31-Aug-2026 07:08:07 | 0 |  |  | Approver | Locate
AO-000532 | MM-ASK-1A-WP02-INS-WIR-0001 | INSTRUMENT WIRING DIAGRAMS - WP02 (PCS) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-Jun-2026 16:40:50 | zm167dc@jutal.com | 24-Jun-2026 11:23:51 | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 14:29:24 | Payut Phatdamrongdet | 03-Jul-2026 | 07-Jul-2026 08:04:11 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 08-Jul-2026 00:41:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 08-Jul-2026 09:16:23 | 08-Jul-2026 02:53:55 | 0 |  |  | Approver | Locate
AO-000800 | MM-ASK-1A-WP02-INS-WIR-0001 | INSTRUMENT WIRING DIAGRAMS - WP02 (PCS) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 26-Jul-2026 22:34:43 | zm167dc@jutal.com | 27-Jul-2026 15:41:25 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:57:50 | Payut Phatdamrongdet | 07-Aug-2026 | 17-Aug-2026 10:20:02 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 20-Aug-2026 16:29:13 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 20-Aug-2026 19:50:19 | 20-Aug-2026 13:16:07 | 0 |  |  | Approver | Locate
AO-001100 | MM-ASK-1A-WP02-INS-WIR-0001 | INSTRUMENT WIRING DIAGRAMS - WP02 (PCS) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:19:31 | zm167dc@jutal.com | 27-Aug-2026 11:37:53 | Jumpol Sudjitjul | 04-Sep-2026 |  | Payut Phatdamrongdet | 07-Sep-2026 | 27-Aug-2026 14:04:09 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 30-Aug-2026 22:59:51 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 31-Aug-2026 13:43:06 | 31-Aug-2026 07:05:30 | 0 |  |  | Approver | Locate
AO-000547 | MM-ASK-1A-WP02-INS-WIR-0002 | INSTRUMENT WIRING DIAGRAMS - WP02 (SIS/FGS SYSTEM) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 25-Jun-2026 14:23:34 | zm167dc@jutal.com | 25-Jun-2026 15:23:58 | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 14:47:54 | Payut Phatdamrongdet | 06-Jul-2026 | 27-Jul-2026 11:14:28 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 28-Jul-2026 21:28:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jul-2026 | 30-Jul-2026 09:15:03 | 30-Jul-2026 02:39:17 | 0 |  |  | Approver | Locate
AO-000900 | MM-ASK-1A-WP02-INS-WIR-0002 | INSTRUMENT WIRING DIAGRAMS - WP02 (SIS/FGS SYSTEM) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:54:36 | zm167dc@jutal.com | 07-Aug-2026 10:21:02 | Jumpol Sudjitjul | 18-Aug-2026 | 07-Aug-2026 13:11:37 | Payut Phatdamrongdet | 19-Aug-2026 | 24-Aug-2026 14:57:04 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 25-Aug-2026 22:47:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 26-Aug-2026 08:36:50 | 26-Aug-2026 02:03:13 | 0 |  |  | Approver | Locate
AO-001151 | MM-ASK-1A-WP02-INS-WIR-0002 | INSTRUMENT WIRING DIAGRAMS - WP02 (SIS/FGS SYSTEM) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 19:22:50 | zm167dc@jutal.com | 02-Sep-2026 22:24:51 | Soontaree Simpitak | 11-Sep-2026 |  | Payut Phatdamrongdet | 14-Sep-2026 | 04-Sep-2026 10:54:54 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 06-Sep-2026 23:44:16 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 07-Sep-2026 10:40:02 | 07-Sep-2026 05:08:47 | 0 |  |  | Approver | Locate
AO-000125 | MM-ASK-1A-WP02-MEC-DTS-0001 | WP02 MECHANICAL DATASHEET FOR TEST SEPARATOR (V-01001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 16:26:56 | zm167dc@jutal.com | 05-May-2026 16:39:25 | Jumpol Sudjitjul | 13-May-2026 | 08-May-2026 11:22:14 | Thanapat Sombatwattana | 14-May-2026 | 18-May-2026 13:17:58 | Pornlert Wanaphattharaphan | 15-May-2026 | 19-May-2026 22:52:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 08:48:20 | 20-May-2026 09:29:07 | 0 |  |  | Approver | Locate
AO-000420 | MM-ASK-1A-WP02-MEC-DTS-0001 | WP02 MECHANICAL DATASHEET FOR TEST SEPARATOR (V-01001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 17:56:27 | zm167dc@jutal.com | 05-Jun-2026 19:53:37 | Jumpol Sudjitjul | 16-Jun-2026 | 16-Jun-2026 09:19:39 | Thanapat Sombatwattana | 17-Jun-2026 | 17-Jun-2026 17:03:33 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 21:02:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 11:31:12 | 22-Jun-2026 04:56:37 | 0 |  |  | Approver | Locate
AO-000670 | MM-ASK-1A-WP02-MEC-DTS-0001 | WP02 MECHANICAL DATASHEET FOR TEST SEPARATOR (V-01001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 14:44:27 | zm167dc@jutal.com | 10-Jul-2026 16:30:06 | Jumpol Sudjitjul | 20-Jul-2026 | 14-Jul-2026 13:43:30 | Thanapat Sombatwattana | 21-Jul-2026 | 17-Jul-2026 13:46:06 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 19-Jul-2026 17:12:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:27:49 | 20-Jul-2026 03:50:11 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-MEC-DTS-0001 | WP02 MECHANICAL DATASHEET FOR TEST SEPARATOR (V-01001) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 15:00:39 | zm167dc@jutal.com | 26-Jul-2026 23:09:41 | Jumpol Sudjitjul | 06-Aug-2026 | 05-Aug-2026 23:26:11 | Thanapat Sombatwattana | 07-Aug-2026 | 06-Aug-2026 16:29:04 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 11:03:48 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:15:09 | 11-Aug-2026 01:29:30 | 0 |  |  | Approver | Locate
AO-000126 | MM-ASK-1A-WP02-MEC-DTS-0002 | WP02 MECHANICAL DATASHEET FOR PRODUCTION SEPARATOR (V-10001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 16:27:21 | zm167dc@jutal.com | 05-May-2026 16:38:55 | Jumpol Sudjitjul | 13-May-2026 | 08-May-2026 11:23:11 | Thanapat Sombatwattana | 14-May-2026 | 19-May-2026 10:44:05 | Pornlert Wanaphattharaphan | 15-May-2026 | 19-May-2026 23:08:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 08:32:15 | 20-May-2026 08:57:03 | 0 |  |  | Approver | Locate
AO-000432 | MM-ASK-1A-WP02-MEC-DTS-0002 | WP02 MECHANICAL DATASHEET FOR PRODUCTION SEPARATOR (V-10001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 09-Jun-2026 11:14:32 | zm167dc@jutal.com | 12-Jun-2026 11:30:02 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 09:42:15 | Thanapat Sombatwattana | 23-Jun-2026 | 25-Jun-2026 13:49:17 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 00:20:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 28-Jun-2026 08:38:44 | 28-Jun-2026 02:13:38 | 0 |  |  | Approver | Locate
AO-000693 | MM-ASK-1A-WP02-MEC-DTS-0002 | WP02 MECHANICAL DATASHEET FOR PRODUCTION SEPARATOR (V-10001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 14-Jul-2026 08:38:11 | zm167dc@jutal.com | 14-Jul-2026 08:58:37 | Jumpol Sudjitjul | 22-Jul-2026 | 14-Jul-2026 16:22:28 | Thanapat Sombatwattana | 23-Jul-2026 | 17-Jul-2026 14:38:03 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 19-Jul-2026 17:13:55 | APPR | Approved | Jumpol Sudjitjul | 27-Jul-2026 | 20-Jul-2026 09:25:34 | 20-Jul-2026 03:46:52 | 0 |  |  | Approver | Locate
AO-000266 | MM-ASK-1A-WP02-MEC-DTS-0004 | WP02 MECHANICAL DATASHEET FOR DE-MULSIFIER / WATER CLARIFIER STORAGE TANK (T-09003) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 14:15:32 | zm167dc@jutal.com | 15-May-2026 17:59:26 | Jumpol Sudjitjul | 26-May-2026 | 25-May-2026 17:32:31 | Thanapat Sombatwattana | 27-May-2026 | 29-May-2026 14:34:44 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 01:15:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:47:17 | 10-Jun-2026 12:19:36 | 0 |  |  | Approver | Locate
AO-000501 | MM-ASK-1A-WP02-MEC-DTS-0004 | WP02 MECHANICAL DATASHEET FOR DE-MULSIFIER / WATER CLARIFIER STORAGE TANK (T-09003) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 18-Jun-2026 14:04:50 | zm167dc@jutal.com | 18-Jun-2026 14:23:30 | Jumpol Sudjitjul | 26-Jun-2026 | 26-Jun-2026 10:14:02 | Thanapat Sombatwattana | 29-Jun-2026 | 29-Jun-2026 22:39:55 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 30-Jun-2026 23:24:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 01-Jul-2026 08:38:46 | 01-Jul-2026 02:17:50 | 0 |  |  | Approver | Locate
AO-000723 | MM-ASK-1A-WP02-MEC-DTS-0004 | WP02 MECHANICAL DATASHEET FOR DE-MULSIFIER / WATER CLARIFIER STORAGE TANK (T-09003) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:04:07 | zm167dc@jutal.com | 20-Jul-2026 11:36:34 | Jumpol Sudjitjul | 30-Jul-2026 | 21-Jul-2026 08:40:25 | Thanapat Sombatwattana | 31-Jul-2026 | 22-Jul-2026 17:35:44 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 18:52:32 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 13:52:56 | 27-Jul-2026 07:10:08 | 0 |  |  | Approver | Locate
AO-000267 | MM-ASK-1A-WP02-MEC-DTS-0005 | WP02 MECHANICAL DATASHEET FOR DE-MULSIFIER / WATER CLARIFIER STORAGE TOTE TANK (T-09013) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 13:27:50 | zm167dc@jutal.com | 15-May-2026 18:00:02 | Jumpol Sudjitjul | 26-May-2026 | 25-May-2026 17:34:28 | Thanapat Sombatwattana | 27-May-2026 | 29-May-2026 14:35:01 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 01:17:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:46:50 | 10-Jun-2026 13:52:55 | 0 |  |  | Approver | Locate
AO-000464 | MM-ASK-1A-WP02-MEC-DTS-0005 | WP02 MECHANICAL DATASHEET FOR DE-MULSIFIER / WATER CLARIFIER STORAGE TOTE TANK (T-09013) |  | X | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Latest | VOID | Withdrawn or Superseded |  | 12-Jun-2026 12:29:05 | zm167dc@jutal.com | 12-Jun-2026 12:55:36 | Jumpol Sudjitjul |  | 12-Jun-2026 15:44:43 | Thanapat Sombatwattana |  | 18-Jun-2026 23:34:56 | Pornlert Wanaphattharaphan |  |  | APPR | Approved |  |  |  |  | 0 |  |  | For Info | Locate
AO-000162 | MM-ASK-1A-WP02-MEC-DTS-0006 | WP02 MECHANICAL DATASHEET FOR CHEMICAL INJECTION PUMPS PACKAGE (SK-09001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:35:13 | zm167dc@jutal.com | 08-May-2026 13:54:52 | Jumpol Sudjitjul | 18-May-2026 | 18-May-2026 21:46:24 | Thanapat Sombatwattana | 19-May-2026 | 20-May-2026 09:01:57 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 16:17:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 19:59:27 | 24-May-2026 20:43:39 | 0 |  |  | Approver | Locate
AO-000446 | MM-ASK-1A-WP02-MEC-DTS-0006 | WP02 MECHANICAL DATASHEET FOR CHEMICAL INJECTION PUMPS PACKAGE (SK-09001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 12:36:47 | zm167dc@jutal.com | 11-Jun-2026 12:50:40 | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 11:44:51 | Thanapat Sombatwattana | 22-Jun-2026 | 23-Jun-2026 15:47:33 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 24-Jun-2026 22:24:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 25-Jun-2026 12:48:22 | 25-Jun-2026 06:27:57 | 0 |  |  | Approver | Locate
AO-000662 | MM-ASK-1A-WP02-MEC-DTS-0006 | WP02 MECHANICAL DATASHEET FOR CHEMICAL INJECTION PUMPS PACKAGE (SK-09001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 09-Jul-2026 12:15:54 | zm167dc@jutal.com | 09-Jul-2026 13:08:46 | Jumpol Sudjitjul | 17-Jul-2026 | 16-Jul-2026 13:50:17 | Thanapat Sombatwattana | 20-Jul-2026 | 16-Jul-2026 14:59:18 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 17-Jul-2026 00:13:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 17-Jul-2026 09:40:58 | 17-Jul-2026 03:08:09 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-MEC-DTS-0006 | WP02 MECHANICAL DATASHEET FOR CHEMICAL INJECTION PUMPS PACKAGE (SK-09001) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 14:09:29 | zm167dc@jutal.com | 24-Jul-2026 14:51:56 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:23:59 | Thanapat Sombatwattana | 06-Aug-2026 | 06-Aug-2026 16:20:14 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 05:41:38 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:14:32 | 07-Aug-2026 05:22:23 | 0 |  |  | Approver | Locate
AO-000168 | MM-ASK-1A-WP02-MEC-DTS-0008 | WP02 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP VESSEL (V-05001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 15:43:51 | zm167dc@jutal.com | 08-May-2026 17:16:53 | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 15:39:30 | Thanapat Sombatwattana | 20-May-2026 | 20-May-2026 11:23:23 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 20:04:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 28-May-2026 09:14:17 | 28-May-2026 09:27:16 | 0 |  |  | Approver | Locate
AO-000442 | MM-ASK-1A-WP02-MEC-DTS-0008 | WP02 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP VESSEL (V-05001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 18:06:55 | zm167dc@jutal.com | 11-Jun-2026 12:52:13 | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 16:06:09 | Thanapat Sombatwattana | 22-Jun-2026 | 23-Jun-2026 23:27:19 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 24-Jun-2026 22:25:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 25-Jun-2026 12:49:04 | 25-Jun-2026 06:38:36 | 0 |  |  | Approver | Locate
AO-000693 | MM-ASK-1A-WP02-MEC-DTS-0008 | WP02 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP VESSEL (V-05001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 14-Jul-2026 08:38:45 | zm167dc@jutal.com | 14-Jul-2026 08:59:09 | Jumpol Sudjitjul | 22-Jul-2026 | 17-Jul-2026 09:35:00 | Thanapat Sombatwattana | 23-Jul-2026 | 17-Jul-2026 16:13:00 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 19-Jul-2026 17:13:35 | APPR | Approved | Jumpol Sudjitjul | 27-Jul-2026 | 20-Jul-2026 09:25:12 | 20-Jul-2026 03:45:44 | 0 |  |  | Approver | Locate
AO-000188 | MM-ASK-1A-WP02-MEC-DTS-0009 | WP02 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP (SK-05001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 10-May-2026 23:37:19 | zm167dc@jutal.com | 11-May-2026 09:19:16 | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 15:40:45 | Thanapat Sombatwattana | 20-May-2026 | 25-May-2026 01:24:53 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 19:32:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 19:34:17 | 29-May-2026 19:58:15 | 0 |  |  | Approver | Locate
AO-000447 | MM-ASK-1A-WP02-MEC-DTS-0009 | WP02 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP (SK-05001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 12:37:13 | zm167dc@jutal.com | 11-Jun-2026 12:45:25 | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 12:49:12 | Thanapat Sombatwattana | 22-Jun-2026 | 23-Jun-2026 14:20:33 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 24-Jun-2026 22:24:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 25-Jun-2026 12:58:29 | 25-Jun-2026 06:35:05 | 0 |  |  | Approver | Locate
AO-000714 | MM-ASK-1A-WP02-MEC-DTS-0009 | WP02 MECHANICAL DATASHEET FOR CLOSED DRAIN SUMP PUMP AND RECOVERY WATER PUMP (SK-05001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 11:59:13 | zm167dc@jutal.com | 17-Jul-2026 12:54:08 | Jumpol Sudjitjul | 27-Jul-2026 | 18-Jul-2026 08:01:43 | Thanapat Sombatwattana | 30-Jul-2026 | 22-Jul-2026 17:27:48 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:13:17 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 14:11:53 | 27-Jul-2026 08:09:46 | 0 |  |  | Approver | Locate
AO-000169 | MM-ASK-1A-WP02-MEC-DTS-0011 | WP02 MECHANICAL DATASHEET FOR SKIM TANK VESSEL (V-10002) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 15:44:17 | zm167dc@jutal.com | 08-May-2026 17:20:36 | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 15:43:06 | Thanapat Sombatwattana | 20-May-2026 | 20-May-2026 11:30:23 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 20:07:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 28-May-2026 09:16:14 | 28-May-2026 09:28:17 | 0 |  |  | Approver | Locate
AO-000443 | MM-ASK-1A-WP02-MEC-DTS-0011 | WP02 MECHANICAL DATASHEET FOR SKIM TANK VESSEL (V-10002) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 18:07:22 | zm167dc@jutal.com | 11-Jun-2026 12:52:31 | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 09:41:14 | Thanapat Sombatwattana | 22-Jun-2026 | 24-Jun-2026 00:02:58 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 24-Jun-2026 22:26:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 25-Jun-2026 13:03:34 | 25-Jun-2026 06:49:01 | 0 |  |  | Approver | Locate
AO-000670 | MM-ASK-1A-WP02-MEC-DTS-0011 | WP02 MECHANICAL DATASHEET FOR SKIM TANK VESSEL (V-10002) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 14:45:11 | zm167dc@jutal.com | 10-Jul-2026 16:30:24 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 09:31:05 | Thanapat Sombatwattana | 21-Jul-2026 | 17-Jul-2026 13:49:04 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 19-Jul-2026 17:12:10 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:24:51 | 20-Jul-2026 03:44:35 | 0 |  |  | Approver | Locate
AO-000079 | MM-ASK-1A-WP02-MEC-DTS-0012 | WPA02 MECHANICAL DATASHEET FOR DE-OILER HYDROCYCLONE PACKAGE (SK-11001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:29:16 | zm167dc@jutal.com | 27-Apr-2026 13:59:58 | Jumpol Sudjitjul | 07-May-2026 | 07-May-2026 20:47:15 | Thanapat Sombatwattana | 08-May-2026 | 08-May-2026 16:09:47 | Pornlert Wanaphattharaphan | 11-May-2026 | 11-May-2026 23:49:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 12-May-2026 08:59:31 | 12-May-2026 09:18:32 | 0 |  |  | Approver | Locate
AO-000370 | MM-ASK-1A-WP02-MEC-DTS-0012 | WPA02 MECHANICAL DATASHEET FOR DE-OILER HYDROCYCLONE PACKAGE (SK-11001) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 17:25:03 | zm167dc@jutal.com | 29-May-2026 09:51:43 | Jumpol Sudjitjul | 10-Jun-2026 | 10-Jun-2026 15:34:47 | Thanapat Sombatwattana | 11-Jun-2026 | 15-Jun-2026 23:36:42 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 18-Jun-2026 09:41:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 18-Jun-2026 09:51:18 | 18-Jun-2026 03:47:38 | 0 |  |  | Approver | Locate
AO-000628 | MM-ASK-1A-WP02-MEC-DTS-0012 | WPA02 MECHANICAL DATASHEET FOR DE-OILER HYDROCYCLONE PACKAGE (SK-11001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 19:10:35 | zm167dc@jutal.com | 04-Jul-2026 13:59:04 | Jumpol Sudjitjul | 13-Jul-2026 | 12-Jul-2026 17:37:31 | Thanapat Sombatwattana | 14-Jul-2026 | 13-Jul-2026 10:03:38 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:25:47 | NA | Not Approved | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:04:26 | 15-Jul-2026 02:33:44 | 0 |  |  | Approver | Locate
AO-000746 | MM-ASK-1A-WP02-MEC-DTS-0012 | WPA02 MECHANICAL DATASHEET FOR DE-OILER HYDROCYCLONE PACKAGE (SK-11001) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 13:53:30 | zm167dc@jutal.com | 21-Jul-2026 14:29:17 | Jumpol Sudjitjul | 31-Jul-2026 | 21-Jul-2026 16:32:58 | Thanapat Sombatwattana | 03-Aug-2026 | 22-Jul-2026 17:48:27 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 29-Jul-2026 08:58:56 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 30-Jul-2026 09:16:08 | 30-Jul-2026 03:09:24 | 0 |  |  | Approver | Locate
AO-000055 | MM-ASK-1A-WP02-MEC-DTS-0013 | WP02 MECHANICAL DATASHEET FOR DEGASSER DRUM-WITH PROVISION TO UPGRADE TO IGF (V-11003) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 23-Apr-2026 18:19:46 | zm167dc@jutal.com | 24-Apr-2026 15:35:11 | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 21:42:58 | Thanapat Sombatwattana | 07-May-2026 | 08-May-2026 15:26:47 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:29:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:04:36 | 09-May-2026 08:56:00 | 0 |  |  | Approver | Locate
AO-000320 | MM-ASK-1A-WP02-MEC-DTS-0013 | WP02 MECHANICAL DATASHEET FOR DEGASSER DRUM-WITH PROVISION TO UPGRADE TO IGF (V-11003) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval | 22-May-2026 | 23-May-2026 08:46:19 | zm167dc@jutal.com | 23-May-2026 09:22:41 | Jumpol Sudjitjul | 02-Jun-2026 | 03-Jun-2026 09:28:19 | Thanapat Sombatwattana | 04-Jun-2026 | 09-Jun-2026 22:11:25 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:18:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:56:38 | 11-Jun-2026 10:27:25 | 0 |  |  | Approver | Locate
AO-000503 | MM-ASK-1A-WP02-MEC-DTS-0013 | WP02 MECHANICAL DATASHEET FOR DEGASSER DRUM-WITH PROVISION TO UPGRADE TO IGF (V-11003) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 18-Jun-2026 16:52:12 | zm167dc@jutal.com | 18-Jun-2026 17:59:40 | Jumpol Sudjitjul | 29-Jun-2026 | 23-Jun-2026 10:13:58 | Thanapat Sombatwattana | 30-Jun-2026 | 29-Jun-2026 13:17:35 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 01-Jul-2026 23:28:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 13:01:25 | 02-Jul-2026 06:13:36 | 0 |  |  | Approver | Locate
AO-000695 | MM-ASK-1A-WP02-MEC-DTS-0013 | WP02 MECHANICAL DATASHEET FOR DEGASSER DRUM-WITH PROVISION TO UPGRADE TO IGF (V-11003) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 14-Jul-2026 08:39:19 | zm167dc@jutal.com | 14-Jul-2026 08:59:37 | Jumpol Sudjitjul | 22-Jul-2026 | 17-Jul-2026 09:45:59 | Thanapat Sombatwattana | 23-Jul-2026 | 20-Jul-2026 10:05:54 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 26-Jul-2026 03:24:11 | APPR | Approved | Jumpol Sudjitjul | 27-Jul-2026 | 27-Jul-2026 14:18:21 | 27-Jul-2026 09:04:29 | 0 |  |  | Approver | Locate
AO-000189 | MM-ASK-1A-WP02-MEC-DTS-0014 | WP02 MECHANICAL DATASHEET FOR OPEN DRAIN CAISSON PUMP PACKAGE (SK-05003) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 10-May-2026 23:37:41 | zm167dc@jutal.com | 11-May-2026 09:19:38 | Jumpol Sudjitjul | 19-May-2026 | 21-May-2026 13:51:08 | Thanapat Sombatwattana | 20-May-2026 | 25-May-2026 01:26:48 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 19:58:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 16:29:06 | 31-May-2026 16:46:38 | 0 |  |  | Approver | Locate
AO-000459 | MM-ASK-1A-WP02-MEC-DTS-0014 | WP02 MECHANICAL DATASHEET FOR OPEN DRAIN CAISSON PUMP PACKAGE (SK-05003) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 09:59:17 | zm167dc@jutal.com | 12-Jun-2026 12:56:51 | Jumpol Sudjitjul | 22-Jun-2026 | 24-Jun-2026 18:14:43 | Thanapat Sombatwattana | 23-Jun-2026 | 25-Jun-2026 14:35:57 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 09:10:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 28-Jun-2026 09:26:53 | 28-Jun-2026 02:41:26 | 0 |  |  | Approver | Locate
AO-000636 | MM-ASK-1A-WP02-MEC-DTS-0014 | WP02 MECHANICAL DATASHEET FOR OPEN DRAIN CAISSON PUMP PACKAGE (SK-05003) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Jul-2026 00:12:23 | zm167dc@jutal.com | 07-Jul-2026 09:59:19 | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 21:53:34 | Thanapat Sombatwattana | 16-Jul-2026 | 16-Jul-2026 14:37:13 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 17-Jul-2026 00:08:10 | APPR | Approved | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 09:41:45 | 17-Jul-2026 03:22:49 | 0 |  |  | Approver | Locate
AO-000954 | MM-ASK-1A-WP02-MEC-DTS-0015 | WP02 MECHANICAL DATASHEET FOR BIOCIDE INJECTION PUMPS PACKAGE (SK-09002) (PROVISION FOR FUTURE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-Aug-2026 17:31:11 | zm167dc@jutal.com | 11-Aug-2026 17:41:05 | Jumpol Sudjitjul | 21-Aug-2026 | 25-Aug-2026 13:33:44 | Thanapat Sombatwattana | 24-Aug-2026 | 28-Aug-2026 15:56:03 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 29-Aug-2026 17:35:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 30-Aug-2026 16:02:14 | 30-Aug-2026 09:47:12 | 0 |  |  | Approver | Locate
AO-001323 | MM-ASK-1A-WP02-MEC-DTS-0015 | WP02 MECHANICAL DATASHEET FOR BIOCIDE INJECTION PUMPS PACKAGE (SK-09002) (PROVISION FOR FUTURE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:47:56 | zm167dc@jutal.com | 11-Sep-2026 20:39:22 | Jumpol Sudjitjul | 22-Sep-2026 | 20-Sep-2026 10:40:01 | Thanapat Sombatwattana | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000232 | MM-ASK-1A-WP02-MEC-LIS-0001 | WP02 MECHANICAL EQUIPMENT LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 16:14:41 | zm167dc@jutal.com | 14-May-2026 16:25:43 | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 09:29:29 | Thanapat Sombatwattana | 25-May-2026 | 27-May-2026 06:42:44 | Pornlert Wanaphattharaphan | 26-May-2026 | 01-Jun-2026 01:41:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-May-2026 | 01-Jun-2026 09:24:17 | 01-Jun-2026 03:03:37 | 0 |  |  | Approver | Locate
AO-000718 | MM-ASK-1A-WP02-MEC-LIS-0001 | WP02 MECHANICAL EQUIPMENT LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:44:29 | zm167dc@jutal.com | 17-Jul-2026 22:09:58 | Jumpol Sudjitjul | 30-Jul-2026 | 30-Jul-2026 07:58:24 | Thanapat Sombatwattana | 31-Jul-2026 | 05-Aug-2026 17:11:31 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 05-Aug-2026 20:59:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 06-Aug-2026 08:58:28 | 06-Aug-2026 03:03:02 | 0 |  |  | Approver | Locate
AO-001072 | MM-ASK-1A-WP02-MEC-LIS-0001 | WP02 MECHANICAL EQUIPMENT LIST |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:42:21 | zm167dc@jutal.com | 24-Aug-2026 18:36:55 | Jumpol Sudjitjul | 02-Sep-2026 | 07-Sep-2026 16:23:35 | Thanapat Sombatwattana | 03-Sep-2026 | 07-Sep-2026 16:37:00 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 23:43:53 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 08-Sep-2026 13:15:16 | 08-Sep-2026 06:47:55 | 0 |  |  | Approver | Locate
AO-000080 | MM-ASK-1A-WP02-MEC-MR-0001 | MATERIAL REQUISITION FOR DE-OILER HYDROCYCLONE PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:29:45 | zm167dc@jutal.com | 27-Apr-2026 13:56:45 | Jumpol Sudjitjul | 07-May-2026 | 01-May-2026 12:10:03 | Thanapat Sombatwattana | 08-May-2026 | 08-May-2026 15:02:30 | Pornlert Wanaphattharaphan | 11-May-2026 | 11-May-2026 22:50:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 12-May-2026 09:08:17 | 12-May-2026 09:37:56 | 0 |  |  | Approver | Locate
AO-000454 | MM-ASK-1A-WP02-MEC-MR-0001 | MATERIAL REQUISITION FOR DE-OILER HYDROCYCLONE PACKAGE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 18:10:22 | zm167dc@jutal.com | 12-Jun-2026 09:18:00 | Jumpol Sudjitjul | 22-Jun-2026 | 21-Jun-2026 17:04:08 | Thanapat Sombatwattana | 23-Jun-2026 | 25-Jun-2026 13:43:29 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 27-Jun-2026 23:57:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 28-Jun-2026 08:39:13 | 28-Jun-2026 02:14:54 | 0 |  |  | Approver | Locate
AO-000595 | MM-ASK-1A-WP02-MEC-MR-0001 | MATERIAL REQUISITION FOR DE-OILER HYDROCYCLONE PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 02-Jul-2026 12:04:23 | zm167dc@jutal.com | 02-Jul-2026 13:20:54 | Jumpol Sudjitjul | 10-Jul-2026 | 07-Jul-2026 09:32:26 | Thanapat Sombatwattana | 13-Jul-2026 | 08-Jul-2026 16:30:27 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 13-Jul-2026 22:30:12 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 14-Jul-2026 08:37:36 | 14-Jul-2026 02:02:04 | 0 |  |  | Approver | Locate
AO-000056 | MM-ASK-1A-WP02-MEC-MR-0002 | MATERIAL REQUISITION FOR DEGASSER DRUM – WITH PROVISION TO UPGRADE TO IGF |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 23-Apr-2026 18:20:11 | zm167dc@jutal.com | 24-Apr-2026 15:33:05 | Jumpol Sudjitjul | 06-May-2026 | 01-May-2026 12:09:10 | Thanapat Sombatwattana | 07-May-2026 | 08-May-2026 14:58:16 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:28:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:02:54 | 09-May-2026 08:54:57 | 0 |  |  | Approver | Locate
AO-000321 | MM-ASK-1A-WP02-MEC-MR-0002 | MATERIAL REQUISITION FOR DEGASSER DRUM – WITH PROVISION TO UPGRADE TO IGF |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval | 22-May-2026 | 23-May-2026 08:46:44 | zm167dc@jutal.com | 23-May-2026 09:21:24 | Jumpol Sudjitjul | 02-Jun-2026 | 03-Jun-2026 09:28:42 | Thanapat Sombatwattana | 04-Jun-2026 | 09-Jun-2026 22:01:25 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:17:47 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 09:58:46 | 11-Jun-2026 10:28:28 | 0 |  |  | Approver | Locate
AO-000475 | MM-ASK-1A-WP02-MEC-MR-0002 | MATERIAL REQUISITION FOR DEGASSER DRUM – WITH PROVISION TO UPGRADE TO IGF |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 13-Jun-2026 08:16:47 | zm167dc@jutal.com | 13-Jun-2026 08:27:51 | Jumpol Sudjitjul | 22-Jun-2026 | 21-Jun-2026 18:55:22 | Thanapat Sombatwattana | 23-Jun-2026 | 25-Jun-2026 13:58:24 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 00:21:10 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 28-Jun-2026 08:39:36 | 28-Jun-2026 02:19:42 | 0 |  |  | Approver | Locate
AO-000166 | MM-ASK-1A-WP02-MEC-MR-0003 | MATERIAL REQUISITION FOR SKIM TANK VESSEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 15:44:43 | zm167dc@jutal.com | 08-May-2026 17:22:28 | Jumpol Sudjitjul | 19-May-2026 | 12-May-2026 13:56:56 | Thanapat Sombatwattana | 20-May-2026 | 21-May-2026 17:27:12 | Pornlert Wanaphattharaphan | 21-May-2026 | 25-May-2026 21:52:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 22:05:56 | 25-May-2026 22:31:21 | 0 |  |  | Approver | Locate
AO-000471 | MM-ASK-1A-WP02-MEC-MR-0003 | MATERIAL REQUISITION FOR SKIM TANK VESSEL |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 18:02:50 | zm167dc@jutal.com | 13-Jun-2026 07:19:26 | Jumpol Sudjitjul | 22-Jun-2026 | 21-Jun-2026 18:53:18 | Thanapat Sombatwattana | 23-Jun-2026 | 25-Jun-2026 14:39:23 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 07:40:19 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Jun-2026 | 28-Jun-2026 08:39:39 | 28-Jun-2026 02:24:35 | 0 |  |  | Approver | Locate
AO-000605 | MM-ASK-1A-WP02-MEC-MR-0003 | MATERIAL REQUISITION FOR SKIM TANK VESSEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 10:42:47 | zm167dc@jutal.com | 03-Jul-2026 13:51:39 | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 10:06:27 | Thanapat Sombatwattana | 14-Jul-2026 | 15-Jul-2026 09:31:42 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:41:21 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:42:12 | 17-Jul-2026 03:42:15 | 0 |  |  | Approver | Locate
AO-000190 | MM-ASK-1A-WP02-MEC-MR-0004 | MATERIAL REQUISITION FOR OPEN DRAIN CAISSON PUMP PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 10-May-2026 23:38:03 | zm167dc@jutal.com | 11-May-2026 09:21:17 | Jumpol Sudjitjul | 19-May-2026 | 21-May-2026 13:51:56 | Thanapat Sombatwattana | 20-May-2026 | 22-May-2026 07:52:23 | Pornlert Wanaphattharaphan | 21-May-2026 | 25-May-2026 21:54:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 22:07:09 | 25-May-2026 22:32:27 | 0 |  |  | Approver | Locate
AO-000401 | MM-ASK-1A-WP02-MEC-MR-0004 | MATERIAL REQUISITION FOR OPEN DRAIN CAISSON PUMP PACKAGE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 12:15:42 | zm167dc@jutal.com | 04-Jun-2026 12:58:21 | Jumpol Sudjitjul | 12-Jun-2026 | 12-Jun-2026 09:54:39 | Thanapat Sombatwattana | 15-Jun-2026 | 16-Jun-2026 23:48:08 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 18-Jun-2026 21:17:34 | APPR | Approved | Jumpol Sudjitjul | 17-Jun-2026 | 19-Jun-2026 10:49:17 | 19-Jun-2026 04:15:42 | 0 |  |  | Approver | Locate
AO-000541 | MM-ASK-1A-WP02-MEC-MR-0004 | MATERIAL REQUISITION FOR OPEN DRAIN CAISSON PUMP PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 25-Jun-2026 08:36:10 | zm167dc@jutal.com | 25-Jun-2026 15:00:58 | Jumpol Sudjitjul | 03-Jul-2026 | 29-Jun-2026 08:06:59 | Thanapat Sombatwattana | 06-Jul-2026 | 08-Jul-2026 16:26:06 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 10-Jul-2026 00:54:42 | APPR | Approved | Jumpol Sudjitjul | 08-Jul-2026 | 10-Jul-2026 10:09:45 | 10-Jul-2026 03:29:35 | 0 |  |  | Approver | Locate
AO-000048 | MM-ASK-1A-WP02-MEC-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR DE-OILER HYDROCYCLONE PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:30:26 | jumpols@pttep.com | 21-Apr-2026 14:10:25 | Jumpol Sudjitjul | 29-Apr-2026 | 23-Apr-2026 18:26:02 | Thanapat Sombatwattana | 30-Apr-2026 | 05-May-2026 15:51:00 | Pornlert Wanaphattharaphan | 05-May-2026 | 06-May-2026 00:50:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 09:10:39 | 06-May-2026 09:16:07 | 0 |  |  | Approver | Locate
AO-000281 | MM-ASK-1A-WP02-MEC-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR DE-OILER HYDROCYCLONE PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 18-May-2026 19:35:50 | zm167dc@jutal.com | 18-May-2026 20:10:24 | Jumpol Sudjitjul | 27-May-2026 | 29-May-2026 10:40:51 | Thanapat Sombatwattana | 28-May-2026 | 02-Jun-2026 10:01:06 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 01:27:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 10-Jun-2026 11:46:23 | 10-Jun-2026 05:18:29 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-WP02-MEC-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR DE-OILER HYDROCYCLONE PACKAGE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:52:37 | zm167dc@jutal.com | 27-Jun-2026 19:54:24 | Jumpol Sudjitjul | 07-Jul-2026 | 28-Jun-2026 18:09:56 | Thanapat Sombatwattana | 08-Jul-2026 | 29-Jun-2026 13:25:28 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 01-Jul-2026 22:15:47 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 13:02:06 | 02-Jul-2026 06:25:18 | 0 |  |  | Approver | Locate
AO-000049 | MM-ASK-1A-WP02-MEC-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR DEGASSER DRUM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:30:57 | jumpols@pttep.com | 21-Apr-2026 14:10:59 | Jumpol Sudjitjul | 29-Apr-2026 | 23-Apr-2026 18:26:51 | Thanapat Sombatwattana | 30-Apr-2026 | 05-May-2026 15:51:15 | Pornlert Wanaphattharaphan | 05-May-2026 | 06-May-2026 00:57:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 09:08:53 | 06-May-2026 09:15:01 | 0 |  |  | Approver | Locate
AO-000282 | MM-ASK-1A-WP02-MEC-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR DEGASSER DRUM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 18-May-2026 19:36:16 | zm167dc@jutal.com | 18-May-2026 20:10:48 | Jumpol Sudjitjul | 27-May-2026 | 29-May-2026 10:42:00 | Thanapat Sombatwattana | 28-May-2026 | 02-Jun-2026 10:01:32 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 01:28:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 10-Jun-2026 11:44:01 | 10-Jun-2026 05:17:17 | 0 |  |  | Approver | Locate
AO-000537 | MM-ASK-1A-WP02-MEC-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR DEGASSER DRUM |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 24-Jun-2026 16:37:41 | zm167dc@jutal.com | 25-Jun-2026 14:50:04 | Jumpol Sudjitjul | 03-Jul-2026 | 26-Jun-2026 17:03:55 | Thanapat Sombatwattana | 06-Jul-2026 | 03-Jul-2026 18:20:06 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 04-Jul-2026 19:21:47 | APPR | Approved | Jumpol Sudjitjul | 08-Jul-2026 | 05-Jul-2026 10:31:29 | 05-Jul-2026 04:17:58 | 0 |  |  | Approver | Locate
AO-000149 | MM-ASK-1A-WP02-MEC-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR SKIM TANK VESSEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 07-May-2026 12:44:09 | zm167dc@jutal.com | 07-May-2026 14:52:43 | Jumpol Sudjitjul | 15-May-2026 | 08-May-2026 16:59:01 | Thanapat Sombatwattana | 18-May-2026 | 18-May-2026 10:37:54 | Pornlert Wanaphattharaphan | 19-May-2026 | 19-May-2026 23:30:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-May-2026 | 20-May-2026 08:45:03 | 20-May-2026 09:26:40 | 0 |  |  | Approver | Locate
AO-000386 | MM-ASK-1A-WP02-MEC-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR SKIM TANK VESSEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 01-Jun-2026 10:52:22 | zm167dc@jutal.com | 02-Jun-2026 10:30:35 | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 09:38:09 | Thanapat Sombatwattana | 12-Jun-2026 | 16-Jun-2026 16:58:29 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 17-Jun-2026 00:16:41 | APPR | Approved | Jumpol Sudjitjul | 16-Jun-2026 | 17-Jun-2026 08:21:23 | 17-Jun-2026 02:18:46 | 0 |  |  | Approver | Locate
AO-000154 | MM-ASK-1A-WP02-MEC-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR OPEN DRAIN CAISSON PUMP PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 07-May-2026 17:06:36 | zm167dc@jutal.com | 07-May-2026 17:10:48 | Jumpol Sudjitjul | 18-May-2026 | 12-May-2026 09:56:50 | Thanapat Sombatwattana | 19-May-2026 | 19-May-2026 15:33:32 | Pornlert Wanaphattharaphan | 20-May-2026 | 20-May-2026 00:25:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 20-May-2026 08:33:30 | 20-May-2026 08:58:06 | 0 |  |  | Approver | Locate
AO-000367 | MM-ASK-1A-WP02-MEC-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR OPEN DRAIN CAISSON PUMP PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 28-May-2026 16:06:53 | zm167dc@jutal.com | 28-May-2026 17:38:40 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 10:31:35 | Thanapat Sombatwattana | 11-Jun-2026 | 15-Jun-2026 23:36:14 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 17-Jun-2026 00:12:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 17-Jun-2026 08:22:07 | 17-Jun-2026 02:06:03 | 0 |  |  | Approver | Locate
AO-000540 | MM-ASK-1A-WP02-MEC-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR OPEN DRAIN CAISSON PUMP PACKAGE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 25-Jun-2026 08:36:41 | zm167dc@jutal.com | 25-Jun-2026 14:56:14 | Jumpol Sudjitjul | 03-Jul-2026 | 29-Jun-2026 08:13:35 | Thanapat Sombatwattana | 06-Jul-2026 | 08-Jul-2026 16:22:13 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 10-Jul-2026 00:53:24 | APPR | Approved | Jumpol Sudjitjul | 08-Jul-2026 | 10-Jul-2026 10:13:12 | 10-Jul-2026 03:30:48 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-WP02-MEC-TBE-0001 | TECHNICAL BID EVALUATION FOR DEOILER HYDRO CYCLONE PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:53:27 | zm167dc@jutal.com | 27-Jun-2026 19:56:39 | Jumpol Sudjitjul | 07-Jul-2026 | 28-Jun-2026 20:14:52 | Thanapat Sombatwattana | 08-Jul-2026 | 29-Jun-2026 17:19:14 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 23:32:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 30-Jun-2026 12:41:10 | 30-Jun-2026 06:54:35 | 0 |  |  | Approver | Locate
AO-000602 | MM-ASK-1A-WP02-MEC-TBE-0001 | TECHNICAL BID EVALUATION FOR DEOILER HYDRO CYCLONE PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 09:44:11 | zm167dc@jutal.com | 03-Jul-2026 13:38:14 | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 13:55:29 | Thanapat Sombatwattana | 14-Jul-2026 | 07-Jul-2026 17:35:22 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 07-Jul-2026 22:17:35 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 08-Jul-2026 09:22:01 | 08-Jul-2026 03:03:40 | 0 |  |  | Approver | Locate
AO-000571 | MM-ASK-1A-WP02-MEC-TBE-0002 | TECHNICAL BID EVALUATION FOR DEGASSER DRUM - WITH PROVISION TO UPGRADE TO IGF |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 12:12:15 | zm167dc@jutal.com | 30-Jun-2026 08:51:18 | Jumpol Sudjitjul | 08-Jul-2026 | 30-Jun-2026 14:37:27 | Thanapat Sombatwattana | 09-Jul-2026 | 30-Jun-2026 17:45:08 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 01-Jul-2026 21:15:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 02-Jul-2026 13:03:31 | 02-Jul-2026 06:15:07 | 0 |  |  | Approver | Locate
AO-000626 | MM-ASK-1A-WP02-MEC-TBE-0002 | TECHNICAL BID EVALUATION FOR DEGASSER DRUM - WITH PROVISION TO UPGRADE TO IGF |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 19:11:13 | zm167dc@jutal.com | 03-Jul-2026 19:57:54 | Jumpol Sudjitjul | 14-Jul-2026 | 07-Jul-2026 13:54:58 | Thanapat Sombatwattana | 15-Jul-2026 | 07-Jul-2026 17:56:49 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 07-Jul-2026 23:52:37 | APPR | Approved | Jumpol Sudjitjul | 17-Jul-2026 | 08-Jul-2026 09:27:43 | 08-Jul-2026 03:28:27 | 0 |  |  | Approver | Locate
AO-000616 | MM-ASK-1A-WP02-MEC-TBE-0003 | TECHNICAL BID EVALUATION FOR SKIM TANK VESSEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 18:23:12 | zm167dc@jutal.com | 03-Jul-2026 19:12:26 | Jumpol Sudjitjul | 14-Jul-2026 | 06-Jul-2026 19:00:42 | Thanapat Sombatwattana | 15-Jul-2026 | 07-Jul-2026 17:36:10 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 07-Jul-2026 23:25:52 | APPR | Approved | Jumpol Sudjitjul | 17-Jul-2026 | 08-Jul-2026 09:34:20 | 08-Jul-2026 02:59:28 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-WP02-MEC-TBE-0004 | TECHNICAL BID EVALUATION FOR OPEN DRAIN CAISSON PUMP PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 16:54:23 | zm167dc@jutal.com | 10-Jul-2026 18:32:29 | Jumpol Sudjitjul | 21-Jul-2026 | 13-Jul-2026 17:02:12 | Thanapat Sombatwattana | 22-Jul-2026 | 15-Jul-2026 16:39:48 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 16-Jul-2026 17:27:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 16-Jul-2026 17:52:55 | 16-Jul-2026 11:21:46 | 0 |  |  | Approver | Locate
AO-000748 | MM-ASK-1A-WP02-MEC-TBE-0004 | TECHNICAL BID EVALUATION FOR OPEN DRAIN CAISSON PUMP PACKAGE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 15:17:34 | zm167dc@jutal.com | 21-Jul-2026 15:31:14 | Jumpol Sudjitjul | 31-Jul-2026 | 21-Jul-2026 17:40:38 | Thanapat Sombatwattana | 03-Aug-2026 | 22-Jul-2026 17:22:17 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 24-Jul-2026 00:47:58 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 24-Jul-2026 10:25:04 | 24-Jul-2026 04:07:36 | 0 |  |  | Approver | Locate
AO-001222 | MM-ASK-1A-WP02-PIP-CAL-0001 | WP02 PIPING STRESS ANALYSIS REPORT (FLOWLINE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 07-Sep-2026 13:17:09 | zm167dc@jutal.com | 08-Sep-2026 10:23:43 | Jumpol Sudjitjul | 16-Sep-2026 |  | Thanapat Sombatwattana | 17-Sep-2026 |  | Pornlert Wanaphattharaphan | 18-Sep-2026 |  |  |  |  | 21-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001491 | MM-ASK-1A-WP02-PIP-CAL-0003 | WP02 PIPING STRESS ANALYSIS REPORT (OTHER GC LINES, IG LINES, AND HP VENT) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 18-Sep-2026 20:15:06 | zm167dc@jutal.com | 20-Sep-2026 14:19:06 | Jumpol Sudjitjul | 28-Sep-2026 |  | Thanapat Sombatwattana | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0001 | WP02 EQUIPMENT LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:44:08 | zm167dc@jutal.com | 08-May-2026 12:59:53 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 13:52:50 | Thanapat Sombatwattana | 19-May-2026 | 21-May-2026 16:06:17 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 19:34:46 | APPR | Approved | Jumpol Sudjitjul | 21-May-2026 | 24-May-2026 19:58:07 | 24-May-2026 13:35:41 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0001 | WP02 EQUIPMENT LAYOUT DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:27:45 | zm167dc@jutal.com | 12-Jul-2026 11:51:35 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 14:58:49 | Thanapat Sombatwattana | 21-Jul-2026 | 22-Jul-2026 16:13:26 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 13:43:47 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 14:16:58 | 24-Jul-2026 07:35:01 | 0 |  |  | Approver | Locate
AO-001365 | MM-ASK-1A-WP02-PIP-LAY-0001 | WP02 EQUIPMENT LAYOUT DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 15-Sep-2026 16:43:17 | zm167dc@jutal.com | 15-Sep-2026 17:26:28 | Jumpol Sudjitjul | 24-Sep-2026 |  | Thanapat Sombatwattana | 25-Sep-2026 |  | Pornlert Wanaphattharaphan | 28-Sep-2026 |  |  |  |  | 29-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0002 | WP02 EQUIPMENT LAYOUT DRAWING UPPER DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:44:34 | zm167dc@jutal.com | 08-May-2026 12:57:11 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 13:58:29 | Thanapat Sombatwattana | 19-May-2026 | 25-May-2026 00:34:21 | Pornlert Wanaphattharaphan | 20-May-2026 | 25-May-2026 21:32:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 22:09:16 | 25-May-2026 15:33:31 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0002 | WP02 EQUIPMENT LAYOUT DRAWING UPPER DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:28:22 | zm167dc@jutal.com | 12-Jul-2026 11:51:38 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 15:06:12 | Thanapat Sombatwattana | 21-Jul-2026 | 23-Jul-2026 14:35:25 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 01:24:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:20:16 | 27-Jul-2026 09:05:50 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP02-PIP-LAY-0002 | WP02 EQUIPMENT LAYOUT DRAWING UPPER DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:12:00 | zm167dc@jutal.com | 15-Sep-2026 08:42:56 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0003 | WP02 EQUIPMENT LAYOUT DRAWING MEZZANINE DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:45:17 | zm167dc@jutal.com | 08-May-2026 12:57:33 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 14:00:59 | Thanapat Sombatwattana | 19-May-2026 | 25-May-2026 00:43:07 | Pornlert Wanaphattharaphan | 20-May-2026 | 25-May-2026 21:33:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 22:11:41 | 25-May-2026 15:34:32 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0003 | WP02 EQUIPMENT LAYOUT DRAWING MEZZANINE DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:28:56 | zm167dc@jutal.com | 12-Jul-2026 11:51:36 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 15:07:58 | Thanapat Sombatwattana | 21-Jul-2026 | 23-Jul-2026 14:34:05 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 00:22:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:17:26 | 27-Jul-2026 09:03:19 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP02-PIP-LAY-0003 | WP02 EQUIPMENT LAYOUT DRAWING MEZZANINE DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:12:32 | zm167dc@jutal.com | 15-Sep-2026 08:42:57 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0004 | WP02 EQUIPMENT LAYOUT DRAWING LOWER DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 10:58:37 | zm167dc@jutal.com | 08-May-2026 12:57:54 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 14:05:50 | Thanapat Sombatwattana | 19-May-2026 | 25-May-2026 00:56:40 | Pornlert Wanaphattharaphan | 20-May-2026 | 25-May-2026 21:34:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 22:17:50 | 25-May-2026 15:36:44 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0004 | WP02 EQUIPMENT LAYOUT DRAWING LOWER DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:29:25 | zm167dc@jutal.com | 12-Jul-2026 11:51:36 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 15:09:44 | Thanapat Sombatwattana | 21-Jul-2026 | 23-Jul-2026 14:35:13 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 00:23:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:22:51 | 27-Jul-2026 09:09:49 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP02-PIP-LAY-0004 | WP02 EQUIPMENT LAYOUT DRAWING LOWER DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:13:01 | zm167dc@jutal.com | 15-Sep-2026 08:42:55 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0005 | WP02 EQUIPMENT LAYOUT DRAWING SUMP DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 10:59:13 | zm167dc@jutal.com | 08-May-2026 12:58:13 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 14:18:12 | Thanapat Sombatwattana | 19-May-2026 | 25-May-2026 01:04:19 | Pornlert Wanaphattharaphan | 20-May-2026 | 25-May-2026 21:34:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 22:22:27 | 25-May-2026 15:40:04 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0005 | WP02 EQUIPMENT LAYOUT DRAWING SUMP DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:29:53 | zm167dc@jutal.com | 12-Jul-2026 11:51:36 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 15:15:12 | Thanapat Sombatwattana | 21-Jul-2026 | 23-Jul-2026 14:34:17 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 00:23:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:20:57 | 27-Jul-2026 09:07:12 | 0 |  |  | Approver | Locate
AO-001349 | MM-ASK-1A-WP02-PIP-LAY-0005 | WP02 EQUIPMENT LAYOUT DRAWING SUMP DECK |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:13:33 | zm167dc@jutal.com | 15-Sep-2026 08:42:57 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0006 | WP02 EQUIPMENT LAYOUT DRAWING BOAT LANDING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 10:59:44 | zm167dc@jutal.com | 08-May-2026 13:00:01 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 14:18:45 | Thanapat Sombatwattana | 19-May-2026 | 25-May-2026 01:10:23 | Pornlert Wanaphattharaphan | 20-May-2026 | 25-May-2026 21:35:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 22:22:00 | 25-May-2026 15:39:00 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0006 | WP02 EQUIPMENT LAYOUT DRAWING BOAT LANDING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:30:19 | zm167dc@jutal.com | 12-Jul-2026 11:51:42 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 15:18:34 | Thanapat Sombatwattana | 21-Jul-2026 | 23-Jul-2026 14:35:49 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 01:28:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:24:30 | 27-Jul-2026 09:14:40 | 0 |  |  | Approver | Locate
AO-001349 | MM-ASK-1A-WP02-PIP-LAY-0006 | WP02 EQUIPMENT LAYOUT DRAWING BOAT LANDING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:14:02 | zm167dc@jutal.com | 15-Sep-2026 08:42:56 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0007 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:00:31 | zm167dc@jutal.com | 08-May-2026 12:53:45 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 14:21:44 | Thanapat Sombatwattana | 19-May-2026 | 25-May-2026 01:14:16 | Pornlert Wanaphattharaphan | 20-May-2026 | 25-May-2026 21:36:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 22:20:30 | 25-May-2026 15:37:56 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0007 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:30:45 | zm167dc@jutal.com | 12-Jul-2026 11:51:38 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 15:20:41 | Thanapat Sombatwattana | 21-Jul-2026 | 23-Jul-2026 18:51:58 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 01:31:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:23:37 | 27-Jul-2026 09:11:12 | 0 |  |  | Approver | Locate
AO-001349 | MM-ASK-1A-WP02-PIP-LAY-0007 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:14:39 | zm167dc@jutal.com | 15-Sep-2026 08:42:56 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0008 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:01:02 | zm167dc@jutal.com | 08-May-2026 12:53:25 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 14:24:31 | Thanapat Sombatwattana | 19-May-2026 | 25-May-2026 01:16:36 | Pornlert Wanaphattharaphan | 20-May-2026 | 25-May-2026 21:37:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 22:15:43 | 25-May-2026 15:35:38 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0008 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:31:14 | zm167dc@jutal.com | 12-Jul-2026 11:51:40 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 15:23:56 | Thanapat Sombatwattana | 21-Jul-2026 | 23-Jul-2026 18:52:19 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 22:11:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:26:44 | 27-Jul-2026 09:17:21 | 0 |  |  | Approver | Locate
AO-001349 | MM-ASK-1A-WP02-PIP-LAY-0008 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:15:15 | zm167dc@jutal.com | 15-Sep-2026 08:42:56 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0009 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:01:26 | zm167dc@jutal.com | 08-May-2026 12:53:05 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 14:35:21 | Thanapat Sombatwattana | 19-May-2026 | 25-May-2026 01:19:31 | Pornlert Wanaphattharaphan | 20-May-2026 | 25-May-2026 21:38:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 21:55:59 | 25-May-2026 15:28:50 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0009 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:31:41 | zm167dc@jutal.com | 12-Jul-2026 11:51:42 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 15:28:49 | Thanapat Sombatwattana | 21-Jul-2026 | 24-Jul-2026 14:33:21 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 02:43:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:11:56 | 27-Jul-2026 09:00:32 | 0 |  |  | Approver | Locate
AO-001349 | MM-ASK-1A-WP02-PIP-LAY-0009 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:15:43 | zm167dc@jutal.com | 15-Sep-2026 08:43:00 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000160 | MM-ASK-1A-WP02-PIP-LAY-0010 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 11:01:56 | zm167dc@jutal.com | 08-May-2026 12:52:22 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 14:38:17 | Thanapat Sombatwattana | 19-May-2026 | 25-May-2026 01:21:36 | Pornlert Wanaphattharaphan | 20-May-2026 | 25-May-2026 21:38:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 21:49:09 | 25-May-2026 15:00:45 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-0010 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:32:15 | zm167dc@jutal.com | 12-Jul-2026 11:51:39 | Jumpol Sudjitjul | 20-Jul-2026 | 17-Jul-2026 15:55:00 | Thanapat Sombatwattana | 21-Jul-2026 | 23-Jul-2026 18:52:08 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 01:42:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:25:15 | 27-Jul-2026 09:16:01 | 0 |  |  | Approver | Locate
AO-001349 | MM-ASK-1A-WP02-PIP-LAY-0010 | WP02 EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:16:21 | zm167dc@jutal.com | 15-Sep-2026 09:33:46 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP02-PIP-LAY-1001 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT DRILLING & WELL COMPLETION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:31:45 | zm167dc@jutal.com | 08-May-2026 13:40:51 | Jumpol Sudjitjul | 18-May-2026 | 21-May-2026 14:39:33 | Thanapat Sombatwattana | 19-May-2026 | 22-May-2026 16:55:28 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 22:11:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 13:20:09 | 25-May-2026 06:32:13 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-1001 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT DRILLING & WELL COMPLETION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:32:46 | zm167dc@jutal.com | 12-Jul-2026 11:53:38 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:50:22 | Thanapat Sombatwattana | 21-Jul-2026 | 24-Jul-2026 07:47:09 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 02:19:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:12:36 | 27-Jul-2026 09:01:58 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP02-PIP-LAY-1001 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT DRILLING & WELL COMPLETION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:16:55 | zm167dc@jutal.com | 15-Sep-2026 08:51:53 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP02-PIP-LAY-1002 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT ACID STIMULATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:32:17 | zm167dc@jutal.com | 08-May-2026 13:42:45 | Jumpol Sudjitjul | 18-May-2026 | 22-May-2026 09:00:50 | Thanapat Sombatwattana | 19-May-2026 | 22-May-2026 16:57:26 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 22:19:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 13:16:51 | 25-May-2026 06:30:57 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-1002 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT ACID STIMULATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:33:19 | zm167dc@jutal.com | 12-Jul-2026 11:53:55 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:52:13 | Thanapat Sombatwattana | 21-Jul-2026 | 24-Jul-2026 07:46:57 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 02:10:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:21:42 | 27-Jul-2026 09:08:31 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP02-PIP-LAY-1002 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT ACID STIMULATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:17:27 | zm167dc@jutal.com | 15-Sep-2026 08:51:34 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP02-PIP-LAY-1003 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT LIGHT WELL INTERVENTION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:32:45 | zm167dc@jutal.com | 08-May-2026 13:46:36 | Jumpol Sudjitjul | 18-May-2026 | 22-May-2026 09:02:35 | Thanapat Sombatwattana | 19-May-2026 | 22-May-2026 17:05:30 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 22:21:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 13:16:18 | 25-May-2026 06:29:50 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-1003 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT LIGHT WELL INTERVENTION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:33:52 | zm167dc@jutal.com | 12-Jul-2026 11:54:13 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:53:58 | Thanapat Sombatwattana | 21-Jul-2026 | 24-Jul-2026 07:46:45 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 02:06:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:27:28 | 27-Jul-2026 09:18:39 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP02-PIP-LAY-1003 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT LIGHT WELL INTERVENTION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:17:56 | zm167dc@jutal.com | 15-Sep-2026 08:51:13 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP02-PIP-LAY-1004 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT COILED TUBING CAMPAIGN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:33:15 | zm167dc@jutal.com | 08-May-2026 13:47:16 | Jumpol Sudjitjul | 18-May-2026 | 22-May-2026 09:03:26 | Thanapat Sombatwattana | 19-May-2026 | 22-May-2026 17:09:57 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 22:28:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 13:15:36 | 25-May-2026 06:28:42 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-1004 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT COILED TUBING CAMPAIGN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:34:23 | zm167dc@jutal.com | 12-Jul-2026 11:54:31 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:55:33 | Thanapat Sombatwattana | 21-Jul-2026 | 24-Jul-2026 07:46:17 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 02:01:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:28:03 | 27-Jul-2026 09:19:58 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP02-PIP-LAY-1004 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT COILED TUBING CAMPAIGN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:18:30 | zm167dc@jutal.com | 15-Sep-2026 08:50:44 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000163 | MM-ASK-1A-WP02-PIP-LAY-1005 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT HEAVY WELL INTERVENTION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 13:34:01 | zm167dc@jutal.com | 08-May-2026 13:47:35 | Jumpol Sudjitjul | 18-May-2026 | 22-May-2026 09:04:45 | Thanapat Sombatwattana | 19-May-2026 | 22-May-2026 17:14:17 | Pornlert Wanaphattharaphan | 20-May-2026 | 24-May-2026 22:31:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 09:11:36 | 25-May-2026 02:40:36 | 0 |  |  | Approver | Locate
AO-000688 | MM-ASK-1A-WP02-PIP-LAY-1005 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT HEAVY WELL INTERVENTION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:34:54 | zm167dc@jutal.com | 12-Jul-2026 11:54:49 | Jumpol Sudjitjul | 20-Jul-2026 | 19-Jul-2026 15:57:02 | Thanapat Sombatwattana | 21-Jul-2026 | 24-Jul-2026 07:46:05 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 01:51:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:28:49 | 27-Jul-2026 09:21:18 | 0 |  |  | Approver | Locate
AO-001356 | MM-ASK-1A-WP02-PIP-LAY-1005 | WP02 DRILLING AND WELL SERVICE EQUIPMENT LAYOUT HEAVY WELL INTERVENTION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Sep-2026 09:19:03 | zm167dc@jutal.com | 15-Sep-2026 08:50:00 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000351 | MM-ASK-1A-WP02-PIP-MTO-0001 | MATERIAL TAKE-OFF FOR MANUAL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 12:07:41 | zm167dc@jutal.com | 26-May-2026 15:14:13 | Jumpol Sudjitjul | 05-Jun-2026 | 09-Jun-2026 11:15:50 | Thanapat Sombatwattana | 08-Jun-2026 | 10-Jun-2026 00:34:27 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 10-Jun-2026 21:25:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 10:05:13 | 11-Jun-2026 03:37:54 | 0 |  |  | Approver | Locate
AO-000801 | MM-ASK-1A-WP02-PIP-MTO-0001 | MATERIAL TAKE-OFF FOR MANUAL VALVES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 26-Jul-2026 22:32:00 | zm167dc@jutal.com | 27-Jul-2026 09:34:20 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:56:15 | Thanapat Sombatwattana | 07-Aug-2026 | 13-Aug-2026 09:03:16 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 15-Aug-2026 13:38:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 15-Aug-2026 14:34:34 | 15-Aug-2026 08:11:31 | 0 |  |  | Approver | Locate
AO-001062 | MM-ASK-1A-WP02-PIP-MTO-0001 | MATERIAL TAKE-OFF FOR MANUAL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 17:27:29 | zm167dc@jutal.com | 21-Aug-2026 17:40:18 | Jumpol Sudjitjul | 01-Sep-2026 | 23-Aug-2026 22:26:43 | Thanapat Sombatwattana | 02-Sep-2026 | 02-Sep-2026 17:06:38 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:47:37 | APPR | Approved | Jumpol Sudjitjul | 04-Sep-2026 | 03-Sep-2026 09:33:26 | 03-Sep-2026 03:01:38 | 0 |  |  | Approver | Locate
AO-000801 | MM-ASK-1A-WP02-PIP-MTO-0002 | MATERIAL TAKE-OFF FOR PIPING BULK |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 26-Jul-2026 22:32:27 | zm167dc@jutal.com | 27-Jul-2026 09:37:03 | Jumpol Sudjitjul | 06-Aug-2026 |  | Thanapat Sombatwattana | 07-Aug-2026 | 13-Aug-2026 17:28:30 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 15-Aug-2026 20:04:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 16-Aug-2026 09:43:59 | 16-Aug-2026 03:02:52 | 0 |  |  | Approver | Locate
AO-001355 | MM-ASK-1A-WP02-PIP-MTO-0002 | MATERIAL TAKE-OFF FOR PIPING BULK |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PIP | Piping | MTO | Material Take Off | 0 | In Review | IFA | Issued for Approval |  | 14-Sep-2026 09:19:45 | zm167dc@jutal.com | 15-Sep-2026 12:03:54 | Jumpol Sudjitjul | 23-Sep-2026 |  | Thanapat Sombatwattana | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000612 | MM-ASK-1A-WP02-PLR-DWG-0007-001 | WP02 NPS 12 RISER HANGER FLANGE DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 14:14:36 | zm167dc@jutal.com | 03-Jul-2026 14:33:30 | Jumpol Sudjitjul | 13-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:18:34 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:26:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:42:48 | 17-Jul-2026 03:34:13 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP02-PLR-DWG-0007-001 | WP02 NPS 12 RISER HANGER FLANGE DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:46:17 | zm167dc@jutal.com | 07-Aug-2026 10:16:28 | Jumpol Sudjitjul | 18-Aug-2026 |  | Akkarapat Suntornsuttiwat | 19-Aug-2026 | 19-Aug-2026 09:29:42 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:42:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 14:14:17 | 24-Aug-2026 08:00:40 | 0 |  |  | Approver | Locate
AO-001216 | MM-ASK-1A-WP02-PLR-DWG-0007-001 | WP02 NPS 12 RISER HANGER FLANGE DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:19:15 | zm167dc@jutal.com | 08-Sep-2026 10:05:52 | Jumpol Sudjitjul | 16-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 17-Sep-2026 10:30:24 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 20-Sep-2026 00:00:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:09:53 | 20-Sep-2026 10:06:48 | 0 |  |  | Approver | Locate
AO-000613 | MM-ASK-1A-WP02-PLR-DWG-0007-002 | WP02 NPS 20 RISER HANGER FLANGE DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 14:15:10 | zm167dc@jutal.com | 03-Jul-2026 14:34:21 | Jumpol Sudjitjul | 13-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:20:34 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:28:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:43:22 | 17-Jul-2026 03:35:24 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP02-PLR-DWG-0007-002 | WP02 NPS 20 RISER HANGER FLANGE DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:46:43 | zm167dc@jutal.com | 07-Aug-2026 10:16:29 | Jumpol Sudjitjul | 18-Aug-2026 |  | Akkarapat Suntornsuttiwat | 19-Aug-2026 | 19-Aug-2026 09:31:05 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:42:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 14:15:26 | 24-Aug-2026 08:02:10 | 0 |  |  | Approver | Locate
AO-001217 | MM-ASK-1A-WP02-PLR-DWG-0007-002 | WP02 NPS 20 RISER HANGER FLANGE DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:19:45 | zm167dc@jutal.com | 08-Sep-2026 10:06:30 | Jumpol Sudjitjul | 16-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 17-Sep-2026 10:32:06 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 23:57:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:05:15 | 20-Sep-2026 10:02:39 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP02-PLR-DWG-2001 | WP02 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:42:08 | zm167dc@jutal.com | 08-Jun-2026 10:15:24 | Jumpol Sudjitjul | 16-Jun-2026 | 10-Jun-2026 12:54:53 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 13:53:03 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 16:58:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:18:30 | 22-Jun-2026 01:28:18 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-PLR-DWG-2001 | WP02 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 18:06:24 | zm167dc@jutal.com | 03-Jul-2026 18:15:15 | Jumpol Sudjitjul | 14-Jul-2026 | 13-Jul-2026 10:47:37 | Akkarapat Suntornsuttiwat | 15-Jul-2026 | 14-Jul-2026 08:21:52 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 19-Jul-2026 13:19:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 20-Jul-2026 09:24:03 | 20-Jul-2026 02:41:33 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP02-PLR-DWG-2001 | WP02 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:47:11 | zm167dc@jutal.com | 07-Aug-2026 17:24:33 | Jumpol Sudjitjul | 19-Aug-2026 | 15-Aug-2026 20:41:13 | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 19-Aug-2026 09:32:22 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:40:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:17:03 | 24-Aug-2026 08:03:30 | 0 |  |  | Approver | Locate
AO-001218 | MM-ASK-1A-WP02-PLR-DWG-2001 | WP02 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:20:12 | zm167dc@jutal.com | 08-Sep-2026 10:07:01 | Jumpol Sudjitjul | 16-Sep-2026 | 14-Sep-2026 15:57:04 | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 17-Sep-2026 10:34:11 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 23:52:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:09:03 | 20-Sep-2026 10:05:28 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP02-PLR-DWG-2002 | WP02 NPS 12 SLIDING CLAMP TYPE 1 DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:42:32 | zm167dc@jutal.com | 08-Jun-2026 10:15:37 | Jumpol Sudjitjul | 16-Jun-2026 | 10-Jun-2026 12:56:31 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 13:54:22 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 17:04:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:19:08 | 22-Jun-2026 01:29:33 | 0 |  |  | Approver | Locate
AO-000614 | MM-ASK-1A-WP02-PLR-DWG-2002 | WP02 NPS 12 SLIDING CLAMP TYPE 1 DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:09:48 | zm167dc@jutal.com | 03-Jul-2026 16:19:39 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 10:49:27 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:23:09 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:29:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:45:32 | 17-Jul-2026 03:45:47 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP02-PLR-DWG-2002 | WP02 NPS 12 SLIDING CLAMP TYPE 1 DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:47:36 | zm167dc@jutal.com | 07-Aug-2026 17:24:33 | Jumpol Sudjitjul | 19-Aug-2026 | 15-Aug-2026 20:42:56 | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 19-Aug-2026 09:32:52 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:40:30 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:23:50 | 24-Aug-2026 08:08:22 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP02-PLR-DWG-2003 | WP02 NPS 12 SLIDING CLAMP TYPE 2 DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:42:55 | zm167dc@jutal.com | 08-Jun-2026 10:15:51 | Jumpol Sudjitjul | 16-Jun-2026 | 10-Jun-2026 12:58:10 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 13:55:44 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 17:06:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:19:50 | 22-Jun-2026 01:30:48 | 0 |  |  | Approver | Locate
AO-000614 | MM-ASK-1A-WP02-PLR-DWG-2003 | WP02 NPS 12 SLIDING CLAMP TYPE 2 DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:10:25 | zm167dc@jutal.com | 03-Jul-2026 16:19:09 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 10:51:39 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:24:27 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:30:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:49:06 | 17-Jul-2026 03:46:59 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP02-PLR-DWG-2003 | WP02 NPS 12 SLIDING CLAMP TYPE 2 DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:48:02 | zm167dc@jutal.com | 07-Aug-2026 17:24:37 | Jumpol Sudjitjul | 19-Aug-2026 | 15-Aug-2026 20:44:41 | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 19-Aug-2026 09:33:20 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:40:59 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:18:06 | 24-Aug-2026 08:04:44 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP02-PLR-DWG-2004 | WP02 NPS 12 SLIDING CLAMP TYPE 3 DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:43:17 | zm167dc@jutal.com | 08-Jun-2026 10:16:03 | Jumpol Sudjitjul | 16-Jun-2026 | 10-Jun-2026 13:02:58 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 13:57:34 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 17:07:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:20:34 | 22-Jun-2026 01:16:57 | 0 |  |  | Approver | Locate
AO-000614 | MM-ASK-1A-WP02-PLR-DWG-2004 | WP02 NPS 12 SLIDING CLAMP TYPE 3 DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:10:57 | zm167dc@jutal.com | 03-Jul-2026 16:19:22 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 10:55:01 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:25:41 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:30:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:49:41 | 17-Jul-2026 03:48:11 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP02-PLR-DWG-2004 | WP02 NPS 12 SLIDING CLAMP TYPE 3 DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:48:28 | zm167dc@jutal.com | 07-Aug-2026 17:24:34 | Jumpol Sudjitjul | 19-Aug-2026 | 15-Aug-2026 20:46:43 | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 19-Aug-2026 09:33:49 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:41:35 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:22:15 | 24-Aug-2026 08:07:11 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP02-PLR-DWG-2005 | WP02 NPS 20 HANGER FLANGE SUPPORT DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:43:41 | zm167dc@jutal.com | 08-Jun-2026 10:19:19 | Jumpol Sudjitjul | 16-Jun-2026 | 10-Jun-2026 13:05:18 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 13:59:01 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 17:10:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:20:59 | 22-Jun-2026 01:20:33 | 0 |  |  | Approver | Locate
AO-000614 | MM-ASK-1A-WP02-PLR-DWG-2005 | WP02 NPS 20 HANGER FLANGE SUPPORT DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:11:30 | zm167dc@jutal.com | 03-Jul-2026 16:19:36 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 11:02:04 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:28:03 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:31:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:51:07 | 17-Jul-2026 03:50:33 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP02-PLR-DWG-2005 | WP02 NPS 20 HANGER FLANGE SUPPORT DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:48:54 | zm167dc@jutal.com | 07-Aug-2026 17:24:33 | Jumpol Sudjitjul | 19-Aug-2026 | 15-Aug-2026 20:48:51 | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 19-Aug-2026 09:35:56 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:46:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 16:38:10 | 24-Aug-2026 09:54:28 | 0 |  |  | Approver | Locate
AO-001248 | MM-ASK-1A-WP02-PLR-DWG-2005 | WP02 NPS 20 HANGER FLANGE SUPPORT DRAWING |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Sep-2026 17:58:50 | zm167dc@jutal.com | 09-Sep-2026 08:43:14 | Jumpol Sudjitjul | 17-Sep-2026 | 14-Sep-2026 16:00:05 | Akkarapat Suntornsuttiwat | 18-Sep-2026 | 17-Sep-2026 10:36:05 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 19-Sep-2026 23:49:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Sep-2026 | 20-Sep-2026 16:07:30 | 20-Sep-2026 10:58:49 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP02-PLR-DWG-2006 | WP02 NPS 20 SLIDING CLAMP TYPE 1 DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:44:02 | zm167dc@jutal.com | 08-Jun-2026 10:19:01 | Jumpol Sudjitjul | 16-Jun-2026 | 10-Jun-2026 13:07:23 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 14:01:48 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 17:11:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:21:21 | 22-Jun-2026 01:19:16 | 0 |  |  | Approver | Locate
AO-000614 | MM-ASK-1A-WP02-PLR-DWG-2006 | WP02 NPS 20 SLIDING CLAMP TYPE 1 DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:12:05 | zm167dc@jutal.com | 03-Jul-2026 16:19:42 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 11:03:42 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:29:30 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:31:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:51:14 | 17-Jul-2026 03:51:48 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP02-PLR-DWG-2006 | WP02 NPS 20 SLIDING CLAMP TYPE 1 DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:49:21 | zm167dc@jutal.com | 07-Aug-2026 17:24:34 | Jumpol Sudjitjul | 19-Aug-2026 | 15-Aug-2026 20:50:51 | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 19-Aug-2026 09:34:18 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:42:29 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:12:38 | 24-Aug-2026 07:59:23 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP02-PLR-DWG-2007 | WP02 NPS 20 SLIDING CLAMP TYPE 2 DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:44:25 | zm167dc@jutal.com | 08-Jun-2026 10:18:42 | Jumpol Sudjitjul | 16-Jun-2026 | 10-Jun-2026 13:10:17 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 14:03:28 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 17:13:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:22:10 | 22-Jun-2026 01:22:03 | 0 |  |  | Approver | Locate
AO-000614 | MM-ASK-1A-WP02-PLR-DWG-2007 | WP02 NPS 20 SLIDING CLAMP TYPE 2 DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:12:38 | zm167dc@jutal.com | 03-Jul-2026 16:19:10 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 11:05:10 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 08:30:55 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:31:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:50:32 | 17-Jul-2026 03:49:22 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WP02-PLR-DWG-2007 | WP02 NPS 20 SLIDING CLAMP TYPE 2 DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 09:49:47 | zm167dc@jutal.com | 07-Aug-2026 17:24:34 | Jumpol Sudjitjul | 19-Aug-2026 | 15-Aug-2026 20:52:52 | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 19-Aug-2026 09:34:41 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:43:54 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:11:54 | 24-Aug-2026 07:58:14 | 0 |  |  | Approver | Locate
AO-000426 | MM-ASK-1A-WP02-PLR-DWG-2008 | WP02 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:16:04 | zm167dc@jutal.com | 08-Jun-2026 10:18:28 | Jumpol Sudjitjul | 16-Jun-2026 | 10-Jun-2026 13:12:25 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 14:05:29 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 17:15:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:22:33 | 22-Jun-2026 00:59:23 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-PLR-DWG-2008 | WP02 NPS 12 HANGER FLANGE SUPPORT DRAWING |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | In Review | VOID | Withdrawn or Superseded |  | 03-Jul-2026 18:06:51 | zm167dc@jutal.com | 03-Jul-2026 18:13:49 | Jumpol Sudjitjul |  | 24-Aug-2026 10:46:10 | Akkarapat Suntornsuttiwat |  |  | Pornlert Wanaphattharaphan | [8 empty] | 0 |  |  | For Info | Locate
AO-000427 | MM-ASK-1A-WP02-PLR-DWG-2009 | WP02 NPS 20 HANGER FLANGE SUPPORT DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:16:27 | zm167dc@jutal.com | 08-Jun-2026 10:18:13 | Jumpol Sudjitjul | 16-Jun-2026 | 10-Jun-2026 13:14:45 | Akkarapat Suntornsuttiwat | 17-Jun-2026 | 16-Jun-2026 14:06:59 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 17:17:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:22:58 | 22-Jun-2026 00:58:09 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-PLR-DWG-2009 | WP02 NPS 20 HANGER FLANGE SUPPORT DRAWING |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | In Review | VOID | Withdrawn or Superseded |  | 03-Jul-2026 18:07:16 | zm167dc@jutal.com | 03-Jul-2026 18:14:05 | Jumpol Sudjitjul |  | 24-Aug-2026 10:44:09 | Akkarapat Suntornsuttiwat |  |  | Pornlert Wanaphattharaphan | [8 empty] | 0 |  |  | For Info | Locate
AO-000767 | MM-ASK-1A-WP02-PLR-DWG-2010 | RISER GENERAL ARRANGEMENT AND DETAIL DRAWINGS AT WP02 - 12" IMPORT RISER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 10:40:23 | zm167dc@jutal.com | 26-Jul-2026 22:16:04 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:08:33 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:36:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 09:11:36 | 13-Aug-2026 03:41:42 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WP02-PLR-DWG-2010 | RISER GENERAL ARRANGEMENT AND DETAIL DRAWINGS AT WP02 - 12" IMPORT RISER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 15:19:55 | zm167dc@jutal.com | 21-Aug-2026 17:07:22 | Jumpol Sudjitjul | 01-Sep-2026 | 25-Aug-2026 16:03:10 | Akkarapat Suntornsuttiwat | 02-Sep-2026 | 02-Sep-2026 14:52:37 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:46:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 03-Sep-2026 10:25:49 | 03-Sep-2026 04:03:54 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP02-PLR-DWG-2011 | RISERS ISOMETRIC DRAWINGSAT WP02 - 20" EXPORT RISER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 10:40:53 | zm167dc@jutal.com | 26-Jul-2026 22:13:02 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:09:42 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:37:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:17:57 | 13-Aug-2026 04:12:51 | 0 |  |  | Approver | Locate
AO-001115 | MM-ASK-1A-WP02-PLR-DWG-2011 | RISERS ISOMETRIC DRAWINGSAT WP02 - 20" EXPORT RISER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 17:58:00 | zm167dc@jutal.com | 28-Aug-2026 13:30:01 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 10:41:37 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 02-Sep-2026 14:53:26 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 06-Sep-2026 23:51:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 10:41:09 | 07-Sep-2026 05:10:09 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP02-PLR-DWG-2012 | RISERS ISOMETRIC DRAWINGSAT WP02 - 12" PRE-INSTALLED RISER (FOR FUTURE) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 10:41:19 | zm167dc@jutal.com | 26-Jul-2026 22:13:04 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:10:54 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:38:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:26:09 | 13-Aug-2026 04:28:47 | 0 |  |  | Approver | Locate
AO-001115 | MM-ASK-1A-WP02-PLR-DWG-2012 | RISERS ISOMETRIC DRAWINGSAT WP02 - 12" PRE-INSTALLED RISER (FOR FUTURE) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 17:58:30 | zm167dc@jutal.com | 28-Aug-2026 13:30:51 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 10:46:27 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 02-Sep-2026 14:54:15 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 06-Sep-2026 23:57:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 10:41:48 | 07-Sep-2026 05:11:30 | 0 |  |  | Approver | Locate
AO-000767 | MM-ASK-1A-WP02-PLR-DWG-2013 | RISERS ISOMETRIC DRAWINGSAT WP02 - 12" IMPORT RISER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 10:41:45 | zm167dc@jutal.com | 26-Jul-2026 22:13:02 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:11:53 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:39:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:26:42 | 13-Aug-2026 04:32:13 | 0 |  |  | Approver | Locate
AO-001054 | MM-ASK-1A-WP02-PLR-DWG-2013 | RISERS ISOMETRIC DRAWINGSAT WP02 - 12" IMPORT RISER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 13:09:15 | zm167dc@jutal.com | 21-Aug-2026 13:47:16 | Jumpol Sudjitjul | 31-Aug-2026 | 02-Sep-2026 09:59:07 | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 02-Sep-2026 14:40:15 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 02-Sep-2026 23:39:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 10:40:48 | 03-Sep-2026 05:30:02 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-PLR-DWG-2014 | RISERS ISOMETRIC DRAWINGS AT WP02 12" PRE-INSTALLED RISER (FOR FUTURE) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:45:08 | zm167dc@jutal.com | 26-Jul-2026 22:13:02 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:13:29 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:39:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:20:34 | 13-Aug-2026 04:19:30 | 0 |  |  | Approver | Locate
AO-001110 | MM-ASK-1A-WP02-PLR-DWG-2014 | RISERS ISOMETRIC DRAWINGS AT WP02 12" PRE-INSTALLED RISER (FOR FUTURE) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 17:59:02 | zm167dc@jutal.com | 28-Aug-2026 13:31:24 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 10:47:39 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 02-Sep-2026 14:41:21 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 06-Sep-2026 23:58:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 10:56:27 | 07-Sep-2026 05:12:49 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-PLR-DWG-2015 | RISERS ISOMETRIC DRAWINGS AT WP02 12" IMPORT RISER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:45:34 | zm167dc@jutal.com | 26-Jul-2026 22:13:04 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 05-Aug-2026 09:14:44 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:40:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:45:09 | 13-Aug-2026 04:37:09 | 0 |  |  | Approver | Locate
AO-001111 | MM-ASK-1A-WP02-PLR-DWG-2015 | RISERS ISOMETRIC DRAWINGS AT WP02 12" IMPORT RISER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 17:59:29 | zm167dc@jutal.com | 28-Aug-2026 13:31:50 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 10:48:44 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 02-Sep-2026 14:42:21 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:00:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 11:00:07 | 07-Sep-2026 05:14:10 | 0 |  |  | Approver | Locate
AO-000366 | MM-ASK-1A-WP02-PLR-RPT-2001 | WP02 RISER CLAMP DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 16:06:27 | zm167dc@jutal.com | 29-May-2026 08:20:52 | Jumpol Sudjitjul | 10-Jun-2026 | 10-Jun-2026 00:56:26 | Akkarapat Suntornsuttiwat | 11-Jun-2026 | 11-Jun-2026 08:38:32 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:20:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 09:04:53 | 12-Jun-2026 02:40:11 | 0 |  |  | Approver | Locate
AO-000601 | MM-ASK-1A-WP02-PLR-RPT-2001 | WP02 RISER CLAMP DESIGN REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:20:01 | zm167dc@jutal.com | 03-Jul-2026 13:19:06 | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 10:44:12 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 14-Jul-2026 09:18:32 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:32:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:49:44 | 17-Jul-2026 03:37:36 | 0 |  |  | Approver | Locate
AO-000921 | MM-ASK-1A-WP02-PLR-RPT-2001 | WP02 RISER CLAMP DESIGN REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 15:29:40 | zm167dc@jutal.com | 07-Aug-2026 16:41:23 | Jumpol Sudjitjul | 18-Aug-2026 | 15-Aug-2026 19:31:39 | Akkarapat Suntornsuttiwat | 19-Aug-2026 | 19-Aug-2026 09:37:38 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:46:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 14:10:57 | 24-Aug-2026 08:18:33 | 0 |  |  | Approver | Locate
AO-000734 | MM-ASK-1A-WP02-PLR-RPT-2003 | WP02 RISER HANGER FLANGE DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 11:13:57 | zm167dc@jutal.com | 20-Jul-2026 13:56:33 | Jumpol Sudjitjul | 30-Jul-2026 | 30-Jul-2026 09:57:38 | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 31-Jul-2026 10:20:19 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 12:36:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 21:11:44 | 02-Aug-2026 14:35:34 | 0 |  |  | Approver | Locate
AO-000978 | MM-ASK-1A-WP02-PLR-RPT-2003 | WP02 RISER HANGER FLANGE DESIGN REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 11:27:12 | zm167dc@jutal.com | 14-Aug-2026 12:48:31 | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:52:03 | Akkarapat Suntornsuttiwat | 25-Aug-2026 | 25-Aug-2026 09:35:49 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:53:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:10:28 | 28-Aug-2026 04:06:11 | 0 |  |  | Approver | Locate
AO-001301 | MM-ASK-1A-WP02-PLR-RPT-2003 | WP02 RISER HANGER FLANGE DESIGN REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PLR | Pipeline | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 08:48:58 | zm167dc@jutal.com | 11-Sep-2026 19:49:55 | Jumpol Sudjitjul | 22-Sep-2026 | 14-Sep-2026 15:54:44 | Akkarapat Suntornsuttiwat | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WP02-PRO-CAL-0001 | PROCESS CALCULATION NOTE FOR PRODUCTION SEPARATOR (V-01001) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 12:44:45 | zm167dc@jutal.com | 29-May-2026 13:31:28 | Jumpol Sudjitjul | 10-Jun-2026 | 07-Jun-2026 17:20:01 | Naphat Nirotsinlapachai | 11-Jun-2026 | 10-Jun-2026 15:48:07 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:34:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 10:07:31 | 11-Jun-2026 03:40:23 | 0 |  |  | Approver | Locate
AO-000907 | MM-ASK-1A-WP02-PRO-CAL-0001 | PROCESS CALCULATION NOTE FOR PRODUCTION SEPARATOR (V-01001) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 15:04:10 | zm167dc@jutal.com | 07-Aug-2026 16:47:11 | Jumpol Sudjitjul | 18-Aug-2026 |  | Naphat Nirotsinlapachai | 19-Aug-2026 | 17-Aug-2026 14:35:33 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:30:58 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:19:32 | 21-Aug-2026 03:06:30 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WP02-PRO-CAL-0002 | PROCESS CALCULATION NOTE FOR SKIM TANK VESSEL (V-10002) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 12:45:08 | zm167dc@jutal.com | 29-May-2026 13:31:51 | Jumpol Sudjitjul | 10-Jun-2026 |  | Naphat Nirotsinlapachai | 11-Jun-2026 | 10-Jun-2026 16:03:33 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:34:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 10:10:16 | 11-Jun-2026 03:41:32 | 0 |  |  | Approver | Locate
AO-000930 | MM-ASK-1A-WP02-PRO-CAL-0002 | PROCESS CALCULATION NOTE FOR SKIM TANK VESSEL (V-10002) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 17:27:34 | zm167dc@jutal.com | 07-Aug-2026 17:36:18 | Jumpol Sudjitjul | 19-Aug-2026 | 18-Aug-2026 23:59:43 | Naphat Nirotsinlapachai | 20-Aug-2026 | 19-Aug-2026 23:30:00 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:47:45 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:10:05 | 24-Aug-2026 07:43:14 | 0 |  |  | Approver | Locate
AO-000410 | MM-ASK-1A-WP02-PRO-CAL-0003 | PROCESS CALCULATION NOTE FOR DEGASSER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:49:40 | zm167dc@jutal.com | 05-Jun-2026 14:11:37 | Jumpol Sudjitjul | 15-Jun-2026 |  | Naphat Nirotsinlapachai | 16-Jun-2026 | 16-Jun-2026 19:09:13 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 11:33:00 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 21:23:21 | 22-Jun-2026 00:34:08 | 0 |  |  | Approver | Locate
AO-000410 | MM-ASK-1A-WP02-PRO-CAL-0004 | PROCESS CALCULATION NOTE FOR DEMULSIFIER / WATER CLARIFIER TANK AND PUMP SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:50:07 | zm167dc@jutal.com | 05-Jun-2026 14:12:01 | Jumpol Sudjitjul | 15-Jun-2026 |  | Naphat Nirotsinlapachai | 16-Jun-2026 | 15-Jun-2026 20:15:26 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 11:31:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 21:23:47 | 22-Jun-2026 00:36:36 | 0 |  |  | Approver | Locate
AO-001056 | MM-ASK-1A-WP02-PRO-CAL-0004 | PROCESS CALCULATION NOTE FOR DEMULSIFIER / WATER CLARIFIER TANK AND PUMP SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 15:24:53 | zm167dc@jutal.com | 21-Aug-2026 17:10:18 | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 22:54:02 | Naphat Nirotsinlapachai | 02-Sep-2026 | 01-Sep-2026 10:11:25 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:42:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 03-Sep-2026 10:26:55 | 03-Sep-2026 04:18:42 | 0 |  |  | Approver | Locate
AO-000410 | MM-ASK-1A-WP02-PRO-CAL-0005 | PROCESS CALCULATION NOTE FOR OPEN DRAIN CAISSON TANK (T-05003) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:50:33 | zm167dc@jutal.com | 05-Jun-2026 14:12:18 | Jumpol Sudjitjul | 15-Jun-2026 |  | Naphat Nirotsinlapachai | 16-Jun-2026 | 16-Jun-2026 19:24:32 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 12:28:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 21:24:18 | 22-Jun-2026 01:03:17 | 0 |  |  | Approver | Locate
AO-001130 | MM-ASK-1A-WP02-PRO-CAL-0005 | PROCESS CALCULATION NOTE FOR OPEN DRAIN CAISSON TANK (T-05003) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:50:39 | zm167dc@jutal.com | 28-Aug-2026 17:37:30 | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 23:37:59 | Naphat Nirotsinlapachai | 09-Sep-2026 | 09-Sep-2026 16:11:55 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 00:09:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 11-Sep-2026 12:31:50 | 11-Sep-2026 06:29:42 | 0 |  |  | Approver | Locate
AO-000410 | MM-ASK-1A-WP02-PRO-CAL-0006 | PROCESS CALCULATION NOTE FOR OPEN DRAIN CAISSON PUMP |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:50:59 | zm167dc@jutal.com | 05-Jun-2026 14:12:36 | Jumpol Sudjitjul | 15-Jun-2026 |  | Naphat Nirotsinlapachai | 16-Jun-2026 | 16-Jun-2026 19:12:27 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 12:03:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 21:24:40 | 22-Jun-2026 00:38:45 | 0 |  |  | Approver | Locate
AO-000906 | MM-ASK-1A-WP02-PRO-CAL-0006 | PROCESS CALCULATION NOTE FOR OPEN DRAIN CAISSON PUMP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 15:04:49 | zm167dc@jutal.com | 07-Aug-2026 16:47:31 | Jumpol Sudjitjul | 18-Aug-2026 |  | Naphat Nirotsinlapachai | 19-Aug-2026 | 17-Aug-2026 14:37:05 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:32:41 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:20:07 | 21-Aug-2026 03:07:42 | 0 |  |  | Approver | Locate
AO-000396 | MM-ASK-1A-WP02-PRO-CAL-0007 | PROCESS CALCULATION NOTE FOR RECOVERED WATER PUMP (P-05002) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 09:14:37 | zm167dc@jutal.com | 04-Jun-2026 13:01:06 | Jumpol Sudjitjul | 12-Jun-2026 |  | Naphat Nirotsinlapachai | 15-Jun-2026 | 16-Jun-2026 19:10:47 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:33:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 11:30:33 | 22-Jun-2026 05:08:54 | 0 |  |  | Approver | Locate
AO-000783 | MM-ASK-1A-WP02-PRO-CAL-0007 | PROCESS CALCULATION NOTE FOR RECOVERED WATER PUMP (P-05002) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 17:36:18 | zm167dc@jutal.com | 26-Jul-2026 23:25:19 | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 23:26:25 | Naphat Nirotsinlapachai | 07-Aug-2026 | 07-Aug-2026 09:50:30 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 10:59:25 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:08:33 | 10-Aug-2026 07:22:59 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP02-PRO-HMB-0001 | HEAT AND MATERIAL BALANCE FOR WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | HMB | Heat And Material Balance | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:47:00 | jumpols@pttep.com | 20-Apr-2026 17:11:52 | Jumpol Sudjitjul | 29-Apr-2026 |  | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 08:46:18 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 18:47:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 03-May-2026 16:13:11 | 03-May-2026 10:18:23 | 0 |  |  | Approver | Locate
AO-000859 | MM-ASK-1A-WP02-PRO-HMB-0001 | HEAT AND MATERIAL BALANCE FOR WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | HMB | Heat And Material Balance | 0 | Submitted | AFC | Approved for Construction |  | 04-Aug-2026 10:50:27 | zm167dc@jutal.com | 04-Aug-2026 11:38:03 | Jumpol Sudjitjul | 13-Aug-2026 | 10-Aug-2026 00:40:07 | Naphat Nirotsinlapachai | 14-Aug-2026 | 10-Aug-2026 09:25:59 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 16-Aug-2026 23:21:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 17-Aug-2026 09:42:10 | 17-Aug-2026 03:40:58 | 0 |  |  | Approver | Locate
AO-001332 | MM-ASK-1A-WP02-PRO-HMB-0001 | HEAT AND MATERIAL BALANCE FOR WP02 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | HMB | Heat And Material Balance | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:49:47 | zm167dc@jutal.com | 11-Sep-2026 20:40:26 | Jumpol Sudjitjul | 22-Sep-2026 |  | Naphat Nirotsinlapachai | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP02-PRO-PFD-0001 | PROCESS FLOW DIAGRAM HYDROCARBON PRODUCTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:47:30 | jumpols@pttep.com | 20-Apr-2026 17:15:49 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:16:20 | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 15:50:58 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 23:38:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 03-May-2026 16:13:59 | 03-May-2026 17:19:24 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP02-PRO-PFD-0001 | PROCESS FLOW DIAGRAM HYDROCARBON PRODUCTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:09:23 | zm167dc@jutal.com | 15-May-2026 18:33:20 | Jumpol Sudjitjul | 26-May-2026 | 27-May-2026 09:40:26 | Naphat Nirotsinlapachai | 27-May-2026 | 27-May-2026 11:15:15 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 15:09:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 15:19:22 | 10-Jun-2026 08:50:32 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP02-PRO-PFD-0001 | PROCESS FLOW DIAGRAM HYDROCARBON PRODUCTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:14:40 | zm167dc@jutal.com | 26-Jul-2026 23:15:58 | Jumpol Sudjitjul | 06-Aug-2026 | 05-Aug-2026 23:21:08 | Naphat Nirotsinlapachai | 07-Aug-2026 | 07-Aug-2026 15:37:12 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:45:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:25:18 | 13-Aug-2026 04:26:28 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP02-PRO-PFD-0002 | PROCESS FLOW DIAGRAM PRODUCTION SEPARATOR AND EXPORT LINE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:47:56 | jumpols@pttep.com | 20-Apr-2026 17:17:18 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:17:29 | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 15:51:44 | Pornlert Wanaphattharaphan | 05-May-2026 | 02-May-2026 00:02:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 03-May-2026 16:11:41 | 03-May-2026 16:16:28 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP02-PRO-PFD-0002 | PROCESS FLOW DIAGRAM PRODUCTION SEPARATOR AND EXPORT LINE |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:09:48 | zm167dc@jutal.com | 15-May-2026 18:33:37 | Jumpol Sudjitjul | 26-May-2026 | 27-May-2026 09:42:01 | Naphat Nirotsinlapachai | 27-May-2026 | 27-May-2026 11:16:11 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 15:12:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 15:18:38 | 10-Jun-2026 08:47:51 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP02-PRO-PFD-0002 | PROCESS FLOW DIAGRAM PRODUCTION SEPARATOR AND EXPORT LINE |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:15:04 | zm167dc@jutal.com | 26-Jul-2026 23:16:19 | Jumpol Sudjitjul | 06-Aug-2026 | 05-Aug-2026 23:21:32 | Naphat Nirotsinlapachai | 07-Aug-2026 | 07-Aug-2026 15:42:30 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:46:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:24:49 | 13-Aug-2026 04:25:11 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP02-PRO-PFD-0003 | PROCESS FLOW DIAGRAM PRODUCED WATER TREATMENT SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:48:21 | jumpols@pttep.com | 20-Apr-2026 17:17:41 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:18:31 | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 15:52:45 | Pornlert Wanaphattharaphan | 05-May-2026 | 06-May-2026 00:10:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 09:08:08 | 06-May-2026 09:25:31 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP02-PRO-PFD-0003 | PROCESS FLOW DIAGRAM PRODUCED WATER TREATMENT SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:10:14 | zm167dc@jutal.com | 15-May-2026 18:33:57 | Jumpol Sudjitjul | 26-May-2026 |  | Naphat Nirotsinlapachai | 27-May-2026 | 27-May-2026 11:17:04 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 15:13:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 15:16:48 | 10-Jun-2026 08:44:24 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP02-PRO-PFD-0003 | PROCESS FLOW DIAGRAM PRODUCED WATER TREATMENT SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:15:28 | zm167dc@jutal.com | 26-Jul-2026 23:16:39 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:54:46 | Naphat Nirotsinlapachai | 07-Aug-2026 | 07-Aug-2026 15:43:25 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:46:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:24:03 | 13-Aug-2026 04:23:53 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0001 | PIPING & INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD (API 10000#) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:08:22 | zm167dc@jutal.com | 29-Apr-2026 10:35:50 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 17:58:29 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:28:23 | Pornlert Wanaphattharaphan | 13-May-2026 | 17-May-2026 23:02:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:04:26 | 18-May-2026 20:05:30 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0001 | PIPING & INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD (API 10000#) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:15:26 | zm167dc@jutal.com | 04-Jun-2026 09:33:09 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:05:16 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:37:27 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:08:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:25:02 | 22-Jun-2026 00:40:02 | 0 |  |  | Approver | Locate
AO-000723 | MM-ASK-1A-WP02-PRO-PID-0001 | PIPING & INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD (API 10000#) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:12:01 | zm167dc@jutal.com | 20-Jul-2026 11:01:22 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:23:55 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 19:49:14 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 20:29:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 21:11:23 | 02-Aug-2026 14:38:26 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0002 | PIPING & INSTRUMENTATION DIAGRAM WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:08:48 | zm167dc@jutal.com | 29-Apr-2026 10:36:07 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 17:59:49 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:29:44 | Pornlert Wanaphattharaphan | 13-May-2026 | 17-May-2026 23:23:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:10:06 | 18-May-2026 20:08:59 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0002 | PIPING & INSTRUMENTATION DIAGRAM WELLHEAD CONTROL PANEL |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:16:04 | zm167dc@jutal.com | 04-Jun-2026 09:34:00 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:04:35 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:38:40 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:12:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:25:22 | 22-Jun-2026 00:41:23 | 0 |  |  | Approver | Locate
AO-000726 | MM-ASK-1A-WP02-PRO-PID-0002 | PIPING & INSTRUMENTATION DIAGRAM WELLHEAD CONTROL PANEL |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:12:27 | zm167dc@jutal.com | 20-Jul-2026 11:01:20 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:27:47 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 19:52:07 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 21:06:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 21:12:25 | 02-Aug-2026 14:39:48 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0003 | PIPING & INSTRUMENTATION DIAGRAM PRODUCTION & TEST MANIFOLDS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:09:11 | zm167dc@jutal.com | 29-Apr-2026 10:39:51 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 18:08:38 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:31:03 | Pornlert Wanaphattharaphan | 13-May-2026 | 17-May-2026 23:32:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:11:36 | 18-May-2026 19:49:15 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0003 | PIPING & INSTRUMENTATION DIAGRAM PRODUCTION & TEST MANIFOLDS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:16:51 | zm167dc@jutal.com | 04-Jun-2026 09:34:36 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 09:01:39 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:40:12 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:12:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:37:58 | 22-Jun-2026 05:52:23 | 0 |  |  | Approver | Locate
AO-000723 | MM-ASK-1A-WP02-PRO-PID-0003 | PIPING & INSTRUMENTATION DIAGRAM PRODUCTION & TEST MANIFOLDS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:12:55 | zm167dc@jutal.com | 20-Jul-2026 11:01:20 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:27:10 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 19:53:14 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 21:19:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 21:30:16 | 02-Aug-2026 15:21:20 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0004 | PIPING & INSTRUMENTATION DIAGRAM PIG LAUNCHER & EXPORT LINE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:09:36 | zm167dc@jutal.com | 29-Apr-2026 10:40:28 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 18:09:18 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:32:24 | Pornlert Wanaphattharaphan | 13-May-2026 | 17-May-2026 23:35:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:12:35 | 18-May-2026 19:50:21 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0004 | PIPING & INSTRUMENTATION DIAGRAM PIG LAUNCHER & EXPORT LINE |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:17:56 | zm167dc@jutal.com | 04-Jun-2026 09:35:17 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:41:53 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:41:08 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:16:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:25:46 | 22-Jun-2026 00:42:36 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP02-PRO-PID-0004 | PIPING & INSTRUMENTATION DIAGRAM PIG LAUNCHER & EXPORT LINE |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:13:26 | zm167dc@jutal.com | 20-Jul-2026 11:01:23 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:28:10 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 19:54:19 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 21:28:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 21:31:54 | 02-Aug-2026 15:22:49 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0005 | PIPING & INSTRUMENTATION DIAGRAM PIG RECEIVER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:09:59 | zm167dc@jutal.com | 29-Apr-2026 10:40:49 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 18:09:48 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:33:54 | Pornlert Wanaphattharaphan | 13-May-2026 | 17-May-2026 23:55:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:15:56 | 18-May-2026 19:35:49 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0005 | PIPING & INSTRUMENTATION DIAGRAM PIG RECEIVER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:18:52 | zm167dc@jutal.com | 04-Jun-2026 09:36:32 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:41:23 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:41:56 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:16:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:36:13 | 22-Jun-2026 05:48:15 | 0 |  |  | Approver | Locate
AO-000727 | MM-ASK-1A-WP02-PRO-PID-0005 | PIPING & INSTRUMENTATION DIAGRAM PIG RECEIVER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:13:51 | zm167dc@jutal.com | 20-Jul-2026 11:01:20 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:26:23 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 19:56:19 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 21:44:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 22:23:49 | 02-Aug-2026 15:49:23 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0006 | PIPING & INSTRUMENTATION DIAGRAM TEST SEPARATOR |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:10:33 | zm167dc@jutal.com | 29-Apr-2026 10:41:06 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:23:59 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:36:14 | Pornlert Wanaphattharaphan | 13-May-2026 | 17-May-2026 23:59:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:17:15 | 18-May-2026 19:36:56 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0006 | PIPING & INSTRUMENTATION DIAGRAM TEST SEPARATOR |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:19:53 | zm167dc@jutal.com | 04-Jun-2026 09:40:20 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:39:59 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:47:00 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:17:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:38:25 | 22-Jun-2026 05:53:49 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP02-PRO-PID-0006 | PIPING & INSTRUMENTATION DIAGRAM TEST SEPARATOR |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:14:18 | zm167dc@jutal.com | 20-Jul-2026 11:01:22 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:27:25 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 19:57:21 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 21:51:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 22:34:55 | 02-Aug-2026 15:53:25 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0007 | PIPING & INSTRUMENTATION DIAGRAM PRODUCTION SEPARATOR |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:10:57 | zm167dc@jutal.com | 29-Apr-2026 10:43:20 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:44:27 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:38:41 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 00:11:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:17:58 | 18-May-2026 19:38:02 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0007 | PIPING & INSTRUMENTATION DIAGRAM PRODUCTION SEPARATOR |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:21:04 | zm167dc@jutal.com | 04-Jun-2026 09:40:51 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:39:28 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:13:17 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:25:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:39:34 | 22-Jun-2026 05:55:22 | 0 |  |  | Approver | Locate
AO-000727 | MM-ASK-1A-WP02-PRO-PID-0007 | PIPING & INSTRUMENTATION DIAGRAM PRODUCTION SEPARATOR |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:14:52 | zm167dc@jutal.com | 20-Jul-2026 11:01:26 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:28:41 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 19:58:55 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 21:52:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 22:30:16 | 02-Aug-2026 15:50:46 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0008 | PIPING & INSTRUMENTATION DIAGRAM PRODUCED WATER MANIFOLD AND SKIM TANK VESSEL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:11:20 | zm167dc@jutal.com | 29-Apr-2026 10:42:15 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:25:44 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:40:11 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 00:29:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:18:36 | 18-May-2026 20:11:14 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0008 | PIPING & INSTRUMENTATION DIAGRAM PRODUCED WATER MANIFOLD AND SKIM TANK VESSEL |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:21:50 | zm167dc@jutal.com | 04-Jun-2026 09:41:13 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:38:57 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:14:50 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:25:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:40:03 | 22-Jun-2026 05:56:56 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP02-PRO-PID-0008 | PIPING & INSTRUMENTATION DIAGRAM PRODUCED WATER MANIFOLD AND SKIM TANK VESSEL |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:15:19 | zm167dc@jutal.com | 20-Jul-2026 11:01:26 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:28:26 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:01:17 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 22:04:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 22:32:09 | 02-Aug-2026 15:52:05 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0009 | PIPING & INSTRUMENTATION DIAGRAM DE-OILER HYDRO CYCLONES |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:11:44 | zm167dc@jutal.com | 29-Apr-2026 10:42:36 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:28:14 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:42:10 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 00:50:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:19:16 | 18-May-2026 19:40:17 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0009 | PIPING & INSTRUMENTATION DIAGRAM DE-OILER HYDRO CYCLONES |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:22:38 | zm167dc@jutal.com | 04-Jun-2026 09:41:40 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:30:41 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:15:20 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:26:20 | APPR | Approved | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:40:33 | 22-Jun-2026 05:58:15 | 0 |  |  | Approver | Locate
AO-000723 | MM-ASK-1A-WP02-PRO-PID-0009 | PIPING & INSTRUMENTATION DIAGRAM DE-OILER HYDRO CYCLONES |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:15:48 | zm167dc@jutal.com | 20-Jul-2026 11:01:22 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:24:13 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:03:24 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 22:19:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 22:35:29 | 02-Aug-2026 15:54:43 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0010-001 | PIPING & INSTRUMENTATION DIAGRAM DEGASSER / IGF (PROVISION) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:12:09 | zm167dc@jutal.com | 29-Apr-2026 10:42:58 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:29:15 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:44:29 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:16:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:01:32 | 18-May-2026 19:17:42 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0010-001 | PIPING & INSTRUMENTATION DIAGRAM DEGASSER / IGF (PROVISION) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:23:24 | zm167dc@jutal.com | 04-Jun-2026 09:44:10 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:28:21 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 19:53:04 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:27:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:41:21 | 22-Jun-2026 05:59:46 | 0 |  |  | Approver | Locate
AO-000726 | MM-ASK-1A-WP02-PRO-PID-0010-001 | PIPING & INSTRUMENTATION DIAGRAM DEGASSER / IGF (PROVISION) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:16:14 | zm167dc@jutal.com | 20-Jul-2026 11:06:56 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:31:28 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:05:04 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 22:48:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 10:00:48 | 03-Aug-2026 03:47:18 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0010-002 | PIPING & INSTRUMENTATION DIAGRAM DEGASSER / IGF (PROVISION) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:23:49 | zm167dc@jutal.com | 29-Apr-2026 10:43:20 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:30:11 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:46:32 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:17:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:21:19 | 18-May-2026 20:12:27 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0010-002 | PIPING & INSTRUMENTATION DIAGRAM DEGASSER / IGF (PROVISION) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:24:05 | zm167dc@jutal.com | 04-Jun-2026 09:44:09 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:29:28 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 19:53:58 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:27:43 | APPR | Approved | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:26:34 | 22-Jun-2026 00:44:55 | 0 |  |  | Approver | Locate
AO-000726 | MM-ASK-1A-WP02-PRO-PID-0010-002 | PIPING & INSTRUMENTATION DIAGRAM DEGASSER / IGF (PROVISION) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:16:39 | zm167dc@jutal.com | 20-Jul-2026 11:06:58 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:32:49 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:06:00 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 22:53:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:47:59 | 03-Aug-2026 03:36:50 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0011-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:12:35 | zm167dc@jutal.com | 29-Apr-2026 10:26:21 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:30:50 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:48:15 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:23:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:04:20 | 18-May-2026 19:45:57 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0011-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:24:35 | zm167dc@jutal.com | 04-Jun-2026 09:44:11 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:28:56 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 19:55:38 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:31:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:27:00 | 22-Jun-2026 00:46:10 | 0 |  |  | Approver | Locate
AO-000726 | MM-ASK-1A-WP02-PRO-PID-0011-001 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:17:04 | zm167dc@jutal.com | 20-Jul-2026 11:06:57 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:31:44 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:34:43 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:54:47 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:44:25 | 03-Aug-2026 02:55:10 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0011-002 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:13:01 | zm167dc@jutal.com | 29-Apr-2026 10:26:54 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:31:47 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:50:07 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:27:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:23:17 | 18-May-2026 19:42:37 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0011-002 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:25:18 | zm167dc@jutal.com | 04-Jun-2026 09:44:07 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:30:06 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 19:57:32 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:31:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:41:45 | 22-Jun-2026 06:01:24 | 0 |  |  | Approver | Locate
AO-000726 | MM-ASK-1A-WP02-PRO-PID-0011-002 | PIPING & INSTRUMENTATION DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:17:32 | zm167dc@jutal.com | 20-Jul-2026 11:06:57 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:32:34 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:08:26 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:06:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 10:06:10 | 03-Aug-2026 03:54:46 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0012-001 | PIPING & INSTRUMENTATION DIAGRAM OPEN AND CLOSED DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:13:25 | zm167dc@jutal.com | 29-Apr-2026 10:27:28 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:35:19 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:51:28 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:30:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:22:34 | 18-May-2026 19:53:55 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0012-001 | PIPING & INSTRUMENTATION DIAGRAM OPEN AND CLOSED DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:25:53 | zm167dc@jutal.com | 04-Jun-2026 09:44:14 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:26:25 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 19:59:00 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:32:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:27:27 | 22-Jun-2026 00:47:22 | 0 |  |  | Approver | Locate
AO-000727 | MM-ASK-1A-WP02-PRO-PID-0012-001 | PIPING & INSTRUMENTATION DIAGRAM OPEN AND CLOSED DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:17:59 | zm167dc@jutal.com | 20-Jul-2026 11:07:00 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:33:05 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:10:26 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:38:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:49:06 | 03-Aug-2026 03:39:31 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0012-002 | PIPING & INSTRUMENTATION DIAGRAM OPEN AND CLOSED DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:13:50 | zm167dc@jutal.com | 29-Apr-2026 10:28:02 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:35:50 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:53:08 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:43:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:11:24 | 18-May-2026 19:48:09 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0012-002 | PIPING & INSTRUMENTATION DIAGRAM OPEN AND CLOSED DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:26:23 | zm167dc@jutal.com | 04-Jun-2026 09:44:11 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:27:08 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 20:00:49 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:32:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:42:16 | 22-Jun-2026 06:03:05 | 0 |  |  | Approver | Locate
AO-000726 | MM-ASK-1A-WP02-PRO-PID-0012-002 | PIPING & INSTRUMENTATION DIAGRAM OPEN AND CLOSED DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:18:27 | zm167dc@jutal.com | 20-Jul-2026 11:06:56 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:32:18 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:11:58 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:00:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 10:03:05 | 03-Aug-2026 03:50:55 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0013 | PIPING & INSTRUMENTATION DIAGRAM DIESEL SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:24:11 | zm167dc@jutal.com | 29-Apr-2026 10:21:17 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:37:37 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:55:04 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:46:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:08:38 | 18-May-2026 19:47:05 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0013 | PIPING & INSTRUMENTATION DIAGRAM DIESEL SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:27:16 | zm167dc@jutal.com | 04-Jun-2026 09:52:07 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:25:53 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:08:26 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:24:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:42:42 | 22-Jun-2026 06:04:41 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP02-PRO-PID-0013 | PIPING & INSTRUMENTATION DIAGRAM DIESEL SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:19:07 | zm167dc@jutal.com | 20-Jul-2026 11:04:46 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:30:53 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:13:36 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:48:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:40:30 | 03-Aug-2026 02:53:56 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0014 | PIPING & INSTRUMENTATION DIAGRAM UTILITY WATER SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:24:34 | zm167dc@jutal.com | 29-Apr-2026 10:21:35 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:38:18 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:56:51 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:47:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:09:52 | 18-May-2026 19:56:05 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0014 | PIPING & INSTRUMENTATION DIAGRAM UTILITY WATER SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:27:59 | zm167dc@jutal.com | 04-Jun-2026 09:52:52 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:25:25 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:03:48 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:23:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:27:56 | 22-Jun-2026 00:48:33 | 0 |  |  | Approver | Locate
AO-000727 | MM-ASK-1A-WP02-PRO-PID-0014 | PIPING & INSTRUMENTATION DIAGRAM UTILITY WATER SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:19:45 | zm167dc@jutal.com | 20-Jul-2026 11:04:43 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:29:33 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:14:28 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:49:43 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:50:06 | 03-Aug-2026 03:40:47 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0015 | PIPING & INSTRUMENTATION DIAGRAM POWER GENERATION SYSTEM (PROVISION) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:24:58 | zm167dc@jutal.com | 29-Apr-2026 10:21:55 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:38:53 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 20:58:09 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:51:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:24:11 | 18-May-2026 19:59:35 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0015 | PIPING & INSTRUMENTATION DIAGRAM POWER GENERATION SYSTEM (PROVISION) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:28:58 | zm167dc@jutal.com | 04-Jun-2026 09:53:18 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:24:57 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:04:33 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:23:48 | APPR | Approved | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:38:04 | 22-Jun-2026 06:21:22 | 0 |  |  | Approver | Locate
AO-000726 | MM-ASK-1A-WP02-PRO-PID-0015 | PIPING & INSTRUMENTATION DIAGRAM POWER GENERATION SYSTEM (PROVISION) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:20:14 | zm167dc@jutal.com | 20-Jul-2026 11:04:41 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:29:15 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:17:13 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:39:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:48:28 | 03-Aug-2026 03:38:13 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0016 | PIPING & INSTRUMENTATION DIAGRAM CORROSION INHIBITOR INJECTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:25:22 | zm167dc@jutal.com | 29-Apr-2026 10:22:13 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:39:38 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 21:01:13 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:52:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:13:08 | 18-May-2026 19:51:43 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0016 | PIPING & INSTRUMENTATION DIAGRAM CORROSION INHIBITOR INJECTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:29:35 | zm167dc@jutal.com | 04-Jun-2026 09:53:38 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:23:15 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:05:24 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:24:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:38:37 | 22-Jun-2026 06:23:04 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP02-PRO-PID-0016 | PIPING & INSTRUMENTATION DIAGRAM CORROSION INHIBITOR INJECTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:20:44 | zm167dc@jutal.com | 20-Jul-2026 11:04:45 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:24:35 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:23:11 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:42:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 10:04:22 | 03-Aug-2026 03:52:17 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0017 | PIPING & INSTRUMENTATION DIAGRAM DEMULSIFIED / WATER CLARIFIER INJECTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:25:44 | zm167dc@jutal.com | 29-Apr-2026 10:36:50 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:40:25 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 21:03:11 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:54:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:26:00 | 18-May-2026 20:02:01 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0017 | PIPING & INSTRUMENTATION DIAGRAM DEMULSIFIED / WATER CLARIFIER INJECTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:30:15 | zm167dc@jutal.com | 04-Jun-2026 09:53:58 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:22:34 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:00:07 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:18:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:43:36 | 22-Jun-2026 06:24:44 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP02-PRO-PID-0017 | PIPING & INSTRUMENTATION DIAGRAM DEMULSIFIED / WATER CLARIFIER INJECTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:21:19 | zm167dc@jutal.com | 20-Jul-2026 11:04:40 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:28:58 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:24:33 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:50:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 10:00:15 | 03-Aug-2026 03:45:52 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0018 | PIPING & INSTRUMENTATION DIAGRAM BIOCIDE INJECTION SYSTEM (PROVISION) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:26:09 | zm167dc@jutal.com | 29-Apr-2026 10:37:08 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:40:56 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 21:04:47 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 01:57:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:26:04 | 18-May-2026 20:03:11 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0018 | PIPING & INSTRUMENTATION DIAGRAM BIOCIDE INJECTION SYSTEM (PROVISION) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:31:01 | zm167dc@jutal.com | 04-Jun-2026 10:21:04 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:22:02 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:01:08 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:21:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:28:24 | 22-Jun-2026 01:00:48 | 0 |  |  | Approver | Locate
AO-000728 | MM-ASK-1A-WP02-PRO-PID-0018 | PIPING & INSTRUMENTATION DIAGRAM BIOCIDE INJECTION SYSTEM (PROVISION) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:21:52 | zm167dc@jutal.com | 20-Jul-2026 11:04:41 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:30:00 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:25:00 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:53:01 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:58:08 | 03-Aug-2026 03:43:16 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0019 | PIPING & INSTRUMENTATION DIAGRAM VENT SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:26:42 | zm167dc@jutal.com | 29-Apr-2026 10:37:25 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:41:29 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 21:56:01 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 02:09:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:25:16 | 18-May-2026 20:00:50 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0019 | PIPING & INSTRUMENTATION DIAGRAM VENT SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:31:53 | zm167dc@jutal.com | 04-Jun-2026 10:21:36 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:21:32 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:02:02 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:22:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:44:22 | 22-Jun-2026 06:26:14 | 0 |  |  | Approver | Locate
AO-000726 | MM-ASK-1A-WP02-PRO-PID-0019 | PIPING & INSTRUMENTATION DIAGRAM VENT SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:22:21 | zm167dc@jutal.com | 20-Jul-2026 11:04:44 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:30:37 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:26:20 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:02:47 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 10:01:21 | 03-Aug-2026 03:49:31 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0020 | PIPING & INSTRUMENTATION DIAGRAM NON-HAZARDOUS OPEN DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:27:07 | zm167dc@jutal.com | 29-Apr-2026 10:12:40 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:41:58 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 21:50:18 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 02:06:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:24:40 | 18-May-2026 19:43:48 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0020 | PIPING & INSTRUMENTATION DIAGRAM NON-HAZARDOUS OPEN DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:32:36 | zm167dc@jutal.com | 04-Jun-2026 10:21:56 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:19:23 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:56:03 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:17:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 22-Jun-2026 12:37:26 | 22-Jun-2026 06:19:50 | 0 |  |  | Approver | Locate
AO-000723 | MM-ASK-1A-WP02-PRO-PID-0020 | PIPING & INSTRUMENTATION DIAGRAM NON-HAZARDOUS OPEN DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:22:50 | zm167dc@jutal.com | 20-Jul-2026 11:04:49 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:31:10 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:27:37 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:02:11 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 10:05:31 | 03-Aug-2026 03:53:27 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0023 | PIPING & INSTRUMENTATION DIAGRAM POWER GENERATION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:27:31 | zm167dc@jutal.com | 29-Apr-2026 10:13:08 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:42:29 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 21:48:45 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 02:03:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:23:23 | 18-May-2026 19:58:32 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0023 | PIPING & INSTRUMENTATION DIAGRAM POWER GENERATION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:33:16 | zm167dc@jutal.com | 04-Jun-2026 10:22:12 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:18:44 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 16:57:03 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:18:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:28:46 | 22-Jun-2026 01:02:09 | 0 |  |  | Approver | Locate
AO-000726 | MM-ASK-1A-WP02-PRO-PID-0023 | PIPING & INSTRUMENTATION DIAGRAM POWER GENERATION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:23:27 | zm167dc@jutal.com | 20-Jul-2026 11:04:43 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:30:17 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:33:29 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:54:20 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:59:40 | 03-Aug-2026 03:44:28 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WP02-PRO-PID-0100 | PIPING & INSTRUMENTATION DIAGRAM WELLHEAD INSTRUMENT INDEX AND FLOWLINES |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:27:57 | zm167dc@jutal.com | 29-Apr-2026 10:13:25 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 10:42:57 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 21:47:41 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 02:00:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:22:27 | 18-May-2026 19:57:17 | 0 |  |  | Approver | Locate
AO-000399 | MM-ASK-1A-WP02-PRO-PID-0100 | PIPING & INSTRUMENTATION DIAGRAM WELLHEAD INSTRUMENT INDEX AND FLOWLINES |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 09:33:55 | zm167dc@jutal.com | 04-Jun-2026 10:22:29 | Jumpol Sudjitjul | 12-Jun-2026 | 15-Jun-2026 08:17:30 | Naphat Nirotsinlapachai | 15-Jun-2026 | 15-Jun-2026 17:10:00 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 20-Jun-2026 00:25:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 21-Jun-2026 21:29:07 | 22-Jun-2026 01:03:26 | 0 |  |  | Approver | Locate
AO-000723 | MM-ASK-1A-WP02-PRO-PID-0100 | PIPING & INSTRUMENTATION DIAGRAM WELLHEAD INSTRUMENT INDEX AND FLOWLINES |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:23:56 | zm167dc@jutal.com | 20-Jul-2026 11:04:45 | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 17:32:01 | Naphat Nirotsinlapachai | 31-Jul-2026 | 31-Jul-2026 20:35:08 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 23:55:25 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:52:16 | 03-Aug-2026 03:42:00 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP02-PRO-UFD-0001 | PROCESS FLOW DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:48:48 | jumpols@pttep.com | 20-Apr-2026 17:25:09 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:24:05 | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 15:53:46 | Pornlert Wanaphattharaphan | 05-May-2026 | 06-May-2026 00:11:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 09:02:45 | 06-May-2026 09:21:32 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP02-PRO-UFD-0001 | PROCESS FLOW DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:10:41 | zm167dc@jutal.com | 18-May-2026 20:41:24 | Jumpol Sudjitjul | 27-May-2026 | 27-May-2026 09:49:05 | Naphat Nirotsinlapachai | 28-May-2026 | 28-May-2026 08:01:25 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 20:59:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 09:21:25 | 11-Jun-2026 03:10:10 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP02-PRO-UFD-0001 | PROCESS FLOW DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:15:53 | zm167dc@jutal.com | 24-Jul-2026 16:44:00 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:20:05 | Naphat Nirotsinlapachai | 06-Aug-2026 | 06-Aug-2026 22:16:42 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 06:00:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:12:56 | 07-Aug-2026 05:06:30 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP02-PRO-UFD-0002 | PROCESS FLOW DIAGRAM DIESEL OIL, UTILITY WATER AND POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:49:14 | jumpols@pttep.com | 20-Apr-2026 17:25:26 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:25:31 | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 15:54:53 | Pornlert Wanaphattharaphan | 05-May-2026 | 06-May-2026 00:17:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 09:05:14 | 06-May-2026 09:23:32 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP02-PRO-UFD-0002 | PROCESS FLOW DIAGRAM DIESEL OIL, UTILITY WATER AND POWER SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:11:05 | zm167dc@jutal.com | 18-May-2026 20:41:05 | Jumpol Sudjitjul | 27-May-2026 | 27-May-2026 09:48:29 | Naphat Nirotsinlapachai | 28-May-2026 | 28-May-2026 08:01:57 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 20:59:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 10:11:28 | 11-Jun-2026 03:20:45 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP02-PRO-UFD-0002 | PROCESS FLOW DIAGRAM DIESEL OIL, UTILITY WATER AND POWER SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:16:19 | zm167dc@jutal.com | 24-Jul-2026 16:44:18 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:20:30 | Naphat Nirotsinlapachai | 06-Aug-2026 | 06-Aug-2026 22:50:04 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 06:02:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:13:21 | 07-Aug-2026 05:08:43 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP02-PRO-UFD-0003 | PROCESS FLOW DIAGRAM CHEMICAL INJECTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:49:41 | jumpols@pttep.com | 20-Apr-2026 17:25:41 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:29:03 | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 15:55:55 | Pornlert Wanaphattharaphan | 05-May-2026 | 06-May-2026 00:25:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 09:04:47 | 06-May-2026 09:22:33 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP02-PRO-UFD-0003 | PROCESS FLOW DIAGRAM CHEMICAL INJECTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:11:28 | zm167dc@jutal.com | 18-May-2026 20:40:47 | Jumpol Sudjitjul | 27-May-2026 | 27-May-2026 09:47:43 | Naphat Nirotsinlapachai | 28-May-2026 | 28-May-2026 08:02:23 | Pornlert Wanaphattharaphan | 29-May-2026 | 31-May-2026 15:17:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 31-May-2026 16:27:52 | 31-May-2026 09:52:59 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP02-PRO-UFD-0003 | PROCESS FLOW DIAGRAM CHEMICAL INJECTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:16:47 | zm167dc@jutal.com | 24-Jul-2026 16:44:36 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:20:25 | Naphat Nirotsinlapachai | 06-Aug-2026 | 06-Aug-2026 22:41:48 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 06:01:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:15:03 | 07-Aug-2026 05:10:01 | 0 |  |  | Approver | Locate
AO-000046 | MM-ASK-1A-WP02-PRO-UFD-0004 | PROCESS FLOW DIAGRAM VENT, OPEN DRAINS AND CLOSED DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 16:50:08 | jumpols@pttep.com | 20-Apr-2026 17:25:58 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 16:34:54 | Naphat Nirotsinlapachai | 30-Apr-2026 | 30-Apr-2026 15:56:54 | Pornlert Wanaphattharaphan | 05-May-2026 | 06-May-2026 00:35:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 09:06:13 | 06-May-2026 09:24:31 | 0 |  |  | Approver | Locate
AO-000273 | MM-ASK-1A-WP02-PRO-UFD-0004 | PROCESS FLOW DIAGRAM VENT, OPEN DRAINS AND CLOSED DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 15-May-2026 18:11:56 | zm167dc@jutal.com | 18-May-2026 20:40:28 | Jumpol Sudjitjul | 27-May-2026 | 27-May-2026 09:46:57 | Naphat Nirotsinlapachai | 28-May-2026 | 28-May-2026 08:03:00 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 20:59:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 10:13:12 | 11-Jun-2026 03:21:58 | 0 |  |  | Approver | Locate
AO-000776 | MM-ASK-1A-WP02-PRO-UFD-0004 | PROCESS FLOW DIAGRAM VENT, OPEN DRAINS AND CLOSED DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 16:17:13 | zm167dc@jutal.com | 24-Jul-2026 16:44:54 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:20:42 | Naphat Nirotsinlapachai | 06-Aug-2026 | 06-Aug-2026 22:52:12 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 06:02:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:15:37 | 07-Aug-2026 05:11:19 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0051 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:36:58 | zm167dc@jutal.com | 10-Jun-2026 14:52:56 | Jumpol Sudjitjul | 18-Jun-2026 | 22-Jun-2026 13:16:51 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 10:56:01 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 13:31:52 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 14:17:36 | 08-Jul-2026 07:50:38 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0051 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:04:25 | zm167dc@jutal.com | 06-Aug-2026 13:44:22 | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 00:45:18 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:22:50 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:19:31 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 14:52:59 | 27-Aug-2026 08:47:53 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0052 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:37:25 | zm167dc@jutal.com | 10-Jun-2026 14:53:31 | Jumpol Sudjitjul | 18-Jun-2026 | 22-Jun-2026 13:20:58 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:07:28 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 16:49:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 17:02:56 | 08-Jul-2026 10:23:29 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0052 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:04:54 | zm167dc@jutal.com | 06-Aug-2026 13:44:22 | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 00:43:48 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:19:55 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:15:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 17:34:15 | 27-Aug-2026 11:31:24 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP02-SAF-DWG-0053 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:57:55 | zm167dc@jutal.com | 11-Jun-2026 15:19:01 | Jumpol Sudjitjul | 19-Jun-2026 | 03-Jul-2026 13:34:43 | Jumpol Sudjitjul | 22-Jun-2026 | 08-Jul-2026 10:45:29 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 08-Jul-2026 23:05:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 09-Jul-2026 10:03:42 | 09-Jul-2026 04:04:25 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0053 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:05:19 | zm167dc@jutal.com | 06-Aug-2026 13:44:19 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:05:53 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:15:19 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:12:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 15:49:10 | 27-Aug-2026 10:43:54 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0054 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:37:54 | zm167dc@jutal.com | 10-Jun-2026 14:53:48 | Jumpol Sudjitjul | 18-Jun-2026 | 22-Jun-2026 13:25:24 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:10:48 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 16:49:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 19:39:12 | 08-Jul-2026 13:17:05 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0054 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:05:45 | zm167dc@jutal.com | 06-Aug-2026 13:44:19 | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 13:05:35 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:14:26 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:12:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 15:24:07 | 27-Aug-2026 08:52:02 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0055 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:38:20 | zm167dc@jutal.com | 10-Jun-2026 14:54:06 | Jumpol Sudjitjul | 18-Jun-2026 | 22-Jun-2026 13:28:05 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:15:57 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 16:50:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 19:39:40 | 08-Jul-2026 13:18:27 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0055 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:06:09 | zm167dc@jutal.com | 06-Aug-2026 13:44:22 | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 00:44:55 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:20:53 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:15:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 14:48:09 | 27-Aug-2026 08:45:37 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0056 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:38:47 | zm167dc@jutal.com | 10-Jun-2026 14:54:23 | Jumpol Sudjitjul | 18-Jun-2026 | 01-Jul-2026 07:54:46 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:21:13 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 16:53:50 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 19:40:20 | 08-Jul-2026 13:19:45 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0056 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:06:35 | zm167dc@jutal.com | 06-Aug-2026 13:44:25 | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 00:45:41 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:24:17 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:20:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 17:33:35 | 27-Aug-2026 11:30:05 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0057 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:39:11 | zm167dc@jutal.com | 10-Jun-2026 14:59:53 | Jumpol Sudjitjul | 18-Jun-2026 | 22-Jun-2026 13:52:13 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:23:04 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 16:54:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 19:40:52 | 08-Jul-2026 13:21:05 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0057 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING EAST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:07:02 | zm167dc@jutal.com | 06-Aug-2026 13:44:25 | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 00:44:32 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:25:12 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:22:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 17:35:34 | 27-Aug-2026 11:32:43 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0058 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:03:29 | zm167dc@jutal.com | 10-Jun-2026 14:18:18 | Jumpol Sudjitjul | 18-Jun-2026 | 22-Jun-2026 12:15:49 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:24:37 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 17:09:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 19:42:07 | 08-Jul-2026 13:23:45 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0058 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING NORTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:07:29 | zm167dc@jutal.com | 06-Aug-2026 13:44:20 | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 00:45:05 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:17:57 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:13:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 14:15:15 | 27-Aug-2026 07:39:11 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0059 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:39:36 | zm167dc@jutal.com | 10-Jun-2026 14:59:50 | Jumpol Sudjitjul | 18-Jun-2026 | 22-Jun-2026 14:05:36 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:26:31 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 22:01:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 09-Jul-2026 10:04:49 | 09-Jul-2026 03:33:16 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0059 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING WEST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:07:55 | zm167dc@jutal.com | 06-Aug-2026 13:44:25 | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 00:44:05 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:21:45 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:17:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 17:32:58 | 27-Aug-2026 11:28:50 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0060 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:40:00 | zm167dc@jutal.com | 10-Jun-2026 14:59:49 | Jumpol Sudjitjul | 18-Jun-2026 | 22-Jun-2026 13:34:21 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:29:04 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 22:10:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 09-Jul-2026 10:06:18 | 09-Jul-2026 03:34:50 | 0 |  |  | Approver | Locate
AO-000896 | MM-ASK-1A-WP02-SAF-DWG-0060 | HAZARDOUS AREA CLASSIFICATION DRAWING (NORMAL OPERATIONS) ELEVATION LOOKING SOUTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:08:21 | zm167dc@jutal.com | 06-Aug-2026 13:44:21 | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 00:43:38 | Pongsakorn Monturat | 18-Aug-2026 | 26-Aug-2026 17:18:52 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 27-Aug-2026 14:14:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 27-Aug-2026 15:52:35 | 27-Aug-2026 10:46:14 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0061 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:40:23 | zm167dc@jutal.com | 10-Jun-2026 14:59:49 | Jumpol Sudjitjul | 18-Jun-2026 | 28-Jun-2026 09:14:20 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:33:09 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 22:11:46 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 09-Jul-2026 10:07:37 | 09-Jul-2026 03:36:09 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0061 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 14:58:34 | zm167dc@jutal.com | 07-Aug-2026 15:12:02 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:45:25 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:18:19 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 23:04:58 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:44:22 | 29-Aug-2026 07:13:05 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0062 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:40:51 | zm167dc@jutal.com | 10-Jun-2026 14:59:49 | Jumpol Sudjitjul | 18-Jun-2026 | 28-Jun-2026 09:13:53 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 10:57:26 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 16:47:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 19:41:17 | 08-Jul-2026 13:22:27 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0062 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 14:59:02 | zm167dc@jutal.com | 07-Aug-2026 15:12:01 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:45:03 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:17:00 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 23:03:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:43:55 | 29-Aug-2026 07:11:58 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP02-SAF-DWG-0063 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:58:22 | zm167dc@jutal.com | 11-Jun-2026 15:19:45 | Jumpol Sudjitjul | 19-Jun-2026 | 03-Jul-2026 13:39:43 | Jumpol Sudjitjul | 22-Jun-2026 | 08-Jul-2026 10:58:46 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 08-Jul-2026 23:09:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 09-Jul-2026 10:10:08 | 09-Jul-2026 04:10:29 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0063 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 14:59:29 | zm167dc@jutal.com | 07-Aug-2026 15:12:04 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:43:47 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:10:51 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 22:47:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:45:16 | 29-Aug-2026 07:14:24 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0064 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:03:54 | zm167dc@jutal.com | 10-Jun-2026 14:18:18 | Jumpol Sudjitjul | 18-Jun-2026 | 28-Jun-2026 09:16:29 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:02:04 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 16:48:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 08-Jul-2026 19:42:43 | 08-Jul-2026 13:25:05 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0064 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 14:59:56 | zm167dc@jutal.com | 07-Aug-2026 15:12:03 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:44:12 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:12:20 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 22:52:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:45:50 | 29-Aug-2026 07:15:44 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0065 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:41:13 | zm167dc@jutal.com | 10-Jun-2026 14:59:48 | Jumpol Sudjitjul | 18-Jun-2026 | 28-Jun-2026 09:17:30 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:38:02 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 22:19:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 09-Jul-2026 10:11:28 | 09-Jul-2026 03:37:40 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0065 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:00:26 | zm167dc@jutal.com | 07-Aug-2026 15:12:03 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:46:07 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:29:29 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 23:09:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:47:05 | 29-Aug-2026 07:16:59 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0066 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:04:17 | zm167dc@jutal.com | 10-Jun-2026 14:18:18 | Jumpol Sudjitjul | 18-Jun-2026 | 28-Jun-2026 09:18:35 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:35:22 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 22:14:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 09-Jul-2026 10:11:21 | 09-Jul-2026 04:12:56 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0066 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:00:53 | zm167dc@jutal.com | 07-Aug-2026 15:12:02 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:45:48 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:28:26 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 23:06:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:47:48 | 29-Aug-2026 07:18:13 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0067 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:04:42 | zm167dc@jutal.com | 10-Jun-2026 14:18:17 | Jumpol Sudjitjul | 18-Jun-2026 | 28-Jun-2026 09:20:15 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:42:30 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 22:55:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 09-Jul-2026 10:08:07 | 09-Jul-2026 04:09:06 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0067 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING EAST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:01:24 | zm167dc@jutal.com | 07-Aug-2026 15:12:02 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:44:36 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:13:23 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 22:57:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:48:13 | 29-Aug-2026 07:19:32 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0068 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:05:08 | zm167dc@jutal.com | 10-Jun-2026 14:18:17 | Jumpol Sudjitjul | 18-Jun-2026 | 28-Jun-2026 09:21:14 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 11:47:34 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 22:56:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 09-Jul-2026 10:05:34 | 09-Jul-2026 04:05:38 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0068 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING NORTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:01:56 | zm167dc@jutal.com | 07-Aug-2026 15:12:05 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:46:47 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:31:11 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 23:39:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:48:38 | 29-Aug-2026 07:20:55 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0069 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:05:42 | zm167dc@jutal.com | 10-Jun-2026 14:18:17 | Jumpol Sudjitjul | 18-Jun-2026 | 28-Jun-2026 09:22:25 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 13:27:49 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 22:57:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 09-Jul-2026 10:06:34 | 09-Jul-2026 04:06:52 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0069 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING WEST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:02:25 | zm167dc@jutal.com | 07-Aug-2026 15:12:08 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:47:12 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:32:44 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 23:41:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:49:02 | 29-Aug-2026 07:22:13 | 0 |  |  | Approver | Locate
AO-000440 | MM-ASK-1A-WP02-SAF-DWG-0070 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 14:06:10 | zm167dc@jutal.com | 10-Jun-2026 14:18:20 | Jumpol Sudjitjul | 18-Jun-2026 | 28-Jun-2026 09:23:27 | Jumpol Sudjitjul | 19-Jun-2026 | 08-Jul-2026 14:14:59 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 08-Jul-2026 22:58:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 09-Jul-2026 10:00:18 | 09-Jul-2026 04:02:07 | 0 |  |  | Approver | Locate
AO-000910 | MM-ASK-1A-WP02-SAF-DWG-0070 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS) ELEVATION LOOKING SOUTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:02:53 | zm167dc@jutal.com | 07-Aug-2026 15:12:09 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:47:36 | Pongsakorn Monturat | 19-Aug-2026 | 28-Aug-2026 11:33:30 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 28-Aug-2026 23:54:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 29-Aug-2026 13:50:35 | 29-Aug-2026 07:23:30 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0135 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:56:59 | zm167dc@jutal.com | 18-Jun-2026 14:12:18 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:38:26 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:28:38 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 09:41:35 | APPR | Approved | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:20:44 | 12-Jul-2026 05:01:43 | 0 |  |  | Approver | Locate
AO-000940 | MM-ASK-1A-WP02-SAF-DWG-0135 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:30:16 | zm167dc@jutal.com | 10-Aug-2026 15:30:38 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:46:06 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 16:07:43 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 16:32:56 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 30-Aug-2026 16:04:17 | 30-Aug-2026 09:40:00 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0136 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:57:28 | zm167dc@jutal.com | 18-Jun-2026 14:14:36 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:39:34 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:29:49 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 10:06:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:22:43 | 12-Jul-2026 05:05:32 | 0 |  |  | Approver | Locate
AO-000934 | MM-ASK-1A-WP02-SAF-DWG-0136 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:31:07 | zm167dc@jutal.com | 10-Aug-2026 15:30:32 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:46:36 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 15:59:39 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 13:30:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 29-Aug-2026 13:51:32 | 29-Aug-2026 07:00:37 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0137 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:57:59 | zm167dc@jutal.com | 18-Jun-2026 14:14:58 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:40:46 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:30:44 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 10:16:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:23:17 | 12-Jul-2026 05:06:46 | 0 |  |  | Approver | Locate
AO-000934 | MM-ASK-1A-WP02-SAF-DWG-0137 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:31:41 | zm167dc@jutal.com | 10-Aug-2026 15:30:27 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:46:50 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 16:01:54 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 13:42:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 29-Aug-2026 13:52:45 | 29-Aug-2026 07:01:57 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0138 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:58:29 | zm167dc@jutal.com | 18-Jun-2026 14:15:21 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:54:11 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:31:47 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 10:24:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:23:46 | 12-Jul-2026 05:07:59 | 0 |  |  | Approver | Locate
AO-000934 | MM-ASK-1A-WP02-SAF-DWG-0138 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:32:20 | zm167dc@jutal.com | 10-Aug-2026 15:30:37 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:45:23 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 16:07:00 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 16:28:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 30-Aug-2026 16:27:36 | 30-Aug-2026 10:04:44 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0139 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:58:59 | zm167dc@jutal.com | 18-Jun-2026 14:15:48 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:46:22 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:33:05 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 10:34:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:24:15 | 12-Jul-2026 05:09:12 | 0 |  |  | Approver | Locate
AO-000934 | MM-ASK-1A-WP02-SAF-DWG-0139 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:32:54 | zm167dc@jutal.com | 10-Aug-2026 15:30:28 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:47:27 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 16:00:50 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 13:31:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 29-Aug-2026 13:55:06 | 29-Aug-2026 07:03:16 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0140 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 13:59:31 | zm167dc@jutal.com | 18-Jun-2026 14:16:10 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:44:40 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:34:01 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 10:39:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:24:50 | 12-Jul-2026 05:10:28 | 0 |  |  | Approver | Locate
AO-000934 | MM-ASK-1A-WP02-SAF-DWG-0140 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:33:26 | zm167dc@jutal.com | 10-Aug-2026 15:30:31 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:46:18 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 15:58:39 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 28-Aug-2026 23:57:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 29-Aug-2026 13:55:34 | 29-Aug-2026 07:05:54 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0141 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 14:00:06 | zm167dc@jutal.com | 18-Jun-2026 14:18:26 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:41:34 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:34:49 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 11:13:34 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:25:18 | 12-Jul-2026 05:11:44 | 0 |  |  | Approver | Locate
AO-000934 | MM-ASK-1A-WP02-SAF-DWG-0141 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING EAST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:34:01 | zm167dc@jutal.com | 10-Aug-2026 15:30:30 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:47:06 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 16:02:44 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 13:44:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 29-Aug-2026 13:55:30 | 29-Aug-2026 07:04:37 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0142 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 14:00:40 | zm167dc@jutal.com | 18-Jun-2026 14:19:32 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:43:50 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:35:09 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 11:19:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:25:47 | 12-Jul-2026 05:12:59 | 0 |  |  | Approver | Locate
AO-000934 | MM-ASK-1A-WP02-SAF-DWG-0142 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING NORTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:34:33 | zm167dc@jutal.com | 10-Aug-2026 15:30:33 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:47:33 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 16:05:46 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 16:24:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 30-Aug-2026 16:28:48 | 30-Aug-2026 10:06:00 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0143 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 14:01:05 | zm167dc@jutal.com | 18-Jun-2026 14:20:02 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:42:56 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:35:30 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 11:25:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:26:19 | 12-Jul-2026 05:14:11 | 0 |  |  | Approver | Locate
AO-000934 | MM-ASK-1A-WP02-SAF-DWG-0143 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING WEST |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:35:03 | zm167dc@jutal.com | 10-Aug-2026 15:30:34 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:47:53 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 16:03:30 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 15:20:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 30-Aug-2026 16:31:36 | 30-Aug-2026 10:08:33 | 0 |  |  | Approver | Locate
AO-000502 | MM-ASK-1A-WP02-SAF-DWG-0144 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 14:01:31 | zm167dc@jutal.com | 18-Jun-2026 14:20:33 | Jumpol Sudjitjul | 26-Jun-2026 | 08-Jul-2026 13:42:08 | Pongsakorn Monturat | 29-Jun-2026 | 10-Jul-2026 11:35:52 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 11-Jul-2026 11:28:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 12-Jul-2026 11:26:45 | 12-Jul-2026 05:15:25 | 0 |  |  | Approver | Locate
AO-000934 | MM-ASK-1A-WP02-SAF-DWG-0144 | HAZARDOUS AREA CLASSIFICATION DRAWING (SIMOPS-WELL SERVICE) ELEVATION LOOKING SOUTH |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:35:34 | zm167dc@jutal.com | 10-Aug-2026 15:30:35 | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 21:48:04 | Pongsakorn Monturat | 20-Aug-2026 | 28-Aug-2026 16:04:22 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 16:11:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 30-Aug-2026 16:24:56 | 30-Aug-2026 10:02:08 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP02-SAF-LAY-0077 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:33:15 | zm167dc@jutal.com | 05-Jun-2026 14:52:17 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:38:31 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:39:06 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 24-Jun-2026 00:21:00 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 24-Jun-2026 08:25:46 | 24-Jun-2026 01:58:05 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP02-SAF-LAY-0077 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:49:31 | zm167dc@jutal.com | 13-Aug-2026 13:49:25 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:51:53 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 22:58:36 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 03-Sep-2026 10:42:58 | 03-Sep-2026 04:55:17 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP02-SAF-LAY-0078 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:33:38 | zm167dc@jutal.com | 05-Jun-2026 14:52:56 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:38:56 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:43:42 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 24-Jun-2026 00:15:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 24-Jun-2026 08:26:16 | 24-Jun-2026 01:59:19 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP02-SAF-LAY-0078 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:50:22 | zm167dc@jutal.com | 13-Aug-2026 13:49:46 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:51:25 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 22:57:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 03-Sep-2026 10:45:39 | 03-Sep-2026 05:31:58 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP02-SAF-LAY-0079 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:34:01 | zm167dc@jutal.com | 05-Jun-2026 14:53:19 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:39:22 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:46:01 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 24-Jun-2026 00:10:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 24-Jun-2026 08:26:48 | 24-Jun-2026 02:00:32 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP02-SAF-LAY-0079 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:51:05 | zm167dc@jutal.com | 13-Aug-2026 13:50:08 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:41:11 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 22:51:10 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 03-Sep-2026 10:32:23 | 03-Sep-2026 05:05:16 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP02-SAF-LAY-0080 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:34:26 | zm167dc@jutal.com | 05-Jun-2026 14:47:35 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:37:31 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:32:02 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 24-Jun-2026 00:25:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 24-Jun-2026 08:27:17 | 24-Jun-2026 02:01:50 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP02-SAF-LAY-0080 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:51:47 | zm167dc@jutal.com | 13-Aug-2026 13:50:30 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:40:32 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 02-Sep-2026 00:02:05 | APPR | Approved | Soontaree Simpitak | 26-Aug-2026 | 02-Sep-2026 10:23:59 | 02-Sep-2026 03:52:51 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP02-SAF-LAY-0081 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:34:49 | zm167dc@jutal.com | 05-Jun-2026 14:47:14 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:37:06 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:29:06 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 24-Jun-2026 00:27:20 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 24-Jun-2026 08:28:20 | 24-Jun-2026 02:15:11 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP02-SAF-LAY-0081 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:52:24 | zm167dc@jutal.com | 13-Aug-2026 13:50:53 | Jumpol Sudjitjul | 21-Aug-2026 |  | Pongsakorn Monturat | 24-Aug-2026 | 31-Aug-2026 14:39:53 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 01-Sep-2026 23:53:25 | APPR | Approved | Soontaree Simpitak | 26-Aug-2026 | 02-Sep-2026 10:24:45 | 02-Sep-2026 03:54:12 | 0 |  |  | Approver | Locate
AO-000405 | MM-ASK-1A-WP02-SAF-LAY-0082 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 21:35:12 | zm167dc@jutal.com | 05-Jun-2026 14:46:53 | Jumpol Sudjitjul | 15-Jun-2026 | 21-Jun-2026 19:36:39 | Warayut Ubolcharoen | 16-Jun-2026 | 21-Jun-2026 17:26:26 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 24-Jun-2026 00:38:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 24-Jun-2026 08:56:46 | 24-Jun-2026 02:19:34 | 0 |  |  | Approver | Locate
AO-000962 | MM-ASK-1A-WP02-SAF-LAY-0082 | ESCAPE ROUTES, LIFESAVING EQUIPMENT & SAFETY EQUIPMENT LAYOUT BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 08:53:01 | zm167dc@jutal.com | 13-Aug-2026 17:16:37 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 31-Aug-2026 14:39:29 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 02-Sep-2026 23:12:53 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 03-Sep-2026 10:30:04 | 03-Sep-2026 03:51:30 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP02-SAF-LAY-0089 | FIREFIGHTING EQUIPMENT LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:18:23 | zm167dc@jutal.com | 10-Jun-2026 09:24:13 | Jumpol Sudjitjul | 18-Jun-2026 | 12-Jun-2026 14:39:28 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:12:39 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 21:52:32 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 13:05:43 | 25-Jun-2026 06:15:56 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP02-SAF-LAY-0089 | FIREFIGHTING EQUIPMENT LAYOUT DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:47:17 | zm167dc@jutal.com | 23-Jul-2026 17:02:51 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 19-Aug-2026 20:23:22 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:20:15 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:50:44 | 20-Aug-2026 13:19:39 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP02-SAF-LAY-0089 | FIREFIGHTING EQUIPMENT LAYOUT DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:19:05 | zm167dc@jutal.com | 20-Sep-2026 14:09:37 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP02-SAF-LAY-0090 | FIREFIGHTING EQUIPMENT LAYOUT UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:19:01 | zm167dc@jutal.com | 10-Jun-2026 09:24:17 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 20:43:00 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:21:25 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 21:56:56 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 13:08:08 | 25-Jun-2026 06:17:23 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP02-SAF-LAY-0090 | FIREFIGHTING EQUIPMENT LAYOUT UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:47:42 | zm167dc@jutal.com | 23-Jul-2026 17:06:00 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 19-Aug-2026 20:23:49 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:21:07 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:51:09 | 20-Aug-2026 13:20:48 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP02-SAF-LAY-0090 | FIREFIGHTING EQUIPMENT LAYOUT UPPER DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:19:36 | zm167dc@jutal.com | 20-Sep-2026 14:09:37 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP02-SAF-LAY-0091 | FIREFIGHTING EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:19:29 | zm167dc@jutal.com | 10-Jun-2026 09:24:13 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 20:39:20 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:14:57 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 21:54:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 13:10:36 | 25-Jun-2026 06:20:15 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP02-SAF-LAY-0091 | FIREFIGHTING EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:48:08 | zm167dc@jutal.com | 23-Jul-2026 17:06:32 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 19-Aug-2026 20:24:19 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:22:29 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:51:35 | 20-Aug-2026 13:21:58 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP02-SAF-LAY-0091 | FIREFIGHTING EQUIPMENT LAYOUT MEZZANINE DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:20:02 | zm167dc@jutal.com | 20-Sep-2026 14:09:38 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP02-SAF-LAY-0092 | FIREFIGHTING EQUIPMENT LAYOUT LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:19:58 | zm167dc@jutal.com | 10-Jun-2026 09:24:17 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 20:41:30 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:17:06 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 21:56:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 13:11:22 | 25-Jun-2026 06:51:04 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP02-SAF-LAY-0092 | FIREFIGHTING EQUIPMENT LAYOUT LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:48:35 | zm167dc@jutal.com | 23-Jul-2026 17:06:58 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 19-Aug-2026 20:24:59 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:23:27 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:47:31 | 20-Aug-2026 13:18:27 | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP02-SAF-LAY-0093 | FIREFIGHTING EQUIPMENT LAYOUT SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:20:27 | zm167dc@jutal.com | 10-Jun-2026 09:24:16 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 20:40:38 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:18:42 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 21:57:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 13:12:04 | 25-Jun-2026 06:52:42 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP02-SAF-LAY-0093 | FIREFIGHTING EQUIPMENT LAYOUT SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:49:06 | zm167dc@jutal.com | 23-Jul-2026 17:07:24 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 19-Aug-2026 20:26:15 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:24:16 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:51:54 | 20-Aug-2026 13:24:15 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP02-SAF-LAY-0093 | FIREFIGHTING EQUIPMENT LAYOUT SUMP DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:20:28 | zm167dc@jutal.com | 20-Sep-2026 14:09:39 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000435 | MM-ASK-1A-WP02-SAF-LAY-0094 | FIREFIGHTING EQUIPMENT LAYOUT BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:20:55 | zm167dc@jutal.com | 10-Jun-2026 09:24:14 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 20:42:18 | Warayut Ubolcharoen | 19-Jun-2026 | 21-Jun-2026 19:10:59 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 21:58:19 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 13:15:31 | 25-Jun-2026 07:36:37 | 0 |  |  | Approver | Locate
AO-000765 | MM-ASK-1A-WP02-SAF-LAY-0094 | FIREFIGHTING EQUIPMENT LAYOUT BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 16:49:36 | zm167dc@jutal.com | 23-Jul-2026 17:07:48 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 19-Aug-2026 20:27:00 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:25:05 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:51:31 | 20-Aug-2026 13:23:05 | 0 |  |  | Approver | Locate
AO-001499 | MM-ASK-1A-WP02-SAF-LAY-0094 | FIREFIGHTING EQUIPMENT LAYOUT BOAT LANDING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 20:20:56 | zm167dc@jutal.com | 20-Sep-2026 14:09:39 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP02-SAF-LAY-0101 | SAFETY SIGNS LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 15:24:30 | zm167dc@jutal.com | 26-Jun-2026 16:31:56 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 16-Jul-2026 14:43:39 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 16-Jul-2026 22:12:34 | APPR | Approved | Jumpol Sudjitjul | 09-Jul-2026 | 17-Jul-2026 09:49:14 | 17-Jul-2026 03:15:35 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP02-SAF-LAY-0101 | SAFETY SIGNS LAYOUT DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:31:35 | zm167dc@jutal.com | 14-Aug-2026 15:40:35 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 13:07:28 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 21:58:13 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:17:27 | 08-Sep-2026 07:14:00 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP02-SAF-LAY-0102 | SAFETY SIGNS LAYOUT UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 15:25:00 | zm167dc@jutal.com | 26-Jun-2026 16:31:54 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 16-Jul-2026 14:44:58 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 16-Jul-2026 22:13:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 17-Jul-2026 09:45:24 | 17-Jul-2026 03:13:36 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP02-SAF-LAY-0102 | SAFETY SIGNS LAYOUT UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:32:04 | zm167dc@jutal.com | 14-Aug-2026 15:40:41 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 13:06:52 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 21:55:11 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:16:47 | 08-Sep-2026 07:12:48 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP02-SAF-LAY-0103 | SAFETY SIGNS LAYOUT MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 15:25:35 | zm167dc@jutal.com | 26-Jun-2026 16:31:57 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 16-Jul-2026 14:43:12 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 16-Jul-2026 22:12:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 17-Jul-2026 09:44:19 | 17-Jul-2026 03:10:35 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP02-SAF-LAY-0103 | SAFETY SIGNS LAYOUT MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:32:32 | zm167dc@jutal.com | 14-Aug-2026 15:40:35 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 13:04:41 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 21:44:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:16:12 | 08-Sep-2026 07:11:36 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP02-SAF-LAY-0104 | SAFETY SIGNS LAYOUT LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 15:26:02 | zm167dc@jutal.com | 26-Jun-2026 16:32:01 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 16-Jul-2026 14:49:44 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 16-Jul-2026 22:16:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 17-Jul-2026 09:43:22 | 17-Jul-2026 03:09:22 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP02-SAF-LAY-0104 | SAFETY SIGNS LAYOUT LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:33:00 | zm167dc@jutal.com | 14-Aug-2026 15:40:32 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 13:05:55 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 21:45:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:15:23 | 08-Sep-2026 07:10:12 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP02-SAF-LAY-0105 | SAFETY SIGNS LAYOUT SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 14:43:26 | zm167dc@jutal.com | 26-Jun-2026 16:31:57 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 16-Jul-2026 14:55:57 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 16-Jul-2026 22:16:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 17-Jul-2026 09:42:53 | 17-Jul-2026 03:44:33 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP02-SAF-LAY-0105 | SAFETY SIGNS LAYOUT SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:33:28 | zm167dc@jutal.com | 14-Aug-2026 15:40:33 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 13:07:10 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 21:57:03 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:14:10 | 08-Sep-2026 07:08:38 | 0 |  |  | Approver | Locate
AO-000557 | MM-ASK-1A-WP02-SAF-LAY-0106 | SAFETY SIGNS LAYOUT BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 14:43:56 | zm167dc@jutal.com | 26-Jun-2026 16:32:02 | Jumpol Sudjitjul | 06-Jul-2026 |  | Pongsakorn Monturat | 07-Jul-2026 | 16-Jul-2026 14:46:42 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 16-Jul-2026 22:15:32 | APPR | Approved | Jumpol Sudjitjul | 09-Jul-2026 | 17-Jul-2026 09:42:17 | 17-Jul-2026 03:43:22 | 0 |  |  | Approver | Locate
AO-000985 | MM-ASK-1A-WP02-SAF-LAY-0106 | SAFETY SIGNS LAYOUT BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 15:34:02 | zm167dc@jutal.com | 14-Aug-2026 15:40:37 | Jumpol Sudjitjul | 24-Aug-2026 |  | Pongsakorn Monturat | 25-Aug-2026 | 07-Sep-2026 13:06:35 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 07-Sep-2026 21:53:09 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 08-Sep-2026 13:13:21 | 08-Sep-2026 07:07:24 | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP02-SAF-LAY-0113 | FIRE AND GAS DETECTOR LAYOUTS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:57:45 | zm167dc@jutal.com | 30-Jun-2026 15:53:42 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:58:01 | Pongsakorn Monturat | 09-Jul-2026 | 20-Jul-2026 14:21:42 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 22-Jul-2026 13:09:49 | APPR | Approved | Jumpol Sudjitjul | 13-Jul-2026 | 22-Jul-2026 13:16:20 | 22-Jul-2026 06:21:53 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-SAF-LAY-0113 | FIRE AND GAS DETECTOR LAYOUTS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:06:29 | zm167dc@jutal.com | 24-Jul-2026 16:08:42 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 17:10:12 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:15:17 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:51:01 | 20-Aug-2026 13:17:16 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP02-SAF-LAY-0113 | FIRE AND GAS DETECTOR LAYOUTS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:54:24 | zm167dc@jutal.com | 18-Sep-2026 16:53:12 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP02-SAF-LAY-0114 | FIRE AND GAS DETECTOR LAYOUT UPPER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:58:18 | zm167dc@jutal.com | 30-Jun-2026 15:53:45 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:57:38 | Pongsakorn Monturat | 09-Jul-2026 | 20-Jul-2026 14:22:11 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 22-Jul-2026 16:34:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 22-Jul-2026 16:38:26 | 22-Jul-2026 10:49:18 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-SAF-LAY-0114 | FIRE AND GAS DETECTOR LAYOUT UPPER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:56:59 | zm167dc@jutal.com | 24-Jul-2026 16:08:44 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 17:11:10 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:19:14 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:50:35 | 20-Aug-2026 13:43:23 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP02-SAF-LAY-0114 | FIRE AND GAS DETECTOR LAYOUT UPPER DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:54:54 | zm167dc@jutal.com | 18-Sep-2026 16:53:12 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP02-SAF-LAY-0115 | FIRE AND GAS DETECTOR LAYOUT MEZZANINE DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:58:49 | zm167dc@jutal.com | 30-Jun-2026 15:53:43 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:57:18 | Pongsakorn Monturat | 09-Jul-2026 | 20-Jul-2026 14:23:17 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 22-Jul-2026 16:35:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 22-Jul-2026 16:37:01 | 22-Jul-2026 10:53:30 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-SAF-LAY-0115 | FIRE AND GAS DETECTOR LAYOUT MEZZANINE DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:57:28 | zm167dc@jutal.com | 24-Jul-2026 16:08:44 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 17:11:55 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:18:13 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:50:07 | 20-Aug-2026 13:42:10 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP02-SAF-LAY-0115 | FIRE AND GAS DETECTOR LAYOUT MEZZANINE DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:55:21 | zm167dc@jutal.com | 18-Sep-2026 16:53:15 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP02-SAF-LAY-0116 | FIRE AND GAS DETECTOR LAYOUT LOWER DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:59:18 | zm167dc@jutal.com | 30-Jun-2026 15:53:41 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:56:19 | Pongsakorn Monturat | 09-Jul-2026 | 20-Jul-2026 14:24:57 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 22-Jul-2026 16:41:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 22-Jul-2026 16:57:53 | 22-Jul-2026 10:54:39 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-SAF-LAY-0116 | FIRE AND GAS DETECTOR LAYOUT LOWER DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:57:59 | zm167dc@jutal.com | 24-Jul-2026 16:08:43 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 17:12:43 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:16:08 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:49:38 | 20-Aug-2026 13:41:02 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP02-SAF-LAY-0116 | FIRE AND GAS DETECTOR LAYOUT LOWER DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:55:48 | zm167dc@jutal.com | 18-Sep-2026 16:53:13 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP02-SAF-LAY-0117 | FIRE AND GAS DETECTOR LAYOUT SUMP DECK PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:59:55 | zm167dc@jutal.com | 30-Jun-2026 15:53:36 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:56:41 | Pongsakorn Monturat | 09-Jul-2026 | 20-Jul-2026 14:25:30 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 22-Jul-2026 16:53:00 | APPR | Approved | Jumpol Sudjitjul | 13-Jul-2026 | 22-Jul-2026 17:02:53 | 22-Jul-2026 10:52:16 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-SAF-LAY-0117 | FIRE AND GAS DETECTOR LAYOUT SUMP DECK PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:58:25 | zm167dc@jutal.com | 24-Jul-2026 16:08:45 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 17:13:21 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:14:32 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:49:15 | 20-Aug-2026 13:39:51 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP02-SAF-LAY-0117 | FIRE AND GAS DETECTOR LAYOUT SUMP DECK PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:56:13 | zm167dc@jutal.com | 18-Sep-2026 16:53:13 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP02-SAF-LAY-0118 | FIRE AND GAS DETECTOR LAYOUT BOAT LANDING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 15:00:30 | zm167dc@jutal.com | 30-Jun-2026 15:53:41 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 17:56:59 | Pongsakorn Monturat | 09-Jul-2026 | 20-Jul-2026 14:26:12 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 22-Jul-2026 16:56:57 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 13-Jul-2026 | 22-Jul-2026 16:58:52 | 22-Jul-2026 10:55:51 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-SAF-LAY-0118 | FIRE AND GAS DETECTOR LAYOUT BOAT LANDING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 14:58:58 | zm167dc@jutal.com | 24-Jul-2026 16:08:46 | Jumpol Sudjitjul | 05-Aug-2026 |  | Pongsakorn Monturat | 06-Aug-2026 | 18-Aug-2026 17:14:02 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 20-Aug-2026 16:17:07 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 20-Aug-2026 19:48:52 | 20-Aug-2026 13:38:39 | 0 |  |  | Approver | Locate
AO-001484 | MM-ASK-1A-WP02-SAF-LAY-0118 | FIRE AND GAS DETECTOR LAYOUT BOAT LANDING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 15:56:38 | zm167dc@jutal.com | 18-Sep-2026 16:53:12 | Jumpol Sudjitjul | 28-Sep-2026 |  | Pongsakorn Monturat | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WP02-STR-DWG-1001 | WP02 TOPSIDE DRAWING INDEX SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:34:02 | zm167dc@jutal.com | 14-Aug-2026 08:39:53 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 08:57:10 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:51:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:20:30 | 28-Aug-2026 03:46:10 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WP02-STR-DWG-1002 | WP02 TOPSIDE DRAWING INDEX SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:34:25 | zm167dc@jutal.com | 14-Aug-2026 08:40:13 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 09:05:30 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:51:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:21:45 | 28-Aug-2026 03:47:23 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1011 | WP02 TOPSIDE DECK LOADING DIAGRAMS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:29:36 | zm167dc@jutal.com | 21-May-2026 09:41:43 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 07:49:55 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:27:18 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:20:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 17:11:39 | 31-May-2026 17:25:41 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1011 | WP02 TOPSIDE DECK LOADING DIAGRAMS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:00:52 | zm167dc@jutal.com | 13-Jun-2026 08:12:00 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:30:09 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:28:35 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:48:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:18:43 | 23-Jun-2026 01:39:55 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1011 | WP02 TOPSIDE DECK LOADING DIAGRAMS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:30:37 | zm167dc@jutal.com | 17-Jul-2026 21:51:55 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:12:45 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:07:29 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:09:09 | 27-Jul-2026 08:07:31 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1101 | WP02 TOPSIDE - UPPER DECK PRIMARY STEEL FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:30:03 | zm167dc@jutal.com | 21-May-2026 09:41:42 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 07:41:19 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:29:24 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:34:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 17:59:16 | 31-May-2026 18:27:54 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP02-STR-DWG-1101 | WP02 TOPSIDE - UPPER DECK PRIMARY STEEL FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:57:42 | zm167dc@jutal.com | 13-Jun-2026 07:12:33 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:56:08 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:31:03 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:43:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:19:11 | 23-Jun-2026 01:55:19 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1101 | WP02 TOPSIDE - UPPER DECK PRIMARY STEEL FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:31:02 | zm167dc@jutal.com | 17-Jul-2026 21:51:55 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:15:14 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 15:22:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:29:36 | 27-Jul-2026 08:17:09 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1102 | WP02 TOPSIDE - LOWER DECK PRIMARY STEEL FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:30:28 | zm167dc@jutal.com | 21-May-2026 09:41:45 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 07:55:05 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:31:29 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:35:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:00:18 | 31-May-2026 18:28:56 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP02-STR-DWG-1102 | WP02 TOPSIDE - LOWER DECK PRIMARY STEEL FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:58:07 | zm167dc@jutal.com | 13-Jun-2026 07:12:48 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:57:32 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:33:20 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:19:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:19:39 | 23-Jun-2026 01:56:32 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1102 | WP02 TOPSIDE - LOWER DECK PRIMARY STEEL FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:31:25 | zm167dc@jutal.com | 17-Jul-2026 21:51:55 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:17:03 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 15:23:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:30:20 | 27-Jul-2026 08:21:02 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1103 | WP02 TOPSIDE - ELEVATION TRUSS ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:30:54 | zm167dc@jutal.com | 21-May-2026 09:41:49 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 07:55:34 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:33:25 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:36:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:01:21 | 31-May-2026 18:29:55 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP02-STR-DWG-1103 | WP02 TOPSIDE - ELEVATION TRUSS ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:03:24 | zm167dc@jutal.com | 10-Jun-2026 13:03:01 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 16:08:45 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:38:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:43:33 | 19-Jun-2026 05:27:21 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1103 | WP02 TOPSIDE - ELEVATION TRUSS ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:31:50 | zm167dc@jutal.com | 17-Jul-2026 21:51:55 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:21:30 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 15:23:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:32:36 | 27-Jul-2026 08:24:53 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1104 | WP02 TOPSIDE - ELEVATION TRUSS ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:31:23 | zm167dc@jutal.com | 21-May-2026 09:41:42 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 07:38:50 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:35:29 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:37:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:01:53 | 31-May-2026 18:30:56 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP02-STR-DWG-1104 | WP02 TOPSIDE - ELEVATION TRUSS ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:03:51 | zm167dc@jutal.com | 10-Jun-2026 13:03:01 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 16:10:21 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:39:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:43:57 | 19-Jun-2026 05:29:57 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1104 | WP02 TOPSIDE - ELEVATION TRUSS ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:32:13 | zm167dc@jutal.com | 17-Jul-2026 21:51:55 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:23:38 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 15:24:35 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:31:13 | 27-Jul-2026 08:22:15 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1105 | WP02 TOPSIDE - ELEVATION TRUSS ROW '1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:31:52 | zm167dc@jutal.com | 21-May-2026 09:41:43 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 07:46:02 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:37:42 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:40:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:02:25 | 31-May-2026 18:31:54 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP02-STR-DWG-1105 | WP02 TOPSIDE - ELEVATION TRUSS ROW '1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:04:19 | zm167dc@jutal.com | 10-Jun-2026 13:03:03 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 16:12:01 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:40:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:44:33 | 19-Jun-2026 05:32:27 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1105 | WP02 TOPSIDE - ELEVATION TRUSS ROW '1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:32:37 | zm167dc@jutal.com | 17-Jul-2026 21:51:55 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:25:34 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 15:25:16 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:34:02 | 27-Jul-2026 08:26:03 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1106 | WP02 TOPSIDE - ELEVATION TRUSS ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:32:24 | zm167dc@jutal.com | 21-May-2026 09:47:39 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:01:04 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:40:37 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:43:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:02:55 | 31-May-2026 18:32:58 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP02-STR-DWG-1106 | WP02 TOPSIDE - ELEVATION TRUSS ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:04:57 | zm167dc@jutal.com | 10-Jun-2026 13:03:06 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 16:13:50 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:40:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:44:57 | 19-Jun-2026 05:34:56 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1106 | WP02 TOPSIDE - ELEVATION TRUSS ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:33:02 | zm167dc@jutal.com | 17-Jul-2026 21:51:56 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:28:24 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 15:25:48 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:34:45 | 27-Jul-2026 08:27:12 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1107 | WP02 TOPSIDE - SECTIONS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:32:53 | zm167dc@jutal.com | 21-May-2026 09:47:53 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:03:32 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:42:51 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:46:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:03:39 | 31-May-2026 18:33:59 | 0 |  |  | Approver | Locate
AO-000439 | MM-ASK-1A-WP02-STR-DWG-1107 | WP02 TOPSIDE - SECTIONS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 12:05:28 | zm167dc@jutal.com | 10-Jun-2026 13:03:00 | Jumpol Sudjitjul | 18-Jun-2026 |  | Washira Kaew-amatawong | 19-Jun-2026 | 16-Jun-2026 16:15:14 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:41:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:44:53 | 19-Jun-2026 05:33:41 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1107 | WP02 TOPSIDE - SECTIONS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:33:24 | zm167dc@jutal.com | 17-Jul-2026 21:52:05 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:30:11 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 15:26:27 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:35:24 | 27-Jul-2026 08:28:19 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1108 | WP02 TOPSIDE - SECTIONS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:33:17 | zm167dc@jutal.com | 21-May-2026 09:48:09 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:05:28 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:44:34 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:46:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:04:07 | 31-May-2026 18:35:02 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP02-STR-DWG-1108 | WP02 TOPSIDE - SECTIONS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:58:32 | zm167dc@jutal.com | 13-Jun-2026 07:13:01 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 00:59:08 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:35:24 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:20:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:20:08 | 23-Jun-2026 01:57:43 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1108 | WP02 TOPSIDE - SECTIONS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:33:47 | zm167dc@jutal.com | 17-Jul-2026 21:51:56 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:31:31 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 15:27:15 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:27:19 | 27-Jul-2026 08:12:17 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1121 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:33:42 | zm167dc@jutal.com | 21-May-2026 13:37:58 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:07:40 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:49:04 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:47:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:04:39 | 31-May-2026 18:36:02 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP02-STR-DWG-1121 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:58:56 | zm167dc@jutal.com | 13-Jun-2026 07:13:53 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 01:00:10 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:37:14 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:22:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:20:34 | 23-Jun-2026 01:59:00 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1121 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:34:11 | zm167dc@jutal.com | 17-Jul-2026 21:53:42 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:32:46 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 21:55:23 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:35:55 | 27-Jul-2026 08:29:30 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1122 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:34:09 | zm167dc@jutal.com | 21-May-2026 13:38:21 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:08:19 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:50:47 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:51:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:05:10 | 31-May-2026 18:37:03 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP02-STR-DWG-1122 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:59:20 | zm167dc@jutal.com | 13-Jun-2026 07:14:06 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 01:02:14 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:39:29 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:31:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:21:02 | 23-Jun-2026 02:00:14 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1122 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:34:33 | zm167dc@jutal.com | 17-Jul-2026 21:53:41 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:34:21 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 21:57:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:20:07 | 27-Jul-2026 08:11:08 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1123 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:34:37 | zm167dc@jutal.com | 21-May-2026 13:38:42 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:11:34 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:52:35 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:50:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:05:41 | 31-May-2026 18:38:03 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP02-STR-DWG-1123 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 17:59:44 | zm167dc@jutal.com | 13-Jun-2026 07:14:18 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 01:02:48 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:41:20 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:30:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:22:00 | 23-Jun-2026 02:01:30 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1123 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:34:57 | zm167dc@jutal.com | 17-Jul-2026 21:53:38 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 15:36:29 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 21:57:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:31:53 | 27-Jul-2026 08:23:32 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1124 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:35:03 | zm167dc@jutal.com | 21-May-2026 13:38:59 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:12:58 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:55:01 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:53:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:06:15 | 31-May-2026 18:39:02 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP02-STR-DWG-1124 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 18:00:08 | zm167dc@jutal.com | 13-Jun-2026 07:14:32 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 01:08:07 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:42:48 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:32:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:24:29 | 23-Jun-2026 02:03:51 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1124 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:35:21 | zm167dc@jutal.com | 17-Jul-2026 21:53:44 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 22-Jul-2026 16:36:46 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 21:58:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:29:39 | 27-Jul-2026 08:18:27 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1125 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:35:26 | zm167dc@jutal.com | 21-May-2026 13:39:12 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:15:41 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:57:03 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:55:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:06:45 | 31-May-2026 18:40:05 | 0 |  |  | Approver | Locate
AO-000472 | MM-ASK-1A-WP02-STR-DWG-1125 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 18:00:32 | zm167dc@jutal.com | 13-Jun-2026 07:14:50 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 01:08:45 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:44:12 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:28:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:33:35 | 22-Jun-2026 07:59:37 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1125 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 5 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:35:45 | zm167dc@jutal.com | 17-Jul-2026 21:53:48 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 06:54:34 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 21:59:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:36:41 | 27-Jul-2026 08:30:50 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1126 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:35:52 | zm167dc@jutal.com | 21-May-2026 13:44:44 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 15:58:57 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:56:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:07:13 | 31-May-2026 18:41:05 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1126 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:01:16 | zm167dc@jutal.com | 13-Jun-2026 08:13:59 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:35:38 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:45:31 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:46:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:24:51 | 23-Jun-2026 01:41:09 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1126 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 6 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:36:09 | zm167dc@jutal.com | 17-Jul-2026 21:53:45 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 06:56:01 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:00:01 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:28:55 | 27-Jul-2026 08:15:43 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1127 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:36:16 | zm167dc@jutal.com | 21-May-2026 13:44:58 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 16:01:25 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:57:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:07:44 | 31-May-2026 18:42:04 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1127 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:01:39 | zm167dc@jutal.com | 13-Jun-2026 08:13:58 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:31:00 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:47:09 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 15:02:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 15:04:38 | 22-Jun-2026 09:40:10 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1127 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:36:32 | zm167dc@jutal.com | 17-Jul-2026 21:53:44 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 06:57:17 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:01:42 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:28:07 | 27-Jul-2026 08:14:35 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1128 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:36:41 | zm167dc@jutal.com | 21-May-2026 13:45:15 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 16:07:12 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:58:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:08:16 | 31-May-2026 18:22:23 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1128 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:02:02 | zm167dc@jutal.com | 13-Jun-2026 08:13:59 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:36:34 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:48:55 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:25:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:29:15 | 22-Jun-2026 07:54:03 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1128 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 8 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:36:56 | zm167dc@jutal.com | 17-Jul-2026 21:53:46 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 07:00:11 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:02:12 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:37:30 | 27-Jul-2026 08:32:01 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1129 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 08:54:06 | zm167dc@jutal.com | 21-May-2026 13:45:30 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 16:09:34 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:59:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:08:56 | 31-May-2026 18:21:21 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1129 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 9 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:02:27 | zm167dc@jutal.com | 13-Jun-2026 08:14:02 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:39:56 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:50:53 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 15:00:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 15:03:12 | 22-Jun-2026 09:38:36 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1129 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 9 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:37:19 | zm167dc@jutal.com | 17-Jul-2026 21:53:46 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 07:02:02 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:02:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:38:04 | 27-Jul-2026 08:33:21 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1130 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 10 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 08:54:31 | zm167dc@jutal.com | 21-May-2026 13:40:16 | Jumpol Sudjitjul | 29-May-2026 |  | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 16:11:17 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 17:00:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:08:13 | 31-May-2026 18:20:18 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1130 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 10 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:02:49 | zm167dc@jutal.com | 13-Jun-2026 08:13:58 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:30:29 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:52:27 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:45:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:25:17 | 23-Jun-2026 01:42:23 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1130 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 10 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:37:42 | zm167dc@jutal.com | 17-Jul-2026 21:53:45 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 07:04:10 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:03:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:39:02 | 27-Jul-2026 08:34:42 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1131 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 11 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 08:54:58 | zm167dc@jutal.com | 21-May-2026 13:40:02 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:30:19 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 16:13:33 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 17:01:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:07:40 | 31-May-2026 18:19:10 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1131 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 11 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:03:12 | zm167dc@jutal.com | 13-Jun-2026 08:13:58 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:34:30 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:53:48 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 15:14:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 15:16:36 | 22-Jun-2026 09:49:08 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1131 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 11 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:38:06 | zm167dc@jutal.com | 17-Jul-2026 21:53:49 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 07:05:49 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:04:10 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:39:28 | 27-Jul-2026 08:35:52 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1132 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 12 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 08:55:25 | zm167dc@jutal.com | 21-May-2026 13:39:49 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:26:11 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 16:15:55 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 17:02:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:07:09 | 31-May-2026 18:47:31 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1132 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 12 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:03:36 | zm167dc@jutal.com | 13-Jun-2026 08:14:00 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:38:38 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:55:20 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 15:11:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 15:15:22 | 22-Jun-2026 09:46:29 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1132 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 12 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:38:29 | zm167dc@jutal.com | 17-Jul-2026 21:53:53 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 07:07:35 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:04:50 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:39:54 | 27-Jul-2026 08:36:59 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1133 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 13 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 08:55:55 | zm167dc@jutal.com | 21-May-2026 13:39:36 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:24:48 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 16:18:07 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 17:03:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 18:00:24 | 31-May-2026 18:46:31 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1133 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 13 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:03:59 | zm167dc@jutal.com | 13-Jun-2026 08:14:01 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:39:34 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:57:07 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 14:25:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 14:34:40 | 22-Jun-2026 08:03:22 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1133 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 13 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:38:53 | zm167dc@jutal.com | 17-Jul-2026 21:53:45 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 07:10:05 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:05:23 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:40:25 | 27-Jul-2026 08:41:44 | 0 |  |  | Approver | Locate
AO-000298 | MM-ASK-1A-WP02-STR-DWG-1134 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 08:56:21 | zm167dc@jutal.com | 21-May-2026 13:39:21 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:23:46 | Washira Kaew-amatawong | 02-Jun-2026 | 29-May-2026 16:20:10 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 21:16:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 21:20:55 | 31-May-2026 22:02:01 | 0 |  |  | Approver | Locate
AO-000477 | MM-ASK-1A-WP02-STR-DWG-1134 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 14 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:04:23 | zm167dc@jutal.com | 13-Jun-2026 08:14:00 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:37:52 | Washira Kaew-amatawong | 23-Jun-2026 | 20-Jun-2026 20:58:46 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:44:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:34:57 | 23-Jun-2026 01:49:22 | 0 |  |  | Approver | Locate
AO-000722 | MM-ASK-1A-WP02-STR-DWG-1134 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 14 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:39:15 | zm167dc@jutal.com | 17-Jul-2026 21:53:51 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 23-Jul-2026 07:11:32 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:06:05 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:41:04 | 27-Jul-2026 08:42:54 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP02-STR-DWG-1135 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 15 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:11:58 | zm167dc@jutal.com | 07-Jul-2026 18:28:08 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:39:14 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 09:47:05 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 00:59:43 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:23:04 | 20-Jul-2026 03:43:30 | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-WP02-STR-DWG-1135 | WP02 TOPSIDE JOINT CONNECTION DETAILS SHEET 15 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 18:33:51 | zm167dc@jutal.com | 06-Aug-2026 14:12:01 | Jumpol Sudjitjul | 17-Aug-2026 |  | Washira Kaew-amatawong | 18-Aug-2026 | 15-Aug-2026 19:45:15 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 17-Aug-2026 00:02:12 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 09:43:11 | 17-Aug-2026 03:15:46 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP02-STR-DWG-1136 | WP02 TOPSIDE PERSONNEL ACCESS RAMP (PAR) SUPPORT DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:12:30 | zm167dc@jutal.com | 07-Jul-2026 18:28:03 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:38:48 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 09:49:16 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 00:59:58 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:17:59 | 20-Jul-2026 03:38:44 | 0 |  |  | Approver | Locate
AO-000889 | MM-ASK-1A-WP02-STR-DWG-1136 | WP02 TOPSIDE PERSONNEL ACCESS RAMP (PAR) SUPPORT DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 18:34:18 | zm167dc@jutal.com | 06-Aug-2026 14:11:57 | Jumpol Sudjitjul | 17-Aug-2026 |  | Washira Kaew-amatawong | 18-Aug-2026 | 15-Aug-2026 19:47:15 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 17-Aug-2026 00:02:38 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 09:50:23 | 17-Aug-2026 03:22:44 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1201 | WP02 TOPSIDE UPPER DECK SECONDARY STEEL FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:52:23 | zm167dc@jutal.com | 29-May-2026 17:01:12 | Jumpol Sudjitjul | 10-Jun-2026 | 04-Jun-2026 08:02:37 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 08:55:22 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:56:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:02:24 | 07-Jun-2026 20:23:09 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1201 | WP02 TOPSIDE UPPER DECK SECONDARY STEEL FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:01:23 | zm167dc@jutal.com | 22-Jun-2026 13:23:19 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:05:13 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:03:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:41:37 | 30-Jun-2026 06:20:41 | 0 |  |  | Approver | Locate
AO-000834 | MM-ASK-1A-WP02-STR-DWG-1201 | WP02 TOPSIDE UPPER DECK SECONDARY STEEL FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:16:39 | zm167dc@jutal.com | 31-Jul-2026 17:19:54 | Jumpol Sudjitjul | 11-Aug-2026 |  | Washira Kaew-amatawong | 13-Aug-2026 | 13-Aug-2026 09:30:18 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 14-Aug-2026 00:03:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 08:23:57 | 14-Aug-2026 02:29:04 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1202 | WP02 TOPSIDE LOWER DECK SECONDARY STEEL FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:53:05 | zm167dc@jutal.com | 29-May-2026 17:01:50 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 08:56:53 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:14:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:23:54 | 07-Jun-2026 20:44:22 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1202 | WP02 TOPSIDE LOWER DECK SECONDARY STEEL FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:01:50 | zm167dc@jutal.com | 22-Jun-2026 13:23:39 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:07:55 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:03:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:40:46 | 30-Jun-2026 06:16:27 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1202 | WP02 TOPSIDE LOWER DECK SECONDARY STEEL FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:01:18 | zm167dc@jutal.com | 31-Jul-2026 14:13:11 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 12:47:55 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:10:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:44:37 | 13-Aug-2026 04:34:37 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1203 | WP02 TOPSIDE MEZZANINE DECK FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:53:47 | zm167dc@jutal.com | 29-May-2026 17:04:40 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 08:58:42 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:14:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:28:05 | 07-Jun-2026 20:45:29 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1203 | WP02 TOPSIDE MEZZANINE DECK FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:02:14 | zm167dc@jutal.com | 22-Jun-2026 13:24:06 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:10:09 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:06:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:40:22 | 30-Jun-2026 06:13:55 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1203 | WP02 TOPSIDE MEZZANINE DECK FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:01:43 | zm167dc@jutal.com | 31-Jul-2026 14:13:15 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 12:52:43 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:11:00 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:18:32 | 13-Aug-2026 04:14:01 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1204 | WP02 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:54:41 | zm167dc@jutal.com | 29-May-2026 17:05:02 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:00:04 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:15:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:29:14 | 07-Jun-2026 20:42:14 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1204 | WP02 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:02:39 | zm167dc@jutal.com | 22-Jun-2026 13:24:26 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:12:08 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:06:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:42:59 | 30-Jun-2026 06:23:29 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1204 | WP02 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:02:11 | zm167dc@jutal.com | 31-Jul-2026 14:13:10 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 12:59:16 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:11:27 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:46:40 | 13-Aug-2026 04:39:30 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1205 | WP02 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:55:24 | zm167dc@jutal.com | 29-May-2026 17:05:16 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:01:28 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:16:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:42:05 | 07-Jun-2026 21:33:23 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1205 | WP02 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:03:04 | zm167dc@jutal.com | 22-Jun-2026 13:24:42 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:14:03 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:07:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:40:00 | 30-Jun-2026 06:11:05 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1205 | WP02 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:02:43 | zm167dc@jutal.com | 31-Jul-2026 14:13:11 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 13:00:56 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:11:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:47:17 | 13-Aug-2026 04:41:50 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1206 | WP02 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:56:09 | zm167dc@jutal.com | 29-May-2026 17:05:30 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:03:02 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:16:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:44:09 | 07-Jun-2026 21:34:30 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1206 | WP02 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:03:30 | zm167dc@jutal.com | 22-Jun-2026 13:46:15 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:16:30 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:07:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:43:39 | 30-Jun-2026 06:28:58 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1206 | WP02 TOPSIDE MEZZANINE DECK SECTION & DETAILS SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:03:16 | zm167dc@jutal.com | 31-Jul-2026 14:13:12 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 13:05:23 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:13:05 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:47:54 | 13-Aug-2026 04:42:59 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1221 | WP02 TOPSIDE SUMP DECK FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:56:45 | zm167dc@jutal.com | 29-May-2026 17:06:31 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:04:49 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:17:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:52:10 | 07-Jun-2026 21:17:11 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1221 | WP02 TOPSIDE SUMP DECK FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:03:55 | zm167dc@jutal.com | 22-Jun-2026 13:27:05 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:18:51 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:08:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:43:17 | 30-Jun-2026 06:27:35 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1221 | WP02 TOPSIDE SUMP DECK FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:03:46 | zm167dc@jutal.com | 31-Jul-2026 14:13:11 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 13:07:29 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:14:00 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:48:51 | 13-Aug-2026 04:46:30 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1222 | WP02 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:57:21 | zm167dc@jutal.com | 29-May-2026 17:06:56 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:06:39 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:21:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:53:54 | 07-Jun-2026 21:21:51 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1222 | WP02 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:04:20 | zm167dc@jutal.com | 22-Jun-2026 13:27:30 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:20:52 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:08:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:42:42 | 30-Jun-2026 06:24:57 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1222 | WP02 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:04:15 | zm167dc@jutal.com | 31-Jul-2026 14:13:13 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 13:19:03 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:14:34 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:48:59 | 13-Aug-2026 04:47:34 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1223 | WP02 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:57:54 | zm167dc@jutal.com | 29-May-2026 17:07:10 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:08:03 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:22:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:41:42 | 07-Jun-2026 21:12:33 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1223 | WP02 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:04:43 | zm167dc@jutal.com | 22-Jun-2026 13:27:55 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:23:02 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:09:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:42:09 | 30-Jun-2026 06:22:06 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1223 | WP02 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:04:44 | zm167dc@jutal.com | 31-Jul-2026 14:13:18 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 13:22:01 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:14:57 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:20:42 | 13-Aug-2026 04:17:20 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1224 | WP02 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:58:29 | zm167dc@jutal.com | 29-May-2026 17:07:25 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:09:42 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:23:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:51:30 | 07-Jun-2026 21:16:05 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1224 | WP02 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:05:06 | zm167dc@jutal.com | 22-Jun-2026 13:28:23 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:24:52 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:10:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:41:28 | 30-Jun-2026 06:19:13 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1224 | WP02 TOPSIDE SUMP DECK SECTION & DETAILS SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:05:15 | zm167dc@jutal.com | 31-Jul-2026 14:13:15 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 13:24:09 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:15:25 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:22:35 | 13-Aug-2026 04:21:43 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1231 | WP02 TOPSIDE STANDARD JOINT DETAILS FOR SECONDARY BEAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:58:55 | zm167dc@jutal.com | 29-May-2026 17:54:12 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:11:08 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:24:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:52:45 | 07-Jun-2026 21:19:33 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1231 | WP02 TOPSIDE STANDARD JOINT DETAILS FOR SECONDARY BEAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:05:30 | zm167dc@jutal.com | 22-Jun-2026 13:50:28 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:26:58 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:10:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:39:38 | 30-Jun-2026 06:09:41 | 0 |  |  | Approver | Locate
AO-000823 | MM-ASK-1A-WP02-STR-DWG-1231 | WP02 TOPSIDE STANDARD JOINT DETAILS FOR SECONDARY BEAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 14:05:43 | zm167dc@jutal.com | 31-Jul-2026 14:13:12 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 13:29:24 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:15:48 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:48:10 | 13-Aug-2026 04:44:03 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1241 | WP02 TOPSIDE VENT BOOM PLAN AND ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:59:23 | zm167dc@jutal.com | 29-May-2026 17:12:28 | Jumpol Sudjitjul | 11-Jun-2026 | 29-May-2026 17:39:11 | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:12:48 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:26:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:53:22 | 07-Jun-2026 21:20:43 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1241 | WP02 TOPSIDE VENT BOOM PLAN AND ELEVATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:05:55 | zm167dc@jutal.com | 22-Jun-2026 13:50:48 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:28:54 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:14:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:41:00 | 30-Jun-2026 06:17:49 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP02-STR-DWG-1241 | WP02 TOPSIDE VENT BOOM PLAN AND ELEVATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:51:43 | zm167dc@jutal.com | 07-Aug-2026 15:16:01 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 15:56:20 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:37:59 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:27:02 | 21-Aug-2026 03:12:21 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1242 | WP02 TOPSIDE VENT BOOM SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 16:59:48 | zm167dc@jutal.com | 29-May-2026 17:12:30 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:14:16 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:26:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:55:20 | 07-Jun-2026 21:24:11 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1242 | WP02 TOPSIDE VENT BOOM SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:06:19 | zm167dc@jutal.com | 22-Jun-2026 13:34:34 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:30:09 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:15:09 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:40:30 | 30-Jun-2026 06:15:04 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP02-STR-DWG-1242 | WP02 TOPSIDE VENT BOOM SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:52:09 | zm167dc@jutal.com | 07-Aug-2026 15:16:01 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 15:58:06 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:38:22 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:28:30 | 21-Aug-2026 03:13:33 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1243 | WP02 TOPSIDE VENT BOOM WALKWAY PLAN AND SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:00:25 | zm167dc@jutal.com | 29-May-2026 17:12:28 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:15:36 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:28:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:54:20 | 07-Jun-2026 21:22:58 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1243 | WP02 TOPSIDE VENT BOOM WALKWAY PLAN AND SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:06:44 | zm167dc@jutal.com | 22-Jun-2026 13:34:53 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:32:01 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:15:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:40:04 | 30-Jun-2026 06:12:30 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP02-STR-DWG-1243 | WP02 TOPSIDE VENT BOOM WALKWAY PLAN AND SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:52:34 | zm167dc@jutal.com | 07-Aug-2026 15:15:58 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 16:00:56 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:39:04 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 10:16:05 | 21-Aug-2026 04:11:30 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1244 | WP02 TOPSIDE VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:00:55 | zm167dc@jutal.com | 29-May-2026 17:12:30 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:17:03 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 20:42:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 20:52:27 | 07-Jun-2026 21:18:19 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1244 | WP02 TOPSIDE VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:07:07 | zm167dc@jutal.com | 22-Jun-2026 13:35:12 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:34:04 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:15:55 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:39:40 | 30-Jun-2026 05:43:10 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP02-STR-DWG-1244 | WP02 TOPSIDE VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:52:59 | zm167dc@jutal.com | 07-Aug-2026 15:15:58 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 16:03:39 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:39:49 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:52:11 | 21-Aug-2026 03:31:01 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1245 | WP02 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:01:27 | zm167dc@jutal.com | 29-May-2026 17:12:28 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:18:33 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:08:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 21:13:05 | 07-Jun-2026 21:51:45 | 0 |  |  | Approver | Locate
AO-000523 | MM-ASK-1A-WP02-STR-DWG-1245 | WP02 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:07:32 | zm167dc@jutal.com | 22-Jun-2026 13:35:29 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 | 25-Jun-2026 15:35:59 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:16:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 12:39:16 | 30-Jun-2026 05:41:58 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP02-STR-DWG-1245 | WP02 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:53:25 | zm167dc@jutal.com | 07-Aug-2026 15:15:56 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 17-Aug-2026 16:07:31 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:40:10 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:44:06 | 21-Aug-2026 03:22:49 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1246 | WP02 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:02:04 | zm167dc@jutal.com | 29-May-2026 17:12:28 | Jumpol Sudjitjul | 11-Jun-2026 | 29-May-2026 17:38:47 | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:20:13 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:11:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 21:14:01 | 07-Jun-2026 21:52:50 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP02-STR-DWG-1246 | WP02 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | Issued for Approval | Issued for Approval |  | 07-Aug-2026 14:53:58 | zm167dc@jutal.com | 07-Aug-2026 15:16:04 | Jumpol Sudjitjul | 30-Jun-2026 |  | Washira Kaew-amatawong | 01-Jul-2026 |  | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 01:16:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 09:56:14 | 30-Jun-2026 03:59:37 | 0 |  |  | Approver | Locate
AO-000911 | MM-ASK-1A-WP02-STR-DWG-1246 | WP02 TOPSIDE VENT BOOM WALKWAY SECTION AND DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  |  | zm167dc@jutal.com |  |  | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 |  | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:40:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 09:46:34 | 21-Aug-2026 03:25:44 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP02-STR-DWG-1251 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:50:51 | zm167dc@jutal.com | 11-Jun-2026 15:11:24 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:44:04 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:55:13 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:04:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:44:04 | 19-Jun-2026 05:31:09 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP02-STR-DWG-1251 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:10:07 | zm167dc@jutal.com | 05-Sep-2026 18:28:26 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:34:45 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 23:00:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 10:17:41 | 16-Sep-2026 03:44:15 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP02-STR-DWG-1252 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:51:19 | zm167dc@jutal.com | 11-Jun-2026 15:11:21 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:40:33 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:57:20 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:15:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:43:37 | 19-Jun-2026 05:28:33 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP02-STR-DWG-1252 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:10:36 | zm167dc@jutal.com | 05-Sep-2026 18:28:16 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:37:14 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 23:03:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 10:18:39 | 16-Sep-2026 03:45:38 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP02-STR-DWG-1253 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:51:55 | zm167dc@jutal.com | 11-Jun-2026 15:11:21 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:39:13 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 09:59:24 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:14:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:42:09 | 19-Jun-2026 05:23:40 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP02-STR-DWG-1253 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:11:04 | zm167dc@jutal.com | 05-Sep-2026 18:28:17 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:39:45 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 23:13:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 17-Sep-2026 08:28:29 | 17-Sep-2026 02:05:37 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP02-STR-DWG-1254 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 14:52:27 | zm167dc@jutal.com | 11-Jun-2026 15:11:20 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:37:56 | Washira Kaew-amatawong | 22-Jun-2026 | 18-Jun-2026 10:01:34 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 18-Jun-2026 23:12:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 11:43:13 | 19-Jun-2026 05:26:05 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP02-STR-DWG-1254 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:11:31 | zm167dc@jutal.com | 05-Sep-2026 18:28:16 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 11:44:13 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 23:13:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 17-Sep-2026 08:27:22 | 17-Sep-2026 02:04:04 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP02-STR-DWG-1255 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 15:54:25 | zm167dc@jutal.com | 10-Jun-2026 16:02:30 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 00:26:58 | Washira Kaew-amatawong | 19-Jun-2026 | 18-Jun-2026 10:05:14 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:44:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:40:58 | 19-Jun-2026 05:37:25 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP02-STR-DWG-1255 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:12:05 | zm167dc@jutal.com | 05-Sep-2026 18:28:19 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 12:50:05 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 23:16:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 10:19:47 | 16-Sep-2026 03:47:00 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP02-STR-DWG-1256 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 15:54:50 | zm167dc@jutal.com | 10-Jun-2026 16:03:03 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 00:27:54 | Washira Kaew-amatawong | 19-Jun-2026 | 18-Jun-2026 10:07:50 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:47:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:40:11 | 19-Jun-2026 05:36:08 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP02-STR-DWG-1256 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:12:32 | zm167dc@jutal.com | 05-Sep-2026 18:28:25 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 12:53:18 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 23:17:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 17-Sep-2026 08:25:40 | 17-Sep-2026 02:02:37 | 0 |  |  | Approver | Locate
AO-000441 | MM-ASK-1A-WP02-STR-DWG-1257 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 15:55:14 | zm167dc@jutal.com | 10-Jun-2026 16:03:19 | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 00:30:12 | Washira Kaew-amatawong | 19-Jun-2026 | 18-Jun-2026 10:10:04 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 18-Jun-2026 22:51:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 11:42:52 | 19-Jun-2026 05:41:21 | 0 |  |  | Approver | Locate
AO-001196 | MM-ASK-1A-WP02-STR-DWG-1257 | WP02 TOPSIDE SOLAR PANEL ARRANGEMENT & SUPPORT DETAILS - SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:12:57 | zm167dc@jutal.com | 05-Sep-2026 18:28:18 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 15-Sep-2026 12:57:14 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 15-Sep-2026 23:17:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 16-Sep-2026 10:53:10 | 16-Sep-2026 04:39:54 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP02-STR-DWG-1301 | WP02 TOPSIDE UPPER DECK FLOORING & HANDRAIL LAYOUT PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:38:57 | zm167dc@jutal.com | 10-Jul-2026 17:31:58 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:08:04 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 16:06:38 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:14:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 14:41:34 | 27-Jul-2026 09:23:50 | 0 |  |  | Approver | Locate
AO-001117 | MM-ASK-1A-WP02-STR-DWG-1301 | WP02 TOPSIDE UPPER DECK FLOORING & HANDRAIL LAYOUT PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 11:33:39 | zm167dc@jutal.com | 28-Aug-2026 13:37:24 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 08:16:54 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 23:47:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 08-Sep-2026 13:12:29 | 08-Sep-2026 06:42:19 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP02-STR-DWG-1302 | WP02 TOPSIDE LOWER DECK FLOORING & HANDRAIL LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:39:25 | zm167dc@jutal.com | 10-Jul-2026 17:32:01 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:08:42 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 16:08:16 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:15:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 14:42:09 | 27-Jul-2026 09:25:04 | 0 |  |  | Approver | Locate
AO-001117 | MM-ASK-1A-WP02-STR-DWG-1302 | WP02 TOPSIDE LOWER DECK FLOORING & HANDRAIL LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 11:34:05 | zm167dc@jutal.com | 28-Aug-2026 13:37:22 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 08:19:10 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:31:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:27:11 | 09-Sep-2026 01:54:59 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP02-STR-DWG-1303 | WP02 TOPSIDE MEZZANINE DECK FLOORING & HANDRAIL LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:39:55 | zm167dc@jutal.com | 10-Jul-2026 17:36:59 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:12:00 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 16:10:24 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:15:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 14:43:34 | 27-Jul-2026 09:28:50 | 0 |  |  | Approver | Locate
AO-001117 | MM-ASK-1A-WP02-STR-DWG-1303 | WP02 TOPSIDE MEZZANINE DECK FLOORING & HANDRAIL LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 11:34:30 | zm167dc@jutal.com | 28-Aug-2026 13:37:25 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 08:21:27 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:32:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:27:35 | 09-Sep-2026 01:56:20 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP02-STR-DWG-1304 | WP02 TOPSIDE SUMP DECK FLOORING & HANDRAIL LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:40:23 | zm167dc@jutal.com | 10-Jul-2026 17:31:59 | Jumpol Sudjitjul | 21-Jul-2026 |  | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 16:11:46 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:16:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 14:43:05 | 27-Jul-2026 09:26:18 | 0 |  |  | Approver | Locate
AO-001117 | MM-ASK-1A-WP02-STR-DWG-1304 | WP02 TOPSIDE SUMP DECK FLOORING & HANDRAIL LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 09:15:27 | zm167dc@jutal.com | 28-Aug-2026 13:37:30 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 10:51:27 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:43:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:28:11 | 09-Sep-2026 01:57:39 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP02-STR-DWG-1305 | WP02 TOPSIDE FLOORING SECTIONS & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:40:51 | zm167dc@jutal.com | 10-Jul-2026 17:40:32 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:20:30 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 16:13:30 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:17:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 14:44:02 | 27-Jul-2026 09:27:35 | 0 |  |  | Approver | Locate
AO-001117 | MM-ASK-1A-WP02-STR-DWG-1305 | WP02 TOPSIDE FLOORING SECTIONS & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 09:16:07 | zm167dc@jutal.com | 28-Aug-2026 13:37:26 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 10:55:47 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:46:03 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:28:42 | 09-Sep-2026 01:59:49 | 0 |  |  | Approver | Locate
AO-000671 | MM-ASK-1A-WP02-STR-DWG-1306 | WP02 TOPSIDE FLOORING SECTIONS & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 14:41:24 | zm167dc@jutal.com | 10-Jul-2026 17:40:44 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 18:20:46 | Washira Kaew-amatawong | 22-Jul-2026 | 23-Jul-2026 16:14:55 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 22:18:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 14:44:36 | 27-Jul-2026 09:30:07 | 0 |  |  | Approver | Locate
AO-001117 | MM-ASK-1A-WP02-STR-DWG-1306 | WP02 TOPSIDE FLOORING SECTIONS & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 08:28:57 | zm167dc@jutal.com | 28-Aug-2026 13:37:36 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 10:58:32 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:50:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:29:10 | 09-Sep-2026 02:01:15 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1311 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:08:11 | zm167dc@jutal.com | 19-Jun-2026 16:16:32 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:22:45 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:46:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:57:17 | 24-Jun-2026 02:23:33 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1311 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:14:01 | zm167dc@jutal.com | 20-Aug-2026 14:29:54 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:37:02 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:45:39 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:09:42 | 30-Aug-2026 09:32:41 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1312 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:08:39 | zm167dc@jutal.com | 19-Jun-2026 16:16:47 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:25:07 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:47:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:58:41 | 24-Jun-2026 02:24:48 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1312 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:14:45 | zm167dc@jutal.com | 20-Aug-2026 14:29:56 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:38:34 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:46:02 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:07:42 | 30-Aug-2026 09:30:28 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1313 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:09:05 | zm167dc@jutal.com | 19-Jun-2026 16:17:02 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:27:35 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:48:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:59:27 | 24-Jun-2026 02:26:01 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1313 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:15:27 | zm167dc@jutal.com | 20-Aug-2026 14:29:54 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:40:07 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:46:50 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:11:25 | 30-Aug-2026 09:33:49 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1314 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:09:33 | zm167dc@jutal.com | 19-Jun-2026 16:17:23 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:29:52 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:48:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 09:15:50 | 24-Jun-2026 02:35:46 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1314 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:16:15 | zm167dc@jutal.com | 20-Aug-2026 14:29:52 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:41:49 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:47:15 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:22:44 | 30-Aug-2026 10:40:44 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1315 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:10:02 | zm167dc@jutal.com | 19-Jun-2026 16:18:11 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:31:49 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:49:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 09:19:13 | 24-Jun-2026 03:01:07 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1315 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:17:06 | zm167dc@jutal.com | 20-Aug-2026 14:29:57 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:43:52 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:47:45 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:23:42 | 30-Aug-2026 10:41:48 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1316 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:10:31 | zm167dc@jutal.com | 19-Jun-2026 16:21:40 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:34:15 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:50:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 09:27:05 | 24-Jun-2026 03:02:28 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1316 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 13:19:25 | zm167dc@jutal.com | 20-Aug-2026 13:32:49 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:45:26 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:48:12 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:12:37 | 30-Aug-2026 09:48:24 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1317 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:10:57 | zm167dc@jutal.com | 19-Jun-2026 16:21:41 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:44:19 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:50:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 09:28:21 | 24-Jun-2026 03:21:54 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1317 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 13:20:20 | zm167dc@jutal.com | 20-Aug-2026 13:33:54 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:46:45 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:48:31 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:13:50 | 30-Aug-2026 09:50:40 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1318 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:11:24 | zm167dc@jutal.com | 19-Jun-2026 16:21:40 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:48:24 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:53:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 09:28:50 | 24-Jun-2026 03:35:33 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1318 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 13:21:04 | zm167dc@jutal.com | 20-Aug-2026 13:34:37 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:48:06 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:48:59 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:16:07 | 30-Aug-2026 09:52:57 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1319 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:11:51 | zm167dc@jutal.com | 19-Jun-2026 16:21:41 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:51:22 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:54:06 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 09:27:51 | 24-Jun-2026 03:03:37 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WP02-STR-DWG-1319 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 9 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 15:20:47 | zm167dc@jutal.com | 21-Aug-2026 17:04:28 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 29-Aug-2026 14:49:46 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 30-Aug-2026 16:16:35 | APPR | Approved | Jumpol Sudjitjul | 04-Sep-2026 | 30-Aug-2026 16:21:55 | 30-Aug-2026 10:57:36 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1320 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 10 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:12:19 | zm167dc@jutal.com | 19-Jun-2026 16:21:45 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:53:58 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:56:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:28:23 | 24-Jun-2026 02:06:46 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1320 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 10 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 13:21:53 | zm167dc@jutal.com | 20-Aug-2026 13:39:01 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:51:51 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:49:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:32:43 | 30-Aug-2026 10:59:58 | 0 |  |  | Approver | Locate
AO-000516 | MM-ASK-1A-WP02-STR-DWG-1321 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 11 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:12:48 | zm167dc@jutal.com | 19-Jun-2026 16:21:41 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 23-Jun-2026 15:55:43 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 24-Jun-2026 00:02:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 08:27:11 | 24-Jun-2026 02:05:26 | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-1321 | WP02 TOPSIDE STAIRWAY LAYOUT & DETAILS SHEET 11 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 13:22:30 | zm167dc@jutal.com | 20-Aug-2026 13:39:20 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 14:53:52 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:50:06 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:19:55 | 30-Aug-2026 09:54:07 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP02-STR-DWG-1401 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:39:49 | zm167dc@jutal.com | 22-Jul-2026 10:46:09 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 15:07:39 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:15:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:04:31 | 06-Aug-2026 03:07:01 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP02-STR-DWG-1401 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:24:17 | zm167dc@jutal.com | 08-Sep-2026 10:04:12 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 15:53:44 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 12:47:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:18:37 | 20-Sep-2026 10:11:55 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP02-STR-DWG-1402 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:40:18 | zm167dc@jutal.com | 22-Jul-2026 10:45:36 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 15:11:42 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:15:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:08:14 | 06-Aug-2026 03:09:39 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP02-STR-DWG-1402 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:24:52 | zm167dc@jutal.com | 08-Sep-2026 10:04:08 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 16:00:13 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 12:48:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:20:32 | 20-Sep-2026 10:15:38 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP02-STR-DWG-1403 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:41:01 | zm167dc@jutal.com | 22-Jul-2026 10:44:48 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 15:15:08 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:16:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:08:47 | 06-Aug-2026 03:11:00 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP02-STR-DWG-1403 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:25:20 | zm167dc@jutal.com | 08-Sep-2026 10:04:14 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 16:02:44 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 12:50:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:21:18 | 20-Sep-2026 10:16:54 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP02-STR-DWG-1404 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:41:35 | zm167dc@jutal.com | 22-Jul-2026 10:54:10 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 15:17:18 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:16:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:09:10 | 06-Aug-2026 03:12:17 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-STR-DWG-1404 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 08:55:45 | zm167dc@jutal.com | 11-Sep-2026 12:36:15 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 16-Sep-2026 16:10:03 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 15:48:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 16:23:24 | 20-Sep-2026 11:02:56 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP02-STR-DWG-1405 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:14:13 | zm167dc@jutal.com | 22-Jul-2026 10:39:55 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 15:19:29 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:17:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:09:36 | 06-Aug-2026 02:49:53 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP02-STR-DWG-1405 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:25:48 | zm167dc@jutal.com | 08-Sep-2026 10:04:16 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 16:06:07 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 12:52:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:24:19 | 20-Sep-2026 10:18:12 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP02-STR-DWG-1406 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:14:43 | zm167dc@jutal.com | 22-Jul-2026 10:40:26 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 15:22:44 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:18:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:10:09 | 06-Aug-2026 02:51:10 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP02-STR-DWG-1406 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:26:16 | zm167dc@jutal.com | 08-Sep-2026 10:04:11 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 16:12:31 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 12:52:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:33:39 | 20-Sep-2026 10:19:32 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP02-STR-DWG-1407 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:15:10 | zm167dc@jutal.com | 22-Jul-2026 10:40:46 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 15:25:34 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:21:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:11:10 | 06-Aug-2026 02:52:29 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-STR-DWG-1407 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 08:56:17 | zm167dc@jutal.com | 11-Sep-2026 12:36:40 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 16-Sep-2026 16:21:08 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 15:50:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 16:38:28 | 20-Sep-2026 11:04:18 | 0 |  |  | Approver | Locate
AO-000756 | MM-ASK-1A-WP02-STR-DWG-1408 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 22-Jul-2026 10:15:42 | zm167dc@jutal.com | 22-Jul-2026 10:41:11 | Jumpol Sudjitjul | 03-Aug-2026 |  | Washira Kaew-amatawong | 04-Aug-2026 | 05-Aug-2026 15:28:33 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 05-Aug-2026 21:22:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 06-Aug-2026 09:13:33 | 06-Aug-2026 02:53:48 | 0 |  |  | Approver | Locate
AO-001219 | MM-ASK-1A-WP02-STR-DWG-1408 | WP02 TOPSIDE DECK HATCH ARRANGEMENT & DETAILS SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:26:45 | zm167dc@jutal.com | 08-Sep-2026 10:04:16 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 16-Sep-2026 16:24:01 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 12:55:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:41:59 | 20-Sep-2026 10:20:50 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-STR-DWG-1420 | WP02 TOPSIDE MONORAIL LAYOUT AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:10:06 | zm167dc@jutal.com | 03-Jul-2026 18:22:44 | Jumpol Sudjitjul | 14-Jul-2026 |  | Washira Kaew-amatawong | 15-Jul-2026 | 14-Jul-2026 16:19:16 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 14-Jul-2026 23:27:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 09:15:21 | 15-Jul-2026 02:39:53 | 0 |  |  | Approver | Locate
AO-001490 | MM-ASK-1A-WP02-STR-DWG-1420 | WP02 TOPSIDE MONORAIL LAYOUT AND DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA01 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 17:19:35 | zm167dc@jutal.com | 18-Sep-2026 17:30:39 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-STR-DWG-1531 | WP02 TOPSIDE CONDENSATE BURNER BOOM SUPPORT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:48:36 | zm167dc@jutal.com | 26-Jul-2026 22:24:09 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 07-Aug-2026 17:35:57 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:47:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:09:50 | 10-Aug-2026 07:51:33 | 0 |  |  | Approver | Locate
AO-001158 | MM-ASK-1A-WP02-STR-DWG-1531 | WP02 TOPSIDE CONDENSATE BURNER BOOM SUPPORT DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:17:29 | zm167dc@jutal.com | 02-Sep-2026 21:52:08 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 12:03:48 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 13-Sep-2026 22:56:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 22:59:00 | 13-Sep-2026 16:35:04 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-STR-DWG-1532 | WP02 TOPSIDE CONDENSATE BURNER BOOM SUPPORT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:04:07 | zm167dc@jutal.com | 26-Jul-2026 22:24:26 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 07-Aug-2026 17:38:04 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:47:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:15:33 | 11-Aug-2026 01:23:57 | 0 |  |  | Approver | Locate
AO-001158 | MM-ASK-1A-WP02-STR-DWG-1532 | WP02 TOPSIDE CONDENSATE BURNER BOOM SUPPORT DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 19:18:02 | zm167dc@jutal.com | 02-Sep-2026 21:53:21 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 12:06:29 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 14-Sep-2026 23:51:21 | AWC | Approved with Comment | Soontaree Simpitak | 16-Sep-2026 | 15-Sep-2026 08:25:04 | 15-Sep-2026 02:22:17 | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-STR-DWG-1551 | WP02 TOPSIDE HELIDECK MARKING AND SAFETY NETTING LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:10:34 | zm167dc@jutal.com | 03-Jul-2026 18:20:36 | Jumpol Sudjitjul | 14-Jul-2026 |  | Washira Kaew-amatawong | 15-Jul-2026 | 14-Jul-2026 17:45:54 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 14-Jul-2026 23:29:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 09:21:11 | 15-Jul-2026 03:44:23 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-STR-DWG-1551 | WP02 TOPSIDE HELIDECK MARKING AND SAFETY NETTING LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 08:56:47 | zm167dc@jutal.com | 11-Sep-2026 12:36:57 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-STR-DWG-1552 | WP02 TOPSIDE HELIDECK MARKING AND SAFETY NETTING DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:11:00 | zm167dc@jutal.com | 03-Jul-2026 18:20:39 | Jumpol Sudjitjul | 14-Jul-2026 |  | Washira Kaew-amatawong | 15-Jul-2026 | 14-Jul-2026 17:47:13 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 14-Jul-2026 23:29:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 09:19:23 | 15-Jul-2026 02:49:06 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-STR-DWG-1552 | WP02 TOPSIDE HELIDECK MARKING AND SAFETY NETTING DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 08:57:18 | zm167dc@jutal.com | 11-Sep-2026 12:37:17 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-STR-DWG-1553 | WP02 TOPSIDE HELIDECK MARKING AND SAFETY NETTING DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:11:28 | zm167dc@jutal.com | 03-Jul-2026 18:20:43 | Jumpol Sudjitjul | 14-Jul-2026 |  | Washira Kaew-amatawong | 15-Jul-2026 | 14-Jul-2026 17:48:40 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 14-Jul-2026 23:30:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 09:16:11 | 15-Jul-2026 02:42:23 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-STR-DWG-1553 | WP02 TOPSIDE HELIDECK MARKING AND SAFETY NETTING DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 08:57:46 | zm167dc@jutal.com | 11-Sep-2026 12:37:35 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001275 | MM-ASK-1A-WP02-STR-DWG-1554 | WP02 TOPSIDE HELIDECK LANDING NET LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFR | Issued for Review |  | 10-Sep-2026 13:16:59 | zm167dc@jutal.com | 10-Sep-2026 15:37:01 | Jumpol Sudjitjul | 18-Sep-2026 |  | Washira Kaew-amatawong | 21-Sep-2026 |  | Pornlert Wanaphattharaphan | 22-Sep-2026 |  |  |  |  | 23-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP02-STR-DWG-1601 | WP02 TOPSIDE UPPER DECK EQUIPMENT SUPPORT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:13:01 | zm167dc@jutal.com | 07-Jul-2026 18:28:08 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:40:15 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 16:01:49 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 00:41:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:22:00 | 20-Jul-2026 03:42:26 | 0 |  |  | Approver | Locate
AO-001139 | MM-ASK-1A-WP02-STR-DWG-1601 | WP02 TOPSIDE UPPER DECK EQUIPMENT SUPPORT LOCATION PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 14:00:38 | zm167dc@jutal.com | 29-Aug-2026 14:04:16 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 16:05:31 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:51:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:30:01 | 09-Sep-2026 02:02:42 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP02-STR-DWG-1602 | WP02 TOPSIDE LOWER DECK EQUIPMENT SUPPORT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:13:34 | zm167dc@jutal.com | 07-Jul-2026 18:28:05 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:38:23 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 16:03:17 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 19-Jul-2026 17:24:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:21:33 | 20-Jul-2026 03:41:13 | 0 |  |  | Approver | Locate
AO-001139 | MM-ASK-1A-WP02-STR-DWG-1602 | WP02 TOPSIDE LOWER DECK EQUIPMENT SUPPORT LOCATION PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 14:01:04 | zm167dc@jutal.com | 29-Aug-2026 14:12:45 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 16:07:14 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:51:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:31:07 | 09-Sep-2026 02:05:37 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP02-STR-DWG-1603 | WP02 TOPSIDE MEZZANINE DECK EQUIPMENT SUPPORT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:14:08 | zm167dc@jutal.com | 07-Jul-2026 18:28:10 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:40:42 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 16:05:18 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 19-Jul-2026 17:21:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:18:44 | 20-Jul-2026 03:39:58 | 0 |  |  | Approver | Locate
AO-001139 | MM-ASK-1A-WP02-STR-DWG-1603 | WP02 TOPSIDE MEZZANINE DECK EQUIPMENT SUPPORT LOCATION PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 14:01:28 | zm167dc@jutal.com | 29-Aug-2026 14:13:01 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 16:09:16 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:51:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:31:00 | 09-Sep-2026 02:04:06 | 0 |  |  | Approver | Locate
AO-000647 | MM-ASK-1A-WP02-STR-DWG-1604 | WP02 TOPSIDE SUMP DECK EQUIPMENT SUPPORT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 16:14:47 | zm167dc@jutal.com | 07-Jul-2026 18:28:10 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 15:39:48 | Washira Kaew-amatawong | 17-Jul-2026 | 17-Jul-2026 16:06:52 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 19-Jul-2026 17:18:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:17:27 | 20-Jul-2026 02:39:19 | 0 |  |  | Approver | Locate
AO-001139 | MM-ASK-1A-WP02-STR-DWG-1604 | WP02 TOPSIDE SUMP DECK EQUIPMENT SUPPORT LOCATION PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 14:01:55 | zm167dc@jutal.com | 29-Aug-2026 14:13:18 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 07-Sep-2026 16:11:17 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:52:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 08:33:51 | 09-Sep-2026 02:07:07 | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP02-STR-DWG-1611 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:05:34 | zm167dc@jutal.com | 26-Jul-2026 22:29:06 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:28:48 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:48:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:14:35 | 11-Aug-2026 01:35:59 | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP02-STR-DWG-1612 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:06:02 | zm167dc@jutal.com | 26-Jul-2026 22:29:23 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:30:47 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:48:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:11:58 | 11-Aug-2026 01:33:22 | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP02-STR-DWG-1613 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:06:28 | zm167dc@jutal.com | 26-Jul-2026 22:29:39 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:32:44 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:48:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:14:12 | 11-Aug-2026 01:34:43 | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP02-STR-DWG-1614 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:06:54 | zm167dc@jutal.com | 26-Jul-2026 22:29:55 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:34:38 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:49:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:11:21 | 11-Aug-2026 01:32:08 | 0 |  |  | Approver | Locate
AO-000778 | MM-ASK-1A-WP02-STR-DWG-1615 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 16:07:23 | zm167dc@jutal.com | 26-Jul-2026 22:30:10 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 09:37:01 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:49:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:10:32 | 11-Aug-2026 01:30:52 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1616 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 15:30:09 | zm167dc@jutal.com | 07-Aug-2026 15:53:48 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 08:03:37 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:57:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:39:28 | 24-Aug-2026 09:57:02 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1617 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 15:30:36 | zm167dc@jutal.com | 07-Aug-2026 15:53:47 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 08:06:18 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:57:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:41:05 | 24-Aug-2026 09:59:33 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1618 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 15:31:02 | zm167dc@jutal.com | 07-Aug-2026 15:53:47 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 08:10:52 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:58:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:42:37 | 24-Aug-2026 10:03:23 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1619 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 15:31:28 | zm167dc@jutal.com | 07-Aug-2026 15:53:50 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 08:16:49 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:58:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:43:51 | 24-Aug-2026 10:04:38 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1620 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 10 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:54:24 | zm167dc@jutal.com | 07-Aug-2026 15:53:49 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 08:18:20 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:59:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 14:20:21 | 24-Aug-2026 07:47:02 | 0 |  |  | Approver | Locate
AO-001366 | MM-ASK-1A-WP02-STR-DWG-1620 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 10 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 15-Sep-2026 16:44:26 | zm167dc@jutal.com | 15-Sep-2026 17:24:50 | Jumpol Sudjitjul | 24-Sep-2026 |  | Washira Kaew-amatawong | 25-Sep-2026 |  | Pornlert Wanaphattharaphan | 28-Sep-2026 |  |  |  |  | 29-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1621 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 11 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 15:31:52 | zm167dc@jutal.com | 07-Aug-2026 15:53:53 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 08:23:34 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:00:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:51:40 | 24-Aug-2026 10:23:45 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1622 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 12 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 15:32:16 | zm167dc@jutal.com | 07-Aug-2026 15:53:51 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 08:28:39 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:00:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:42:29 | 24-Aug-2026 10:02:11 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1623 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 13 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:54:49 | zm167dc@jutal.com | 07-Aug-2026 15:53:56 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 08:32:09 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:02:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:58:14 | 24-Aug-2026 10:38:48 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1624 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 14:55:17 | zm167dc@jutal.com | 07-Aug-2026 15:53:48 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 08:34:00 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:04:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 14:19:23 | 24-Aug-2026 07:45:46 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1625 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 15 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 15:32:44 | zm167dc@jutal.com | 07-Aug-2026 15:53:55 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 09:23:56 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:05:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:49:59 | 24-Aug-2026 10:21:18 | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1626 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 16 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 15:33:18 | zm167dc@jutal.com | 07-Aug-2026 15:53:51 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 09:43:57 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:06:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:50:45 | 24-Aug-2026 10:22:30 | 0 |  |  | Approver | Locate
AO-001366 | MM-ASK-1A-WP02-STR-DWG-1626 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 16 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 15-Sep-2026 16:44:58 | zm167dc@jutal.com | 15-Sep-2026 17:25:14 | Jumpol Sudjitjul | 24-Sep-2026 |  | Washira Kaew-amatawong | 25-Sep-2026 |  | Pornlert Wanaphattharaphan | 28-Sep-2026 |  |  |  |  | 29-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000917 | MM-ASK-1A-WP02-STR-DWG-1627 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 17 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 15:33:50 | zm167dc@jutal.com | 07-Aug-2026 15:53:53 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 09:48:47 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:06:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:22:44 | 24-Aug-2026 10:53:31 | 0 |  |  | Approver | Locate
AO-001366 | MM-ASK-1A-WP02-STR-DWG-1627 | WP02 TOPSIDE EQUIPMENT SUPPORT DETAILS SHEET 17 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 15-Sep-2026 16:45:28 | zm167dc@jutal.com | 15-Sep-2026 17:25:45 | Jumpol Sudjitjul | 24-Sep-2026 |  | Washira Kaew-amatawong | 25-Sep-2026 |  | Pornlert Wanaphattharaphan | 28-Sep-2026 |  |  |  |  | 29-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-STR-DWG-1721 | WP02 TOPSIDE PLATFORM NAME PLATE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 13:15:31 | zm167dc@jutal.com | 26-Jul-2026 22:33:58 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 08-Aug-2026 14:38:32 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:50:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:26:41 | 10-Aug-2026 08:14:39 | 0 |  |  | Approver | Locate
AO-001490 | MM-ASK-1A-WP02-STR-DWG-1721 | WP02 TOPSIDE PLATFORM NAME PLATE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 17:20:14 | zm167dc@jutal.com | 18-Sep-2026 17:30:56 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1801 | WP02 TOPSIDE LIFTING CONFIGURATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:02:47 | zm167dc@jutal.com | 29-May-2026 17:15:51 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:21:52 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:13:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 21:17:18 | 07-Jun-2026 14:53:52 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP02-STR-DWG-1801 | WP02 TOPSIDE LIFTING CONFIGURATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 15:44:30 | zm167dc@jutal.com | 18-Sep-2026 17:00:03 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1802 | WP02 TOPSIDE LIFTING PADEYE DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:03:18 | zm167dc@jutal.com | 29-May-2026 17:16:05 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:23:17 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:14:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 21:20:12 | 07-Jun-2026 14:56:00 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP02-STR-DWG-1802 | WP02 TOPSIDE LIFTING PADEYE DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 15:45:06 | zm167dc@jutal.com | 18-Sep-2026 17:02:09 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1803 | WP02 TOPSIDE LIFTING PADEYE DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:03:52 | zm167dc@jutal.com | 29-May-2026 17:16:19 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:24:38 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:15:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 21:20:18 | 07-Jun-2026 14:57:02 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP02-STR-DWG-1803 | WP02 TOPSIDE LIFTING PADEYE DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 14:50:06 | zm167dc@jutal.com | 18-Sep-2026 17:02:40 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1804 | WP02 TOPSIDE LIFTING PADEYE DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:04:17 | zm167dc@jutal.com | 29-May-2026 17:16:32 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:25:59 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:16:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 07-Jun-2026 21:19:55 | 07-Jun-2026 14:54:57 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP02-STR-DWG-1804 | WP02 TOPSIDE LIFTING PADEYE DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 15:45:33 | zm167dc@jutal.com | 18-Sep-2026 17:03:01 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-DWG-1805 | WP02 TOPSIDE LIFTING PADEYE DETAILS SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:04:40 | zm167dc@jutal.com | 29-May-2026 17:16:50 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 07-Jun-2026 09:28:01 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:20:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 08-Jun-2026 08:44:42 | 08-Jun-2026 02:19:36 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP02-STR-DWG-1805 | WP02 TOPSIDE LIFTING PADEYE DETAILS SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 14:51:00 | zm167dc@jutal.com | 18-Sep-2026 17:03:18 | Jumpol Sudjitjul | 29-Sep-2026 |  | Washira Kaew-amatawong | 30-Sep-2026 |  | Pornlert Wanaphattharaphan | 01-Oct-2026 |  |  |  |  | 02-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2001 | WP02 JACKET - DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:52:22 | zm167dc@jutal.com | 29-May-2026 09:15:25 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:17:12 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 09:29:36 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:57:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:03:57 | 07-Jun-2026 13:21:02 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP02-STR-DWG-2001 | WP02 JACKET - DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:52:27 | zm167dc@jutal.com | 06-Aug-2026 17:17:08 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 12:59:07 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:11:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:24:35 | 24-Aug-2026 11:06:08 | 0 |  |  | Approver | Locate
AO-001180 | MM-ASK-1A-WP02-STR-DWG-2001 | WP02 JACKET - DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 17:26:51 | zm167dc@jutal.com | 03-Sep-2026 17:34:24 | Jumpol Sudjitjul | 14-Sep-2026 |  | Washira Kaew-amatawong | 15-Sep-2026 | 14-Sep-2026 15:17:40 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 14-Sep-2026 23:59:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 15-Sep-2026 16:59:09 | 15-Sep-2026 10:36:25 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2101 | WP02 JACKET - ELEVATION ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:52:46 | zm167dc@jutal.com | 29-May-2026 09:18:43 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:17:53 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 09:31:55 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:59:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:05:56 | 07-Jun-2026 13:22:05 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP02-STR-DWG-2101 | WP02 JACKET - ELEVATION ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:52:55 | zm167dc@jutal.com | 06-Aug-2026 17:17:07 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:02:32 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:12:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:54:55 | 24-Aug-2026 10:29:39 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP02-STR-DWG-2101 | WP02 JACKET - ELEVATION ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:54:57 | zm167dc@jutal.com | 03-Sep-2026 16:10:16 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:28:27 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:59:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:37:45 | 12-Sep-2026 17:16:32 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2102 | WP02 JACKET - ELEVATION ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:53:10 | zm167dc@jutal.com | 29-May-2026 09:19:03 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:19:06 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 09:33:27 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 20:00:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:19:40 | 07-Jun-2026 13:43:19 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP02-STR-DWG-2102 | WP02 JACKET - ELEVATION ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:53:22 | zm167dc@jutal.com | 06-Aug-2026 17:17:07 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:04:49 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:13:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:58:57 | 24-Aug-2026 10:33:29 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP02-STR-DWG-2102 | WP02 JACKET - ELEVATION ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:55:24 | zm167dc@jutal.com | 03-Sep-2026 16:10:30 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:30:39 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 23:00:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:23:36 | 12-Sep-2026 16:55:19 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2103 | WP02 JACKET - ELEVATION ROW '1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:53:35 | zm167dc@jutal.com | 29-May-2026 09:19:22 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:20:12 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 09:36:39 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 20:01:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:55:46 | 07-Jun-2026 14:31:04 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP02-STR-DWG-2103 | WP02 JACKET - ELEVATION ROW '1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:53:50 | zm167dc@jutal.com | 06-Aug-2026 17:17:07 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:06:54 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:13:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:40:43 | 24-Aug-2026 09:58:20 | 0 |  |  | Approver | Locate
AO-001170 | MM-ASK-1A-WP02-STR-DWG-2103 | WP02 JACKET - ELEVATION ROW '1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 14:55:52 | zm167dc@jutal.com | 03-Sep-2026 16:10:17 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:33:02 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 23:01:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:36:55 | 12-Sep-2026 16:57:48 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2104 | WP02 JACKET - ELEVATION ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:53:58 | zm167dc@jutal.com | 29-May-2026 09:19:41 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:01:45 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 09:38:37 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 20:01:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:56:25 | 07-Jun-2026 14:32:21 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP02-STR-DWG-2104 | WP02 JACKET - ELEVATION ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:54:17 | zm167dc@jutal.com | 06-Aug-2026 17:17:10 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:08:37 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:14:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:38:16 | 24-Aug-2026 09:55:47 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP02-STR-DWG-2104 | WP02 JACKET - ELEVATION ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:45:43 | zm167dc@jutal.com | 02-Sep-2026 21:57:17 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:36:30 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 22:55:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:33:04 | 12-Sep-2026 17:07:22 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2111 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:54:26 | zm167dc@jutal.com | 29-May-2026 09:13:07 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:13:09 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 09:41:29 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 20:05:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:55:49 | 07-Jun-2026 14:29:55 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP02-STR-DWG-2111 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 8000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:54:43 | zm167dc@jutal.com | 06-Aug-2026 17:32:22 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:11:02 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:15:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:41:30 | 24-Aug-2026 10:00:52 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP02-STR-DWG-2111 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 8000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:46:21 | zm167dc@jutal.com | 02-Sep-2026 21:55:10 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:39:21 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 23:02:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:34:04 | 12-Sep-2026 17:08:43 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2112 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 0000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:54:52 | zm167dc@jutal.com | 29-May-2026 09:13:21 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:14:15 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 09:46:54 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 20:06:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:55:23 | 07-Jun-2026 14:28:52 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP02-STR-DWG-2112 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 0000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:55:12 | zm167dc@jutal.com | 06-Aug-2026 17:32:22 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:13:24 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:15:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:26:20 | 24-Aug-2026 11:08:40 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP02-STR-DWG-2112 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 0000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:46:58 | zm167dc@jutal.com | 02-Sep-2026 21:56:09 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:41:36 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 23:02:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:32:16 | 12-Sep-2026 17:06:01 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2113 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 9000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:55:18 | zm167dc@jutal.com | 29-May-2026 09:13:37 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:16:05 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 09:48:39 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 20:07:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:54:23 | 07-Jun-2026 14:27:47 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP02-STR-DWG-2113 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 9000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:55:38 | zm167dc@jutal.com | 06-Aug-2026 17:32:22 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:16:11 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:16:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:56:31 | 24-Aug-2026 10:30:58 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP02-STR-DWG-2113 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 9000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:47:31 | zm167dc@jutal.com | 02-Sep-2026 21:58:21 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:44:24 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 23:02:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 23:13:00 | 12-Sep-2026 16:18:08 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2114 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 17900 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:55:42 | zm167dc@jutal.com | 29-May-2026 09:13:53 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:16:39 | Washira Kaew-amatawong | 11-Jun-2026 | 07-Jun-2026 09:50:32 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 20:08:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:54:01 | 07-Jun-2026 14:26:39 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WP02-STR-DWG-2114 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 17900 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 16:56:08 | zm167dc@jutal.com | 06-Aug-2026 17:32:25 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:18:39 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:16:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 16:59:51 | 24-Aug-2026 10:34:46 | 0 |  |  | Approver | Locate
AO-001164 | MM-ASK-1A-WP02-STR-DWG-2114 | WP02 JACKET - HORIZONTAL FRAMING PLAN EL (+) 17900 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 20:48:04 | zm167dc@jutal.com | 02-Sep-2026 21:59:40 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 12-Sep-2026 14:47:19 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 13-Sep-2026 11:55:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 22:44:21 | 13-Sep-2026 16:03:14 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-STR-DWG-2115 | WP02 JACKET - SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:04:31 | zm167dc@jutal.com | 26-Jul-2026 22:32:22 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 06-Aug-2026 15:35:37 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:50:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:25:22 | 10-Aug-2026 07:25:18 | 0 |  |  | Approver | Locate
AO-001109 | MM-ASK-1A-WP02-STR-DWG-2115 | WP02 JACKET - SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 15:00:54 | zm167dc@jutal.com | 27-Aug-2026 17:37:47 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 07:17:48 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:03:55 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 17:49:57 | 10-Sep-2026 11:12:12 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP02-STR-DWG-2115 | WP02 JACKET - SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 18-Sep-2026 14:51:33 | zm167dc@jutal.com | 18-Sep-2026 16:57:58 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2121 | WP02 JACKET - PILE MAKE UP & DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:56:07 | zm167dc@jutal.com | 29-May-2026 09:10:48 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:10:58 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 20:21:06 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:36:53 | NA | Not Approved | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 20:52:51 | 07-Jun-2026 14:25:30 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-STR-DWG-2121 | WP02 JACKET - PILE MAKE UP & DETAILS - SHEET 1 |  | A2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 08:58:16 | zm167dc@jutal.com | 11-Sep-2026 12:37:10 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 14-Sep-2026 14:28:02 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 15-Sep-2026 23:18:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 16-Sep-2026 10:35:37 | 16-Sep-2026 04:35:49 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP02-STR-DWG-2121 | WP02 JACKET - PILE MAKE UP & DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 14:52:07 | zm167dc@jutal.com | 18-Sep-2026 16:58:14 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2122 | WP02 JACKET - PILE MAKE UP & DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:56:34 | zm167dc@jutal.com | 29-May-2026 09:10:45 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:06:15 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 20:23:29 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:39:07 | NA | Not Approved | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 19:58:12 | 07-Jun-2026 13:18:50 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-STR-DWG-2122 | WP02 JACKET - PILE MAKE UP & DETAILS - SHEET 2 |  | A2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 08:58:53 | zm167dc@jutal.com | 11-Sep-2026 12:37:11 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 14-Sep-2026 14:30:58 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 15-Sep-2026 23:19:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 16-Sep-2026 11:26:46 | 16-Sep-2026 05:22:13 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP02-STR-DWG-2122 | WP02 JACKET - PILE MAKE UP & DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 14:52:42 | zm167dc@jutal.com | 18-Sep-2026 16:58:30 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2123 | WP02 JACKET - PILE MARKING DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:56:59 | zm167dc@jutal.com | 29-May-2026 09:10:44 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 17:07:32 | Washira Kaew-amatawong | 11-Jun-2026 | 06-Jun-2026 20:25:14 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 19:39:42 | NA | Not Approved | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 19:52:25 | 07-Jun-2026 13:16:38 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-STR-DWG-2123 | WP02 JACKET - PILE MARKING DETAILS |  | A2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 08:59:22 | zm167dc@jutal.com | 11-Sep-2026 12:37:11 | Jumpol Sudjitjul | 21-Sep-2026 |  | Washira Kaew-amatawong | 22-Sep-2026 | 14-Sep-2026 14:33:45 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 15-Sep-2026 23:20:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 16-Sep-2026 10:53:13 | 16-Sep-2026 04:41:18 | 0 |  |  | Approver | Locate
AO-001477 | MM-ASK-1A-WP02-STR-DWG-2123 | WP02 JACKET - PILE MARKING DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 18-Sep-2026 14:53:18 | zm167dc@jutal.com | 18-Sep-2026 16:58:46 | Jumpol Sudjitjul | 28-Sep-2026 |  | Washira Kaew-amatawong | 29-Sep-2026 |  | Pornlert Wanaphattharaphan | 30-Sep-2026 |  |  |  |  | 01-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001307 | MM-ASK-1A-WP02-STR-DWG-2124 | WP02 JACKET - PILE MAKE UP & DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 12:34:10 | zm167dc@jutal.com | 11-Sep-2026 20:21:38 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 | 14-Sep-2026 14:36:25 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 15-Sep-2026 22:57:18 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 16-Sep-2026 10:36:30 | 16-Sep-2026 04:45:18 | 0 |  |  | Approver | Locate
AO-000983 | MM-ASK-1A-WP02-STR-DWG-2201 | WP02 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 14:00:27 | zm167dc@jutal.com | 14-Aug-2026 14:16:57 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:40:00 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:57:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:24:42 | 28-Aug-2026 03:48:33 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP02-STR-DWG-2201 | WP02 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:32:02 | zm167dc@jutal.com | 11-Sep-2026 20:08:14 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000983 | MM-ASK-1A-WP02-STR-DWG-2202 | WP02 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 14:01:02 | zm167dc@jutal.com | 14-Aug-2026 14:16:57 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:43:30 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 18:08:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:28:21 | 28-Aug-2026 03:49:47 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP02-STR-DWG-2202 | WP02 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:32:33 | zm167dc@jutal.com | 11-Sep-2026 20:08:29 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000983 | MM-ASK-1A-WP02-STR-DWG-2203 | WP02 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 14:01:39 | zm167dc@jutal.com | 14-Aug-2026 14:16:57 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:45:31 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 20:56:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:29:36 | 28-Aug-2026 03:51:03 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP02-STR-DWG-2203 | WP02 JACKET - ACCESS WALKWAY LAYOUT & DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:33:04 | zm167dc@jutal.com | 11-Sep-2026 20:08:46 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000983 | MM-ASK-1A-WP02-STR-DWG-2204 | WP02 JACKET - DAVIT & MONORAIL LAYOUT & DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 14:02:11 | zm167dc@jutal.com | 14-Aug-2026 14:35:55 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:48:05 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 21:00:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:33:43 | 28-Aug-2026 04:41:28 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP02-STR-DWG-2204 | WP02 JACKET - DAVIT & MONORAIL LAYOUT & DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:33:42 | zm167dc@jutal.com | 11-Sep-2026 20:09:06 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000983 | MM-ASK-1A-WP02-STR-DWG-2211 | WP02 JACKET - ANODE LAYOUT & DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 14:02:47 | zm167dc@jutal.com | 14-Aug-2026 14:36:16 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:50:27 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 21:10:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:34:18 | 28-Aug-2026 04:42:40 | 0 |  |  | Approver | Locate
AO-001419 | MM-ASK-1A-WP02-STR-DWG-2211 | WP02 JACKET - ANODE LAYOUT & DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 16-Sep-2026 17:37:25 | zm167dc@jutal.com | 17-Sep-2026 08:41:33 | Jumpol Sudjitjul | 25-Sep-2026 |  | Washira Kaew-amatawong | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000926 | MM-ASK-1A-WP02-STR-DWG-2221 | WP02 JACKET - MUDMAT LAYOUT & DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 17:25:03 | zm167dc@jutal.com | 07-Aug-2026 17:34:29 | Jumpol Sudjitjul | 19-Aug-2026 |  | Washira Kaew-amatawong | 20-Aug-2026 | 20-Aug-2026 15:09:01 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 20:01:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 16:57:30 | 24-Aug-2026 10:32:12 | 0 |  |  | Approver | Locate
AO-001181 | MM-ASK-1A-WP02-STR-DWG-2221 | WP02 JACKET - MUDMAT LAYOUT & DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 17:27:20 | zm167dc@jutal.com | 03-Sep-2026 17:34:25 | Jumpol Sudjitjul | 14-Sep-2026 |  | Washira Kaew-amatawong | 15-Sep-2026 | 14-Sep-2026 15:05:17 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 14-Sep-2026 23:57:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 15-Sep-2026 16:58:39 | 15-Sep-2026 10:34:01 | 0 |  |  | Approver | Locate
AO-000926 | MM-ASK-1A-WP02-STR-DWG-2222 | WP02 JACKET - MUDMAT LAYOUT & DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 17:25:32 | zm167dc@jutal.com | 07-Aug-2026 17:34:50 | Jumpol Sudjitjul | 19-Aug-2026 |  | Washira Kaew-amatawong | 20-Aug-2026 | 20-Aug-2026 15:11:12 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 20:02:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:00:57 | 24-Aug-2026 10:35:57 | 0 |  |  | Approver | Locate
AO-001181 | MM-ASK-1A-WP02-STR-DWG-2222 | WP02 JACKET - MUDMAT LAYOUT & DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 17:27:52 | zm167dc@jutal.com | 03-Sep-2026 17:34:30 | Jumpol Sudjitjul | 14-Sep-2026 |  | Washira Kaew-amatawong | 15-Sep-2026 | 14-Sep-2026 15:07:10 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 14-Sep-2026 23:58:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 15-Sep-2026 16:58:04 | 15-Sep-2026 10:32:38 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2231 | WP02 JACKET - CAISSON SUPPORT LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:57:23 | zm167dc@jutal.com | 29-May-2026 09:30:32 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:02:49 | Washira Kaew-amatawong | 11-Jun-2026 | 08-Jun-2026 09:27:44 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:30:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 10:14:10 | 11-Jun-2026 03:42:36 | 0 |  |  | Approver | Locate
AO-001109 | MM-ASK-1A-WP02-STR-DWG-2231 | WP02 JACKET - CAISSON SUPPORT LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 15:01:26 | zm167dc@jutal.com | 27-Aug-2026 17:38:06 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 09:42:53 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:07:38 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 17:50:48 | 10-Sep-2026 11:13:28 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WP02-STR-DWG-2232 | WP02 JACKET - CAISSON SUPPORT SECTION & DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 20:57:47 | zm167dc@jutal.com | 29-May-2026 09:30:57 | Jumpol Sudjitjul | 10-Jun-2026 | 03-Jun-2026 23:07:39 | Washira Kaew-amatawong | 11-Jun-2026 | 08-Jun-2026 09:29:12 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:31:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 10:15:12 | 11-Jun-2026 03:43:46 | 0 |  |  | Approver | Locate
AO-001115 | MM-ASK-1A-WP02-STR-DWG-2232 | WP02 JACKET - CAISSON SUPPORT SECTION & DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 18:00:01 | zm167dc@jutal.com | 28-Aug-2026 13:37:28 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 09:44:43 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:13:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 17:51:18 | 10-Sep-2026 11:09:59 | 0 |  |  | Approver | Locate
AO-000980 | MM-ASK-1A-WP02-STR-DWG-2301 | WP02 JACKET - LIFTING CONFIGURATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 13:23:41 | zm167dc@jutal.com | 14-Aug-2026 14:36:41 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:53:06 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 21:12:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:30:48 | 28-Aug-2026 03:37:49 | 0 |  |  | Approver | Locate
AO-001415 | MM-ASK-1A-WP02-STR-DWG-2301 | WP02 JACKET - LIFTING CONFIGURATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 16-Sep-2026 14:51:47 | zm167dc@jutal.com | 17-Sep-2026 08:42:11 | Jumpol Sudjitjul | 25-Sep-2026 |  | Washira Kaew-amatawong | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000975 | MM-ASK-1A-WP02-STR-DWG-2302 | WP02 JACKET - LIFTING PADEYE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 11:28:04 | zm167dc@jutal.com | 14-Aug-2026 12:56:30 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 15:55:32 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 21:12:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:35:17 | 28-Aug-2026 04:23:33 | 0 |  |  | Approver | Locate
AO-001335 | MM-ASK-1A-WP02-STR-DWG-2302 | WP02 JACKET - LIFTING PADEYE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:34:11 | zm167dc@jutal.com | 11-Sep-2026 20:09:24 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001036 | MM-ASK-1A-WP02-STR-DWG-2411 | WP02 JACKET - LOWERING SEQUENCE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Aug-2026 13:23:20 | zm167dc@jutal.com | 20-Aug-2026 13:39:40 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 28-Aug-2026 15:49:31 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:35:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:33:51 | 30-Aug-2026 11:01:12 | 0 |  |  | Approver | Locate
AO-001416 | MM-ASK-1A-WP02-STR-DWG-2411 | WP02 JACKET - LOWERING SEQUENCE |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 16-Sep-2026 14:52:17 | zm167dc@jutal.com | 17-Sep-2026 08:42:34 | Jumpol Sudjitjul | 25-Sep-2026 |  | Washira Kaew-amatawong | 28-Sep-2026 |  | Pornlert Wanaphattharaphan | 29-Sep-2026 |  |  |  |  | 30-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000353 | MM-ASK-1A-WP02-STR-MTO-1001 | WP02 TOPSIDE PRIMARY AND SECONDARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 16:45:14 | zm167dc@jutal.com | 27-May-2026 09:09:47 | Jumpol Sudjitjul | 08-Jun-2026 |  | Washira Kaew-amatawong | 09-Jun-2026 | 05-Jun-2026 15:08:26 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 06-Jun-2026 22:14:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 07-Jun-2026 17:19:11 | 07-Jun-2026 11:30:31 | 0 |  |  | Approver | Locate
AO-000670 | MM-ASK-1A-WP02-STR-MTO-1001 | WP02 TOPSIDE PRIMARY AND SECONDARY STEEL MTO REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 14:41:58 | zm167dc@jutal.com | 10-Jul-2026 14:49:08 | Jumpol Sudjitjul | 20-Jul-2026 |  | Washira Kaew-amatawong | 21-Jul-2026 | 20-Jul-2026 15:40:27 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 22-Jul-2026 23:04:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 23-Jul-2026 08:52:35 | 23-Jul-2026 02:37:48 | 0 |  |  | Approver | Locate
AO-000997 | MM-ASK-1A-WP02-STR-MTO-1001 | WP02 TOPSIDE PRIMARY AND SECONDARY STEEL MTO REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 18:10:30 | zm167dc@jutal.com | 15-Aug-2026 14:55:03 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 07:31:07 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 17:48:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 10:36:48 | 28-Aug-2026 04:35:39 | 0 |  |  | Approver | Locate
AO-000381 | MM-ASK-1A-WP02-STR-MTO-1002 | WP02 TOPSIDE SECONDARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 17:05:11 | zm167dc@jutal.com | 29-May-2026 17:17:42 | Jumpol Sudjitjul | 11-Jun-2026 |  | Washira Kaew-amatawong | 12-Jun-2026 | 10-Jun-2026 10:29:57 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 10-Jun-2026 21:39:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 11-Jun-2026 10:16:28 | 11-Jun-2026 03:30:01 | 0 |  |  | Approver | Locate
AO-000670 | MM-ASK-1A-WP02-STR-MTO-1002 | WP02 TOPSIDE SECONDARY STEEL MTO REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 14:42:36 | zm167dc@jutal.com | 10-Jul-2026 14:49:33 | Jumpol Sudjitjul | 20-Jul-2026 | 15-Jul-2026 17:50:47 | Washira Kaew-amatawong | 21-Jul-2026 | 20-Jul-2026 15:43:13 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 22-Jul-2026 23:05:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 23-Jul-2026 08:51:27 | 23-Jul-2026 02:34:52 | 0 |  |  | Approver | Locate
AO-001102 | MM-ASK-1A-WP02-STR-MTO-1002 | WP02 TOPSIDE SECONDARY STEEL MTO REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:16:40 | zm167dc@jutal.com | 27-Aug-2026 09:18:18 | Jumpol Sudjitjul | 04-Sep-2026 |  | Washira Kaew-amatawong | 07-Sep-2026 | 07-Sep-2026 07:20:27 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 08-Sep-2026 23:10:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 09-Sep-2026 08:36:06 | 09-Sep-2026 02:08:34 | 0 |  |  | Approver | Locate
AO-000423 | MM-ASK-1A-WP02-STR-MTO-2001 | WP02 JACKET PRIMARY AND SECONDARY STEEL MTO |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 18:45:19 | zm167dc@jutal.com | 07-Jun-2026 19:28:51 | Jumpol Sudjitjul | 16-Jun-2026 |  | Washira Kaew-amatawong | 17-Jun-2026 | 16-Jun-2026 14:52:35 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 20:49:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 19-Jun-2026 11:42:29 | 19-Jun-2026 05:40:04 | 0 |  |  | Approver | Locate
AO-000678 | MM-ASK-1A-WP02-STR-MTO-2001 | WP02 JACKET PRIMARY AND SECONDARY STEEL MTO |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 17:23:42 | zm167dc@jutal.com | 10-Jul-2026 17:54:18 | Jumpol Sudjitjul | 21-Jul-2026 |  | Washira Kaew-amatawong | 22-Jul-2026 | 24-Jul-2026 07:51:28 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 24-Jul-2026 23:22:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 14:45:05 | 27-Jul-2026 09:31:30 | 0 |  |  | Approver | Locate
AO-000840 | MM-ASK-1A-WP02-STR-MTO-2001 | WP02 JACKET PRIMARY AND SECONDARY STEEL MTO |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 18:14:09 | zm167dc@jutal.com | 31-Jul-2026 21:52:58 | Jumpol Sudjitjul | 11-Aug-2026 |  | Washira Kaew-amatawong | 13-Aug-2026 | 13-Aug-2026 10:03:04 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 14-Aug-2026 00:08:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 08:25:11 | 14-Aug-2026 01:58:20 | 0 |  |  | Approver | Locate
AO-000838 | MM-ASK-1A-WP02-STR-MTO-2002 | WP02 JACKET SECONDARY STEEL MTO |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 16:43:58 | zm167dc@jutal.com | 31-Jul-2026 17:04:43 | Jumpol Sudjitjul | 11-Aug-2026 |  | Washira Kaew-amatawong | 13-Aug-2026 | 13-Aug-2026 10:37:32 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 14-Aug-2026 00:08:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 08:26:49 | 14-Aug-2026 02:11:58 | 0 |  |  | Approver | Locate
AO-001146 | MM-ASK-1A-WP02-STR-MTO-2002 | WP02 JACKET SECONDARY STEEL MTO |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 20:48:49 | zm167dc@jutal.com | 02-Sep-2026 22:00:56 | Soontaree Simpitak | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 13-Sep-2026 07:07:55 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 13-Sep-2026 11:50:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 22:44:58 | 13-Sep-2026 16:04:48 | 0 |  |  | Approver | Locate
AO-000400 | MM-ASK-1A-WP02-STR-RPT-1001 | WP02 TOPSIDE COMPUTER MODELING AND LOAD FORMULATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 09:54:15 | zm167dc@jutal.com | 04-Jun-2026 10:54:33 | Jumpol Sudjitjul | 12-Jun-2026 |  | Washira Kaew-amatawong | 15-Jun-2026 | 15-Jun-2026 16:19:36 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 18-Jun-2026 16:01:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 16:12:31 | 18-Jun-2026 09:37:00 | 0 |  |  | Approver | Locate
AO-000412 | MM-ASK-1A-WP02-STR-RPT-1002 | WP02 TOPSIDE IN-PLACE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 14:36:36 | zm167dc@jutal.com | 05-Jun-2026 15:11:02 | Jumpol Sudjitjul | 15-Jun-2026 |  | Washira Kaew-amatawong | 16-Jun-2026 | 16-Jun-2026 11:56:07 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 18-Jun-2026 16:04:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 16:13:39 | 18-Jun-2026 09:38:22 | 0 |  |  | Approver | Locate
AO-000455 | MM-ASK-1A-WP02-STR-RPT-1003 | WP02 TOPSIDE LOADOUT ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:08:29 | zm167dc@jutal.com | 12-Jun-2026 09:37:15 | Jumpol Sudjitjul | 22-Jun-2026 | 19-Jun-2026 01:26:52 | Washira Kaew-amatawong | 23-Jun-2026 | 21-Jun-2026 15:21:58 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:43:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:40:33 | 23-Jun-2026 02:18:18 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-WP02-STR-RPT-1004 | WP02 TOPSIDE TRANSPORTATION ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:30:38 | zm167dc@jutal.com | 27-Jun-2026 19:37:52 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 09-Jul-2026 17:08:04 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 13:59:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:19:50 | 12-Jul-2026 04:42:34 | 0 |  |  | Approver | Locate
AO-000580 | MM-ASK-1A-WP02-STR-RPT-1005 | WP02 TOPSIDE TRANSPORTATION FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 14:51:18 | zm167dc@jutal.com | 30-Jun-2026 16:08:33 | Jumpol Sudjitjul | 08-Jul-2026 |  | Washira Kaew-amatawong | 09-Jul-2026 | 10-Jul-2026 13:52:22 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 14-Jul-2026 20:11:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 09:07:45 | 15-Jul-2026 07:04:27 | 0 |  |  | Approver | Locate
AO-000515 | MM-ASK-1A-WP02-STR-RPT-1006 | WP02 TOPSIDE LIFTING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 16:13:34 | zm167dc@jutal.com | 19-Jun-2026 16:39:11 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 28-Jun-2026 10:17:58 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 29-Jun-2026 00:33:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 30-Jun-2026 09:52:50 | 30-Jun-2026 03:29:49 | 0 |  |  | Approver | Locate
AO-001041 | MM-ASK-1A-WP02-STR-RPT-1009 | WP02 TOPSIDE MISCELLANEOUS DESIGN, FINITE ELEMENT ANALYSIS FOR CASING SLOT AND UNIHEAD SPACER AND STRUCTURAL DESIGN FOR DROPPED OBJECT REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-Aug-2026 17:22:04 | zm167dc@jutal.com | 21-Aug-2026 10:44:57 | Jumpol Sudjitjul | 31-Aug-2026 |  | Washira Kaew-amatawong | 01-Sep-2026 | 01-Sep-2026 14:17:02 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 02-Sep-2026 23:39:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 10:28:00 | 03-Sep-2026 04:35:07 | 0 |  |  | Approver | Locate
AO-000136 | MM-ASK-1A-WP02-STR-RPT-2001 | WP02 JACKET COMPUTER MODELLING & LOAD FORMULATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:01:14 | zm167dc@jutal.com | 06-May-2026 10:48:26 | Jumpol Sudjitjul | 14-May-2026 |  | Washira Kaew-amatawong | 15-May-2026 | 14-May-2026 14:10:35 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 22:03:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 20-May-2026 08:35:13 | 20-May-2026 01:52:43 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WP02-STR-RPT-2001 | WP02 JACKET COMPUTER MODELLING & LOAD FORMULATION REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:21:38 | zm167dc@jutal.com | 03-Jul-2026 13:24:32 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 14-Jul-2026 15:40:33 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:31:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:21:41 | 15-Jul-2026 03:17:24 | 0 |  |  | Approver | Locate
AO-000175 | MM-ASK-1A-WP02-STR-RPT-2002 | WP02 JACKET IN-PLACE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 18:10:40 | zm167dc@jutal.com | 08-May-2026 20:18:26 | Jumpol Sudjitjul | 19-May-2026 |  | Washira Kaew-amatawong | 20-May-2026 | 19-May-2026 15:51:14 | Pornlert Wanaphattharaphan | 21-May-2026 | 25-May-2026 21:51:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 22:21:07 | 25-May-2026 15:27:42 | 0 |  |  | Approver | Locate
AO-001126 | MM-ASK-1A-WP02-STR-RPT-2002 | WP02 JACKET IN-PLACE ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 14:45:13 | zm167dc@jutal.com | 28-Aug-2026 17:57:35 | Jumpol Sudjitjul | 08-Sep-2026 |  | Washira Kaew-amatawong | 09-Sep-2026 | 09-Sep-2026 16:10:13 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:58:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:23:50 | 12-Sep-2026 13:52:09 | 0 |  |  | Approver | Locate
AO-000269 | MM-ASK-1A-WP02-STR-RPT-2003 | WP02 JACKET DYNAMIC ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 15:28:35 | zm167dc@jutal.com | 15-May-2026 18:10:10 | Jumpol Sudjitjul | 26-May-2026 |  | Washira Kaew-amatawong | 27-May-2026 | 24-May-2026 20:17:59 | Pornlert Wanaphattharaphan | 28-May-2026 | 28-May-2026 00:36:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 28-May-2026 09:18:46 | 28-May-2026 02:29:28 | 0 |  |  | Approver | Locate
AO-001178 | MM-ASK-1A-WP02-STR-RPT-2003 | WP02 JACKET DYNAMIC ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 16:40:47 | zm167dc@jutal.com | 03-Sep-2026 16:44:19 | Jumpol Sudjitjul | 11-Sep-2026 |  | Washira Kaew-amatawong | 14-Sep-2026 | 13-Sep-2026 14:45:30 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 13-Sep-2026 16:54:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 22:45:44 | 13-Sep-2026 15:56:48 | 0 |  |  | Approver | Locate
AO-001194 | MM-ASK-1A-WP02-STR-RPT-2004 | WP02 PLATFORM SPECTRAL FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Sep-2026 12:40:01 | zm167dc@jutal.com | 05-Sep-2026 18:30:38 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 18-Sep-2026 10:58:00 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:15:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 16:44:03 | 20-Sep-2026 10:36:31 | 0 |  |  | Approver | Locate
AO-000902 | MM-ASK-1A-WP02-STR-RPT-2005 | WP02 JACKET LOADOUT ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 11:33:56 | zm167dc@jutal.com | 07-Aug-2026 15:21:23 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 21-Aug-2026 19:40:43 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 22-Aug-2026 12:54:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:28:19 | 24-Aug-2026 10:54:50 | 0 |  |  | Approver | Locate
AO-001203 | MM-ASK-1A-WP02-STR-RPT-2005 | WP02 JACKET LOADOUT ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 17:19:32 | zm167dc@jutal.com | 05-Sep-2026 18:22:12 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 18-Sep-2026 15:13:45 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:17:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 16:45:55 | 20-Sep-2026 10:38:41 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WP02-STR-RPT-2006 | WP02 JACKET TRANSPORTATION ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 15:21:28 | zm167dc@jutal.com | 21-Aug-2026 17:22:51 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 03-Sep-2026 08:53:08 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 05-Sep-2026 17:54:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 05-Sep-2026 17:58:44 | 05-Sep-2026 11:28:11 | 0 |  |  | Approver | Locate
AO-000508 | MM-ASK-1A-WP02-STR-RPT-2007 | WP02 JACKET LIFTING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 10:30:17 | zm167dc@jutal.com | 19-Jun-2026 10:33:36 | Jumpol Sudjitjul | 29-Jun-2026 |  | Washira Kaew-amatawong | 30-Jun-2026 | 29-Jun-2026 15:49:05 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 01-Jul-2026 23:47:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 13:02:58 | 02-Jul-2026 06:28:13 | 0 |  |  | Approver | Locate
AO-000777 | MM-ASK-1A-WP02-STR-RPT-2007 | WP02 JACKET LIFTING ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 16:07:53 | zm167dc@jutal.com | 26-Jul-2026 23:11:37 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 09-Aug-2026 15:25:13 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:51:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:23:18 | 10-Aug-2026 08:10:43 | 0 |  |  | Approver | Locate
AO-000310 | MM-ASK-1A-WP02-STR-RPT-2008 | WP02 PILE FATIGUE ANALYSIS , PILE STICK-UP AND HANDLING ANALYSIS AND PILE DRIVABILITY ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 16:59:48 | zm167dc@jutal.com | 21-May-2026 17:28:40 | Jumpol Sudjitjul | 02-Jun-2026 | 01-Jun-2026 21:51:52 | Washira Kaew-amatawong | 04-Jun-2026 | 03-Jun-2026 19:36:36 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 06-Jun-2026 21:51:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 07-Jun-2026 17:19:59 | 07-Jun-2026 10:48:51 | 0 |  |  | Approver | Locate
AO-000564 | MM-ASK-1A-WP02-STR-RPT-2008 | WP02 PILE FATIGUE ANALYSIS , PILE STICK-UP AND HANDLING ANALYSIS AND PILE DRIVABILITY ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:31:29 | zm167dc@jutal.com | 27-Jun-2026 19:36:21 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 09-Jul-2026 11:03:57 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 14:00:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:27:15 | 12-Jul-2026 04:45:18 | 0 |  |  | Approver | Locate
AO-000457 | MM-ASK-1A-WP02-STR-RPT-2009 | WP02 JACKET ON-BOTTOM STABILITY ANALYSIS & MUDMAT DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:09:04 | zm167dc@jutal.com | 12-Jun-2026 09:39:00 | Jumpol Sudjitjul | 22-Jun-2026 | 19-Jun-2026 01:29:07 | Washira Kaew-amatawong | 23-Jun-2026 | 22-Jun-2026 08:11:55 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 23:04:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 23-Jun-2026 08:41:29 | 23-Jun-2026 02:19:46 | 0 |  |  | Approver | Locate
AO-000660 | MM-ASK-1A-WP02-STR-RPT-2009 | WP02 JACKET ON-BOTTOM STABILITY ANALYSIS & MUDMAT DESIGN REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 08-Jul-2026 20:00:41 | zm167dc@jutal.com | 09-Jul-2026 10:26:55 | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 17:26:05 | Washira Kaew-amatawong | 20-Jul-2026 | 20-Jul-2026 14:31:24 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 23:00:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 08:50:12 | 23-Jul-2026 02:07:14 | 0 |  |  | Approver | Locate
AO-000904 | MM-ASK-1A-WP02-STR-RPT-2009 | WP02 JACKET ON-BOTTOM STABILITY ANALYSIS & MUDMAT DESIGN REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 11:34:27 | zm167dc@jutal.com | 07-Aug-2026 15:18:42 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 21-Aug-2026 18:48:58 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 22-Aug-2026 12:55:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:28:25 | 24-Aug-2026 10:56:19 | 0 |  |  | Approver | Locate
AO-000957 | MM-ASK-1A-WP02-STR-RPT-2012 | WP02 JACKET CATHODIC PROTECTION DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 11-Aug-2026 17:29:48 | zm167dc@jutal.com | 11-Aug-2026 17:47:37 | Jumpol Sudjitjul | 21-Aug-2026 |  | Washira Kaew-amatawong | 24-Aug-2026 | 24-Aug-2026 17:32:14 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 27-Aug-2026 14:55:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 27-Aug-2026 15:43:23 | 27-Aug-2026 10:29:18 | 0 |  |  | Approver | Locate
AO-001353 | MM-ASK-1A-WP02-STR-RPT-2012 | WP02 JACKET CATHODIC PROTECTION DESIGN REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 14-Sep-2026 09:21:55 | zm167dc@jutal.com | 15-Sep-2026 13:45:45 | Jumpol Sudjitjul | 23-Sep-2026 |  | Washira Kaew-amatawong | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  |  |  |  | 28-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000615 | MM-ASK-1A-WP02-STR-RPT-2013 | WP02 JACKET MISCELLANEOUS DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:12:00 | zm167dc@jutal.com | 03-Jul-2026 18:24:42 | Jumpol Sudjitjul | 14-Jul-2026 | 15-Jul-2026 15:26:53 | Washira Kaew-amatawong | 15-Jul-2026 | 16-Jul-2026 09:28:54 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 17-Jul-2026 00:34:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 17-Jul-2026 09:41:48 | 17-Jul-2026 03:24:05 | 0 |  |  | Approver | Locate
AO-000987 | MM-ASK-1A-WP02-STR-RPT-2014 | WP02 JACKET TRANSPORTATION FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 15:28:15 | zm167dc@jutal.com | 14-Aug-2026 15:33:41 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 28-Aug-2026 13:47:47 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 29-Aug-2026 19:58:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 30-Aug-2026 16:35:41 | 30-Aug-2026 10:49:11 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WP02-STR-RPT-2015 | WP02 JACKET LEVELING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 15:21:58 | zm167dc@jutal.com | 21-Aug-2026 17:20:12 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 03-Sep-2026 11:14:56 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 04-Sep-2026 23:59:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 05-Sep-2026 17:59:09 | 05-Sep-2026 12:16:13 | 0 |  |  | Approver | Locate
AO-000560 | MM-ASK-1A-WP02-STR-RPT-2021 | WP02 JACKET SEISMIC ANALYSIS REPORT- ELE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:35:11 | zm167dc@jutal.com | 26-Jun-2026 16:44:15 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 13:56:16 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 04-Jul-2026 19:37:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 05-Jul-2026 10:32:24 | 05-Jul-2026 03:51:40 | 0 |  |  | Approver | Locate
AO-001201 | MM-ASK-1A-WP02-STR-RPT-2021 | WP02 JACKET SEISMIC ANALYSIS REPORT- ELE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 17:20:08 | zm167dc@jutal.com | 05-Sep-2026 18:22:36 | Jumpol Sudjitjul | 15-Sep-2026 |  | Washira Kaew-amatawong | 16-Sep-2026 | 18-Sep-2026 15:19:08 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:18:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 16:42:14 | 20-Sep-2026 10:35:11 | 0 |  |  | Approver | Locate
AO-000789 | MM-ASK-1A-WP02-STR-RPT-2022 | WP02 JACKET SEISMIC ANALYSIS REPORT - ALE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 25-Jul-2026 09:50:40 | zm167dc@jutal.com | 26-Jul-2026 23:11:55 | Jumpol Sudjitjul | 06-Aug-2026 |  | Washira Kaew-amatawong | 07-Aug-2026 | 10-Aug-2026 19:37:20 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:03:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:47:35 | 13-Aug-2026 04:45:21 | 0 |  |  | Approver | Locate
AO-000731 | MM-ASK-1A-WP02-STR-RPT-2031 | WP02 BOAT IMPACT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 09:49:41 | zm167dc@jutal.com | 20-Jul-2026 13:19:24 | Jumpol Sudjitjul | 30-Jul-2026 |  | Washira Kaew-amatawong | 31-Jul-2026 | 31-Jul-2026 14:26:26 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 20:02:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 21:08:39 | 02-Aug-2026 14:51:56 | 0 |  |  | Approver | Locate
AO-001060 | MM-ASK-1A-WP02-STR-RPT-2031 | WP02 BOAT IMPACT ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 17:28:46 | zm167dc@jutal.com | 21-Aug-2026 17:31:45 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 03-Sep-2026 13:35:07 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 04-Sep-2026 23:57:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 05-Sep-2026 17:59:41 | 05-Sep-2026 11:30:16 | 0 |  |  | Approver | Locate
AO-001343 | MM-ASK-1A-WP02-STR-RPT-2031 | WP02 BOAT IMPACT ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:34:45 | zm167dc@jutal.com | 11-Sep-2026 20:27:09 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000994 | MM-ASK-1A-WP02-STR-RPT-2032 | WP02 NON-LINEAR STATIC PUSHOVER ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 17:24:10 | zm167dc@jutal.com | 14-Aug-2026 17:29:03 | Jumpol Sudjitjul | 25-Aug-2026 |  | Washira Kaew-amatawong | 26-Aug-2026 | 28-Aug-2026 15:13:30 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 23:07:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 16:37:39 | 30-Aug-2026 10:26:11 | 0 |  |  | Approver | Locate
AO-000639 | MM-ASK-1A-WP02-STR-WCR-1001 | WP02 TOPSIDE WEIGHT CONTROL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFR | Issued for Review |  | 07-Jul-2026 00:09:40 | zm167dc@jutal.com | 07-Jul-2026 10:17:01 | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 15:30:43 | Washira Kaew-amatawong | 16-Jul-2026 | 16-Jul-2026 12:47:18 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 19-Jul-2026 17:10:43 | NA | Not Approved | Jumpol Sudjitjul | 20-Jul-2026 | 20-Jul-2026 09:17:06 | 20-Jul-2026 02:37:59 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-STR-WCR-1001 | WP02 TOPSIDE WEIGHT CONTROL REPORT |  | A2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:05:07 | zm167dc@jutal.com | 24-Jul-2026 14:57:36 | Jumpol Sudjitjul | 05-Aug-2026 | 24-Jul-2026 16:19:18 | Washira Kaew-amatawong | 06-Aug-2026 | 06-Aug-2026 14:36:04 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 05:39:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 11:16:00 | 07-Aug-2026 05:23:52 | 0 |  |  | Approver | Locate
AO-001340 | MM-ASK-1A-WP02-STR-WCR-2001 | WP02 JACKET WEIGHT CONTROL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | STR | Structural | WCR | Weight Control Report | 0 | In Review | IFR | Issued for Review |  | 11-Sep-2026 19:35:30 | zm167dc@jutal.com | 11-Sep-2026 20:28:53 | Jumpol Sudjitjul | 22-Sep-2026 |  | Washira Kaew-amatawong | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-WP02-TEL-DTS-0001 | DATA SHEET FOR WIMAX RADIO - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 15:29:56 | zm167dc@jutal.com | 10-Jun-2026 13:56:12 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 13:36:10 | Noppadol Iamtanasinchai | 19-Jun-2026 | 17-Jun-2026 08:51:09 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 06:49:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 12:45:10 | 22-Jun-2026 06:18:13 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP02-TEL-DTS-0001 | DATA SHEET FOR WIMAX RADIO - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 02-Jul-2026 16:05:50 | zm167dc@jutal.com | 02-Jul-2026 16:38:53 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:30:56 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:32:58 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:00:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:20:07 | 15-Jul-2026 03:34:21 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WP02-TEL-DTS-0001 | DATA SHEET FOR WIMAX RADIO - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 14:05:32 | zm167dc@jutal.com | 24-Jul-2026 14:49:44 | Jumpol Sudjitjul | 05-Aug-2026 | 24-Jul-2026 16:18:25 | Danai Chaisalee | 06-Aug-2026 | 04-Aug-2026 15:15:25 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 05-Aug-2026 23:35:36 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 06-Aug-2026 09:09:28 | 06-Aug-2026 03:13:28 | 0 |  |  | Approver | Locate
AO-000251 | MM-ASK-1A-WP02-TEL-DTS-0002 | DATA SHEET FOR RADAR BEACON - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 17:43:17 | zm167dc@jutal.com | 15-May-2026 17:40:00 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 20:18:26 | Noppadol Iamtanasinchai | 27-May-2026 | 26-May-2026 10:10:46 | Pornlert Wanaphattharaphan | 28-May-2026 | 09-Jun-2026 00:57:12 | APPR | Approved | Jumpol Sudjitjul | 29-May-2026 | 09-Jun-2026 07:44:50 | 09-Jun-2026 08:28:56 | 0 |  |  | Approver | Locate
AO-000452 | MM-ASK-1A-WP02-TEL-DTS-0002 | DATA SHEET FOR RADAR BEACON - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 17:14:32 | zm167dc@jutal.com | 11-Jun-2026 17:42:10 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 17:12:05 | Noppadol Iamtanasinchai | 23-Jun-2026 | 21-Jun-2026 10:44:05 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:27:21 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:16:17 | 25-Jun-2026 07:37:53 | 0 |  |  | Approver | Locate
AO-000581 | MM-ASK-1A-WP02-TEL-DTS-0002 | DATA SHEET FOR RADAR BEACON - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 01-Jul-2026 08:37:59 | zm167dc@jutal.com | 01-Jul-2026 10:17:40 | Jumpol Sudjitjul | 09-Jul-2026 | 03-Jul-2026 15:21:55 | Danai Chaisalee | 10-Jul-2026 | 09-Jul-2026 16:28:12 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 14-Jul-2026 23:44:56 | APPR | Approved | Jumpol Sudjitjul | 14-Jul-2026 | 15-Jul-2026 09:22:18 | 15-Jul-2026 03:36:49 | 0 |  |  | Approver | Locate
AO-000252 | MM-ASK-1A-WP02-TEL-DTS-0003 | DATA SHEET FOR AUTOMATIC IDENTIFICATION SYSTEM - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 17:43:42 | zm167dc@jutal.com | 15-May-2026 17:40:00 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 20:15:15 | Noppadol Iamtanasinchai | 27-May-2026 | 26-May-2026 10:13:24 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 00:00:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:42:39 | 10-Jun-2026 14:25:17 | 0 |  |  | Approver | Locate
AO-000476 | MM-ASK-1A-WP02-TEL-DTS-0003 | DATA SHEET FOR AUTOMATIC IDENTIFICATION SYSTEM - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:06:28 | zm167dc@jutal.com | 13-Jun-2026 08:17:33 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 23-Jun-2026 10:40:03 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:07:24 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:16:50 | 25-Jun-2026 07:39:07 | 0 |  |  | Approver | Locate
AO-000581 | MM-ASK-1A-WP02-TEL-DTS-0003 | DATA SHEET FOR AUTOMATIC IDENTIFICATION SYSTEM - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 01-Jul-2026 08:38:38 | zm167dc@jutal.com | 01-Jul-2026 10:18:15 | Jumpol Sudjitjul | 09-Jul-2026 | 03-Jul-2026 15:23:05 | Danai Chaisalee | 10-Jul-2026 | 09-Jul-2026 16:29:37 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 14-Jul-2026 23:54:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 15-Jul-2026 09:08:05 | 15-Jul-2026 02:35:19 | 0 |  |  | Approver | Locate
AO-000829 | MM-ASK-1A-WP02-TEL-DTS-0003 | DATA SHEET FOR AUTOMATIC IDENTIFICATION SYSTEM - WP02 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 17:18:07 | zm167dc@jutal.com | 31-Jul-2026 21:43:48 | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 13:11:02 | Danai Chaisalee | 13-Aug-2026 | 05-Aug-2026 09:15:18 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 19:40:57 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 10:46:57 | 13-Aug-2026 04:40:36 | 0 |  |  | Approver | Locate
AO-000253 | MM-ASK-1A-WP02-TEL-DTS-0004 | DATA SHEET FOR VHF-DMR - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 17:44:07 | zm167dc@jutal.com | 15-May-2026 17:40:00 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 19:32:49 | Noppadol Iamtanasinchai | 27-May-2026 | 26-May-2026 10:11:43 | Pornlert Wanaphattharaphan | 28-May-2026 | 09-Jun-2026 12:24:50 | APPR | Approved | Jumpol Sudjitjul | 29-May-2026 | 09-Jun-2026 13:31:44 | 09-Jun-2026 13:48:18 | 0 |  |  | Approver | Locate
AO-000452 | MM-ASK-1A-WP02-TEL-DTS-0004 | DATA SHEET FOR VHF-DMR - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 11-Jun-2026 15:57:09 | zm167dc@jutal.com | 16-Jun-2026 17:38:56 | Jumpol Sudjitjul | 19-Jun-2026 | 24-Jun-2026 15:23:01 | Noppadol Iamtanasinchai | 22-Jun-2026 | 25-Jun-2026 17:00:36 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 27-Jun-2026 23:55:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 28-Jun-2026 08:39:14 | 28-Jun-2026 02:23:26 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP02-TEL-DTS-0004 | DATA SHEET FOR VHF-DMR - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 02-Jul-2026 15:30:08 | zm167dc@jutal.com | 02-Jul-2026 16:39:02 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:35:13 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:37:54 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:04:43 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:20:39 | 15-Jul-2026 03:14:34 | 0 |  |  | Approver | Locate
AO-000254 | MM-ASK-1A-WP02-TEL-DTS-0005 | DATA SHEET FOR VHF-FM - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 17:44:31 | zm167dc@jutal.com | 15-May-2026 17:40:01 | Jumpol Sudjitjul | 26-May-2026 | 24-May-2026 19:44:21 | Noppadol Iamtanasinchai | 27-May-2026 | 26-May-2026 10:16:12 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 00:20:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:42:01 | 10-Jun-2026 14:26:24 | 0 |  |  | Approver | Locate
AO-000476 | MM-ASK-1A-WP02-TEL-DTS-0005 | DATA SHEET FOR VHF-FM - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 13-Jun-2026 08:06:57 | zm167dc@jutal.com | 13-Jun-2026 08:17:48 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 23-Jun-2026 10:41:22 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:07:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:17:37 | 25-Jun-2026 07:40:26 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP02-TEL-DTS-0005 | DATA SHEET FOR VHF-FM - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 02-Jul-2026 15:30:48 | zm167dc@jutal.com | 02-Jul-2026 16:38:57 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:34:07 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:35:41 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:02:33 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:25:24 | 15-Jul-2026 03:45:32 | 0 |  |  | Approver | Locate
AO-000278 | MM-ASK-1A-WP02-TEL-DTS-0006 | DATA SHEET FOR TELEPHONE - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 18:50:20 | zm167dc@jutal.com | 17-May-2026 10:35:45 | Jumpol Sudjitjul | 25-May-2026 |  | Noppadol Iamtanasinchai | 26-May-2026 | 23-May-2026 12:48:19 | Pornlert Wanaphattharaphan | 27-May-2026 | 01-Jun-2026 15:45:55 | APPR | Approved | Jumpol Sudjitjul | 28-May-2026 | 01-Jun-2026 22:10:32 | 01-Jun-2026 22:27:52 | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-WP02-TEL-DTS-0006 | DATA SHEET FOR TELEPHONE - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 13:47:09 | zm167dc@jutal.com | 10-Jun-2026 13:56:10 | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 14:06:33 | Noppadol Iamtanasinchai | 19-Jun-2026 | 17-Jun-2026 08:47:50 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 06:40:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 12:49:29 | 22-Jun-2026 06:33:34 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP02-TEL-DTS-0006 | DATA SHEET FOR TELEPHONE - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 02-Jul-2026 15:31:59 | zm167dc@jutal.com | 02-Jul-2026 16:38:58 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:34:33 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:36:33 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:03:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:31:59 | 15-Jul-2026 03:46:57 | 0 |  |  | Approver | Locate
AO-000714 | MM-ASK-1A-WP02-TEL-DTS-0006 | DATA SHEET FOR TELEPHONE - WP02 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 11:57:22 | zm167dc@jutal.com | 17-Jul-2026 12:00:54 | Jumpol Sudjitjul | 27-Jul-2026 |  | Danai Chaisalee | 30-Jul-2026 | 22-Jul-2026 15:17:27 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:12:17 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 14:41:47 | 27-Jul-2026 08:44:04 | 0 |  |  | Approver | Locate
AO-000255 | MM-ASK-1A-WP02-TEL-DTS-0007 | DATA SHEET FOR BULK MATERIAL - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 11:31:43 | zm167dc@jutal.com | 15-May-2026 11:39:04 | Jumpol Sudjitjul | 25-May-2026 |  | Noppadol Iamtanasinchai | 26-May-2026 | 23-May-2026 12:40:09 | Pornlert Wanaphattharaphan | 27-May-2026 | 01-Jun-2026 16:01:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 01-Jun-2026 22:10:55 | 01-Jun-2026 22:28:54 | 0 |  |  | Approver | Locate
AO-000437 | MM-ASK-1A-WP02-TEL-DTS-0007 | DATA SHEET FOR BULK MATERIAL - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 13:02:18 | zm167dc@jutal.com | 10-Jun-2026 13:56:14 | Jumpol Sudjitjul | 18-Jun-2026 | 16-Jun-2026 15:57:20 | Noppadol Iamtanasinchai | 19-Jun-2026 | 17-Jun-2026 08:52:05 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 06:59:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 12:51:30 | 22-Jun-2026 06:38:36 | 0 |  |  | Approver | Locate
AO-000672 | MM-ASK-1A-WP02-TEL-DTS-0007 | DATA SHEET FOR BULK MATERIAL - WP02 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 16:50:50 | zm167dc@jutal.com | 10-Jul-2026 17:26:29 | Jumpol Sudjitjul | 21-Jul-2026 | 14-Jul-2026 11:24:17 | Danai Chaisalee | 22-Jul-2026 | 17-Jul-2026 09:52:18 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:31:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 09:16:26 | 20-Jul-2026 03:22:04 | 0 |  |  | Approver | Locate
AO-000913 | MM-ASK-1A-WP02-TEL-DTS-0007 | DATA SHEET FOR BULK MATERIAL - WP02 |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:57:01 | zm167dc@jutal.com | 07-Aug-2026 16:43:19 | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 10:49:25 | Danai Chaisalee | 19-Aug-2026 | 19-Aug-2026 13:10:19 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:47:47 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:31:50 | 24-Aug-2026 11:12:25 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-TEL-DWG-0001 | TELECOMMUNICTION INSTALLATION AND MOUNTING DETAIL - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 09:03:31 | zm167dc@jutal.com | 11-Sep-2026 19:54:00 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 | 17-Sep-2026 14:59:10 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 23:44:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 16:41:28 | 20-Sep-2026 11:05:33 | 0 |  |  | Approver | Locate
AO-001124 | MM-ASK-1A-WP02-TEL-LAY-0001 | TELECOMMUNICTION CABLE ROUTING PLAN - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-Aug-2026 14:45:45 | zm167dc@jutal.com | 28-Aug-2026 17:42:35 | Jumpol Sudjitjul | 08-Sep-2026 |  | Danai Chaisalee | 09-Sep-2026 | 08-Sep-2026 15:13:34 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 22:57:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 19:53:29 | 12-Sep-2026 13:24:22 | 0 |  |  | Approver | Locate
AO-000948 | MM-ASK-1A-WP02-TEL-LAY-0002 | TELECOMMUNICTION EQUIPMENT LAYOUT - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Aug-2026 10:42:57 | zm167dc@jutal.com | 11-Aug-2026 11:47:05 | Jumpol Sudjitjul | 20-Aug-2026 | 13-Aug-2026 12:17:52 | Danai Chaisalee | 21-Aug-2026 | 20-Aug-2026 14:17:52 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 21-Aug-2026 20:05:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Aug-2026 | 24-Aug-2026 17:30:28 | 24-Aug-2026 11:11:17 | 0 |  |  | Approver | Locate
AO-001305 | MM-ASK-1A-WP02-TEL-LAY-0002 | TELECOMMUNICTION EQUIPMENT LAYOUT - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 09:04:25 | zm167dc@jutal.com | 11-Sep-2026 19:54:55 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP02-TEL-LIS-0001 | TELECOMMUNICTION DOCUMENT INDEX - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 02-Jul-2026 15:32:56 | zm167dc@jutal.com | 02-Jul-2026 16:41:14 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:36:25 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:40:35 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:30:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:38:17 | 15-Jul-2026 03:48:07 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WP02-TEL-LIS-0001 | TELECOMMUNICTION DOCUMENT INDEX - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:37:13 | zm167dc@jutal.com | 14-Aug-2026 08:44:54 | Jumpol Sudjitjul | 24-Aug-2026 |  | Danai Chaisalee | 25-Aug-2026 | 21-Aug-2026 10:57:28 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 13:00:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 17:32:24 | 24-Aug-2026 11:13:42 | 0 |  |  | Approver | Locate
AO-001304 | MM-ASK-1A-WP02-TEL-LIS-0001 | TELECOMMUNICTION DOCUMENT INDEX - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 09:05:16 | zm167dc@jutal.com | 11-Sep-2026 12:41:16 | Jumpol Sudjitjul | 21-Sep-2026 |  | Danai Chaisalee | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000704 | MM-ASK-1A-WP02-TEL-LIS-0002 | TELECOMMUNICTION EQUIPMENT LIST - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 15-Jul-2026 17:58:35 | zm167dc@jutal.com | 15-Jul-2026 18:03:15 | Jumpol Sudjitjul | 24-Jul-2026 |  | Danai Chaisalee | 27-Jul-2026 | 22-Jul-2026 15:10:27 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 09:19:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 14:41:12 | 27-Jul-2026 09:22:33 | 0 |  |  | Approver | Locate
AO-000888 | MM-ASK-1A-WP02-TEL-LIS-0002 | TELECOMMUNICTION EQUIPMENT LIST - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 11:49:30 | zm167dc@jutal.com | 05-Aug-2026 12:00:04 | Jumpol Sudjitjul | 14-Aug-2026 | 05-Aug-2026 17:30:02 | Danai Chaisalee | 17-Aug-2026 | 07-Aug-2026 13:55:01 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 12-Aug-2026 23:50:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 13-Aug-2026 10:45:45 | 13-Aug-2026 04:38:24 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WP02-TEL-LIS-0003 | TELECOMMUNICTION CABLE SCHEDULE - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 12:11:04 | zm167dc@jutal.com | 16-Jul-2026 14:42:52 | Jumpol Sudjitjul | 24-Jul-2026 |  | Danai Chaisalee | 27-Jul-2026 | 22-Jul-2026 15:12:16 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 09:56:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 14:40:29 | 27-Jul-2026 08:40:32 | 0 |  |  | Approver | Locate
AO-001316 | MM-ASK-1A-WP02-TEL-LIS-0003 | TELECOMMUNICTION CABLE SCHEDULE - WP02 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | In Review | IFA | Issued for Approval |  | 11-Sep-2026 19:38:13 | zm167dc@jutal.com | 11-Sep-2026 20:31:02 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001053 | MM-ASK-1A-WP02-TEL-LIS-0004 | TELECOMMUNICTION POWER CPNSTRUCTION AND HEAT DISSIPATION LIST - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 11:31:04 | zm167dc@jutal.com | 21-Aug-2026 14:15:59 | Jumpol Sudjitjul | 31-Aug-2026 |  | Danai Chaisalee | 01-Sep-2026 | 01-Sep-2026 08:02:36 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 02-Sep-2026 23:37:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 10:37:44 | 03-Sep-2026 05:16:34 | 0 |  |  | Approver | Locate
AO-000596 | MM-ASK-1A-WP02-TEL-LIS-0005 | TELECOMMUNICTION DRAWING INDEX - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 02-Jul-2026 15:33:42 | zm167dc@jutal.com | 02-Jul-2026 16:41:30 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 15:37:14 | Danai Chaisalee | 13-Jul-2026 | 09-Jul-2026 16:41:28 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 15-Jul-2026 00:30:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 09:40:58 | 15-Jul-2026 03:49:21 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WP02-TEL-LIS-0005 | TELECOMMUNICTION DRAWING INDEX - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:37:38 | zm167dc@jutal.com | 14-Aug-2026 08:45:10 | Jumpol Sudjitjul | 24-Aug-2026 |  | Danai Chaisalee | 25-Aug-2026 | 21-Aug-2026 10:58:28 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 12:59:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 17:29:49 | 24-Aug-2026 11:10:00 | 0 |  |  | Approver | Locate
AO-001304 | MM-ASK-1A-WP02-TEL-LIS-0005 | TELECOMMUNICTION DRAWING INDEX - WP02 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 09:06:00 | zm167dc@jutal.com | 11-Sep-2026 12:41:31 | Jumpol Sudjitjul | 21-Sep-2026 |  | Danai Chaisalee | 22-Sep-2026 |  | Pornlert Wanaphattharaphan | 23-Sep-2026 |  |  |  |  | 24-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001319 | MM-ASK-1A-WP02-TEL-MTO-0001 | TELECOMMUNICTION BULK MATERIAL TAKE -OFF - WP02 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | WPA02 |  |  | TEL | Telecommunication | MTO | Material Take Off | 0 | In Review | IFR | Issued for Review |  | 11-Sep-2026 19:38:40 | zm167dc@jutal.com | 11-Sep-2026 20:32:23 | Jumpol Sudjitjul | 22-Sep-2026 |  | Danai Chaisalee | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001185 | MM-ASK-1A-WP02-TEL-SCH-0001 | TELECOMMUNICTION SCHEMATIC DIAGRAM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | SCH | Schematic | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 18:06:36 | zm167dc@jutal.com | 04-Sep-2026 11:27:29 | Jumpol Sudjitjul | 14-Sep-2026 |  | Danai Chaisalee | 15-Sep-2026 | 14-Sep-2026 11:05:39 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 18-Sep-2026 22:52:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 20-Sep-2026 16:21:14 | 20-Sep-2026 10:32:56 | 0 |  |  | Approver | Locate
AO-000829 | MM-ASK-1A-WP02-TEL-SLD-0001 | TELECOMMUNICTION SYSTEM BLOCK DIAGRAM - WP02 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 17:18:36 | zm167dc@jutal.com | 31-Jul-2026 21:56:47 | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 13:10:47 | Danai Chaisalee | 13-Aug-2026 | 05-Aug-2026 14:35:13 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 19:50:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 10:44:46 | 13-Aug-2026 04:35:54 | 0 |  |  | Approver | Locate
AO-001172 | MM-ASK-1A-WP02-TEL-SLD-0001 | TELECOMMUNICTION SYSTEM BLOCK DIAGRAM - WP02 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPA02 |  |  | TEL | Telecommunication | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 14:56:50 | zm167dc@jutal.com | 03-Sep-2026 16:28:09 | Jumpol Sudjitjul | 11-Sep-2026 |  | Danai Chaisalee | 14-Sep-2026 | 14-Sep-2026 10:41:58 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 17-Sep-2026 22:52:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 18-Sep-2026 18:03:49 | 18-Sep-2026 12:04:02 | 0 |  |  | Approver | Locate
AO-000150 | MM-ASK-1A-WPAX-ELE-DWG-0001 | ELECTRICAL SYMBOLS AND LEGENDS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-May-2026 14:33:08 | zm167dc@jutal.com | 07-May-2026 14:55:45 | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 08:54:12 | Noppadol Iamtanasinchai | 18-May-2026 | 20-May-2026 10:48:44 | Pornlert Wanaphattharaphan | 19-May-2026 | 21-May-2026 21:46:26 | APPR | Approved | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 08:19:00 | 22-May-2026 08:31:47 | 0 |  |  | Approver | Locate
AO-000508 | MM-ASK-1A-WPAX-ELE-DWG-0001 | ELECTRICAL SYMBOLS AND LEGENDS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Jun-2026 10:33:09 | zm167dc@jutal.com | 19-Jun-2026 10:39:58 | Jumpol Sudjitjul | 29-Jun-2026 | 29-Jun-2026 15:16:02 | Danai Chaisalee | 30-Jun-2026 | 30-Jun-2026 09:45:32 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 01-Jul-2026 22:53:21 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 02-Jul-2026 13:05:17 | 02-Jul-2026 06:30:00 | 0 |  |  | Approver | Locate
AO-000197 | MM-ASK-1A-WPAX-ELE-TYP-0001-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - LIGHTING AND SMALL POWER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:45:24 | zm167dc@jutal.com | 11-May-2026 17:53:17 | Jumpol Sudjitjul | 20-May-2026 | 21-May-2026 14:20:29 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:43:37 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:06:03 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:42:46 | 01-Jun-2026 15:17:39 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0001-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - LIGHTING AND SMALL POWER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 11:59:11 | zm167dc@jutal.com | 12-Jun-2026 12:33:39 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 09:49:13 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:36:16 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:46:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:10:34 | 25-Jun-2026 06:21:43 | 0 |  |  | Approver | Locate
AO-000198 | MM-ASK-1A-WPAX-ELE-TYP-0001-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - LIGHTING AND SMALL POWER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:45:48 | zm167dc@jutal.com | 11-May-2026 17:53:32 | Jumpol Sudjitjul | 20-May-2026 | 21-May-2026 14:22:04 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:44:45 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:06:56 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:44:03 | 31-May-2026 17:53:14 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0001-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - LIGHTING AND SMALL POWER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 11:59:35 | zm167dc@jutal.com | 12-Jun-2026 12:33:39 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 09:51:29 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 10:32:29 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 22-Jun-2026 12:14:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 12:52:10 | 22-Jun-2026 06:40:06 | 0 |  |  | Approver | Locate
AO-000199 | MM-ASK-1A-WPAX-ELE-TYP-0001-003 | ELECTRICAL TYPICAL INSTALLATION DETAILS - LIGHTING AND SMALL POWER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:46:11 | zm167dc@jutal.com | 11-May-2026 17:53:45 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 09:48:58 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:45:18 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:08:36 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:45:09 | 31-May-2026 17:54:08 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0001-003 | ELECTRICAL TYPICAL INSTALLATION DETAILS - LIGHTING AND SMALL POWER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 11:59:57 | zm167dc@jutal.com | 12-Jun-2026 12:33:38 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 09:46:57 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:32:26 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:43:32 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:11:19 | 25-Jun-2026 06:23:11 | 0 |  |  | Approver | Locate
AO-000200 | MM-ASK-1A-WPAX-ELE-TYP-0002-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:46:34 | zm167dc@jutal.com | 11-May-2026 17:54:02 | Jumpol Sudjitjul | 20-May-2026 | 24-May-2026 19:11:30 | Noppadol Iamtanasinchai | 21-May-2026 | 25-May-2026 08:56:39 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 13:31:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:46:28 | 31-May-2026 17:49:30 | 0 |  |  | Approver | Locate
AO-000471 | MM-ASK-1A-WPAX-ELE-TYP-0002-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 18:01:26 | zm167dc@jutal.com | 13-Jun-2026 07:15:53 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 22-Jun-2026 12:20:58 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:30:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:18:34 | 25-Jun-2026 07:08:52 | 0 |  |  | Approver | Locate
AO-000201 | MM-ASK-1A-WPAX-ELE-TYP-0002-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:46:57 | zm167dc@jutal.com | 11-May-2026 17:57:05 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 13:04:00 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:51:04 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:09:02 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:47:00 | 31-May-2026 17:50:28 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0002-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:00:21 | zm167dc@jutal.com | 12-Jun-2026 12:33:38 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 10:45:21 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:33:23 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:44:10 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:23:02 | 25-Jun-2026 07:27:45 | 0 |  |  | Approver | Locate
AO-000202 | MM-ASK-1A-WPAX-ELE-TYP-0002-003 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:47:21 | zm167dc@jutal.com | 11-May-2026 17:57:22 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 13:08:30 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:51:36 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:09:31 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:47:36 | 31-May-2026 17:51:28 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0002-003 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:00:44 | zm167dc@jutal.com | 12-Jun-2026 12:33:39 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 10:46:34 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:34:23 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:45:23 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:21:46 | 25-Jun-2026 07:44:18 | 0 |  |  | Approver | Locate
AO-000203 | MM-ASK-1A-WPAX-ELE-TYP-0002-004 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:47:46 | zm167dc@jutal.com | 11-May-2026 17:57:36 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 13:21:31 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:52:06 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:10:00 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:47:41 | 31-May-2026 17:52:20 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0002-004 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:01:07 | zm167dc@jutal.com | 12-Jun-2026 12:33:41 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 10:47:46 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:37:06 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:46:47 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:23:56 | 25-Jun-2026 07:46:43 | 0 |  |  | Approver | Locate
AO-000204 | MM-ASK-1A-WPAX-ELE-TYP-0002-005 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:48:12 | zm167dc@jutal.com | 11-May-2026 17:57:51 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 13:26:34 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:54:30 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:13:04 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:48:21 | 31-May-2026 18:42:58 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0002-005 | ELECTRICAL TYPICAL INSTALLATION DETAILS - EARTHING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:01:31 | zm167dc@jutal.com | 12-Jun-2026 12:33:44 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 10:49:14 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:37:45 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:47:20 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:24:47 | 25-Jun-2026 07:48:00 | 0 |  |  | Approver | Locate
AO-000205 | MM-ASK-1A-WPAX-ELE-TYP-0003-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - CABLE LADDER/ TRAY |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:48:41 | zm167dc@jutal.com | 11-May-2026 17:57:41 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 13:23:08 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:52:57 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:11:02 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:49:14 | 31-May-2026 18:43:49 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0003-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - CABLE LADDER/ TRAY |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:01:54 | zm167dc@jutal.com | 12-Jun-2026 12:34:41 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 11:17:51 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:42:03 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:49:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:13:09 | 25-Jun-2026 06:36:38 | 0 |  |  | Approver | Locate
AO-000206 | MM-ASK-1A-WPAX-ELE-TYP-0003-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - CABLE LADDER/ TRAY |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:49:06 | zm167dc@jutal.com | 11-May-2026 17:57:55 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 17:31:00 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:55:29 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:14:20 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:49:56 | 31-May-2026 18:44:41 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0003-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - CABLE LADDER/ TRAY |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:02:17 | zm167dc@jutal.com | 12-Jun-2026 12:34:43 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 11:19:52 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:48:33 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:53:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:25:58 | 25-Jun-2026 07:49:30 | 0 |  |  | Approver | Locate
AO-000207 | MM-ASK-1A-WPAX-ELE-TYP-0003-003 | ELECTRICAL TYPICAL INSTALLATION DETAILS - CABLE LADDER/ TRAY |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:49:29 | zm167dc@jutal.com | 11-May-2026 17:58:10 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 17:32:09 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:55:53 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:14:53 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:51:06 | 31-May-2026 18:45:33 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0003-003 | ELECTRICAL TYPICAL INSTALLATION DETAILS - CABLE LADDER/ TRAY |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:02:39 | zm167dc@jutal.com | 12-Jun-2026 12:34:43 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 11:21:53 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:50:03 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:53:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:27:29 | 25-Jun-2026 07:51:13 | 0 |  |  | Approver | Locate
AO-000208 | MM-ASK-1A-WPAX-ELE-TYP-0004-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - NAVIGATION AID SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:49:51 | zm167dc@jutal.com | 11-May-2026 17:58:50 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 17:34:41 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:57:08 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:16:04 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:50:39 | 31-May-2026 18:23:18 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0004-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - NAVIGATION AID SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:03:02 | zm167dc@jutal.com | 12-Jun-2026 12:34:41 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 14:14:39 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:39:54 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:48:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:28:48 | 25-Jun-2026 07:52:33 | 0 |  |  | Approver | Locate
AO-000209 | MM-ASK-1A-WPAX-ELE-TYP-0004-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - NAVIGATION AID SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 17:50:15 | zm167dc@jutal.com | 11-May-2026 17:59:03 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 17:35:36 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:57:45 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:17:45 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:51:51 | 31-May-2026 18:24:11 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0004-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - NAVIGATION AID SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:03:26 | zm167dc@jutal.com | 12-Jun-2026 12:34:43 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 14:16:08 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:45:17 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:50:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:29:56 | 25-Jun-2026 07:53:55 | 0 |  |  | Approver | Locate
AO-000211 | MM-ASK-1A-WPAX-ELE-TYP-0005-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - POWER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:06:06 | zm167dc@jutal.com | 11-May-2026 18:08:38 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 17:37:21 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:58:25 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:18:19 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:52:29 | 31-May-2026 18:25:04 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0005-001 | ELECTRICAL TYPICAL INSTALLATION DETAILS - POWER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:03:49 | zm167dc@jutal.com | 12-Jun-2026 12:34:42 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 15:18:00 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:43:32 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:50:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:31:05 | 25-Jun-2026 07:55:15 | 0 |  |  | Approver | Locate
AO-000212 | MM-ASK-1A-WPAX-ELE-TYP-0005-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - POWER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:06:39 | zm167dc@jutal.com | 11-May-2026 18:08:51 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 17:41:24 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:59:04 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:19:07 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:53:03 | 31-May-2026 18:25:59 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0005-002 | ELECTRICAL TYPICAL INSTALLATION DETAILS - POWER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:04:12 | zm167dc@jutal.com | 12-Jun-2026 12:34:43 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 15:17:11 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:46:38 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:52:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:32:01 | 25-Jun-2026 07:56:42 | 0 |  |  | Approver | Locate
AO-000213 | MM-ASK-1A-WPAX-ELE-TYP-0005-003 | ELECTRICAL TYPICAL INSTALLATION DETAILS - POWER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:07:07 | zm167dc@jutal.com | 11-May-2026 18:09:05 | Jumpol Sudjitjul | 20-May-2026 | 22-May-2026 17:42:43 | Noppadol Iamtanasinchai | 21-May-2026 | 23-May-2026 10:59:42 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 01:19:30 | APPR | Approved | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 17:53:38 | 31-May-2026 18:26:53 | 0 |  |  | Approver | Locate
AO-000460 | MM-ASK-1A-WPAX-ELE-TYP-0005-003 | ELECTRICAL TYPICAL INSTALLATION DETAILS - POWER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 12:04:35 | zm167dc@jutal.com | 12-Jun-2026 12:34:43 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 15:19:01 | Noppadol Iamtanasinchai | 23-Jun-2026 | 22-Jun-2026 16:50:54 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 22:54:15 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:33:07 | 25-Jun-2026 07:57:52 | 0 |  |  | Approver | Locate
AO-000170 | MM-ASK-1A-WPAX-ELE-TYP-0006 | ELECTRICAL TYPICAL INSTALLATION DETAILS - SOLAR PANEL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-May-2026 15:42:23 | zm167dc@jutal.com | 08-May-2026 17:10:22 | Jumpol Sudjitjul | 19-May-2026 | 21-May-2026 12:07:17 | Noppadol Iamtanasinchai | 20-May-2026 | 23-May-2026 10:28:09 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 22:28:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 28-May-2026 09:20:51 | 28-May-2026 09:43:24 | 0 |  |  | Approver | Locate
AO-000471 | MM-ASK-1A-WPAX-ELE-TYP-0006 | ELECTRICAL TYPICAL INSTALLATION DETAILS - SOLAR PANEL |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | ELE | Electrical | TYP | Typical Drawing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 18:01:50 | zm167dc@jutal.com | 13-Jun-2026 07:16:06 | Jumpol Sudjitjul | 22-Jun-2026 |  | Danai Chaisalee | 23-Jun-2026 | 18-Jun-2026 13:45:20 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 21-Jun-2026 15:54:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 12:52:44 | 22-Jun-2026 06:41:36 | 0 |  |  | Approver | Locate
AO-000422 | MM-ASK-1A-WPAX-INS-DWG-0001 | INSTRUMENT CABLE BLOCK DIAGRAM FOR SCADA SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 17:54:34 | zm167dc@jutal.com | 15-Jun-2026 13:28:54 | Jumpol Sudjitjul | 16-Jun-2026 | 26-Jun-2026 08:48:42 | Payut Phatdamrongdet | 17-Jun-2026 | 29-Jun-2026 09:00:59 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 29-Jun-2026 23:47:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 30-Jun-2026 09:46:27 | 30-Jun-2026 03:58:19 | 0 |  |  | Approver | Locate
AO-000675 | MM-ASK-1A-WPAX-INS-DWG-0001 | INSTRUMENT CABLE BLOCK DIAGRAM FOR SCADA SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 16:53:54 | zm167dc@jutal.com | 10-Jul-2026 17:46:04 | Jumpol Sudjitjul | 21-Jul-2026 | 29-Jul-2026 20:07:40 | Payut Phatdamrongdet | 22-Jul-2026 | 31-Jul-2026 21:48:39 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 02-Aug-2026 09:18:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 02-Aug-2026 21:10:21 | 02-Aug-2026 14:32:47 | 0 |  |  | Approver | Locate
AO-000893 | MM-ASK-1A-WPAX-INS-DWG-0001 | INSTRUMENT CABLE BLOCK DIAGRAM FOR SCADA SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 06-Aug-2026 08:54:18 | zm167dc@jutal.com | 06-Aug-2026 10:06:45 | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 11:31:35 | Payut Phatdamrongdet | 18-Aug-2026 | 17-Aug-2026 13:41:52 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 20-Aug-2026 23:01:37 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 21-Aug-2026 09:43:11 | 21-Aug-2026 03:20:05 | 0 |  |  | Approver | Locate
AO-000414 | MM-ASK-1A-WPAX-INS-DWG-0002 | OVERALL INSTRUMENT EARTHING DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 15:01:33 | zm167dc@jutal.com | 05-Jun-2026 18:08:05 | Jumpol Sudjitjul | 16-Jun-2026 | 12-Jun-2026 17:42:02 | Payut Phatdamrongdet | 17-Jun-2026 | 15-Jun-2026 11:22:15 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 16:41:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 21-Jun-2026 21:29:31 | 22-Jun-2026 01:08:21 | 0 |  |  | Approver | Locate
AO-000598 | MM-ASK-1A-WPAX-INS-DWG-0002 | OVERALL INSTRUMENT EARTHING DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Jul-2026 17:55:14 | zm167dc@jutal.com | 03-Jul-2026 13:15:49 | Jumpol Sudjitjul | 13-Jul-2026 | 03-Jul-2026 15:39:01 | Payut Phatdamrongdet | 14-Jul-2026 | 27-Jul-2026 11:15:20 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 28-Jul-2026 21:42:07 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 30-Jul-2026 09:18:18 | 30-Jul-2026 03:16:38 | 0 |  |  | Approver | Locate
AO-000857 | MM-ASK-1A-WPAX-INS-DWG-0002 | OVERALL INSTRUMENT EARTHING DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:40:24 | zm167dc@jutal.com | 04-Aug-2026 07:59:16 | Jumpol Sudjitjul | 13-Aug-2026 | 04-Aug-2026 10:31:09 | Payut Phatdamrongdet | 14-Aug-2026 | 17-Aug-2026 10:22:10 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 20-Aug-2026 22:56:30 | APPR | Approved | Jumpol Sudjitjul | 18-Aug-2026 | 21-Aug-2026 09:42:22 | 21-Aug-2026 03:17:19 | 0 |  |  | Approver | Locate
AO-000769 | MM-ASK-1A-WPAX-INS-TYP-0001 | INSTRUMENT TYPICAL INSTALLATION DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | INS | Instrumentation and Control | TYP | Typical Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 14:09:00 | zm167dc@jutal.com | 26-Jul-2026 22:51:34 | Jumpol Sudjitjul | 06-Aug-2026 | 02-Aug-2026 12:39:17 | Payut Phatdamrongdet | 07-Aug-2026 | 11-Aug-2026 11:20:51 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:05:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:26:35 | 13-Aug-2026 04:29:59 | 0 |  |  | Approver | Locate
AO-000521 | MM-ASK-1A-WPAX-PIP-DWG-0001 | PIPING DESIGN STANDARD |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PIP | Piping | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 21:53:40 | zm167dc@jutal.com | 22-Jun-2026 13:16:25 | Jumpol Sudjitjul | 30-Jun-2026 | 29-Jun-2026 16:32:04 | Thanapat Sombatwattana | 01-Jul-2026 | 30-Jun-2026 15:32:17 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:30:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 16:02:12 | 03-Jul-2026 09:50:20 | 0 |  |  | Approver | Locate
AO-000715 | MM-ASK-1A-WPAX-PIP-DWG-0001 | PIPING DESIGN STANDARD |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PIP | Piping | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 13:17:43 | zm167dc@jutal.com | 17-Jul-2026 13:30:36 | Jumpol Sudjitjul | 27-Jul-2026 | 03-Aug-2026 17:58:15 | Thanapat Sombatwattana | 30-Jul-2026 | 06-Aug-2026 10:09:36 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 07-Aug-2026 05:30:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 07-Aug-2026 11:16:55 | 07-Aug-2026 05:12:42 | 0 |  |  | Approver | Locate
AO-000522 | MM-ASK-1A-WPAX-PIP-DWG-0002 | PIPE SUPPORT STANDARD |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PIP | Piping | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 21:54:11 | zm167dc@jutal.com | 22-Jun-2026 13:16:52 | Jumpol Sudjitjul | 30-Jun-2026 |  | Thanapat Sombatwattana | 01-Jul-2026 | 02-Jul-2026 17:29:10 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:47:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 15:59:36 | 03-Jul-2026 09:46:13 | 0 |  |  | Approver | Locate
AO-000727 | MM-ASK-1A-WPAX-PIP-DWG-0002 | PIPE SUPPORT STANDARD |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PIP | Piping | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 09:47:59 | zm167dc@jutal.com | 20-Jul-2026 12:50:14 | Jumpol Sudjitjul | 30-Jul-2026 | 03-Aug-2026 21:21:07 | Thanapat Sombatwattana | 31-Jul-2026 | 06-Aug-2026 10:08:46 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:30:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 11:18:03 | 07-Aug-2026 05:18:04 | 0 |  |  | Approver | Locate
AO-001339 | MM-ASK-1A-WPAX-PLR-DWG-2001 | PIPELINE FIELD JOINT COATING DETAILS DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | In Review | IFR | Issued for Review |  | 11-Sep-2026 19:22:35 | zm167dc@jutal.com | 11-Sep-2026 20:25:22 | Jumpol Sudjitjul | 22-Sep-2026 | 18-Sep-2026 13:32:48 | Akkarapat Suntornsuttiwat | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000461 | MM-ASK-1A-WPAX-PRO-ESD-0001 | ESD LOGIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 12:29:31 | zm167dc@jutal.com | 12-Jun-2026 12:59:37 | Jumpol Sudjitjul | 22-Jun-2026 | 23-Jun-2026 14:39:55 | Naphat Nirotsinlapachai | 23-Jun-2026 | 23-Jun-2026 21:45:11 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:13:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:20:29 | 25-Jun-2026 07:42:52 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WPAX-PRO-PID-0001-001 | PIPING & INSTRUMENTATION DIAGRAM PROCESS DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:18:36 | zm167dc@jutal.com | 27-Apr-2026 13:35:39 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:28:23 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:32:27 | Pornlert Wanaphattharaphan | 11-May-2026 | 15-May-2026 00:28:32 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:26:20 | 15-May-2026 10:51:21 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WPAX-PRO-PID-0001-001 | PIPING & INSTRUMENTATION DIAGRAM PROCESS DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 12:45:33 | zm167dc@jutal.com | 29-May-2026 13:15:54 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 08:02:12 | Naphat Nirotsinlapachai | 11-Jun-2026 | 11-Jun-2026 15:26:36 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:26:17 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 09:04:00 | 12-Jun-2026 02:58:12 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0001-001 | PIPING & INSTRUMENTATION DIAGRAM PROCESS DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:11:33 | zm167dc@jutal.com | 16-Jul-2026 14:40:10 | Jumpol Sudjitjul | 24-Jul-2026 | 26-Jul-2026 13:09:52 | Naphat Nirotsinlapachai | 27-Jul-2026 | 27-Jul-2026 09:32:13 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 29-Jul-2026 00:08:34 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:20:12 | 30-Jul-2026 02:49:10 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WPAX-PRO-PID-0001-002 | PIPING & INSTRUMENTATION DIAGRAM PROCESS DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:19:03 | zm167dc@jutal.com | 27-Apr-2026 13:32:47 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:27:23 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:46:12 | Pornlert Wanaphattharaphan | 11-May-2026 | 15-May-2026 00:40:04 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:29:03 | 15-May-2026 03:52:17 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WPAX-PRO-PID-0001-002 | PIPING & INSTRUMENTATION DIAGRAM PROCESS DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 12:45:55 | zm167dc@jutal.com | 29-May-2026 13:15:51 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 07:48:58 | Naphat Nirotsinlapachai | 11-Jun-2026 | 11-Jun-2026 10:38:19 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:23:11 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 09:01:01 | 12-Jun-2026 02:57:13 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0001-002 | PIPING & INSTRUMENTATION DIAGRAM PROCESS DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:12:10 | zm167dc@jutal.com | 16-Jul-2026 14:40:11 | Jumpol Sudjitjul | 24-Jul-2026 | 26-Jul-2026 13:10:55 | Naphat Nirotsinlapachai | 27-Jul-2026 | 27-Jul-2026 09:30:19 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 28-Jul-2026 23:51:46 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:20:36 | 30-Jul-2026 02:50:20 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WPAX-PRO-PID-0002 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS EQUIPMENT SYMBOLS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:19:24 | zm167dc@jutal.com | 27-Apr-2026 13:32:31 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:26:44 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:47:05 | Pornlert Wanaphattharaphan | 11-May-2026 | 15-May-2026 00:15:16 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:30:14 | 15-May-2026 10:53:13 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WPAX-PRO-PID-0002 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS EQUIPMENT SYMBOLS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 12:46:19 | zm167dc@jutal.com | 29-May-2026 13:15:51 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 07:50:39 | Naphat Nirotsinlapachai | 11-Jun-2026 | 11-Jun-2026 10:37:34 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:22:35 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 09:00:00 | 12-Jun-2026 02:56:12 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0002 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS EQUIPMENT SYMBOLS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:12:36 | zm167dc@jutal.com | 16-Jul-2026 14:40:10 | Jumpol Sudjitjul | 24-Jul-2026 | 26-Jul-2026 13:12:35 | Naphat Nirotsinlapachai | 27-Jul-2026 | 27-Jul-2026 09:31:32 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 29-Jul-2026 00:21:49 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:21:13 | 30-Jul-2026 02:51:25 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WPAX-PRO-PID-0003 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS PIPING SYMBOLS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:19:45 | zm167dc@jutal.com | 27-Apr-2026 13:32:15 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:25:59 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:22:45 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:44:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:21:46 | 15-May-2026 10:50:23 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WPAX-PRO-PID-0003 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS PIPING SYMBOLS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 12:46:43 | zm167dc@jutal.com | 29-May-2026 13:15:52 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 07:53:03 | Naphat Nirotsinlapachai | 11-Jun-2026 | 11-Jun-2026 15:23:34 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:24:31 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 08:59:26 | 12-Jun-2026 02:55:15 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0003 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS PIPING SYMBOLS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:13:13 | zm167dc@jutal.com | 16-Jul-2026 14:40:10 | Jumpol Sudjitjul | 24-Jul-2026 | 26-Jul-2026 12:11:07 | Naphat Nirotsinlapachai | 27-Jul-2026 | 26-Jul-2026 20:23:32 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 23:31:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 14:39:51 | 27-Jul-2026 08:39:18 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WPAX-PRO-PID-0004 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS INSTRUMENT SYMBOLS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:20:11 | zm167dc@jutal.com | 27-Apr-2026 13:31:57 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:25:24 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 21:19:29 | Pornlert Wanaphattharaphan | 11-May-2026 | 14-May-2026 23:41:09 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 15-May-2026 10:20:09 | 15-May-2026 10:48:25 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WPAX-PRO-PID-0004 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS INSTRUMENT SYMBOLS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 12:47:07 | zm167dc@jutal.com | 29-May-2026 13:15:51 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 07:55:11 | Naphat Nirotsinlapachai | 11-Jun-2026 | 11-Jun-2026 10:37:11 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:21:48 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 08:58:39 | 12-Jun-2026 02:52:43 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0004 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS INSTRUMENT SYMBOLS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:13:48 | zm167dc@jutal.com | 16-Jul-2026 14:40:11 | Jumpol Sudjitjul | 24-Jul-2026 | 26-Jul-2026 13:14:59 | Naphat Nirotsinlapachai | 27-Jul-2026 | 27-Jul-2026 09:33:00 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 29-Jul-2026 00:23:23 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:21:38 | 30-Jul-2026 02:52:30 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WPAX-PRO-PID-0005 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS ON/OFF VALVE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:20:34 | zm167dc@jutal.com | 27-Apr-2026 13:26:07 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:16:10 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:28:37 | Pornlert Wanaphattharaphan | 11-May-2026 | 13-May-2026 00:07:47 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 13-May-2026 08:45:18 | 13-May-2026 09:29:24 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WPAX-PRO-PID-0005 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS ON/OFF VALVE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 12:47:35 | zm167dc@jutal.com | 29-May-2026 13:15:52 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 07:57:22 | Naphat Nirotsinlapachai | 11-Jun-2026 | 11-Jun-2026 11:12:34 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:23:52 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 08:56:17 | 12-Jun-2026 02:51:42 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0005 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS ON/OFF VALVE DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:14:15 | zm167dc@jutal.com | 16-Jul-2026 14:40:11 | Jumpol Sudjitjul | 24-Jul-2026 | 26-Jul-2026 13:21:16 | Naphat Nirotsinlapachai | 27-Jul-2026 | 27-Jul-2026 09:36:18 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 29-Jul-2026 00:29:30 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:23:31 | 30-Jul-2026 02:53:37 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WPAX-PRO-PID-0006 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS SAMPLING ARRANGEMENTS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:20:56 | zm167dc@jutal.com | 27-Apr-2026 13:25:52 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:15:30 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:27:08 | Pornlert Wanaphattharaphan | 11-May-2026 | 13-May-2026 00:07:13 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 13-May-2026 08:39:43 | 13-May-2026 09:09:58 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WPAX-PRO-PID-0006 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS SAMPLING ARRANGEMENTS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 12:47:59 | zm167dc@jutal.com | 29-May-2026 13:15:52 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 07:58:22 | Naphat Nirotsinlapachai | 11-Jun-2026 | 11-Jun-2026 15:25:51 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:25:43 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 08:52:57 | 12-Jun-2026 02:48:14 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0006 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS SAMPLING ARRANGEMENTS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:14:41 | zm167dc@jutal.com | 16-Jul-2026 14:40:10 | Jumpol Sudjitjul | 24-Jul-2026 | 26-Jul-2026 13:24:09 | Naphat Nirotsinlapachai | 27-Jul-2026 | 27-Jul-2026 09:35:03 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 29-Jul-2026 00:28:59 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:24:02 | 30-Jul-2026 02:54:45 | 0 |  |  | Approver | Locate
AO-000096 | MM-ASK-1A-WPAX-PRO-PID-0007 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS INSTRUMENT CONNECTION & ARRANGEMENTS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 08:28:20 | zm167dc@jutal.com | 29-Apr-2026 10:13:46 | Jumpol Sudjitjul | 11-May-2026 | 08-May-2026 11:31:11 | Naphat Nirotsinlapachai | 12-May-2026 | 12-May-2026 21:53:45 | Pornlert Wanaphattharaphan | 13-May-2026 | 18-May-2026 02:06:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 18-May-2026 19:19:44 | 18-May-2026 19:41:31 | 0 |  |  | Approver | Locate
AO-000410 | MM-ASK-1A-WPAX-PRO-PID-0007 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS INSTRUMENT CONNECTION & ARRANGEMENTS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 13:03:09 | zm167dc@jutal.com | 05-Jun-2026 14:01:15 | Jumpol Sudjitjul | 15-Jun-2026 | 15-Jun-2026 08:16:53 | Naphat Nirotsinlapachai | 16-Jun-2026 | 15-Jun-2026 20:01:56 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 20-Jun-2026 00:34:08 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 21-Jun-2026 21:29:13 | 22-Jun-2026 01:04:31 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0007 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS INSTRUMENT CONNECTION & ARRANGEMENTS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:15:08 | zm167dc@jutal.com | 16-Jul-2026 14:40:13 | Jumpol Sudjitjul | 24-Jul-2026 | 23-Jul-2026 17:16:51 | Naphat Nirotsinlapachai | 27-Jul-2026 | 27-Jul-2026 09:36:59 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 29-Jul-2026 00:30:28 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:24:55 | 30-Jul-2026 02:55:54 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WPAX-PRO-PID-0008 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS PSVS CONTROL VALVES AND POSITIVE ISOLATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:21:17 | zm167dc@jutal.com | 27-Apr-2026 13:25:37 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:15:00 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:26:08 | Pornlert Wanaphattharaphan | 11-May-2026 | 13-May-2026 00:06:32 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 13-May-2026 08:38:14 | 13-May-2026 09:08:56 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WPAX-PRO-PID-0008 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS PSVS CONTROL VALVES AND POSITIVE ISOLATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 12:48:23 | zm167dc@jutal.com | 29-May-2026 13:15:52 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 08:00:34 | Naphat Nirotsinlapachai | 11-Jun-2026 | 11-Jun-2026 15:25:25 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:25:05 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 08:52:12 | 12-Jun-2026 02:46:06 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0008 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS PSVS CONTROL VALVES AND POSITIVE ISOLATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:15:31 | zm167dc@jutal.com | 16-Jul-2026 14:40:09 | Jumpol Sudjitjul | 24-Jul-2026 | 26-Jul-2026 13:22:58 | Naphat Nirotsinlapachai | 27-Jul-2026 | 27-Jul-2026 09:31:08 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 29-Jul-2026 00:19:02 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:25:43 | 30-Jul-2026 02:57:05 | 0 |  |  | Approver | Locate
AO-000085 | MM-ASK-1A-WPAX-PRO-PID-0009 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS WELLHEAD PLATFORMS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:21:39 | zm167dc@jutal.com | 27-Apr-2026 13:24:36 | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 16:14:19 | Naphat Nirotsinlapachai | 08-May-2026 | 08-May-2026 20:25:27 | Pornlert Wanaphattharaphan | 11-May-2026 | 13-May-2026 00:00:52 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 13-May-2026 08:32:11 | 13-May-2026 09:06:49 | 0 |  |  | Approver | Locate
AO-000379 | MM-ASK-1A-WPAX-PRO-PID-0009 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS WELLHEAD PLATFORMS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 12:48:57 | zm167dc@jutal.com | 29-May-2026 13:15:58 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 08:04:32 | Naphat Nirotsinlapachai | 11-Jun-2026 | 11-Jun-2026 15:27:27 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 11-Jun-2026 23:27:01 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 12-Jun-2026 08:49:56 | 12-Jun-2026 02:44:08 | 0 |  |  | Approver | Locate
AO-000706 | MM-ASK-1A-WPAX-PRO-PID-0009 | PIPING & INSTRUMENTATION DIAGRAM SYMBOLS AND LEGENDS WELLHEAD PLATFORMS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:15:54 | zm167dc@jutal.com | 16-Jul-2026 14:40:13 | Jumpol Sudjitjul | 24-Jul-2026 | 26-Jul-2026 13:22:08 | Naphat Nirotsinlapachai | 27-Jul-2026 | 27-Jul-2026 09:29:54 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 28-Jul-2026 23:50:58 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:26:08 | 30-Jul-2026 03:10:38 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1001 | TOPSIDE GENERAL NOTES SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:14:34 | zm167dc@jutal.com | 27-Apr-2026 11:07:58 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:13:33 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 13:37:27 | Pornlert Wanaphattharaphan | 11-May-2026 | 09-May-2026 00:30:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 09-May-2026 08:01:52 | 09-May-2026 01:04:06 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WPAX-STR-DWG-1001 | TOPSIDE GENERAL NOTES SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 20:58:13 | zm167dc@jutal.com | 29-May-2026 09:33:12 | Jumpol Sudjitjul | 10-Jun-2026 |  | Washira Kaew-amatawong | 11-Jun-2026 | 02-Jun-2026 15:19:13 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 19:37:02 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 08:59:36 | 03-Jun-2026 02:24:47 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1001 | TOPSIDE GENERAL NOTES SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:32:01 | zm167dc@jutal.com | 27-Jun-2026 19:40:54 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:07:15 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 00:58:51 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:35:16 | 08-Jul-2026 03:08:31 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1002 | TOPSIDE GENERAL NOTES SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:46:30 | zm167dc@jutal.com | 27-Apr-2026 11:08:20 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:14:16 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 13:39:13 | Pornlert Wanaphattharaphan | 11-May-2026 | 09-May-2026 23:15:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:04:40 | 10-May-2026 16:17:05 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WPAX-STR-DWG-1002 | TOPSIDE GENERAL NOTES SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 20:58:42 | zm167dc@jutal.com | 29-May-2026 09:33:41 | Jumpol Sudjitjul | 10-Jun-2026 |  | Washira Kaew-amatawong | 11-Jun-2026 | 02-Jun-2026 15:22:15 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 19:51:42 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 08:58:23 | 03-Jun-2026 02:23:50 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1002 | TOPSIDE GENERAL NOTES SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 19:20:48 | zm167dc@jutal.com | 27-Jun-2026 19:40:56 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:11:54 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:00:04 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 08:54:39 | 08-Jul-2026 02:45:24 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1011 | TOPSIDE STANDARD DETAILS WELDING DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:46:55 | zm167dc@jutal.com | 27-Apr-2026 11:08:33 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:16:16 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 13:41:16 | Pornlert Wanaphattharaphan | 11-May-2026 | 09-May-2026 23:16:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:05:57 | 10-May-2026 23:18:11 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1011 | TOPSIDE STANDARD DETAILS WELDING DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:22:31 | zm167dc@jutal.com | 24-May-2026 15:31:45 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:29:52 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:06:07 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:02:39 | 03-Jun-2026 02:25:42 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1011 | TOPSIDE STANDARD DETAILS WELDING DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 19:21:16 | zm167dc@jutal.com | 27-Jun-2026 19:40:54 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:31:03 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:01:32 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:36:06 | 08-Jul-2026 03:29:44 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1012 | TOPSIDE STANDARD DETAILS WELDING DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:22:16 | zm167dc@jutal.com | 27-Apr-2026 11:08:45 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:17:16 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 13:49:08 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:10:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:10:21 | 10-May-2026 23:23:31 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1012 | TOPSIDE STANDARD DETAILS WELDING DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:22:59 | zm167dc@jutal.com | 24-May-2026 15:31:44 | Jumpol Sudjitjul | 02-Jun-2026 | 01-Jun-2026 21:56:49 | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:31:32 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:07:47 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:03:11 | 03-Jun-2026 02:26:36 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1012 | TOPSIDE STANDARD DETAILS WELDING DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 19:21:48 | zm167dc@jutal.com | 27-Jun-2026 19:40:55 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:32:39 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:02:16 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 08:59:41 | 08-Jul-2026 02:48:55 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1013 | TOPSIDE STANDARD DETAILS BEAM CONNECTIONS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:22:40 | zm167dc@jutal.com | 27-Apr-2026 11:10:56 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:20:16 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 13:51:33 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:11:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:11:38 | 10-May-2026 23:24:32 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1013 | TOPSIDE STANDARD DETAILS BEAM CONNECTIONS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:23:25 | zm167dc@jutal.com | 24-May-2026 15:31:44 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:33:43 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:09:02 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:03:47 | 03-Jun-2026 02:27:30 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1013 | TOPSIDE STANDARD DETAILS BEAM CONNECTIONS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 19:22:25 | zm167dc@jutal.com | 27-Jun-2026 19:40:54 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:34:38 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:02:55 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:13:07 | 08-Jul-2026 02:51:21 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1014 | TOPSIDE STANDARD DETAILS BEAM CONNECTIONS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:23:06 | zm167dc@jutal.com | 27-Apr-2026 11:11:09 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:21:13 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 13:55:19 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:13:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:14:54 | 11-May-2026 00:14:05 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1014 | TOPSIDE STANDARD DETAILS BEAM CONNECTIONS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:23:49 | zm167dc@jutal.com | 24-May-2026 15:31:48 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:35:56 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:11:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:04:17 | 03-Jun-2026 02:28:35 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1014 | TOPSIDE STANDARD DETAILS BEAM CONNECTIONS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 19:23:06 | zm167dc@jutal.com | 27-Jun-2026 19:40:57 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:36:37 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:04:08 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:04:04 | 08-Jul-2026 02:50:08 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1015 | TOPSIDE STANDARD DETAILS BEAM CONNECTIONS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:14:56 | zm167dc@jutal.com | 27-Apr-2026 11:11:24 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:25:56 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 13:57:11 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:15:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:06:34 | 10-May-2026 23:16:02 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1015 | TOPSIDE STANDARD DETAILS BEAM CONNECTIONS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:24:13 | zm167dc@jutal.com | 24-May-2026 15:31:43 | Jumpol Sudjitjul | 02-Jun-2026 | 01-Jun-2026 21:57:22 | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:37:33 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:12:28 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:05:14 | 03-Jun-2026 02:29:33 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1015 | TOPSIDE STANDARD DETAILS BEAM CONNECTIONS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:32:38 | zm167dc@jutal.com | 27-Jun-2026 19:40:54 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:39:05 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:05:06 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:37:06 | 08-Jul-2026 03:12:01 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1016 | TOPSIDE STANDARD DETAILS BEAMCONNECTIONS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:15:19 | zm167dc@jutal.com | 27-Apr-2026 11:11:44 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:27:00 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:00:24 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:19:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:15:51 | 11-May-2026 00:11:33 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1016 | TOPSIDE STANDARD DETAILS BEAMCONNECTIONS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:24:37 | zm167dc@jutal.com | 24-May-2026 15:31:44 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:39:29 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:15:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:05:59 | 03-Jun-2026 02:30:42 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1016 | TOPSIDE STANDARD DETAILS BEAMCONNECTIONS - SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:33:08 | zm167dc@jutal.com | 27-Jun-2026 19:40:58 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:41:12 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:06:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:38:02 | 08-Jul-2026 03:14:31 | 0 |  |  | Approver | Locate
AO-000890 | MM-ASK-1A-WPAX-STR-DWG-1016 | TOPSIDE STANDARD DETAILS BEAMCONNECTIONS - SHEET 4 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 18:34:45 | zm167dc@jutal.com | 06-Aug-2026 14:11:56 | Jumpol Sudjitjul | 17-Aug-2026 |  | Washira Kaew-amatawong | 18-Aug-2026 | 15-Aug-2026 19:37:23 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 17-Aug-2026 00:01:08 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 09:44:33 | 17-Aug-2026 03:21:31 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1017 | TOPSIDE STANDARD DETAILS TUBULAR CONNECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:23:33 | zm167dc@jutal.com | 27-Apr-2026 11:15:22 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:25:03 | Washira Kaew-amatawong | 08-May-2026 | 11-May-2026 15:25:23 | Pornlert Wanaphattharaphan | 11-May-2026 | 13-May-2026 16:36:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 13-May-2026 17:15:45 | 13-May-2026 18:25:21 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1017 | TOPSIDE STANDARD DETAILS TUBULAR CONNECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:25:03 | zm167dc@jutal.com | 24-May-2026 15:31:48 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:40:58 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:16:24 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:06:34 | 03-Jun-2026 02:31:37 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1017 | TOPSIDE STANDARD DETAILS TUBULAR CONNECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:33:47 | zm167dc@jutal.com | 27-Jun-2026 19:40:58 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:42:54 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:07:09 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:16:05 | 08-Jul-2026 02:24:12 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1018 | TOPSIDE STANDARD DETAILS HANDRAIL DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:24:03 | zm167dc@jutal.com | 27-Apr-2026 11:15:41 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:24:48 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:04:32 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:40:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:17:36 | 11-May-2026 00:15:09 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1018 | TOPSIDE STANDARD DETAILS HANDRAIL DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:25:27 | zm167dc@jutal.com | 24-May-2026 15:34:56 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:42:43 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:17:26 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:07:04 | 03-Jun-2026 02:32:31 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1018 | TOPSIDE STANDARD DETAILS HANDRAIL DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:34:35 | zm167dc@jutal.com | 27-Jun-2026 19:40:54 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:44:30 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:07:53 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:38:42 | 08-Jul-2026 03:15:41 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1019 | TOPSIDE STANDARD DETAILS HANDRAIL DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:47:22 | zm167dc@jutal.com | 27-Apr-2026 11:15:57 | Jumpol Sudjitjul | 07-May-2026 |  | Washira Kaew-amatawong | 08-May-2026 | 29-Apr-2026 13:21:03 | Pornlert Wanaphattharaphan | 11-May-2026 | 01-May-2026 18:25:22 | NA | Not Approved | Jumpol Sudjitjul | 12-May-2026 | 03-May-2026 16:12:27 | 03-May-2026 16:15:27 | 0 |  |  | Approver | Locate
AO-000398 | MM-ASK-1A-WPAX-STR-DWG-1019 | TOPSIDE STANDARD DETAILS HANDRAIL DETAILS - SHEET 2 |  | A2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 09:01:57 | zm167dc@jutal.com | 04-Jun-2026 10:56:25 | Jumpol Sudjitjul | 12-Jun-2026 |  | Washira Kaew-amatawong | 15-Jun-2026 | 15-Jun-2026 13:05:14 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 18-Jun-2026 10:00:03 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 10:23:59 | 18-Jun-2026 04:18:10 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1019 | TOPSIDE STANDARD DETAILS HANDRAIL DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:35:12 | zm167dc@jutal.com | 27-Jun-2026 19:40:58 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:46:15 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:08:43 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:38:04 | 08-Jul-2026 03:13:11 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1020 | TOPSIDE STANDARD DETAILS LADDER DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:24:29 | zm167dc@jutal.com | 27-Apr-2026 11:16:12 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:24:00 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:07:30 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:47:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:09:22 | 10-May-2026 23:21:24 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1020 | TOPSIDE STANDARD DETAILS LADDER DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:25:51 | zm167dc@jutal.com | 24-May-2026 15:33:45 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:44:16 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:18:30 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:07:34 | 03-Jun-2026 02:33:25 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1020 | TOPSIDE STANDARD DETAILS LADDER DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:35:56 | zm167dc@jutal.com | 27-Jun-2026 19:40:54 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:47:57 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:10:03 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:36:44 | 08-Jul-2026 03:10:51 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1021 | TOPSIDE STANDARD DETAILS LADDER DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:24:59 | zm167dc@jutal.com | 27-Apr-2026 11:21:50 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:23:37 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:08:54 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:48:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:07:29 | 10-May-2026 23:19:20 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1021 | TOPSIDE STANDARD DETAILS LADDER DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:26:14 | zm167dc@jutal.com | 24-May-2026 15:33:29 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:45:31 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:20:03 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:08:36 | 03-Jun-2026 02:34:20 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1021 | TOPSIDE STANDARD DETAILS LADDER DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:36:30 | zm167dc@jutal.com | 27-Jun-2026 19:40:58 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:49:34 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:10:25 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:35:33 | 08-Jul-2026 03:09:43 | 0 |  |  | Approver | Locate
AO-000077 | MM-ASK-1A-WPAX-STR-DWG-1022 | TOPSIDE STANDARD DETAILS LADDER DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:25:28 | zm167dc@jutal.com | 27-Apr-2026 11:22:06 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:22:28 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:10:40 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:50:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:18:55 | 11-May-2026 00:16:12 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1022 | TOPSIDE STANDARD DETAILS LADDER DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:26:38 | zm167dc@jutal.com | 24-May-2026 15:33:15 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:48:44 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:21:09 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:09:14 | 03-Jun-2026 02:35:13 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1022 | TOPSIDE STANDARD DETAILS LADDER DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:37:09 | zm167dc@jutal.com | 27-Jun-2026 19:40:59 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:51:43 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:10:44 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:34:37 | 08-Jul-2026 03:07:22 | 0 |  |  | Approver | Locate
AO-000084 | MM-ASK-1A-WPAX-STR-DWG-1023 | TOPSIDE STANDARD DETAILS PLATING AND GRATING DETAIL – SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:25:55 | zm167dc@jutal.com | 27-Apr-2026 11:22:20 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:22:20 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:12:33 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 00:52:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:08:21 | 10-May-2026 23:20:22 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1023 | TOPSIDE STANDARD DETAILS PLATING AND GRATING DETAIL – SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:27:01 | zm167dc@jutal.com | 24-May-2026 15:33:01 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:50:22 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:22:08 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:09:45 | 03-Jun-2026 02:36:09 | 0 |  |  | Approver | Locate
AO-000563 | MM-ASK-1A-WPAX-STR-DWG-1023 | TOPSIDE STANDARD DETAILS PLATING AND GRATING DETAIL – SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 18:37:38 | zm167dc@jutal.com | 27-Jun-2026 19:41:01 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 13:54:02 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:11:03 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:27:58 | 08-Jul-2026 03:06:12 | 0 |  |  | Approver | Locate
AO-000084 | MM-ASK-1A-WPAX-STR-DWG-1024 | TOPSIDE STANDARD DETAILS PLATING AND GRATING DETAIL – SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:47:45 | zm167dc@jutal.com | 27-Apr-2026 11:15:09 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:29:30 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:14:47 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 01:00:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:19:57 | 11-May-2026 00:17:16 | 0 |  |  | Approver | Locate
AO-000330 | MM-ASK-1A-WPAX-STR-DWG-1024 | TOPSIDE STANDARD DETAILS PLATING AND GRATING DETAIL – SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-May-2026 15:27:26 | zm167dc@jutal.com | 24-May-2026 15:32:44 | Jumpol Sudjitjul | 02-Jun-2026 |  | Washira Kaew-amatawong | 04-Jun-2026 | 02-Jun-2026 10:52:35 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 02-Jun-2026 20:23:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 03-Jun-2026 09:10:13 | 03-Jun-2026 02:37:11 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WPAX-STR-DWG-1024 | TOPSIDE STANDARD DETAILS PLATING AND GRATING DETAIL – SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 09:22:25 | zm167dc@jutal.com | 03-Jul-2026 13:28:11 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 07-Jul-2026 14:21:15 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:56:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:36:17 | 15-Jul-2026 03:22:21 | 0 |  |  | Approver | Locate
AO-000891 | MM-ASK-1A-WPAX-STR-DWG-1024 | TOPSIDE STANDARD DETAILS PLATING AND GRATING DETAIL – SHEET 2 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Aug-2026 18:35:12 | zm167dc@jutal.com | 06-Aug-2026 14:12:05 | Jumpol Sudjitjul | 17-Aug-2026 |  | Washira Kaew-amatawong | 18-Aug-2026 | 15-Aug-2026 19:39:00 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 17-Aug-2026 00:01:40 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 09:42:30 | 17-Aug-2026 03:20:14 | 0 |  |  | Approver | Locate
AO-000084 | MM-ASK-1A-WPAX-STR-DWG-1025 | TOPSIDE STANDARD DETAILS DECK DRAIN DETAIL – SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:26:19 | zm167dc@jutal.com | 27-Apr-2026 11:14:46 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:28:39 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:17:28 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 01:10:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:10:14 | 10-May-2026 23:22:27 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WPAX-STR-DWG-1025 | TOPSIDE STANDARD DETAILS DECK DRAIN DETAIL – SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 20:59:12 | zm167dc@jutal.com | 29-May-2026 09:35:46 | Jumpol Sudjitjul | 10-Jun-2026 |  | Washira Kaew-amatawong | 11-Jun-2026 | 02-Jun-2026 15:25:48 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 20:25:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:11:15 | 03-Jun-2026 02:39:16 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WPAX-STR-DWG-1025 | TOPSIDE STANDARD DETAILS DECK DRAIN DETAIL – SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 09:23:32 | zm167dc@jutal.com | 03-Jul-2026 13:28:07 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 07-Jul-2026 14:24:03 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:56:34 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:43:41 | 15-Jul-2026 03:26:04 | 0 |  |  | Approver | Locate
AO-000084 | MM-ASK-1A-WPAX-STR-DWG-1026 | TOPSIDE STANDARD DETAILS DECK DRAIN DETAIL – SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:26:45 | zm167dc@jutal.com | 27-Apr-2026 11:14:28 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:28:26 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:19:33 | Pornlert Wanaphattharaphan | 11-May-2026 | 10-May-2026 01:14:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:12:37 | 10-May-2026 23:25:34 | 0 |  |  | Approver | Locate
AO-000371 | MM-ASK-1A-WPAX-STR-DWG-1026 | TOPSIDE STANDARD DETAILS DECK DRAIN DETAIL – SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 20:59:39 | zm167dc@jutal.com | 29-May-2026 09:36:13 | Jumpol Sudjitjul | 10-Jun-2026 |  | Washira Kaew-amatawong | 11-Jun-2026 | 02-Jun-2026 15:31:02 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 20:33:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:10:42 | 03-Jun-2026 02:38:14 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WPAX-STR-DWG-1026 | TOPSIDE STANDARD DETAILS DECK DRAIN DETAIL – SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 09:24:17 | zm167dc@jutal.com | 03-Jul-2026 13:28:19 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 07-Jul-2026 14:26:14 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:57:01 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:44:32 | 15-Jul-2026 03:27:22 | 0 |  |  | Approver | Locate
AO-000084 | MM-ASK-1A-WPAX-STR-DWG-1027 | TOPSIDE STANDARD DETAILS LOGO PAINTING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:27:09 | zm167dc@jutal.com | 27-Apr-2026 11:14:14 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:29:14 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:22:34 | Pornlert Wanaphattharaphan | 11-May-2026 | 11-May-2026 21:18:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 12-May-2026 09:09:58 | 12-May-2026 02:39:00 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WPAX-STR-DWG-1027 | TOPSIDE STANDARD DETAILS LOGO PAINTING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:24:59 | zm167dc@jutal.com | 03-Jul-2026 13:28:19 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 07-Jul-2026 14:28:58 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:57:33 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:41:30 | 15-Jul-2026 03:23:27 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WPAX-STR-DWG-1027 | TOPSIDE STANDARD DETAILS LOGO PAINTING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 17:34:54 | zm167dc@jutal.com | 14-Aug-2026 08:40:32 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 06:55:43 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 14:59:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 27-Aug-2026 15:42:45 | 27-Aug-2026 10:41:49 | 0 |  |  | Approver | Locate
AO-001139 | MM-ASK-1A-WPAX-STR-DWG-1027 | TOPSIDE STANDARD DETAILS LOGO PAINTING |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:02:25 | zm167dc@jutal.com | 29-Aug-2026 14:13:35 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 10:33:41 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:35:42 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 17:51:42 | 10-Sep-2026 11:04:22 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1901 | TOPSIDE CASING SLOT ARRANGEMENT SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:48:27 | zm167dc@jutal.com | 15-May-2026 11:14:28 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 22-May-2026 15:59:26 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 00:02:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 09:06:21 | 25-May-2026 02:34:42 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WPAX-STR-DWG-1901 | TOPSIDE CASING SLOT ARRANGEMENT SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:25:32 | zm167dc@jutal.com | 03-Jul-2026 13:28:39 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 07-Jul-2026 16:02:30 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:15:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:42:59 | 15-Jul-2026 03:24:46 | 0 |  |  | Approver | Locate
AO-001127 | MM-ASK-1A-WPAX-STR-DWG-1901 | TOPSIDE CASING SLOT ARRANGEMENT SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:44:57 | zm167dc@jutal.com | 28-Aug-2026 17:33:18 | Jumpol Sudjitjul | 08-Sep-2026 |  | Washira Kaew-amatawong | 09-Sep-2026 | 08-Sep-2026 14:06:56 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 22:49:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 19:51:05 | 12-Sep-2026 13:21:31 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1902 | TOPSIDE CASING SLOT ARRANGEMENT SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:48:55 | zm167dc@jutal.com | 15-May-2026 11:15:00 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 22-May-2026 16:04:23 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 00:12:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 09:10:23 | 25-May-2026 02:35:50 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1902 | TOPSIDE CASING SLOT ARRANGEMENT SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:38:17 | zm167dc@jutal.com | 27-Jun-2026 19:43:23 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 16:04:20 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 01:13:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:22:11 | 08-Jul-2026 03:05:02 | 0 |  |  | Approver | Locate
AO-001127 | MM-ASK-1A-WPAX-STR-DWG-1902 | TOPSIDE CASING SLOT ARRANGEMENT SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:45:23 | zm167dc@jutal.com | 28-Aug-2026 17:33:41 | Jumpol Sudjitjul | 08-Sep-2026 |  | Washira Kaew-amatawong | 09-Sep-2026 | 08-Sep-2026 14:09:03 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 10-Sep-2026 00:02:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 10-Sep-2026 17:52:52 | 10-Sep-2026 11:05:47 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1911 | TOPSIDE UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:49:22 | zm167dc@jutal.com | 15-May-2026 11:15:16 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 22-May-2026 16:07:41 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 00:21:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 09:03:55 | 25-May-2026 02:33:37 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1911 | TOPSIDE UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:38:44 | zm167dc@jutal.com | 27-Jun-2026 19:43:21 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 16:06:25 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:18:13 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 09:52:19 | 10-Jul-2026 03:40:48 | 0 |  |  | Approver | Locate
AO-001127 | MM-ASK-1A-WPAX-STR-DWG-1911 | TOPSIDE UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:46:09 | zm167dc@jutal.com | 28-Aug-2026 17:34:02 | Jumpol Sudjitjul | 08-Sep-2026 |  | Washira Kaew-amatawong | 09-Sep-2026 | 08-Sep-2026 14:11:33 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 09-Sep-2026 23:56:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 10-Sep-2026 17:53:18 | 10-Sep-2026 11:07:09 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1912 | TOPSIDE UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:49:47 | zm167dc@jutal.com | 15-May-2026 11:15:31 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 22-May-2026 16:10:02 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 00:23:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 08:58:12 | 25-May-2026 02:32:27 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1912 | TOPSIDE UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:39:21 | zm167dc@jutal.com | 27-Jun-2026 19:43:21 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 07-Jul-2026 16:07:56 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:18:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 10:13:46 | 10-Jul-2026 03:49:43 | 0 |  |  | Approver | Locate
AO-001127 | MM-ASK-1A-WPAX-STR-DWG-1912 | TOPSIDE UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:46:40 | zm167dc@jutal.com | 28-Aug-2026 17:34:19 | Jumpol Sudjitjul | 08-Sep-2026 |  | Washira Kaew-amatawong | 09-Sep-2026 | 08-Sep-2026 14:13:42 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 09-Sep-2026 23:52:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 10-Sep-2026 17:53:44 | 10-Sep-2026 11:08:35 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1921 | TOPSIDE DECK TO PILE CONNECTION DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:50:10 | zm167dc@jutal.com | 15-May-2026 11:36:10 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 22-May-2026 16:16:42 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 00:25:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 08:54:39 | 25-May-2026 02:27:01 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1921 | TOPSIDE DECK TO PILE CONNECTION DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:39:52 | zm167dc@jutal.com | 27-Jun-2026 19:43:21 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 08-Jul-2026 09:16:29 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:19:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 10:13:51 | 10-Jul-2026 03:48:26 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WPAX-STR-DWG-1921 | TOPSIDE DECK TO PILE CONNECTION DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 15:22:36 | zm167dc@jutal.com | 21-Aug-2026 17:05:05 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 02-Sep-2026 08:27:40 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:43:45 | APPR | Approved | Jumpol Sudjitjul | 04-Sep-2026 | 03-Sep-2026 10:44:35 | 03-Sep-2026 04:56:28 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1931 | TOPSIDE E&I ROOM PLANS AND ELEVATIONS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:50:37 | zm167dc@jutal.com | 15-May-2026 11:27:30 | Jumpol Sudjitjul | 25-May-2026 | 20-May-2026 11:06:46 | Washira Kaew-amatawong | 26-May-2026 | 22-May-2026 16:20:57 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 00:34:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 08:53:16 | 25-May-2026 02:25:58 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1931 | TOPSIDE E&I ROOM PLANS AND ELEVATIONS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:40:33 | zm167dc@jutal.com | 27-Jun-2026 19:43:26 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 15:07:08 | Washira Kaew-amatawong | 08-Jul-2026 | 08-Jul-2026 09:18:51 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:19:39 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 10:13:17 | 10-Jul-2026 03:47:09 | 0 |  |  | Approver | Locate
AO-001120 | MM-ASK-1A-WPAX-STR-DWG-1931 | TOPSIDE E&I ROOM PLANS AND ELEVATIONS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 08:29:25 | zm167dc@jutal.com | 28-Aug-2026 13:37:26 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 10:36:31 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:51:38 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 17:52:40 | 10-Sep-2026 11:17:21 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1932 | TOPSIDE E&I ROOM PLANS AND ELEVATIONS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:51:00 | zm167dc@jutal.com | 15-May-2026 11:27:45 | Jumpol Sudjitjul | 25-May-2026 | 20-May-2026 11:06:31 | Washira Kaew-amatawong | 26-May-2026 | 22-May-2026 16:23:27 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 00:55:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 08:49:24 | 25-May-2026 02:24:58 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1932 | TOPSIDE E&I ROOM PLANS AND ELEVATIONS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:41:05 | zm167dc@jutal.com | 27-Jun-2026 19:43:23 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 14:59:54 | Washira Kaew-amatawong | 08-Jul-2026 | 08-Jul-2026 09:21:37 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:19:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 10:12:08 | 10-Jul-2026 03:46:03 | 0 |  |  | Approver | Locate
AO-001120 | MM-ASK-1A-WPAX-STR-DWG-1932 | TOPSIDE E&I ROOM PLANS AND ELEVATIONS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 08:29:57 | zm167dc@jutal.com | 28-Aug-2026 13:37:39 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 10:38:51 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:49:49 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 17:53:54 | 10-Sep-2026 11:19:58 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1933 | TOPSIDE E&I ROOM SECTIONS AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:51:23 | zm167dc@jutal.com | 15-May-2026 11:28:01 | Jumpol Sudjitjul | 25-May-2026 | 20-May-2026 11:07:01 | Washira Kaew-amatawong | 26-May-2026 | 22-May-2026 16:26:17 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 01:11:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 08:46:25 | 25-May-2026 02:22:08 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1933 | TOPSIDE E&I ROOM SECTIONS AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:41:45 | zm167dc@jutal.com | 27-Jun-2026 19:43:25 | Jumpol Sudjitjul | 07-Jul-2026 | 03-Jul-2026 15:00:18 | Washira Kaew-amatawong | 08-Jul-2026 | 08-Jul-2026 09:24:07 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:25:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 10:11:23 | 10-Jul-2026 03:44:44 | 0 |  |  | Approver | Locate
AO-001120 | MM-ASK-1A-WPAX-STR-DWG-1933 | TOPSIDE E&I ROOM SECTIONS AND DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 08:30:28 | zm167dc@jutal.com | 28-Aug-2026 13:37:29 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 10:41:20 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:48:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 17:51:16 | 10-Sep-2026 11:14:50 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1934 | TOPSIDE E&I ROOM SECTIONS AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:51:51 | zm167dc@jutal.com | 15-May-2026 11:28:17 | Jumpol Sudjitjul | 25-May-2026 | 20-May-2026 11:07:17 | Washira Kaew-amatawong | 26-May-2026 | 22-May-2026 16:28:20 | Pornlert Wanaphattharaphan | 27-May-2026 | 27-May-2026 23:03:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 28-May-2026 09:15:05 | 28-May-2026 02:42:22 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WPAX-STR-DWG-1934 | TOPSIDE E&I ROOM SECTIONS AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:26:10 | zm167dc@jutal.com | 03-Jul-2026 13:28:39 | Jumpol Sudjitjul | 13-Jul-2026 | 03-Jul-2026 15:39:45 | Washira Kaew-amatawong | 14-Jul-2026 | 08-Jul-2026 09:26:00 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:21:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:24:56 | 15-Jul-2026 03:20:05 | 0 |  |  | Approver | Locate
AO-001120 | MM-ASK-1A-WPAX-STR-DWG-1934 | TOPSIDE E&I ROOM SECTIONS AND DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 08:31:08 | zm167dc@jutal.com | 28-Aug-2026 13:37:34 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 10:43:28 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:42:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 17:53:17 | 10-Sep-2026 11:18:44 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1941 | TOPSIDE CRANE BOOM REST DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:52:17 | zm167dc@jutal.com | 15-May-2026 11:36:26 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 23-May-2026 09:05:57 | Pornlert Wanaphattharaphan | 27-May-2026 | 28-May-2026 00:05:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 28-May-2026 09:04:14 | 28-May-2026 02:37:41 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1941 | TOPSIDE CRANE BOOM REST DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:42:15 | zm167dc@jutal.com | 27-Jun-2026 19:43:25 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 08-Jul-2026 09:28:30 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 00:58:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 10:09:49 | 10-Jul-2026 03:43:26 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WPAX-STR-DWG-1941 | TOPSIDE CRANE BOOM REST DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 15:23:11 | zm167dc@jutal.com | 21-Aug-2026 17:05:28 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 02-Sep-2026 08:30:12 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:44:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Sep-2026 | 03-Sep-2026 10:46:29 | 03-Sep-2026 04:57:46 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1951 | TOPSIDE AMENITIES CUBICLE PLAN, SECTIONS AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:52:43 | zm167dc@jutal.com | 15-May-2026 11:21:04 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 23-May-2026 20:05:29 | Pornlert Wanaphattharaphan | 27-May-2026 | 28-May-2026 00:14:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 28-May-2026 09:02:31 | 28-May-2026 02:36:41 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1951 | TOPSIDE AMENITIES CUBICLE PLAN, SECTIONS AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:42:52 | zm167dc@jutal.com | 27-Jun-2026 19:43:24 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 08-Jul-2026 09:32:55 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 10-Jul-2026 01:04:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 10-Jul-2026 10:08:53 | 10-Jul-2026 03:42:07 | 0 |  |  | Approver | Locate
AO-001085 | MM-ASK-1A-WPAX-STR-DWG-1951 | TOPSIDE AMENITIES CUBICLE PLAN, SECTIONS AND DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 13:09:16 | zm167dc@jutal.com | 24-Aug-2026 20:30:33 | Jumpol Sudjitjul | 02-Sep-2026 |  | Washira Kaew-amatawong | 03-Sep-2026 | 03-Sep-2026 16:06:29 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:02:56 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:03:51 | 07-Sep-2026 05:02:24 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1952 | TOPSIDE AMENITIES CUBICLE PLAN, SECTIONS AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:53:12 | zm167dc@jutal.com | 15-May-2026 11:20:44 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 23-May-2026 20:07:20 | Pornlert Wanaphattharaphan | 27-May-2026 | 28-May-2026 00:23:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 28-May-2026 09:00:29 | 28-May-2026 02:35:35 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WPAX-STR-DWG-1952 | TOPSIDE AMENITIES CUBICLE PLAN, SECTIONS AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:26:48 | zm167dc@jutal.com | 03-Jul-2026 13:28:43 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 08-Jul-2026 09:34:45 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:22:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:22:07 | 15-Jul-2026 03:18:44 | 0 |  |  | Approver | Locate
AO-001085 | MM-ASK-1A-WPAX-STR-DWG-1952 | TOPSIDE AMENITIES CUBICLE PLAN, SECTIONS AND DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 12:33:07 | zm167dc@jutal.com | 24-Aug-2026 20:30:30 | Jumpol Sudjitjul | 02-Sep-2026 |  | Washira Kaew-amatawong | 03-Sep-2026 | 03-Sep-2026 16:08:54 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:06:15 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:06:02 | 07-Sep-2026 05:03:37 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1961 | TOPSIDE SWING ROPES AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:53:44 | zm167dc@jutal.com | 15-May-2026 11:18:42 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 24-May-2026 08:34:02 | Pornlert Wanaphattharaphan | 27-May-2026 | 28-May-2026 00:44:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 28-May-2026 08:59:19 | 28-May-2026 02:34:33 | 0 |  |  | Approver | Locate
AO-000604 | MM-ASK-1A-WPAX-STR-DWG-1961 | TOPSIDE SWING ROPES AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:28:06 | zm167dc@jutal.com | 03-Jul-2026 13:28:20 | Jumpol Sudjitjul | 13-Jul-2026 |  | Washira Kaew-amatawong | 14-Jul-2026 | 08-Jul-2026 09:36:36 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:22:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 09:21:38 | 15-Jul-2026 03:15:56 | 0 |  |  | Approver | Locate
AO-001055 | MM-ASK-1A-WPAX-STR-DWG-1961 | TOPSIDE SWING ROPES AND DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 15:23:48 | zm167dc@jutal.com | 21-Aug-2026 17:05:47 | Jumpol Sudjitjul | 01-Sep-2026 |  | Washira Kaew-amatawong | 02-Sep-2026 | 02-Sep-2026 08:32:54 | Pornlert Wanaphattharaphan | 03-Sep-2026 | 02-Sep-2026 23:44:30 | APPR | Approved | Jumpol Sudjitjul | 04-Sep-2026 | 03-Sep-2026 10:38:56 | 03-Sep-2026 04:54:07 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1962 | TOPSIDE SWING ROPES AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:54:12 | zm167dc@jutal.com | 15-May-2026 11:19:03 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 24-May-2026 08:36:05 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 21:12:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 21:26:08 | 25-May-2026 14:57:23 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1962 | TOPSIDE SWING ROPES AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:43:25 | zm167dc@jutal.com | 27-Jun-2026 19:43:27 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 08-Jul-2026 09:38:53 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 13-Jul-2026 00:25:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 13-Jul-2026 08:02:39 | 13-Jul-2026 01:22:01 | 0 |  |  | Approver | Locate
AO-001085 | MM-ASK-1A-WPAX-STR-DWG-1962 | TOPSIDE SWING ROPES AND DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 12:33:36 | zm167dc@jutal.com | 24-Aug-2026 20:30:30 | Jumpol Sudjitjul | 02-Sep-2026 |  | Washira Kaew-amatawong | 03-Sep-2026 | 03-Sep-2026 16:11:06 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:07:11 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:08:05 | 07-Sep-2026 05:04:48 | 0 |  |  | Approver | Locate
AO-000244 | MM-ASK-1A-WPAX-STR-DWG-1971 | TOPSIDE LIFE RAFT AND DESCENDING DEVICE SUPPORT DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 08:54:36 | zm167dc@jutal.com | 15-May-2026 11:19:18 | Jumpol Sudjitjul | 25-May-2026 |  | Washira Kaew-amatawong | 26-May-2026 | 24-May-2026 10:07:58 | Pornlert Wanaphattharaphan | 27-May-2026 | 25-May-2026 21:00:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 25-May-2026 21:26:35 | 25-May-2026 14:58:28 | 0 |  |  | Approver | Locate
AO-000566 | MM-ASK-1A-WPAX-STR-DWG-1971 | TOPSIDE LIFE RAFT AND DESCENDING DEVICE SUPPORT DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:44:11 | zm167dc@jutal.com | 27-Jun-2026 19:43:22 | Jumpol Sudjitjul | 07-Jul-2026 |  | Washira Kaew-amatawong | 08-Jul-2026 | 08-Jul-2026 09:40:29 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 14-Jul-2026 20:10:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 15-Jul-2026 09:21:07 | 15-Jul-2026 03:35:41 | 0 |  |  | Approver | Locate
AO-001085 | MM-ASK-1A-WPAX-STR-DWG-1971 | TOPSIDE LIFE RAFT AND DESCENDING DEVICE SUPPORT DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 12:34:02 | zm167dc@jutal.com | 24-Aug-2026 20:30:33 | Jumpol Sudjitjul | 02-Sep-2026 |  | Washira Kaew-amatawong | 03-Sep-2026 | 03-Sep-2026 16:12:53 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:08:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:12:36 | 07-Sep-2026 05:06:11 | 0 |  |  | Approver | Locate
AO-000078 | MM-ASK-1A-WPAX-STR-DWG-2001 | JACKET GENERAL NOTES SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:27:39 | zm167dc@jutal.com | 27-Apr-2026 11:09:49 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:26:19 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:24:37 | Pornlert Wanaphattharaphan | 11-May-2026 | 11-May-2026 21:21:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 12-May-2026 09:15:26 | 12-May-2026 02:42:07 | 0 |  |  | Approver | Locate
AO-000665 | MM-ASK-1A-WPAX-STR-DWG-2001 | JACKET GENERAL NOTES SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 09-Jul-2026 15:31:17 | zm167dc@jutal.com | 09-Jul-2026 15:45:22 | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 17:48:30 | Washira Kaew-amatawong | 20-Jul-2026 | 20-Jul-2026 10:21:20 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 22:59:47 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 08:49:46 | 23-Jul-2026 02:05:45 | 0 |  |  | Approver | Locate
AO-000920 | MM-ASK-1A-WPAX-STR-DWG-2001 | JACKET GENERAL NOTES SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 15:34:20 | zm167dc@jutal.com | 07-Aug-2026 16:49:10 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 15-Aug-2026 21:00:36 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 16-Aug-2026 23:59:26 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 17-Aug-2026 08:52:00 | 17-Aug-2026 02:34:42 | 0 |  |  | Approver | Locate
AO-000078 | MM-ASK-1A-WPAX-STR-DWG-2002 | JACKET GENERAL NOTES SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 09:15:43 | zm167dc@jutal.com | 27-Apr-2026 11:09:35 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:27:15 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:27:18 | Pornlert Wanaphattharaphan | 11-May-2026 | 11-May-2026 21:25:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 12-May-2026 09:11:50 | 12-May-2026 02:43:09 | 0 |  |  | Approver | Locate
AO-000665 | MM-ASK-1A-WPAX-STR-DWG-2002 | JACKET GENERAL NOTES SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 09-Jul-2026 15:31:47 | zm167dc@jutal.com | 09-Jul-2026 15:45:22 | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 17:46:22 | Washira Kaew-amatawong | 20-Jul-2026 | 20-Jul-2026 10:23:26 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 23:00:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 08:49:20 | 23-Jul-2026 02:04:33 | 0 |  |  | Approver | Locate
AO-000920 | MM-ASK-1A-WPAX-STR-DWG-2002 | JACKET GENERAL NOTES SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 15:34:48 | zm167dc@jutal.com | 07-Aug-2026 16:49:08 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 15-Aug-2026 21:03:12 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 17-Aug-2026 00:00:14 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 17-Aug-2026 08:51:04 | 17-Aug-2026 02:33:22 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WPAX-STR-DWG-2011 | JACKET STANDARD DETAILS WELDING DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 16:56:36 | zm167dc@jutal.com | 06-Aug-2026 17:32:26 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 15-Aug-2026 21:15:48 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 17-Aug-2026 00:03:52 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Aug-2026 | 17-Aug-2026 08:50:10 | 17-Aug-2026 02:47:51 | 0 |  |  | Approver | Locate
AO-001208 | MM-ASK-1A-WPAX-STR-DWG-2011 | JACKET STANDARD DETAILS WELDING DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:27:16 | zm167dc@jutal.com | 08-Sep-2026 10:04:18 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 18-Sep-2026 07:22:42 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 15:00:51 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:20:36 | 20-Sep-2026 10:14:18 | 0 |  |  | Approver | Locate
AO-000897 | MM-ASK-1A-WPAX-STR-DWG-2012 | JACKET STANDARD DETAILS WELDING DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 16:57:03 | zm167dc@jutal.com | 06-Aug-2026 17:32:23 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 15-Aug-2026 21:18:24 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 17-Aug-2026 00:05:03 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Aug-2026 | 17-Aug-2026 08:49:15 | 17-Aug-2026 02:45:36 | 0 |  |  | Approver | Locate
AO-001209 | MM-ASK-1A-WPAX-STR-DWG-2012 | JACKET STANDARD DETAILS WELDING DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:27:53 | zm167dc@jutal.com | 08-Sep-2026 10:04:11 | Jumpol Sudjitjul | 16-Sep-2026 |  | Washira Kaew-amatawong | 17-Sep-2026 | 18-Sep-2026 07:24:22 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 15:02:37 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:19:39 | 20-Sep-2026 10:13:06 | 0 |  |  | Approver | Locate
AO-000504 | MM-ASK-1A-WPAX-STR-DWG-2901 | JACKET CASING GUIDES LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 16:50:17 | zm167dc@jutal.com | 18-Jun-2026 17:56:02 | Jumpol Sudjitjul | 29-Jun-2026 | 19-Jun-2026 00:52:09 | Washira Kaew-amatawong | 30-Jun-2026 | 22-Jun-2026 09:39:10 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 22:51:43 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Jul-2026 | 23-Jun-2026 08:44:11 | 23-Jun-2026 02:20:52 | 0 |  |  | Approver | Locate
AO-000665 | MM-ASK-1A-WPAX-STR-DWG-2901 | JACKET CASING GUIDES LAYOUT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 09-Jul-2026 15:32:21 | zm167dc@jutal.com | 09-Jul-2026 15:45:23 | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 17:46:56 | Washira Kaew-amatawong | 20-Jul-2026 | 20-Jul-2026 10:00:06 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 22:58:17 | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 08:48:36 | 23-Jul-2026 02:03:13 | 0 |  |  | Approver | Locate
AO-000504 | MM-ASK-1A-WPAX-STR-DWG-2902 | JACKET CASING GUIDES SECTION & DETAILS SHEET1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 16:50:51 | zm167dc@jutal.com | 18-Jun-2026 17:56:21 | Jumpol Sudjitjul | 29-Jun-2026 | 19-Jun-2026 00:53:30 | Washira Kaew-amatawong | 30-Jun-2026 | 22-Jun-2026 09:42:53 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 22:48:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 23-Jun-2026 08:47:02 | 23-Jun-2026 02:23:04 | 0 |  |  | Approver | Locate
AO-000665 | MM-ASK-1A-WPAX-STR-DWG-2902 | JACKET CASING GUIDES SECTION & DETAILS SHEET1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 09-Jul-2026 15:32:56 | zm167dc@jutal.com | 09-Jul-2026 15:45:25 | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 17:49:39 | Washira Kaew-amatawong | 20-Jul-2026 | 20-Jul-2026 10:02:09 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 22:58:31 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 08:47:57 | 23-Jul-2026 02:02:02 | 0 |  |  | Approver | Locate
AO-000920 | MM-ASK-1A-WPAX-STR-DWG-2902 | JACKET CASING GUIDES SECTION & DETAILS SHEET1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 15:35:15 | zm167dc@jutal.com | 07-Aug-2026 16:49:08 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:46:43 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:17:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:29:03 | 24-Aug-2026 10:57:33 | 0 |  |  | Approver | Locate
AO-000504 | MM-ASK-1A-WPAX-STR-DWG-2903 | JACKET CASING GUIDES SECTION & DETAILS SHEET2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 16:51:18 | zm167dc@jutal.com | 18-Jun-2026 17:56:35 | Jumpol Sudjitjul | 29-Jun-2026 | 19-Jun-2026 00:54:56 | Washira Kaew-amatawong | 30-Jun-2026 | 22-Jun-2026 09:44:45 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 22:46:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 23-Jun-2026 08:47:28 | 23-Jun-2026 02:24:18 | 0 |  |  | Approver | Locate
AO-000665 | MM-ASK-1A-WPAX-STR-DWG-2903 | JACKET CASING GUIDES SECTION & DETAILS SHEET2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 09-Jul-2026 15:33:26 | zm167dc@jutal.com | 09-Jul-2026 15:45:24 | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 17:49:03 | Washira Kaew-amatawong | 20-Jul-2026 | 20-Jul-2026 10:03:49 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 22:58:53 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 08:46:54 | 23-Jul-2026 01:59:26 | 0 |  |  | Approver | Locate
AO-000920 | MM-ASK-1A-WPAX-STR-DWG-2903 | JACKET CASING GUIDES SECTION & DETAILS SHEET2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:55:44 | zm167dc@jutal.com | 07-Aug-2026 16:49:10 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 13:52:42 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:17:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:26:14 | 24-Aug-2026 11:07:25 | 0 |  |  | Approver | Locate
AO-000504 | MM-ASK-1A-WPAX-STR-DWG-2904 | JACKET CASING GUIDES SECTION & DETAILS SHEET3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 16:51:43 | zm167dc@jutal.com | 18-Jun-2026 17:56:48 | Jumpol Sudjitjul | 29-Jun-2026 | 19-Jun-2026 00:54:26 | Washira Kaew-amatawong | 30-Jun-2026 | 22-Jun-2026 09:46:50 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 22:43:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 23-Jun-2026 08:34:16 | 23-Jun-2026 01:48:07 | 0 |  |  | Approver | Locate
AO-000665 | MM-ASK-1A-WPAX-STR-DWG-2904 | JACKET CASING GUIDES SECTION & DETAILS SHEET3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 09-Jul-2026 15:34:01 | zm167dc@jutal.com | 09-Jul-2026 15:45:25 | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 17:50:03 | Washira Kaew-amatawong | 20-Jul-2026 | 20-Jul-2026 10:05:16 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 22-Jul-2026 22:59:24 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jul-2026 | 23-Jul-2026 08:47:19 | 23-Jul-2026 02:00:41 | 0 |  |  | Approver | Locate
AO-000920 | MM-ASK-1A-WPAX-STR-DWG-2904 | JACKET CASING GUIDES SECTION & DETAILS SHEET3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:56:07 | zm167dc@jutal.com | 07-Aug-2026 16:49:10 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 14:15:51 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:18:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:24:13 | 24-Aug-2026 11:04:49 | 0 |  |  | Approver | Locate
AO-000561 | MM-ASK-1A-WPAX-STR-DWG-2911 | JACKET PILE TO JACKET CONNECTION DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:35:42 | zm167dc@jutal.com | 26-Jun-2026 16:40:10 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 01-Jul-2026 11:10:15 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 02-Jul-2026 00:22:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 02-Jul-2026 13:05:49 | 02-Jul-2026 06:38:06 | 0 |  |  | Approver | Locate
AO-000713 | MM-ASK-1A-WPAX-STR-DWG-2911 | JACKET PILE TO JACKET CONNECTION DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 11:56:34 | zm167dc@jutal.com | 17-Jul-2026 11:58:11 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 28-Jul-2026 10:41:00 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:43:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:26:39 | 30-Jul-2026 02:58:25 | 0 |  |  | Approver | Locate
AO-000975 | MM-ASK-1A-WPAX-STR-DWG-2911 | JACKET PILE TO JACKET CONNECTION DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 11:28:32 | zm167dc@jutal.com | 14-Aug-2026 12:53:44 | Jumpol Sudjitjul | 24-Aug-2026 |  | Washira Kaew-amatawong | 25-Aug-2026 | 25-Aug-2026 07:04:55 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 14:59:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 27-Aug-2026 15:42:13 | 27-Aug-2026 09:56:00 | 0 |  |  | Approver | Locate
AO-000561 | MM-ASK-1A-WPAX-STR-DWG-2921 | JACKET BOATLANDING ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:36:09 | zm167dc@jutal.com | 26-Jun-2026 16:56:58 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 11:37:56 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 03-Jul-2026 00:50:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 03-Jul-2026 15:56:38 | 03-Jul-2026 09:38:51 | 0 |  |  | Approver | Locate
AO-000715 | MM-ASK-1A-WPAX-STR-DWG-2921 | JACKET BOATLANDING ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 13:18:20 | zm167dc@jutal.com | 17-Jul-2026 13:28:38 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 28-Jul-2026 10:43:14 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:43:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:27:03 | 30-Jul-2026 02:59:46 | 0 |  |  | Approver | Locate
AO-001030 | MM-ASK-1A-WPAX-STR-DWG-2921 | JACKET BOATLANDING ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 10:54:26 | zm167dc@jutal.com | 20-Aug-2026 13:19:56 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 20:30:43 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:50:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:38:58 | 30-Aug-2026 10:12:24 | 0 |  |  | Approver | Locate
AO-000561 | MM-ASK-1A-WPAX-STR-DWG-2922 | JACKET BOATLANDING SECTION & DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:04:55 | zm167dc@jutal.com | 26-Jun-2026 16:36:51 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 11:39:05 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 03-Jul-2026 00:51:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 03-Jul-2026 15:02:25 | 03-Jul-2026 08:25:00 | 0 |  |  | Approver | Locate
AO-000715 | MM-ASK-1A-WPAX-STR-DWG-2922 | JACKET BOATLANDING SECTION & DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 13:19:18 | zm167dc@jutal.com | 17-Jul-2026 13:28:39 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 28-Jul-2026 10:45:08 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:43:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:27:24 | 30-Jul-2026 03:02:05 | 0 |  |  | Approver | Locate
AO-001031 | MM-ASK-1A-WPAX-STR-DWG-2922 | JACKET BOATLANDING SECTION & DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 10:55:10 | zm167dc@jutal.com | 20-Aug-2026 13:20:57 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 20:32:20 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:51:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:37:43 | 30-Aug-2026 10:09:48 | 0 |  |  | Approver | Locate
AO-000561 | MM-ASK-1A-WPAX-STR-DWG-2923 | JACKET BOATLANDING SECTION & DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:05:29 | zm167dc@jutal.com | 26-Jun-2026 16:36:52 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 11:40:47 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 03-Jul-2026 00:51:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 03-Jul-2026 15:01:21 | 03-Jul-2026 08:23:29 | 0 |  |  | Approver | Locate
AO-000715 | MM-ASK-1A-WPAX-STR-DWG-2923 | JACKET BOATLANDING SECTION & DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 13:20:02 | zm167dc@jutal.com | 17-Jul-2026 13:28:52 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 28-Jul-2026 10:47:16 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:44:15 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:27:54 | 30-Jul-2026 03:03:19 | 0 |  |  | Approver | Locate
AO-001037 | MM-ASK-1A-WPAX-STR-DWG-2923 | JACKET BOATLANDING SECTION & DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 15:00:20 | zm167dc@jutal.com | 20-Aug-2026 15:14:01 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 20:33:51 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:52:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:25:31 | 30-Aug-2026 10:44:09 | 0 |  |  | Approver | Locate
AO-000561 | MM-ASK-1A-WPAX-STR-DWG-2924 | JACKET BOATLANDING SECTION & DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:05:57 | zm167dc@jutal.com | 26-Jun-2026 16:36:58 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 11:42:19 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 03-Jul-2026 00:52:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 03-Jul-2026 15:55:54 | 03-Jul-2026 09:35:46 | 0 |  |  | Approver | Locate
AO-000715 | MM-ASK-1A-WPAX-STR-DWG-2924 | JACKET BOATLANDING SECTION & DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 13:20:36 | zm167dc@jutal.com | 17-Jul-2026 13:28:38 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 28-Jul-2026 10:49:20 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:44:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:28:27 | 30-Jul-2026 02:45:48 | 0 |  |  | Approver | Locate
AO-001032 | MM-ASK-1A-WPAX-STR-DWG-2924 | JACKET BOATLANDING SECTION & DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 10:55:54 | zm167dc@jutal.com | 20-Aug-2026 13:21:31 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 20:35:53 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:52:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:27:31 | 30-Aug-2026 10:03:26 | 0 |  |  | Approver | Locate
AO-000561 | MM-ASK-1A-WPAX-STR-DWG-2925 | JACKET BOATLANDING SECTION & DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:06:25 | zm167dc@jutal.com | 26-Jun-2026 16:36:55 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 11:44:17 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 03-Jul-2026 01:31:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 03-Jul-2026 15:00:43 | 03-Jul-2026 08:22:03 | 0 |  |  | Approver | Locate
AO-000715 | MM-ASK-1A-WPAX-STR-DWG-2925 | JACKET BOATLANDING SECTION & DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 13:21:09 | zm167dc@jutal.com | 17-Jul-2026 13:28:38 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 28-Jul-2026 10:51:07 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:44:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:24:38 | 30-Jul-2026 02:44:34 | 0 |  |  | Approver | Locate
AO-001033 | MM-ASK-1A-WPAX-STR-DWG-2925 | JACKET BOATLANDING SECTION & DETAILS - SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 10:56:44 | zm167dc@jutal.com | 20-Aug-2026 13:22:00 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 20:37:32 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:53:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:28:53 | 30-Aug-2026 10:07:17 | 0 |  |  | Approver | Locate
AO-000561 | MM-ASK-1A-WPAX-STR-DWG-2926 | JACKET BOATLANDING SECTION & DETAILS - SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:06:54 | zm167dc@jutal.com | 26-Jun-2026 16:36:52 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 11:45:39 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 04-Jul-2026 19:26:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 05-Jul-2026 10:33:31 | 05-Jul-2026 03:52:51 | 0 |  |  | Approver | Locate
AO-000715 | MM-ASK-1A-WPAX-STR-DWG-2926 | JACKET BOATLANDING SECTION & DETAILS - SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 13:21:41 | zm167dc@jutal.com | 17-Jul-2026 13:28:39 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 28-Jul-2026 10:53:30 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:45:19 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:23:49 | 30-Jul-2026 02:43:15 | 0 |  |  | Approver | Locate
AO-001034 | MM-ASK-1A-WPAX-STR-DWG-2926 | JACKET BOATLANDING SECTION & DETAILS - SHEET 5 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 10:57:44 | zm167dc@jutal.com | 20-Aug-2026 13:22:34 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 20:39:59 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:53:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:38:31 | 30-Aug-2026 10:11:07 | 0 |  |  | Approver | Locate
AO-000561 | MM-ASK-1A-WPAX-STR-DWG-2927 | JACKET BOATLANDING SECTION & DETAILS - SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:07:44 | zm167dc@jutal.com | 26-Jun-2026 16:36:53 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 11:46:58 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 04-Jul-2026 19:34:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 05-Jul-2026 10:34:18 | 05-Jul-2026 03:55:13 | 0 |  |  | Approver | Locate
AO-000715 | MM-ASK-1A-WPAX-STR-DWG-2927 | JACKET BOATLANDING SECTION & DETAILS - SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 13:22:09 | zm167dc@jutal.com | 17-Jul-2026 13:28:38 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 28-Jul-2026 10:56:18 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:45:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:22:36 | 30-Jul-2026 02:42:01 | 0 |  |  | Approver | Locate
AO-001037 | MM-ASK-1A-WPAX-STR-DWG-2927 | JACKET BOATLANDING SECTION & DETAILS - SHEET 6 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 15:00:54 | zm167dc@jutal.com | 20-Aug-2026 15:14:46 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 20:42:10 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:53:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:34:46 | 30-Aug-2026 10:47:54 | 0 |  |  | Approver | Locate
AO-000561 | MM-ASK-1A-WPAX-STR-DWG-2928 | JACKET BOATLANDING SECTION & DETAILS - SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:08:09 | zm167dc@jutal.com | 26-Jun-2026 16:36:53 | Jumpol Sudjitjul | 06-Jul-2026 |  | Washira Kaew-amatawong | 07-Jul-2026 | 02-Jul-2026 11:48:22 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 04-Jul-2026 19:35:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 05-Jul-2026 10:33:57 | 05-Jul-2026 03:54:02 | 0 |  |  | Approver | Locate
AO-000715 | MM-ASK-1A-WPAX-STR-DWG-2928 | JACKET BOATLANDING SECTION & DETAILS - SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 13:22:41 | zm167dc@jutal.com | 17-Jul-2026 13:28:39 | Jumpol Sudjitjul | 27-Jul-2026 |  | Washira Kaew-amatawong | 30-Jul-2026 | 28-Jul-2026 10:58:35 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:46:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:21:58 | 30-Jul-2026 02:40:38 | 0 |  |  | Approver | Locate
AO-001037 | MM-ASK-1A-WPAX-STR-DWG-2928 | JACKET BOATLANDING SECTION & DETAILS - SHEET 7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 15:01:25 | zm167dc@jutal.com | 20-Aug-2026 15:15:08 | Jumpol Sudjitjul | 28-Aug-2026 |  | Washira Kaew-amatawong | 31-Aug-2026 | 29-Aug-2026 20:44:23 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:54:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:32:46 | 30-Aug-2026 10:46:40 | 0 |  |  | Approver | Locate
AO-000078 | MM-ASK-1A-WPAX-STR-DWG-2941 | JACKET PAINT MARKING DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:28:11 | zm167dc@jutal.com | 27-Apr-2026 11:09:20 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:19:02 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:30:27 | Pornlert Wanaphattharaphan | 11-May-2026 | 11-May-2026 21:29:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 12-May-2026 09:13:28 | 12-May-2026 02:40:02 | 0 |  |  | Approver | Locate
AO-000820 | MM-ASK-1A-WPAX-STR-DWG-2941 | JACKET PAINT MARKING DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 10:41:26 | zm167dc@jutal.com | 31-Jul-2026 10:44:03 | Jumpol Sudjitjul | 10-Aug-2026 |  | Washira Kaew-amatawong | 11-Aug-2026 | 11-Aug-2026 07:34:29 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 01:05:51 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 10:26:04 | 13-Aug-2026 04:27:36 | 0 |  |  | Approver | Locate
AO-001109 | MM-ASK-1A-WPAX-STR-DWG-2941 | JACKET PAINT MARKING DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Aug-2026 15:02:06 | zm167dc@jutal.com | 27-Aug-2026 17:38:25 | Jumpol Sudjitjul | 07-Sep-2026 |  | Washira Kaew-amatawong | 08-Sep-2026 | 08-Sep-2026 10:48:31 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:41:31 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 17:52:14 | 10-Sep-2026 11:16:05 | 0 |  |  | Approver | Locate
AO-000078 | MM-ASK-1A-WPAX-STR-DWG-2951 | JACKET VORTEX SHEDDING PREVENTION PLAN & DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:28:43 | zm167dc@jutal.com | 27-Apr-2026 11:09:01 | Jumpol Sudjitjul | 07-May-2026 | 06-May-2026 17:18:27 | Washira Kaew-amatawong | 08-May-2026 | 07-May-2026 14:33:05 | Pornlert Wanaphattharaphan | 11-May-2026 | 11-May-2026 22:42:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 12-May-2026 09:14:21 | 12-May-2026 02:41:06 | 0 |  |  | Approver | Locate
AO-000899 | MM-ASK-1A-WPAX-STR-DWG-2951 | JACKET VORTEX SHEDDING PREVENTION PLAN & DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 09:50:17 | zm167dc@jutal.com | 07-Aug-2026 10:14:11 | Jumpol Sudjitjul | 18-Aug-2026 |  | Washira Kaew-amatawong | 19-Aug-2026 | 20-Aug-2026 14:37:11 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 19:19:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 17:22:41 | 24-Aug-2026 11:22:11 | 0 |  |  | Approver | Locate
AO-001249 | MM-ASK-1A-WPAX-STR-DWG-2951 | JACKET VORTEX SHEDDING PREVENTION PLAN & DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Sep-2026 17:59:22 | zm167dc@jutal.com | 09-Sep-2026 08:44:43 | Jumpol Sudjitjul | 17-Sep-2026 |  | Washira Kaew-amatawong | 18-Sep-2026 | 18-Sep-2026 07:26:10 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 19-Sep-2026 15:01:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Sep-2026 | 20-Sep-2026 16:18:42 | 20-Sep-2026 11:01:35 | 0 |  |  | Approver | Locate
AO-000562 | MM-ASK-1A-WPAX-TEL-SLD-0001 | OVERALL TELECOMMUNICATION SYSTEM BLOCK DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | TEL | Telecommunication | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:37:45 | zm167dc@jutal.com | 26-Jun-2026 17:01:18 | Jumpol Sudjitjul | 07-Jul-2026 |  | Danai Chaisalee | 08-Jul-2026 | 02-Jul-2026 09:04:00 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 04-Jul-2026 19:50:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 05-Jul-2026 10:33:18 | 05-Jul-2026 03:50:17 | 0 |  |  | Approver | Locate
AO-000970 | MM-ASK-1A-WPAX-TEL-SLD-0001 | OVERALL TELECOMMUNICATION SYSTEM BLOCK DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | TEL | Telecommunication | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:38:06 | zm167dc@jutal.com | 14-Aug-2026 08:47:36 | Jumpol Sudjitjul | 24-Aug-2026 |  | Danai Chaisalee | 25-Aug-2026 | 19-Aug-2026 13:16:32 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:08:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 17:21:21 | 24-Aug-2026 11:03:30 | 0 |  |  | Approver | Locate
AO-001315 | MM-ASK-1A-WPAX-TEL-SLD-0001 | OVERALL TELECOMMUNICATION SYSTEM BLOCK DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | WPAX |  |  | TEL | Telecommunication | SLD | Single Line Diagram | 0 | In Review | AFC | Approved for Construction |  | 11-Sep-2026 19:39:10 | zm167dc@jutal.com | 11-Sep-2026 20:33:40 | Jumpol Sudjitjul | 22-Sep-2026 | 18-Sep-2026 09:55:11 | Danai Chaisalee | 23-Sep-2026 |  | Pornlert Wanaphattharaphan | 24-Sep-2026 |  |  |  |  | 25-Sep-2026 |  |  | 0 |  |  | Approver | Locate